## Sheet1
subject | body | issue_type | category | correspondence_type | synthetic | generated_date | generator
Reminder: Outstanding Supervision Charges for NHAI Project NH-27 Utility Shifting Works | Ref: NHAI/PIU/2023-24/UC/276 Date: 15.09.2023 To, The Project Director National Highways Authority of India PIU-Bangalore Sub: NH-27 Six-Laning from km 235.000 to km 287.000 - Pending Supervision Charges for Utility Shifting Ref: 1. Contract Agreement dated 05.03.2022 2. KPTCL Demand Note dated 12.07.2023 Dear Sir, This is to bring to your kind attention that supervision charges amounting to Rs. 42.35 lakhs are pending towards KPTCL for utility shifting works executed between Ch. 245+000 to Ch. 256+000. As per Article 11.3.2 of the Contract Agreement, these charges were to be reimbursed within 30 days of submission. The delay in payment is affecting our relationship with the utility department and may impact future shifting works. Request your intervention for early release of payment. Yours faithfully, For ABC-XYZ (JV) [Authorized Signatory] | Delay in payment of Supervision Charges to utility departments | ('EoT', 0.91) | contractor_to_authority | TRUE | 2025-09-18T12:19:38.902493 | claude
Payment Status Update - Utility Department Supervision Charges | From: ae.bangalore@nhai.org To: projectmanager@abcxyzjv.com Date: 18.09.2023 Dear Sir, With reference to your letter dated 15.09.2023 regarding pending supervision charges for KPTCL, please note that the matter has been taken up with our finance division. The payment process has been initiated and the amount shall be released within 15 working days. Kindly submit the following pending documents to expedite the process: 1. Original supervision charge receipt from KPTCL 2. Utility shifting completion certificate 3. Joint verification report Regards, Authority Engineer NHAI PIU-Bangalore | Delay in payment of Supervision Charges to utility departments | ('EoT', 0.91) | authority_to_contractor | TRUE | 2025-09-18T12:19:38.902514 | claude
Notice for Delay in Payment of BSNL Supervision Charges - NH-27 Project | Ref: ABC/NHAI/2023/Notice/42 Date: 25.09.2023 The Chief General Manager NHAI Regional Office Bangalore Sub: Notice under Clause 19.2 - Delay in Payment of Utility Supervision Charges Dear Sir, We are constrained to issue this notice regarding persistent delay in payment of supervision charges to BSNL amounting to Rs. 38.67 lakhs for utility shifting works at Ch. 262+000 to Ch. 267+500. As per Schedule-H of the Contract Agreement, such payments are to be processed within the stipulated timeline. The delay has resulted in additional costs and time implications for which we reserve our rights under the Contract. Request immediate intervention and release of payment. Yours sincerely, Project Manager ABC-XYZ (JV) | Delay in payment of Supervision Charges to utility departments | ('EoT', 0.91) | contractor_to_authority | TRUE | 2025-09-18T12:19:38.902517 | claude
Processing of Utility Department Supervision Charges - Status Update | NHAI/RO/BLR/2023/UC/156 Date: 02.10.2023 M/s ABC-XYZ (JV) Bangalore Sub: Six-Laning of NH-27 - Status of Utility Supervision Charges Ref: Your notice dated 25.09.2023 Dear Sir, This is regarding the pending supervision charges for utility departments. We wish to inform that: 1. KPTCL payment of Rs. 42.35 lakhs - Processing completed, payment by 10.10.2023 2. BSNL payment of Rs. 38.67 lakhs - Under verification, queries raised Request submission of clarifications for BSNL payment as per checklist attached. Yours faithfully, Project Director NHAI, PIU-Bangalore | Delay in payment of Supervision Charges to utility departments | ('EoT', 0.91) | authority_to_contractor | TRUE | 2025-09-18T12:19:38.902519 | claude
Submission of Documents for BSNL Supervision Charges | From: projectmanager@abcxyzjv.com To: pd.bangalore@nhai.org Date: 05.10.2023 Dear Sir, With reference to your letter dated 02.10.2023, please find attached the following documents for BSNL supervision charges: 1. Revised estimate verification report 2. Stage-wise completion certificates 3. Joint measurement sheets 4. Photographs of shifted utilities 5. BSNL approval letters Request expeditious processing of payment to avoid further delays in utility shifting works. Best regards, Project Manager ABC-XYZ (JV) | Delay in payment of Supervision Charges to utility departments | ('EoT', 0.91) | contractor_to_authority | TRUE | 2025-09-18T12:19:38.902522 | claude
Release of Payment - Utility Supervision Charges | NHAI/PIU/2023-24/UC/298 Date: 12.10.2023 The Project Manager ABC-XYZ (JV) Bangalore Sub: Release of Payment for Utility Supervision Charges - NH-27 Project Ref: 1. Your email dated 05.10.2023 2. Contract Agreement dated 05.03.2022 Dear Sir, This is to inform that following payments have been processed: 1. KPTCL - Rs. 42.35 lakhs (UTR No: NHAI/KP/2023/4567) 2. BSNL - Rs. 38.67 lakhs (UTR No: NHAI/BS/2023/4568) Kindly confirm receipt of payment and submit completion report for the shifted utilities. Yours faithfully, Project Director NHAI, PIU-Bangalore | Delay in payment of Supervision Charges to utility departments | ('EoT', 0.91) | authority_to_contractor | TRUE | 2025-09-18T12:19:38.902524 | claude
Notice for Change in Structural Dimensions of Major Bridge at Ch. 145+200 | Ref: NHAI/PIU/UP/234/2023-24 Date: 15.09.2023 To, Project Manager ABC-XYZ (JV) NH-48 Project Office Ref: Contract Agreement No. NHAI/EPC/UP/2022-23/456 Dear Sir, This is with reference to the detailed design submission for the major bridge at Ch. 145+200. Based on the revised hydraulic studies and recommendations from the Authority's Expert Committee, the structural dimensions need to be modified as follows: 1. Increase in overall bridge length from 250m to 280m 2. Modification of pier dimensions from 2.0m x 4.0m to 2.5m x 4.5m 3. Enhancement of foundation depth by 2.0m As per Article 13.1(a) of the EPC Agreement, this constitutes a Change of Scope. You are requested to submit the detailed cost implications as per Schedule-H within 15 days. Yours faithfully, Project Director NHAI PIU-Lucknow | Change of scope due to change in structural dimensions | ('Change of Scope', 0.91) | authority_to_contractor | TRUE | 2025-09-18T12:20:11.546576 | claude
Cost Impact Assessment for Revised ROB Dimensions at Ch. 67+500 | From: contractor.pm@abcxyzjv.com To: pd.lucknow@nhai.org Date: 22.09.2023 Dear Sir, Subject: NH-48 Six-Laning Project - ROB Dimensional Changes With reference to your letter dated 15.09.2023 regarding modifications to the ROB structure, we hereby submit the cost impact analysis: 1. Additional concrete quantity: 450 cum 2. Additional steel reinforcement: 65 MT 3. Additional foundation works: Rs. 1.25 crore 4. Time impact: 45 days Total financial impact: Rs. 3.85 crore The above calculations are based on current SOR rates and as per Schedule-H provisions. Detailed BOQ attached. Request your review and approval. Regards, Project Manager ABC-XYZ (JV) | Change of scope due to change in structural dimensions | ('Change of Scope', 0.91) | contractor_to_authority | TRUE | 2025-09-18T12:20:11.546592 | claude
Intimation - Structural Changes in Flyover Design at Km 89.400 | Ref: AE/UP/2023-24/789 Date: 05.10.2023 To, The Project Manager ABC-XYZ (JV) Sub: Four-laning of NH-48 from km 67.000 to km 115.000 Sir, Based on the recent traffic survey and structural safety audit, following modifications are required in the flyover design at Km 89.400: 1. Deck slab thickness increase from 250mm to 300mm 2. Additional span of 30m on LHS 3. Modified crash barrier details as per latest MORTH specifications The above changes shall be treated as Change of Scope under Article 13.1(b). Please submit the revised designs within 21 days. Yours sincerely, Authority Engineer | Change of scope due to change in structural dimensions | ('Change of Scope', 0.91) | authority_to_contractor | TRUE | 2025-09-18T12:20:11.546596 | claude
Request for Time Extension - VUP Structure Modifications | Ref: ABC-XYZ/NH48/2023/334 Date: 12.10.2023 The Project Director NHAI PIU-Lucknow Sub: Time Impact Due to VUP Structural Changes Dear Sir, This refers to the revised design requirements for Vehicle Underpass at Ch. 78+900. The increased box dimensions from 12m x 5m to 14m x 5.5m have resulted in: 1. Additional excavation: 1200 cum 2. Modified protection works 3. Additional construction time requirement As per Article 13.3, we request for time extension of 60 days with cost compensation of Rs. 45.5 lakh. Detailed calculations enclosed. Yours faithfully, Project Manager ABC-XYZ (JV) | Change of scope due to change in structural dimensions | ('Change of Scope', 0.91) | contractor_to_authority | TRUE | 2025-09-18T12:20:11.546600 | claude
RE: Revised Foundation Design for High-Level Bridge | From: se.technical@nhai.org To: contractor.design@abcxyzjv.com Cc: pd.lucknow@nhai.org Date: 25.10.2023 Dear Sir, Referred to your design submission dated 18.10.2023. The modified foundation design for high-level bridge at Ch. 156+700 is approved with following observations: 1. Well foundation diameter increase accepted 2. Additional soil investigation results noted 3. Revised quantities to be processed under COS provisions Please submit the detailed cost break-up as per latest DSR rates. Regards, Superintending Engineer (Technical) NHAI | Change of scope due to change in structural dimensions | ('Change of Scope', 0.91) | authority_to_contractor | TRUE | 2025-09-18T12:20:11.546603 | claude
Monthly Progress Update - Structural Modifications Status | Ref: ABC-XYZ/MPR/OCT23/56 Date: 31.10.2023 The Authority Engineer NH-48 Project Sir, Status update on ongoing structural modifications: 1. Major Bridge (Ch. 145+200): - Foundation works 60% complete - Additional steel procurement initiated - Cost impact Rs. 2.75 crore incurred 2. ROB (Ch. 67+500): - Revised drawings implemented - Time extension pending approval 3. VUP (Ch. 78+900): - Modified works commenced - Material procurement in progress Detailed progress charts attached. Yours truly, Project Manager ABC-XYZ (JV) | Change of scope due to change in structural dimensions | ('Change of Scope', 0.91) | contractor_to_authority | TRUE | 2025-09-18T12:20:11.546606 | claude