## Sheet1
issue_type | category | reference_sentence | source_file | subject | body | is_synthetic | generation_method | generated_date | generator_version
Memorandum & Appendix | Appointed Date; Contractor's Obligations; Authority's Obligations | This has reference to Joint Memorandum of Site Inventory signed jointly by PD, Krishnagiri and the EPC Contractor submitted vide your letter dated 01.02.2019 in terms of Clause 8.2.1 of Agreement regarding declaration of Appointed Date for the subject Project. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/Lr.No.130404_08022019_ Declaration of Appointment Date.pdf | Six Laning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km. 71+015 to Km 107+091 on EPC Mode in the state of Tamil Nadu under NHDP Phase-V - Regarding declaration of Appointed Date. | This has reference to Joint Memorandum of Site Inventory signed jointly by PD, Krishnagiri and the EPC Contractor submitted vide your letter dated 01.02.2019 in terms of Clause 8.2.1 of Agreement regarding declaration of Appointed Date for the subject Project. By In this context, it is to convey that the Competent Authority has accorded approval to declare the Appointed Date as 11.02.2019, to commence the work. Further, it has also been directed to arrange handing over of balance ROW as per Clause 8.2.2 of Contract Agreement and to ensure that encumbrances due to Tree Cutting, removal of Structures, shifting of Electric Poles and Water Supply Lines etc., don’t hinder the construction of Project. This is for kind information and further necessary action, please. | FALSE | real_data
Memorandum & Appendix | Appointed Date; Contractor's Obligations; Authority's Obligations | We also bring to your kind notice that the memorandum and appendix jointly signed on 11.01.2019 and submitted vide ref (3) cited above was prepared based on the available area without taking into consideration, the requirement of the contract provision as per Clause 4.1.3 (a) of the EPC agreement which talks about the handing over of land only in terms of length of the Project Highway. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/29_13052019_ Modifying the Appointed Date.pdf | Modifying the Appointed Date based on the length of project highway handed over in pursuant to Article 8 of EPC agreement - reg | 1. Pursuant to Clause 8.2.2 and 8.2.3 of the EPC Agreement, the Authority should have provided Right of way for 100% length of the project highway on appointed date plus 90 days, i.e. 11.05.2019. It is brought to your notice that this requirement has not been fulfilled by the Authority. 2. We also bring to your kind notice that the memorandum and appendix jointly signed on 11.01.2019 and submitted vide ref (3) cited above was prepared based on the available area without taking into consideration, the requirement of the contract provision as per Clause 4.1.3 (a) of the EPC agreement which talks about the handing over of land only in terms of length of the Project Highway. 3. When we started assessing the stretches affected in terms of length, we come to know that substantial length is affected due to existing buildings which are to be dismantled. The Authority has not started dismantling buildings at any location. The stretches passing through the villages are badly affected. 4. The memorandum and appendix prepared in terms of area is giving a deceptive/false picture about the availability of the vacant access. Power line and HT lines are still to be shifted and this work has not been started by the utility. 5. We have prepared a strip chart showing the existing encumbrance already enumerated in the Joint memorandum and appendix which is giving a clear picture of the percentage of length of project highway available on Appointed Date. As per this strip chart, only 63.26% of encumbrance free length has been made available. The minimum requirement of handing over of 90% of length of Project Highway as per Cl. 4.1.3 is not fulfilled for declaration of the Appointed Date. 6. Similarly, as per Clause 10.1.2 and Clause 18.1.2 of EPC agreement, the Authority Engineer should have been mobilised within 30 days from the date of signing of Agreement which was due on 14.11.2018. Even after seven months (from the date of signing of Agreement), the Authority Engineer has not been mobilised which is having its impact on the approvals of program, design and materials. 7. The Authority vide its recent circular — NHAI / Policy Guidelines / COS / 2019 / No.9.2.24 / 2019 dated 29.04.2019 has categorically mentioned that any Change of Scope / Reduction in Scope shall be finalised within a maximum period of 6 months from the Appointed Date. Hence the appointment of Authority Engineer is very crucial in deciding the COS / RIS and any further delay in appointment of Authority Engineer will have its impact on the as per the programme submitted by us as some crucial decisions and reviews are affected. Already three months have elapsed in the duration of six months given by the Authority. 8. In view of the above circumstances, we request you to kindly take a practical view and modify the Appointed Date already declared as 11.02.2019. This may be kindly modified to a date on which 90% of encumbrance free length of the Project Highway is made available to us. 9. Strip chart along with some photographs of the buildings to be dismantled, HT tower etc. are enclosed with this letter for your ready reference. This is for your information and further necessary action. | FALSE | real_data
Memorandum & Appendix | Appointed Date; Contractor's Obligations; Authority's Obligations | The memorandum and appendix prepared in terms of area is giving a deceptive/false picture about the availability of the vacant access. Power line and HT lines are still to be shifted and this work has not been started by the entity owning the utility | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/29_13052019_ Modifying the Appointed Date.pdf | Modifying the Appointed Date based on the length of project highway handed over in pursuant to Article 8 of EPC agreement - reg | 1. Pursuant to Clause 8.2.2 and 8.2.3 of the EPC Agreement, the Authority should have provided Right of way for 100% length of the project highway on appointed date plus 90 days, i.e. 11.05.2019. It is brought to your notice that this requirement has not been fulfilled by the Authority. 2. We also bring to your kind notice that the memorandum and appendix jointly signed on 11.01.2019 and submitted vide ref (3) cited above was prepared based on the available area without taking into consideration, the requirement of the contract provision as per Clause 4.1.3 (a) of the EPC agreement which talks about the handing over of land only in terms of length of the Project Highway. 3. When we started assessing the stretches affected in terms of length, we come to know that substantial length is affected due to existing buildings which are to be dismantled. The Authority has not started dismantling buildings at any location. The stretches passing through the villages are badly affected. 4. The memorandum and appendix prepared in terms of area is giving a deceptive/false picture about the availability of the vacant access. Power line and HT lines are still to be shifted and this work has not been started by the utility. 5. We have prepared a strip chart showing the existing encumbrance already enumerated in the Joint memorandum and appendix which is giving a clear picture of the percentage of length of project highway available on Appointed Date. As per this strip chart, only 63.26% of encumbrance free length has been made available. The minimum requirement of handing over of 90% of length of Project Highway as per Cl. 4.1.3 is not fulfilled for declaration of the Appointed Date. 6. Similarly, as per Clause 10.1.2 and Clause 18.1.2 of EPC agreement, the Authority Engineer should have been mobilised within 30 days from the date of signing of Agreement which was due on 14.11.2018. Even after seven months (from the date of signing of Agreement), the Authority Engineer has not been mobilised which is having its impact on the approvals of program, design and materials. 7. The Authority vide its recent circular — NHAI / Policy Guidelines / COS / 2019 / No.9.2.24 / 2019 dated 29.04.2019 has categorically mentioned that any Change of Scope / Reduction in Scope shall be finalised within a maximum period of 6 months from the Appointed Date. Hence the appointment of Authority Engineer is very crucial in deciding the COS / RIS and any further delay in appointment of Authority Engineer will have its impact on the as per the programme submitted by us as some crucial decisions and reviews are affected. Already three months have elapsed in the duration of six months given by the Authority. 8. In view of the above circumstances, we request you to kindly take a practical view and modify the Appointed Date already declared as 11.02.2019. This may be kindly modified to a date on which 90% of encumbrance free length of the Project Highway is made available to us. 9. Strip chart along with some photographs of the buildings to be dismantled, HT tower etc. are enclosed with this letter for your ready reference. This is for your information and further necessary action. | FALSE | real_data
Memorandum & Appendix | Appointed Date; Contractor's Obligations; Authority's Obligations | Hence, we are pleased to inform you that we will send our Authorized representative to the Project Site in the next week along with his team members to record the encumbrances like Buildings, Structures, Trees, Electrical poles with live lines, Electrical Crossings, visible Water & Gas pipe lines (if any) etc. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-3/2. Arranging representative to record the list of encumbrances for joint memorandum of encumbrances.pdf | Arranging representative to record the list of encumbrances for joint memorandum of encumbrances reg. | We acknowledge the receipt of your letter cited through mail on 5th May 2017, we express our great pleasure and happiness for your kind initiation. In this occasion, we would like to take the opportunity to mention as per the Clause 8.2.1 of the EPC agreement, once again for your convenience as follows “The Authority representative and the contractor shall, within 15 (fifteen) days of the date of this Agreement. inspect the Site and prepare a memorandum containing an inventory of the Site including the vacant and unencumbered land, buildings, structures, road works, frees and any other immovable property on or affached fo the sife. Subjected to the provisions of the Clause 8.2.3, such memorandum shall have appended thereto an appendix {ihe “Appendix") specifying in reasonable detail those parts of the sife to which vacant access and Right of Way has not been given to the Contractor.” Hence, we are pleased fo inform you that we will send our Authorized representative to the Project Site in the next week along with his team members fo record the encumbrances like Buildings, Structures, Trees, Electrical poles with live lines, Electrical Crossings, visible Water & Gas pipe lines {if any) efc. | FALSE | real_data
Memorandum & Appendix | Appointed Date; Contractor's Obligations; Authority's Obligations | We submitted memorandum along with strip charts of each Km, which explicitly detailed encumbrances at site. Please refer page no 131 regarding definition of ROW, which should be free from encumbrances. Also please refer letter no RCM P VR JV/MH PWD/2017-18/71, dated 10th Aug 2017, stating that land for bus bay, Toll plaza, Truck lay bye also were not handed over(Annexure-ll) . | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-3/15. Revision of Appointed date 30.01.2018.pdf | Revision of Appointed Date - Reg. | The Appointed Date intimated vide letter no. NHD/Abad/TS-2/864, dated 05th May 2017 was on the assumptions that 90% of land/ROW is available to work. Please refer our letter no. RCM PVR JV/MH PWD/2017-18/71, dated 10th Aug 2017(Annexure-l). We submitted memorandum along with strip charts of each Km, which explicitly detailed encumbrances at site. Please refer page no 131 regarding definition of ROW, which should be free from encumbrances. Also please refer letter no RCM PVR JV/MH PWD/2017-18/71, dated 10th Aug 2017, stating that land for bus bay, Toll plaza, Truck lay bye also were not handed over(Annexure-ll). Later on, when we commenced work, we faced stiff resistance from property owners which was intimated vide letter no. RCM PVR JV/MH PWD/2018-19/70, dated 10th Aug 2017 and RCM PVR JV/MH PWD/2017-18/75, dated 23rd August 2017(Annexure-lll). Surprisingly, during the site visits of Tehsildars of Beed Taluka, Paithan Taluka, Sevgaon Taluka, Pathardi Taluka and Shirur Taluka, we were given to understand that PWD is not in possession of even a square inch of land even though NH752E is plying in these talukas. Thereafter the process of Land Acquisition started. Please refer our MPR's for all the months up to Dec17 for affected chainages (Annexure-IV). Even though the length of obstructed stretches was listed in the MPRs, contractually PWD, the Authority was not in possession of even 1% land. Hence, the date decided as 02nd Jun 2017 as Appointed Date without any ROW is contractually incorrect. Please refer Executive Engineer's letter no. NHD/Abad/1787. Dated 6th Sep 2017 last Para also (Annexure-V), in this connection. The 180 days from milestone —-I should be reckoned from the Appointed Date when 90% land is made available to the contractor to proceed with work. We understand from few correspondences (copies of 5 letters enclosed) (Annexure-Vi) that the commencement of joint survey to acquire land acquisition was from Dec17 and propagation on newspapers is yet to be made. Under these circumstances, we have been attempting to convince property owners to allow us to do work and the execution is being done in the limited land available at the mercy of land owners. This has resulted in idling of equipment/demobilization of plant & machinery due to disruption and the mobilization/un gainful deployment of equipment, delay in achieving milestones etc. The detailed financial impact will be intimated to you separately, since the above disadvantages are still ongoing. We now request you to expedite acquisition of land required for execution on priority and revise the day of Appointed Date as the date when 90% land is practically available. | FALSE | real_data
Memorandum & Appendix | Appointed Date; Contractor's Obligations; Authority's Obligations | The Appointed Date was accepted and encumbrances and existing utilities were recorded in Memorandum by us. The statement is yet to be countersigned by Authority / Authority Engineer. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-3/18. Application of EOT or revision of milestone dates 14.06.2018.pdf | Application for extension of time/Revision of Mile Stone dates - Reg. | As the construction of project highway/structures could not proceed, as scheduled in the construction programme, submitted vide our letter no RCM PVR JV/MH PWD/2017-18/40, dated 02nd Jun 2018, we requested for the following. Annexure- i. Amendment of Appointment date (Please refer our letter no. RCM PVR JV/MH PWD/2018-19/151, date 30 Jan 2018) Annexure-I ii. Modification of date of milestone(s) by 120 days (Please refer our Letter no. RCM PVR JV/MH PWD/2018-19/165, date 10th Feb 2018) Annexure-III In your reply to our letter dated 10th Feb 2018 stated above, reference has been made to article/clause 10.1.3 We submit that a) as per terms of contract conditions, we submitted the original construction programme vide letter no. RCM PVR JV/MH PWD/2017-18/40, Dated 02nd Jun 2018 and Annexure-I b) the revised programme, as per article 10.1.3, vide letter no. RCM PVR JV/MH PWD/2018-19/235, date 02nd May 2018 guner regarding Appointed Date, in sl no. 3, you have stated that as the Appointed Date is declared, no EOT can be determined. We had a detailed discussion with the Team Leader on 03rd May 2018 and clarified the following. Schedule-A states that the site comprises of PROW width, which is the same as existing ROW, which implies that the land for 50.587 Km is already in possession of Authority. Please refer clause 5.2 (g) Annexure-V On good faith, The Appointed Date was accepted and encumbrances and existing utilities were recorded in Memorandum by Us. The statement is yet to be countersigned by Authority/Authority Engineer (Please refer our letter no. RCM PVR JV/MH PWD/2017-18/71, dated 10th August 2018). On commencement of works, we were intimated by revenue department of Maharashtra state (Tahsildar) that even the land on which the existing road is running is also not registered/alienated as a property/possession of PWD. Kindly refer our letter no. RCM PVR JV/MH PWD/2018-19/151, date 10th Jan 2018(Annexure-II). The reason for acceptance of Appointed Date was only good faith and the ground reality, when enlightened to Authority, the Authority commenced action for acquisition of entire land width. Kindly refer clause 5.2(h) regarding the commitment of Authority which is a warranty given by Authority Annexure-VI(a,b) The scope of the project {21.a) states that construction, as specified in schedule B & C. will conform to schedule D the technical specification. In order to achieve 80 Kmph in plain terrain & 40 kmph in hilly terrain (reference schedule B of 2.2 page 174) all the kinks, sharp Curves require geometric improvements. Hence, when the horizontal alignment gets changed/improved. deviating from the existing center line, such shifting of center line, results in additional land width requirement. Annexure-VII The assumption and decision of Authority/DPR consultants to procure land for major realignment (only for 5.35 Km) is absurd due to the reasons explained above. You have rightly stated in sl. No 4 referring to article 10.5.2/10.5.1 regarding the entitlement of extension of time by the contractor which is applicable as the works were affected and the Mile Stone could not be achieved. The details of programme of work achieved quantities etc are regularly furnished in all MPR's. The deficit in financial progress is also reflected in the S-Curve forming part of MPR. We reproduce the summary here under: SI.No. Targeted - Achieved Up to Sep 4.37 - 4.35 Oct 8.98 - 8.295 Nov 16.44 - 11.491 Dec 25.9 - 14.691 Jan 33.65 - 21.002 Feb 44.29 - 24.322 March 54.45 - 34.270 Please refer page 15 of MPR wherein a tabulation showing the affected length stretches are given in detail (copy enclosed all MPR) enable a proper evaluation of the time lost. | FALSE | real_data
Memorandum & Appendix | Appointed Date; Contractor's Obligations; Authority's Obligations | We had submitted the Memorandum / Appendix through our letter no. 71 dated 10th Aug 201 7, which indicates that the vacant access and ROW have not been granted at certain locations. Despite several requests, joint site inspection was not done and till date duly countersigned copy of the Memorandum / Appendix prepared by us is not returned till to date. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/19. Intention to issue cure period notice 02.11.2019.pdf | Intention to issue Cure Period Notice to the Authority under clause 23.2.1 for temporary demobilization | This is regarding non-availability of encroachment and encumbrance free Right of Way (ROW) along the project highway, regarding which we wish to mention the following: 1. Subsequent to the signing of EPC Agreement dated 18.04.2017 the Appointed Date was fixed on 02.06.2017 and was communicated through Authority's letter no. 1190. It was mentioned in the letter that requirements under Clause 8.2 and obligations under 4.1.3(a), Annex II of Schedule-A are fulfilled by the Authority. 2. However, when we actually mobilised to site, we realised that the Obligations are not fulfilled by the Authority, in terms of the provisions relating to ROW and Appointed Date cited above. We noticed that there is no clarity even on the existing ROW widths. 3. We had submitted the Memorandum / Appendix through our letter no. 71 dated 10th Aug 2017, which indicates that the vacant access and ROW have not been granted at certain locations. Despite several requests, joint site inspection was not done and till date duly countersigned copy of the Memorandum / Appendix prepared by us is not returned till to date. 4. We have been reporting the lack of ROW through our Monthly Progress Reports every month, in addition among various letters on the subject. It is pertinent to mention that even as on date, not a single kilometre/ hectare of additional land has been acquired by the Authority under this project. However, we had convinced the local public and could get some progress in the project due to our efforts. 5. The dispute regarding land acquisition still continues among landowners, Authority and Revenue Authority (CALA). 6. There are realignments in the project for a length of 5.350 Kms, the land acquisition of which is not yet taken up where in there are no ROW boundaries and which area can be acquired directly. Two minor bridges are held up in the realignments. 7. As mentioned in Authority’s and AE's EOT recommendations, Gazette notification for land acquisition was issued on 31st December 2018, after a lapse of 18 months from appointed date. 8. It is also mentioned in your letter no. 78 dated 02.03.2019, that the EOT duration determined was subject to the condition that the ROW for the affected reaches will be handed over to the Contractor by 31.03.2019 and all the hindrances/obstructions will also be removed by 31.03.2019. 9. However, even till date, no further land has been handed over by the Authority we regret to maintain that even the existing ROW width is disputed between land owners concerned Authority. In addition the Acquisition was to be mobilized: the area of ACQUISITION FOR DIFFERENT Land owners is a single survey numbers. Some of them in this case having different survey numbers. 10. As intimated earlier, we have been facing financial losses due to idling of resources and simultaneously incurring fixed and renewing costs. In view of the above, we intend to issue a Notice to the Authority under clause 23.2.1 of the Contract to cure their material default in handing over of ROW which has a huge material adverse effect on our works. We once again request you to pursue with the Authority in expediting handing over of the balance ROW as soon as possible. Due to the above breach of the obligations by the Authority in terms of land handing over, a situation has arisen wherein we have no option other than temporarily demobilizing from site, to avoid further financial loss to us. We shall remobilize upon intimation from you / Authority regarding the availability of balance ROW. | FALSE | real_data
Memorandum & Appendix | Appointed Date; Contractor's Obligations; Authority's Obligations | The memorandum and appendix prepared in in terms of area gave a deceptive /false picture about the availability of the vacant access. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/40_07082019_Rescheduling of Project Milestones – Request for Extension of time.pdf | Rescheduling of Project Milestones - Request for Extension of time - Reg. | The Contract agreement for the above mentioned project was executed on 15.10.2018. The appointed date was fixed as 11.02.2019 and the same was communicated vide ref (3) cited above. The Copy of the same is herewith enclosed as Annexure 1. The Authority in its response vide ref (5) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. The copy of the same is enclosed as Annexure 3. The EPC contractor vide ref (6) cited above reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that still the condition remained the same and dismantling/ removal of structures fouling was not started and shifting of Electric pole and power line also not started. The impacted length due to encroachments and encumbrances was 12.18 Km which accounted to 33.77% of the project highway. The workable length available to the Contractor based on the impacted length was 66.23% of the Project Highway length. The EPC Contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of removal of encumbrance / encroachment / obstruction. The copy of ref (7) is herewith enclosed as Annexure 4. It is almost six months since the declaration of appointed date, removal/ dismantling of structures/encroachments have not been started. Also, the work of shifting of power line and electric pole of LT line and HT lines crossings have not been started yet. The following are some of the key contractual dates and events since the inception of the project to till date: 1. Total length of the project highway: 36.076 Km 2. Date of Signing of agreement: 152018 3. Submission of Performance BG as per Clause 7.1.1 of the Contract Agreement: 262018 4. Target date for preparation of Memorandum as per Clause 8.2.1 of the Contract Agreement: 142018 5. Actual date of signing of Memorandum of land handing over: 112019 6. Declaration of appointed date by the Authority: 112019 7. ROW to be handed over as on appointed date as per Clause 8.2.2 & Annexure II: 35.468 Km | FALSE | real_data
Memorandum & Appendix | Appointed Date; Contractor's Obligations; Authority's Obligations | The memorandum and appendix prepared in in terms of area gave a deceptive /false picture about the availability of the vacant access. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20201119_SPK_AE_160_Contractor failure in achieving mile stone 1,2,&3.pdf | Six laning of Karaipcttai to Walajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - Contractor’s failure in achieving Project Mile Stone 1,2 & 3 applying of Damages vide Contract Article No. 10.3.2 & 10.3.3 - Reply made -Reg. | We are in receipt of your letter ref (26) cited above, our reply for the same is as follows: 1. The Contract Agreement for this Project was executed on 15.10.2018. The Appointed Date was fixed as 11.02.2019 and the same was communicated vide ref (2) cited above. 2. The Appointed date was declared as 11.02.2019 by the Authority taking into account the land handed over in terms of the available area without taking into consideration, the requirement of the Contract provision as per Clause 4.1.3 (a) of the EPC agreement which talks about the handing over of land only in terms of length of the Project Highway. The memorandum and appendix prepared in terms of area gave a deceptive / false picture about the availability of vacant access. Taking into consideration all the encumbrances, hindrances, utilities etc. the vacant access available on the appointed date declared was worked out and it was less than 90% and hence requested the Authority vide letter under ref (3) cited above for modification of the appointed date on which 90% of encumbrance free land would be made available to the Contractor. 3. The Authority in its response vide ref (4) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. 4. The EPC contractor vide ref (5) cited above in reply reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that the impacted length due to encroachments and encumbrances was 12.18 km which accounted to 33.77% of the project length. The workable length available to the contractor was only 66.23% of the project length. The EPC contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of encumbrance / encroachment / obstruction. | FALSE | real_data
Memorandum & Appendix | Appointed Date; Contractor's Obligations; Authority's Obligations | The memorandum and appendix prepared in in terms of area gave a deceptive /false picture about the availability of the vacant access. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20210416_SPK_AE_067_EOT request with Delay analysis.pdf | Six laning of Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V -EOT recommendation by the Authority for a period of 112 days not agreeable to the EPC Contractor — Request for considering EOT as discussed during the Review Meetings- reg | We are writing to express our concerns regarding the EOT recommendation by the Authority for a period of 112 days, which is not agreeable to the EPC Contractor. We request that the EOT be considered as discussed during the Review Meetings. The project involves six laning of the Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km 71+015 to km 107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase-V. We have referenced several documents and meetings in support of our request, and we hope for a favorable consideration. | FALSE | real_data
Memorandum & Appendix | Appointed Date; Contractor's Obligations; Authority's Obligations | Accordingly, a memorandum has been prepared by the Authority and the Contractor jointly. In this regard, Contractor informed vide reference letter cited (24), that Joint site inspection has been conducted along •with Authorized Representative of the NHAI on 11.01.2019. An inventory of the site including the vacant and unencumbered land, Buildings, structures, road works, trees and other immovable property on or attached to the site has been prepared. Details of tree cutting and Electrical utilities has also been mentioned in this Memorandum and being submitted herewith as Annexure - 2. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/189_Rescheduling of Project Milestones - EOT - 1.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under BharatmalaPariyojana on EPC mode — Rescheduling of Project Mile Stone- Request for Extension of Time -Reg. | Having gone through your documents related to Rescheduling of Project Milestone-Request for Extension of Time EoT-1 please find enclosed herewith the Authority Engineers recommendations on the same subject. This is for your information and necessary action. | FALSE | real_data
Memorandum & Appendix | Appointed Date; Contractor's Obligations; Authority's Obligations | It is well evident that the lands specified in Annexure-Il, Schedule-A of agreement are available from the day one and as on appointed date, the existing and proposed ROW is same and no parts of the site is mentioned as not available in Schedule-A and joint memorandum signed on 1 1.01.2019 except for the lands for widening of plaza at Chennasamudram. Hence authority has fulfilled the obligation. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/264_18022020_Rescheduling of Project Milestones – Request for Extension of Time.pdf | Rescheduling of Project Milestones — Request for Extension of Time -Reg. | In reference to the above-mentioned subject and Contractor letter No. SPK/KW/SAIC/NH-48/2020/001 dated 29.01.2020 regarding the rescheduling of Project Milestone, in this regard, it is submitted that AE has computed the 176 days for extension of time in Milestones I and II. The same was recommended vide AE letter No. SAICPL/Kar-Wal/H.O./NH-48/TN/2019/10451 dated 30.11.2019 to the Authority for their acceptance and further needful. However, the Contractor submitted his reservations on the computation of the nos. of delay days and requested for rescheduling of Project Milestones for a period of 324 days instead of recommended 176 nos. of days. In this regard, AE is hereby submitted point wise reply of your raised observations for your ready reference and record, please; 4. Modification of Appointed date and Handing Over in % of area. The appointed date was communicated by the Authority letter No. NHAI/PIU.K.giri/NH-4/SPK/PS/2019/972 Dated 03.06.2019. it is also submitted that as per cl 8.2.2 the authority shall provide the Right of Way to the Contractor in respect of all land included in the Appendix by the date specified in Schedule-A for those parts of the site referred to therein, or no later than 90 days of the appointed date for those parts of the site which have not been specified in Schedule-A. It is well evident that the lands specified in Annexure-II, Schedule-A of agreement are available from the day one and as on appointed date, the existing and proposed ROW is same and no parts of the site is mentioned as not available in Schedule-A and joint memorandum signed on 11.01.2019 except for the lands for widening of plaza at Chennasamudram. Hence authority has fulfilled the obligation. This was informed vide Authority letter No. NHAI/PIU.K.giri/NH-4/SPK/PS/2019/972 Dated 03.06.2019. In view of above, the request of the Contractor to modify the appointed date is not eligible as per agreement due to the following reasons (i) As per cl 4.1.3, 8.2.1 & 8.2.2, 8.2.3 — The agreement is signed on 15.10.2018 and the Joint memorandum is signed by both the parties on 30.01.2019 and appointed date is declared for the project on 11.02.2019 to commence the work. (i) The Authority Engineer vide Letter No. SAICPL/Kar-Wal/H.O./NH-48/TN/2019/10451 Dated 30.11.2019. informed that the contractor consciously agreed and signed the Joint memorandum and aware that the unencumbered and the vacant land available after joint inspection is 93.65%. (iii) Further, it is submitted that the Joint memorandum was signed on 11.01.2019 & the appointment date is declared as 11.02.2019. The Contractor has requested the Authority for modifying the Appointment date based on the length of Project Highway handed over, vide letter No. 29/SPK/Kar-Wal/PD/NHAI/ Dated 13.05.2019. On this account and in view of clause 8.3.2 of the Contract Agreement, the Contractor cited reason of land not handed over pursuant to Clause 4.1.3 (a) is not acceptable and cannot be considered for Entitlement for EOT. 2. Assessment of Hindrance length. The assessment of hindrance length is already enumerated in Point No. 01 above. It is to remind the contractor that the Joint memorandum was signed by both the parties on 30.01.2019 as per the provisions of the Contract Agreement. The AE hereby like to reiterate the clause 8.2.1. “The Authority Representative and the Contractor shall, within 30 (thirty) days of the date of this Agreement, inspect the Site and prepare a memorandum containing an inventory of the Site including the vacant and unencumbered land, buildings, structures, road works, trees and any other immovable property on or attached to the Site. Subject to the provisions of Clause 8.2.3, such memorandum shall have appended thereto an appendix (the “Appendix”) specifying in reasonable detail those parts of the Site to which vacant access and Right of Way has not been given to the Contractor. Signing of the memorandum, in two counterparts (each of which shall constitute an original), by the authorized representatives of the Parties shall be deemed to constitute a valid evidence of giving the Right of Way to the Contractor for discharging its obligations under and in accordance with the provisions of this Agreement and for no other purpose whatsoever’. AE would like to further clarify that cl. 8.3.1 last para stating that “For the avoidance of doubt, the Parties expressly agree that the Damages specified hereunder and the Time Extension specified in Clause 10.5 shall be restricted only to failure of the Authority to provide the Right of Way for and in respect of the width of the roadway, its embankment and a parallel working strip at least 3 (three) meters wide”. The width of the roadway can be treated as one side of the road since it is neither mentioned “Total width nor Full width’. Hence the Authority Engineer has done the analysis of Hindrance free length is clear with the above illustrated iteration. | FALSE | real_data
Memorandum & Appendix | Appointed Date; Contractor's Obligations; Authority's Obligations | Accordingly, a memorandum has been prepared by the Authority and the Contractor jointly. In this regard, Contractor informed vide reference letter cited (24), that Joint site inspection has been conducted along with Authorized Representative of the NHAI on 11.01.2019. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/20191130_AE_PD_10451_Recommendation of EOT I for a period of 178 days.pdf | Application for EOT | This is with reference to the captioned subject and application for EOT received from the Contractor, in this regard, it is submitted that the Contract Agreement was signed between Contractor M/s SPK & Co. and the NHAI for Six Laning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km 71+015 to Km 107+091 in the State of Tamil Nadu under NHDP Phase - V. The following are the main contractual data ; Contract Seen Date : 15/10/2018 Length of the Project 36.076 Km Project Cost INR 533,36,67,000 Appointed Date : 11/02/2019 Construction Period : 730 days from Appointed Date Scheduled Completion Date: 09/02/2021 DLP Period : 4 years from the Provisional Certificate Project Milestone ~ Days from Project Milestone Appointed Date Milestone - -1 180 Days 09/08/2019 Not achieved 365 Days 10/02/2020 To be achieved 550 Days 13/08/2020 730 Days 09/02/2021 To be Achieved In view of the above, Authority's Engineer has scrutinized the EOT application and Authority's Engineer observations are being summarized hereunder in light of the Contract Agreement; Scheduled Date ¦ Status Procurement of the Site; As mentioned in the Clause 8.2.1 of the Contract Agreement, which reproduced herewith “the Authority Representative and the Contractor shall, within 30 days of the date of this Agreement, inspect the Site and prepare a memorandum containing an inventory of the site including the vacant and unencumbered land, buildings, structures, road works, trees and any other immovable property on or attached to the site. Subject to the provisions of Clause 8.2.3, such memorandum shall have appended thereto an appendix (the “Appendix”) specifying in reasonable detail those parts of the site to which vacant access and Right of Way has not been given to the Contractor. Signing of the memorandum, in two counterparts (each of which shall constitute an original), by the Authorized Representatives of the Parties shall be deemed to constitute a valid evidence of giving the Right of Way to the Contractor for discharging its obligations under and in accordance with the provisions of this Agreement and for no other purpose whatsoever.” | FALSE | real_data
Memorandum & Appendix | Appointed Date; Contractor's Obligations; Authority's Obligations | The AE do not agree the affected length as mentioned by the Contractor, however in case Contractor feels that encumbrances are not allowing him to proceed with the works, then Contractor may discuss with the Authority for the length not handed over in the Memorandum signed between the parties in light of Article 8 Right of Way of the Contract Agreement. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/20200827_AE_SPK_394_Delay in achieving of Project Milestones I and II.pdf | Delay in achieving of Project Milestones I and II - Reg | Dear Sir, In reference to the above-mentioned subject and Contractor letter refereed at (12) cited above, we would like to submit the following para wise reply: 1. Having gone through your disagreement with the approved for 112 days vide above said reference was reviewed and our comments was communicated through Ref. No.6. However, your contention for 324 vide above said No.4 by mentioning the points such as 1. Delay in handing over of ROW, 2. Delay in shifting of utilities, 3. Delay in Appointment of Authority Engineer 4. Delay in appointment of Proof & Safety Consultant & 5. Delay in procurement of Borrow earth was already addressed in our EoT recommendations letter. Hence, we stand by our earlier observations and reiterating the same issue is unprofitable. Further your request for 324 days and justifying yourself based on the above same grounds can’t be accepted. More ever, it should be noted that reasons submitted by the Contractor for delay, are nowhere concern with the delay in the works, such appointment of AE and the procurement of borrow earth, is the prime responsibility of the Contactor. He has to apply for such permits before the Appointed Date, but unfortunately, these permits applied very late by the Contractor. 2. The Extension of Time justifying for Mile Stone -1 based on the above said/suitable grounds was recommended vide C.C. CL. No. 10.5.1. & 2. Hence any delay in the Works effected due to the above reasons is already compensated in the EOT. However, mixing the same with WHOLE WORKS according Schedule “J” Point 6 is not accepted. This should also be noted that the progress of works is not appreciable even as on date. So, Contractor requested to please expedite the work progress instead of finding the reasons of delay. 3. Same as Point No.2 4. We reiterate that the approval of EoT for 112 days from the Competent Authority based on our recommendations and their own assessment. However, your disagreement on the same issue with the Authority is noted. 5. Same as point No.4. 6. Your contention for availability of land is deviating from the Joint Memorandum signed by both the parties. This issue was already addressed in the Point No.1. However, considering the balance in shifting of electrical utilities the EoT was recommended. But your contention to delay in achieving the Mile Stone due to non-shifting total electrical utilities is not acceptable. The AE do not agree the affected length as mentioned by the Contractor, however in case Contractor feels that encumbrances are not allowing him to proceed with the works, then Contractor may discuss with the Authority for the length not handed over in the Memorandum signed between the parties in light of Article 8 Right of Way of the Contract Agreement. 7. At no point of time the Authority Engineer has agreed to your contention of 324 days EoT. The AE opinion has been submitted while processing the EOT request. Presenting your grievances will not be accepted as approval of your contention for 324 days. It is requested to such one side conclusions shall not be accepted and they are beyond the good industry practice. Noted, but as mentioned in our letter as referenced No.9 and as on date the Project Mile Stone -3 has also lapsed where in which your stage payment certification should be 60% against which you achieved only 14.38%. This clear cut indicates in lack of progress at with in the available land itself. The delay in progress with specific points has already intimated to you vide our letter No’s SAICPL/Kar-Wal/TL/NH-48/TN/02B//71/2020/361, 367 & 380 Dated 10th July 2020, 23 July and 07th August 2020 respectively. Hence once again it is asked to mobilize your resources to achieve the required progress as per the scheduled completion date. | FALSE | real_data
Memorandum & Appendix | Appointed Date; Contractor's Obligations; Authority's Obligations | 1. Handover memorandum of ROW, were signed by both the parties on 22.07.2021. 2. In the Handover memorandum of ROW, it is mentioned that ROW in a cumulative length of 83.245 Km (97.41 %) out of the total project length. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-2/1. 20210724_325_SE_Cont_Declaration of Appointed date.pdf | (R&B) NH Circle, Hyderabad — “Balance Works of Rehabilitation and Upgradation of Nakrekal to Nagarjunasagar section to 2L+PS/4L from Km 1.000 to Km 86.057 of NH-565 under NH(O) for the year 2020-21 in the State of Telangana on EPC Mode” — Declaration of Appointed date - Reg. | Adverting to the reference 1* cited, the contract agreement for the subject work has been concluded on 12.07.2021. The Executive Engineer vide reference 2" cited has informed that Joint inspection was conducted by the Executive Engineer (R&B) NH division, Kalwakurthy with Sri B. Venkat Reddy, M/s SLMI Infra Projects Private Limited, in terms of clause 8.2 of contract agreement on 22.07.2021. Subsequently, Handover memorandum of ROW, were signed by both the parties on 22.07.2021. The same is herewith enclosed. In the Handover memorandum of ROW, it is mentioned that ROW in a cumulative length of 83.245 Km (97.41%) out of the total project length of 85.451 Km is handed over to the contractor. Since the project site (including existing ROW which is more than 90% as indicated by the Executive Engineer (R&B) NH Division, Kalwakurthy) was handed over to you by the authorized representative of the Authority i.e., Executive Engineer (R&B) NH Division, Kalwakurthy as per Schedule-A and as per clause 8.2 of the agreement, therefore this day 24" of July 2021 is here by declared as the Appointed date for the project “Balance Works of Rehabilitation and Upgradation of Nakrekal to Nagarjunasagar section to 2L+PS/4L from Km 1.000 to Km 86.057 of NH-565 under NH(O) for the year 2020-21 in the State of Telangana on EPC Mode” in terms of article 3 and 8 of the contract agreement. | FALSE | real_data
Providing of GAD drawings from Railway Authorities | Authority's Obligations | Approval of GAD from Railway Authorities to enable the contractor to construct ROBs | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/188_30012019_Procurement of Site Submission of Memorandum.pdf | NHAL, PIU ~ Krishnagiri - Six Laning of (New NH48) from km 71.015 to km 107.0 - Right-of-Way Procurement of the site Submission of Memorandum-Reg. | Kindly refer to the letter 24 cited wherein it is requested to submit joint memorandum signed by the Contractor along, with status of approval of GAD for ROBs, Environmental clearance as per clause 4.13 of Agreement and status of shifting of obstructing utilities and felling of trees as per cl 9.2 & 9.4 of Agreement. 2. The status report is submitted below: (i) Joint Signed copy of the Joint Memorandum submitted by the Contractor vide reference 1 is enclosed as Annexure. (ii) The status of Obligations of the Authority as per Article 4 is as below: (a) The Authority has to give Right of Way to the Contractor no less than 90% of the total length of the Project Highway. Accordingly, as per clause 62 the memorandum containing an inventory is prepared by the Contractor and Authority. As per Appendix to memorandum the percent of unencumbered and vacant area is coming out to 93.65% which is more than 90% as per cl 8.23 of contract and also as per clause 83.2 Schedule-A, Annex-II dates for providing right of way is more than 80% of the total length of the project on appointed date in compliance to clause 10.3 of agreement, hence fulfilled the obligation. (b) Approval of GAD from Railway Authorities to enable the contractor to construct ROBs. One No of 6 lane ROB is existing and only Repair/Rehabilitation is to be carried out no fresh approval of GAD is required from Railways, hence fulfilled the obligation. (c) Environmental clearance is required under cl 4.3 and shall be procured by Authority before issue of LOA. As per MOEF Notification S.O No 2559, 22.8.2013 Environmental clearance is required for the expansion of NHs greater than 100 Km involving additional right of way or land acquisition greater than 40m on existing alignments and 60m on realignments or by passes. In this case the length of project is only 36.076 Km and additional land acquired is less than 40m, hence no clearance is required from MOEF. (d) As per Article 9.2 of Agreement the status of shifting of obstructing Utilities are as below: (i) Balance Electrical Utilities are to be shifted. The subcontractor of the terminated Concessionaire has shifted the Electrical Utilities partially and the authority has decided to shift the balance utilities through the same agency at the old SOR rates. In this regard RO Chennai vide letter No 3921 dt 03.10.2018 has forwarded report to GM(T)-TN NHAI HQ Delhi. Approval is awaited. (ii) Tree cutting is already completed and few left out trees were identified and cutting is under progress. Hence it is requested to communicate appointed date for the project at the earliest. | FALSE | real_data
Providing of GAD drawings from Railway Authorities | Authority's Obligations | GAD Approval from the Railway Authorities. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-2/2. 20231215_165_Cont_AE_Accumulated delays till Nov-23.pdf | Notice under clause 10.5.(V)- Accumulated delays till 30" November 2023 - Reg. | We refer to the above letters, wherein we have intimated the Authority about the following issues/Bottlenecks prevailing in the project which are hampering the progress of the works: 1. Handing over of the Balance land. 2. Clearance from the Forest department. 3. GAD Approval from the Railway Authorities. However, the issues are yet to be cleared and hence the same continue to hamper the progress. In this regard, pursuant to clause 10.5.(V) of the EPC Contract agreement, we herewith submit the accumulated delays as on 30" November 2023. SLMI — DMCPL (JV) (A Joint Venture of M/s. SLMI Infra Projects Private Limited & M/s. Dwarakamai Constructions Pvt. Ltd.) H.No.1223, Street No.5, Tarnaka, Secunderabad — 500017. Accumulated delays Till 30-Nov-2023. Description of Delay Events From the above the total accumulated delay as on 30.11.2023 is 303 days. Handing over of ROW/Construction Zone on at least 90% of the total length of the Project Highway Still Continuing. Handing over of the balance Land (to be handed over in 150 days) Still Continuing. Clearance from Forest Department Still Continuing. GAD Approval from Railway Authorities ~ Owing to the above delays, we may not be able to achieve Milestone-II which is due in April’24. It may please be noted that we may run out of work fronts and our resources may become idle as all the available work fronts are already being tackled. In view of the above, we request your office to pursue with the Authority to clear the issues at the earliest and provide hindrance free work fronts over the entire length of the Project Highway. | FALSE | real_data
Providing of GAD drawings from Railway Authorities | Authority's Obligations | GAD Approval from the Railway Authorities. | synthetic_template_20250913 | Notice under clause 10.5.(V)- Accumulated delays till 30" November 2023 - Reg. | We refer to the above letters, wherein we have intimated the Authority about the following issues/Bottlenecks prevailing in the project which are hampering the progress of the works: 1. Handing over of the Balance land. 2. Clearance from the Forest department. 3. GAD Approval from the Railway Authorities. However, the issues are yet to be cleared and hence the same continue to hamper the progress. In this regard, pursuant to clause 10.5.(V) of the EPC Contract agreement, we herewith submit the accumulated delays as on 30" November 2023. SLMI — DMCPL (JV) (A Joint Venture of M/s. SLMI Infra Projects Private Limited & M/s. Dwarakamai Constructions Pvt. Ltd.) H.No.1223, Street No.5, Tarnaka, Secunderabad — 500017. Accumulated delays Till 30-Nov-2023. Description of Delay Events From the above the total accumulated delay as on 30.11.2023 is 303 days. Handing over of ROW/Construction Zone on at least 90% of the total length of the Project Highway Still Continuing. Handing over of the balance Land (to be handed over in 150 days) Still Continuing. Clearance from Forest Department Still Continuing. GAD Approval from Railway Authorities ~ Owing to the above delays, we may not be able to achieve Milestone-II which is due in April’24. It may please be noted that we may run out of work fronts and our resources may become idle as all the available work fronts are already being tackled. In view of the above, we request your office to pursue with the Authority to clear the issues at the earliest and provide hindrance free work fronts over the entire length of the Project Highway. Please confirm receipt of this correspondence. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Providing of GAD drawings from Railway Authorities | Authority's Obligations | The Authority was supposed to provide GAD approval Irom he Railway Authorities within 60 clays Irom he Appointed Daei | synthetic_template_20250913 | Request for General Arrangement Drawing Approval (GAD) of RUB at Km.16+676 - Reg. | This is with reference to the construction of Road under Bridge (RUB) at km 16+676 as per Clause 7.4.3 of the Schedule-B of the EPC Contract Agreement (CA). As per Clause 3.1 (iii) of the CA, “The Authority shall, upon submission of the Performance Security as per the RFP by the Contractor, shall provide to the Contractor: (a) No less than 90% (ninety per cent) of the required Right of Way of the Construction Zone of total length of the Project Highway within a period of 30 (thirty) days from the date of this Agreement, which shall be in contiguous stretches of length not less than 5 (five) kilometer. (b) approval of the general arrangement drawings (the "GAD") from railway authorities to enable the Contractor to construct road over- bridges/ under- bridges at level crossings on the Project Highway in accordance with the Specifications and Standards, and subject to the terms and conditions specified in such approval, within a period of 60 (sixty) days from the Appointed Date, and reimbursement of all the costs and expenses paid by the Contractor to the railway authorities for and in respect of the road over-bridges/ under bridges; and (c) all environmental clearances as he 4.3.” As per Clause 3.1 (ili) (6) mentioned above, the Authority was supposed to provide GAD approval from the Railway Authorities within 60 days from the Appointed Date (i.e., 1-Apr-23 which is within 60 days from 31.01.2023). However, even as on date, the GAD is yet to be provided by the Authority. Thus, there is a delay of around 213 days up to 31-Oct-2023, in providing the GAD. As you are aware, even JEWS approval of the GAD, the construction of Se has to be done delay in the approval of the GAD may disturb the planned schedule, and may lead to ding of our resources and delay in the completion of the Project. In view of the above, we request the Authority to provide the GAD approval from the Railway Authorities at the earliest. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Providing of GAD drawings from Railway Authorities | Authority's Obligations | Approval of GAD from Railway Authorities to enable the contractor to construct ROBs | synthetic_template_20250913 | NHAL, PIU ~ Krishnagiri - Six Laning of (New NH48) from km 71.015 to km 107.0 - Right-of-Way Procurement of the site Submission of Memorandum-Reg. | Kindly refer to the letter 24 cited wherein it is requested to submit joint memorandum signed by the Contractor along, with status of approval of GAD for ROBs, Environmental clearance as per clause 4.13 of Agreement and status of shifting of obstructing utilities and felling of trees as per cl 9.2 & 9.4 of Agreement. 2. The status report is submitted below: (i) Joint Signed copy of the Joint Memorandum submitted by the Contractor vide reference 1 is enclosed as Annexure. (ii) The status of Obligations of the Authority as per Article 4 is as below: (a) The Authority has to give Right of Way to the Contractor no less than 90% of the total length of the Project Highway. Accordingly, as per clause 62 the memorandum containing an inventory is prepared by the Contractor and Authority. As per Appendix to memorandum the percent of unencumbered and vacant area is coming out to 93.65% which is more than 90% as per cl 8.23 of contract and also as per clause 83.2 Schedule-A, Annex-II dates for providing right of way is more than 80% of the total length of the project on appointed date in compliance to clause 10.3 of agreement, hence fulfilled the obligation. (b) Approval of GAD from Railway Authorities to enable the contractor to construct ROBs. One No of 6 lane ROB is existing and only Repair/Rehabilitation is to be carried out no fresh approval of GAD is required from Railways, hence fulfilled the obligation. (c) Environmental clearance is required under cl 4.3 and shall be procured by Authority before issue of LOA. As per MOEF Notification S.O No 2559, 22.8.2013 Environmental clearance is required for the expansion of NHs greater than 100 Km involving additional right of way or land acquisition greater than 40m on existing alignments and 60m on realignments or by passes. In this case the length of project is only 36.076 Km and additional land acquired is less than 40m, hence no clearance is required from MOEF. (d) As per Article 9.2 of Agreement the status of shifting of obstructing Utilities are as below: (i) Balance Electrical Utilities are to be shifted. The subcontractor of the terminated Concessionaire has shifted the Electrical Utilities partially and the authority has decided to shift the balance utilities through the same agency at the old SOR rates. In this regard RO Chennai vide letter No 3921 dt 03.10.2018 has forwarded report to GM(T)-TN NHAI HQ Delhi. Approval is awaited. (ii) Tree cutting is already completed and few left out trees were identified and cutting is under progress. Hence it is requested to communicate appointed date for the project at the earliest. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Providing of GAD drawings from Railway Authorities | Authority's Obligations | The Authority was supposed to provide GAD approval Irom he Railway Authorities within 60 clays Irom he Appointed Daei | synthetic_template_20250913 | Request for General Arrangement Drawing Approval (GAD) of RUB at Km.16+676 - Reg. | This is with reference to the construction of Road under Bridge (RUB) at km 16+676 as per Clause 7.4.3 of the Schedule-B of the EPC Contract Agreement (CA). As per Clause 3.1 (iii) of the CA, “The Authority shall, upon submission of the Performance Security as per the RFP by the Contractor, shall provide to the Contractor: (a) No less than 90% (ninety per cent) of the required Right of Way of the Construction Zone of total length of the Project Highway within a period of 30 (thirty) days from the date of this Agreement, which shall be in contiguous stretches of length not less than 5 (five) kilometer. (b) approval of the general arrangement drawings (the "GAD") from railway authorities to enable the Contractor to construct road over- bridges/ under- bridges at level crossings on the Project Highway in accordance with the Specifications and Standards, and subject to the terms and conditions specified in such approval, within a period of 60 (sixty) days from the Appointed Date, and reimbursement of all the costs and expenses paid by the Contractor to the railway authorities for and in respect of the road over-bridges/ under bridges; and (c) all environmental clearances as he 4.3.” As per Clause 3.1 (ili) (6) mentioned above, the Authority was supposed to provide GAD approval from the Railway Authorities within 60 days from the Appointed Date (i.e., 1-Apr-23 which is within 60 days from 31.01.2023). However, even as on date, the GAD is yet to be provided by the Authority. Thus, there is a delay of around 213 days up to 31-Oct-2023, in providing the GAD. As you are aware, even JEWS approval of the GAD, the construction of Se has to be done delay in the approval of the GAD may disturb the planned schedule, and may lead to ding of our resources and delay in the completion of the Project. In view of the above, we request the Authority to provide the GAD approval from the Railway Authorities at the earliest. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Providing of GAD drawings from Railway Authorities | Authority's Obligations | GAD Approval from the Railway Authorities. | synthetic_template_20250913 | Notice under clause 10.5.(V)- Accumulated delays till 30" November 2023 - Reg. | We refer to the above letters, wherein we have intimated the Authority about the following issues/Bottlenecks prevailing in the project which are hampering the progress of the works: 1. Handing over of the Balance land. 2. Clearance from the Forest department. 3. GAD Approval from the Railway Authorities. However, the issues are yet to be cleared and hence the same continue to hamper the progress. In this regard, pursuant to clause 10.5.(V) of the EPC Contract agreement, we herewith submit the accumulated delays as on 30" November 2023. SLMI — DMCPL (JV) (A Joint Venture of M/s. SLMI Infra Projects Private Limited & M/s. Dwarakamai Constructions Pvt. Ltd.) H.No.1223, Street No.5, Tarnaka, Secunderabad — 500017. Accumulated delays Till 30-Nov-2023. Description of Delay Events From the above the total accumulated delay as on 30.11.2023 is 303 days. Handing over of ROW/Construction Zone on at least 90% of the total length of the Project Highway Still Continuing. Handing over of the balance Land (to be handed over in 150 days) Still Continuing. Clearance from Forest Department Still Continuing. GAD Approval from Railway Authorities ~ Owing to the above delays, we may not be able to achieve Milestone-II which is due in April’24. It may please be noted that we may run out of work fronts and our resources may become idle as all the available work fronts are already being tackled. In view of the above, we request your office to pursue with the Authority to clear the issues at the earliest and provide hindrance free work fronts over the entire length of the Project Highway. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Clearances from Environmental & Forest Departments | Authority's Obligations | we request your office to kindly arrange for necessary approval from the Forest Department. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-1/3. Change in location of flyover @72+760.pdf | Change of location for Flyover @ 72+760 - Reg. | We wish to draw your kind attention to our site visit along with RO regarding various issues. As per Schedule-B of the Contract Agreement (CA), a Flyover / Animal Underpass (3v x 25 m) is to be constructed at Km. 72+760 and the stretch falls under Wildlife Zone. The width of the structure is 12m, resting on RCC open foundations and I-girders. The applicable cross-section on the approaches of the flyover as per Schedule-B is TCS-9 for the stretch from Km. 72+350 to Km. 73+290. As per Annex-ll of Schedule-A, the Right of Way (ROW) is 20m between Km 72+460 to Km 73+396. The scope of work includes olf the existing 7m road to 12.9m overall width. The existing road level is 200.399 and the FRL of the proposed structure is 208.685, thus the road top level is increasing by more than 8m at this location. As you are aware, two High Tension (HT) grid lines are crossing the Project Highway at Km. 72+850 and Km 72+940 at a height of 10.2 m and 7.6 m respectively from the existing road top, with FRL of 208.403 and 207.251 respectively. Hence the minimum vertical clearance requirement of 8.5m (5.5m vertical clearance + 3m for Induction) is not being met at these two locations. During the recent Site Visit with RO and your good self, this issue was discussed at site and it Was proposed to shift the Flyover to Km. 72+650. The original ground level at this location is 4m below the existing road top level, i.e., approximately 196.77m. Thus, the structure can be fitted as per the proposed GAD in the CA, simultaneously ensuring the vertical clearance between the ground level and soffit of the structure. In view of the above, we request your office to kindly arrange for necessary approval from the Forest Department, to proceed with construction of the Flyover/Animal Underpass at the revised location at the earliest. | FALSE | real_data
Clearances from Environmental & Forest Departments | Authority's Obligations | Joint signed copy of the Joint Memorandum submitted by the contractor | synthetic_template_20250913 | NHAL, PIU ~ Krishnagiri - Six Laning of (New NH48) from km 71.015 to km 107.0 - Right-of-Way Procurement of the site Submission of Memorandum-Reg. | Kindly be informed that Kindly refer to the letter 24 cited wherein it is requested to submit joint memorandum signed by the Contractor along, with status of approval of GAD for ROBs, Environmental clearance as per clause 4.13 of Agreement and status of shifting of obstructing utilities and felling of trees as per cl 9.2 & 9.4 of Agreement. 2. The status report is submitted below: (i) Joint Signed copy of the Joint Memorandum submitted by the Contractor vide reference 1 is enclosed as Annexure. (ii) The status of Obligations of the Authority as per Article 4 is as below: (a) The Authority has to give Right of Way to the Contractor no less than 90% of the total length of the Project Highway. Accordingly, as per clause 62 the memorandum containing an inventory is prepared by the Contractor and Authority. As per Appendix to memorandum the percent of unencumbered and vacant area is coming out to 93.65% which is more than 90% as per cl 8.23 of contract and also as per clause 83.2 Schedule-A, Annex-II dates for providing right of way is more than 80% of the total length of the project on appointed date in compliance to clause 10.3 of agreement, hence fulfilled the obligation. (b) Approval of GAD from Railway Authorities to enable the contractor to construct ROBs. One No of 6 lane ROB is existing and only Repair/Rehabilitation is to be carried out no fresh approval of GAD is required from Railways, hence fulfilled the obligation. (c) Environmental clearance is required under cl 4.3 and shall be procured by Authority before issue of LOA. As per MOEF Notification S.O No 2559, 22.8.2013 Environmental clearance is required for the expansion of NHs greater than 100 Km involving additional right of way or land acquisition greater than 40m on existing alignments and 60m on realignments or by passes. In this case the length of project is only 36.076 Km and additional land acquired is less than 40m, hence no clearance is required from MOEF. (d) As per Article 9.2 of Agreement the status of shifting of obstructing Utilities are as below: (i) Balance Electrical Utilities are to be shifted. The subcontractor of the terminated Concessionaire has shifted the Electrical Utilities partially and the authority has decided to shift the balance utilities through the same agency at the old SOR rates. In this regard RO Chennai vide letter No 3921 dt 03.10.2018 has forwarded report to GM(T)-TN NHAI HQ Delhi. Approval is awaited. (ii) Tree cutting is already completed and few left out trees were identified and cutting is under progress. Hence it is requested to communicate appointed date for the project at the earliest. We await your further instructions. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Clearances from Environmental & Forest Departments | Authority's Obligations | we request your office to kindly arrange for necessary approval from the Forest Department. | synthetic_template_20250913 | Change of location for Flyover @ 72+760 - Reg. | It is brought to your attention that We wish to draw your kind attention to our site visit along with RO regarding various issues. As per Schedule-B of the Contract Agreement (CA), a Flyover / Animal Underpass (3v x 25 m) is to be constructed at Km. 72+760 and the stretch falls under Wildlife Zone. The width of the structure is 12m, resting on RCC open foundations and I-girders. The applicable cross-section on the approaches of the flyover as per Schedule-B is TCS-9 for the stretch from Km. 72+350 to Km. 73+290. As per Annex-ll of Schedule-A, the Right of Way (ROW) is 20m between Km 72+460 to Km 73+396. The scope of work includes olf the existing 7m road to 12.9m overall width. The existing road level is 200.399 and the FRL of the proposed structure is 208.685, thus the road top level is increasing by more than 8m at this location. As you are aware, two High Tension (HT) grid lines are crossing the Project Highway at Km. 72+850 and Km 72+940 at a height of 10.2 m and 7.6 m respectively from the existing road top, with FRL of 208.403 and 207.251 respectively. Hence the minimum vertical clearance requirement of 8.5m (5.5m vertical clearance + 3m for Induction) is not being met at these two locations. During the recent Site Visit with RO and your good self, this issue was discussed at site and it Was proposed to shift the Flyover to Km. 72+650. The original ground level at this location is 4m below the existing road top level, i.e., approximately 196.77m. Thus, the structure can be fitted as per the proposed GAD in the CA, simultaneously ensuring the vertical clearance between the ground level and soffit of the structure. In view of the above, we request your office to kindly arrange for necessary approval from the Forest Department, to proceed with construction of the Flyover/Animal Underpass at the revised location at the earliest. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Clearances from Environmental & Forest Departments | Authority's Obligations | we request your office to kindly arrange for necessary approval from the Forest Department. | synthetic_template_20250913 | Change of location for Flyover @ 72+760 - Reg. | We wish to draw your kind attention to our site visit along with RO regarding various issues. As per Schedule-B of the Contract Agreement (CA), a Flyover / Animal Underpass (3v x 25 m) is to be constructed at Km. 72+760 and the stretch falls under Wildlife Zone. The width of the structure is 12m, resting on RCC open foundations and I-girders. The applicable cross-section on the approaches of the flyover as per Schedule-B is TCS-9 for the stretch from Km. 72+350 to Km. 73+290. As per Annex-ll of Schedule-A, the Right of Way (ROW) is 20m between Km 72+460 to Km 73+396. The scope of work includes olf the existing 7m road to 12.9m overall width. The existing road level is 200.399 and the FRL of the proposed structure is 208.685, thus the road top level is increasing by more than 8m at this location. As you are aware, two High Tension (HT) grid lines are crossing the Project Highway at Km. 72+850 and Km 72+940 at a height of 10.2 m and 7.6 m respectively from the existing road top, with FRL of 208.403 and 207.251 respectively. Hence the minimum vertical clearance requirement of 8.5m (5.5m vertical clearance + 3m for Induction) is not being met at these two locations. During the recent Site Visit with RO and your good self, this issue was discussed at site and it Was proposed to shift the Flyover to Km. 72+650. The original ground level at this location is 4m below the existing road top level, i.e., approximately 196.77m. Thus, the structure can be fitted as per the proposed GAD in the CA, simultaneously ensuring the vertical clearance between the ground level and soffit of the structure. In view of the above, we request your office to kindly arrange for necessary approval from the Forest Department, to proceed with construction of the Flyover/Animal Underpass at the revised location at the earliest. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Clearances from Environmental & Forest Departments | Authority's Obligations | we request your office to kindly arrange for necessary approval from the Forest Department. | synthetic_template_20250913 | Change of location for Flyover @ 72+760 - Reg. | This is to notify you that We wish to draw your kind attention to our site visit along with RO regarding various issues. As per Schedule-B of the Contract Agreement (CA), a Flyover / Animal Underpass (3v x 25 m) is to be constructed at Km. 72+760 and the stretch falls under Wildlife Zone. The width of the structure is 12m, resting on RCC open foundations and I-girders. The applicable cross-section on the approaches of the flyover as per Schedule-B is TCS-9 for the stretch from Km. 72+350 to Km. 73+290. As per Annex-ll of Schedule-A, the Right of Way (ROW) is 20m between Km 72+460 to Km 73+396. The scope of work includes olf the existing 7m road to 12.9m overall width. The existing road level is 200.399 and the FRL of the proposed structure is 208.685, thus the road top level is increasing by more than 8m at this location. As you are aware, two High Tension (HT) grid lines are crossing the Project Highway at Km. 72+850 and Km 72+940 at a height of 10.2 m and 7.6 m respectively from the existing road top, with FRL of 208.403 and 207.251 respectively. Hence the minimum vertical clearance requirement of 8.5m (5.5m vertical clearance + 3m for Induction) is not being met at these two locations. During the recent Site Visit with RO and your good self, this issue was discussed at site and it Was proposed to shift the Flyover to Km. 72+650. The original ground level at this location is 4m below the existing road top level, i.e., approximately 196.77m. Thus, the structure can be fitted as per the proposed GAD in the CA, simultaneously ensuring the vertical clearance between the ground level and soffit of the structure. In view of the above, we request your office to kindly arrange for necessary approval from the Forest Department, to proceed with construction of the Flyover/Animal Underpass at the revised location at the earliest. We appreciate your cooperation in this regard. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Clearances from Environmental & Forest Departments | Authority's Obligations | we request your office to kindly arrange for necessary approval from the Forest Department. | synthetic_template_20250913 | Change of location for Flyover @ 72+760 - Reg. | This is to notify you that We wish to draw your kind attention to our site visit along with RO regarding various issues. As per Schedule-B of the Contract Agreement (CA), a Flyover / Animal Underpass (3v x 25 m) is to be constructed at Km. 72+760 and the stretch falls under Wildlife Zone. The width of the structure is 12m, resting on RCC open foundations and I-girders. The applicable cross-section on the approaches of the flyover as per Schedule-B is TCS-9 for the stretch from Km. 72+350 to Km. 73+290. As per Annex-ll of Schedule-A, the Right of Way (ROW) is 20m between Km 72+460 to Km 73+396. The scope of work includes olf the existing 7m road to 12.9m overall width. The existing road level is 200.399 and the FRL of the proposed structure is 208.685, thus the road top level is increasing by more than 8m at this location. As you are aware, two High Tension (HT) grid lines are crossing the Project Highway at Km. 72+850 and Km 72+940 at a height of 10.2 m and 7.6 m respectively from the existing road top, with FRL of 208.403 and 207.251 respectively. Hence the minimum vertical clearance requirement of 8.5m (5.5m vertical clearance + 3m for Induction) is not being met at these two locations. During the recent Site Visit with RO and your good self, this issue was discussed at site and it Was proposed to shift the Flyover to Km. 72+650. The original ground level at this location is 4m below the existing road top level, i.e., approximately 196.77m. Thus, the structure can be fitted as per the proposed GAD in the CA, simultaneously ensuring the vertical clearance between the ground level and soffit of the structure. In view of the above, we request your office to kindly arrange for necessary approval from the Forest Department, to proceed with construction of the Flyover/Animal Underpass at the revised location at the earliest. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Utility shifting | Authority's Obligations; Contractor's Obligations; EoT | Authority has decided to shift the balance utilities though same agency | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/188_30012019_Procurement of Site Submission of Memorandum.pdf | NHAL, PIU ~ Krishnagiri - Six Laning of (New NH48) from km 71.015 to km 107.0 - Right-of-Way Procurement of the site Submission of Memorandum-Reg. | Kindly refer to the letter 24 cited wherein it is requested to submit joint memorandum signed by the Contractor along, with status of approval of GAD for ROBs, Environmental clearance as per clause 4.13 of Agreement and status of shifting of obstructing utilities and felling of trees as per cl 9.2 & 9.4 of Agreement. 2. The status report is submitted below: (i) Joint Signed copy of the Joint Memorandum submitted by the Contractor vide reference 1 is enclosed as Annexure. (ii) The status of Obligations of the Authority as per Article 4 is as below: (a) The Authority has to give Right of Way to the Contractor no less than 90% of the total length of the Project Highway. Accordingly, as per clause 62 the memorandum containing an inventory is prepared by the Contractor and Authority. As per Appendix to memorandum the percent of unencumbered and vacant area is coming out to 93.65% which is more than 90% as per cl 8.23 of contract and also as per clause 83.2 Schedule-A, Annex-II dates for providing right of way is more than 80% of the total length of the project on appointed date in compliance to clause 10.3 of agreement, hence fulfilled the obligation. (b) Approval of GAD from Railway Authorities to enable the contractor to construct ROBs. One No of 6 lane ROB is existing and only Repair/Rehabilitation is to be carried out no fresh approval of GAD is required from Railways, hence fulfilled the obligation. (c) Environmental clearance is required under cl 4.3 and shall be procured by Authority before issue of LOA. As per MOEF Notification S.O No 2559, 22.8.2013 Environmental clearance is required for the expansion of NHs greater than 100 Km involving additional right of way or land acquisition greater than 40m on existing alignments and 60m on realignments or by passes. In this case the length of project is only 36.076 Km and additional land acquired is less than 40m, hence no clearance is required from MOEF. (d) As per Article 9.2 of Agreement the status of shifting of obstructing Utilities are as below: (i) Balance Electrical Utilities are to be shifted. The subcontractor of the terminated Concessionaire has shifted the Electrical Utilities partially and the authority has decided to shift the balance utilities through the same agency at the old SOR rates. In this regard RO Chennai vide letter No 3921 dt 03.10.2018 has forwarded report to GM(T)-TN NHAI HQ Delhi. Approval is awaited. (ii) Tree cutting is already completed and few left out trees were identified and cutting is under progress. Hence it is requested to communicate appointed date for the project at the earliest. | FALSE | real_data
Utility shifting | Authority's Obligations; Contractor's Obligations; EoT | Action is already taken to by the authority to shift the balance affected Electric poles the authority has issued approval to M/s Sai Sri Engineers | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/972_03062019_Non acceptance of shifting of appointed date.pdf | NHAI, PIU - Krishnagiri — Six Laning of Karaipettai to Walajhapet section of NH+4 ( New NH~8) from km.71.015 to km.107.091 in the State of Tamil Nadu under NHDP Phase-V under EPC Mode- M's SPK &Co —Request for modification of Appointed date -Reg. | With reference to the letter 1* cited the following observations are made Para-I:- As per Annexure-II , Schedule-A dates for providing Right of Way the existing and proposed ROW is 60m at Plaza is 80m and is available as On appointed date . As per cl 8.2.2 the authority shall provide the Right of Way to the Contractor in respect of all land included in the Appendix by the date specified in Schedule-A for those parts of the site referred to therein, or no later than 90 days of the appointed date for those parts of the site which have not been specified in Schedule-A. From the above it is evident that the lands specified in Annexure-II, Schedule-A of agreement are available from the day one and as on appointed date, the existing and proposed ROW is same and no parts of the site is mentioned as not available in Schedule-A and joint memorandum signed on 11.01.2019 except for the lands for widening of plaza at Chennasamudram.Hence authority has fulfilled the obligation. ParaAs per cl 4.1.3 (a) — the authority shall provide to the contractor upon receiving the performance security under cl 7.1.] sthe right of way in accordance with the provisions of cl $.2 and 8.3 , within a period of 30 days from the date of this agreement , on no less than 90% of the total length of the project highway . As per joint memorandum signed by both the parties the length of project Highway covered is 36.076 Km _ on both sides and the total balance to be handed over ( length affected due to obstructions of structures and utilities ) is 6.35% ie 2.29 Km ( 36.076*6.35/100). Hence in length terms of the project highway also satisfied. It is a fact that the length affected due to structures and utility shifting for a length of 2.29 Km is not available to the contractor as on date. Para-4 — The joint memorandum signed by both the parties and as explained in para-3 the authority has taken action in shifting the Electrical utilities and dismantling of structures and the af! fected length is 2.29 Km out of total length of 36.076 Km. The unencumbered and vacant area available to the Contractor as per signed JM is 33.786 Km. Para-5 — From the strip map submitted the information regarding two types of encumbrances shown (Blue & Red Colour) and the Electrical poles the offset from centre line is not shown in the strip map. From the joint memorandum signed by both the parties the structures to be dismantled are almost at the edge of ROW and the length of highway affected is only 2.29 Km ,hence the encumbrance length handed over is coming out to 33.786 Km and hence the obligations are fulfilled by the authority as per cl 4.1.3 of agreement .Details is enclosed as Annexure-1. Para-6 — As per cl 10.1.2 of agreement the Authority has appointed the Authority Engineer M/s SA Infrastructure Consultants Pvt Ltd on 20.02.2019 and Mobilization is under progress .The Contractor has not submitted any designs for approval of AE. Para-7 — Mobilization of A E is under progress. ParaThe request of the Contractor to modify the appointed date is not eligible as per agreement due to the following reasons (i) As per cl 4.1.3, 8.2.1 & 8.2.2, 8.2.3-The agreement is signed on 15.10.2018 and the Joint memorandum is signed by both the parties on 30.01.2019 and appointed date is declared for the project on 11.2.2019 to commence the work. (it) As per cl 10.1.1 of agreement, the contractor has not submitted the details till date to the Authority. Further the Designs and Drawings as per cl 10.2.1 of agreement is not submitted for review of the Authority Engineer. (iii) The Camp Office and the laboratory of the Contractor is not yet established and Staff is not mobilized at site. (iv) The Contractor has not submitted the fulfilment of the obligations of the Contractor as per Article 3 of the agreement. | FALSE | real_data
Utility shifting | Authority's Obligations; Contractor's Obligations; EoT | two High Tension (HT) grid lines are crossing the Project Highway at Km. 72+850 and Km 72+940. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-1/3. Change in location of flyover @72+760.pdf | Change of location for Flyover @ 72+760 - Reg. | We wish to draw your kind attention to our site visit along with RO regarding various issues. As per Schedule-B of the Contract Agreement (CA), a Flyover / Animal Underpass (3v x 25 m) is to be constructed at Km. 72+760 and the stretch falls under Wildlife Zone. The width of the structure is 12m, resting on RCC open foundations and I-girders. The applicable cross-section on the approaches of the flyover as per Schedule-B is TCS-9 for the stretch from Km. 72+350 to Km. 73+290. As per Annex-ll of Schedule-A, the Right of Way (ROW) is 20m between Km 72+460 to Km 73+396. The scope of work includes olf the existing 7m road to 12.9m overall width. The existing road level is 200.399 and the FRL of the proposed structure is 208.685, thus the road top level is increasing by more than 8m at this location. As you are aware, two High Tension (HT) grid lines are crossing the Project Highway at Km. 72+850 and Km 72+940 at a height of 10.2 m and 7.6 m respectively from the existing road top, with FRL of 208.403 and 207.251 respectively. Hence the minimum vertical clearance requirement of 8.5m (5.5m vertical clearance + 3m for Induction) is not being met at these two locations. During the recent Site Visit with RO and your good self, this issue was discussed at site and it Was proposed to shift the Flyover to Km. 72+650. The original ground level at this location is 4m below the existing road top level, i.e., approximately 196.77m. Thus, the structure can be fitted as per the proposed GAD in the CA, simultaneously ensuring the vertical clearance between the ground level and soffit of the structure. In view of the above, we request your office to kindly arrange for necessary approval from the Forest Department, to proceed with construction of the Flyover/Animal Underpass at the revised location at the earliest. | FALSE | real_data
Utility shifting | Authority's Obligations; Contractor's Obligations; EoT | there are existing utilities within the proposed Right of Way which need to be relocated. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-1/4. Additional land required @20+100 VOP.pdf | Additional Land required at 20+100 VOP - Reg. | With reference to the subject matter, we wish to bring to your kind notice that as per Schedule-B of the Contract Agreement (CA), an Overpass (VOP) should be constructed at Km 20+100 along the N.A.M expressway, as a Grade separated structure. As per the typical cross section (TCS-6), there is no provision for utility corridor at the edge of the slip roads. The available ROW of 45m is not adequate to accommodate the carriageways, slip roads, drain along with utility corridors on both sides. However, there are existing utilities within the proposed Right of Way which need to be relocated. In view of the above we request you to take-up the issue with the concerned Authorities and take necessary action for acquiring the necessary land and resolve the issue so that the work progress will not be affected. | FALSE | real_data
Utility shifting | Authority's Obligations; Contractor's Obligations; EoT | Subjected to the provisions of the Clause 9.2, kindly send your recommended letter to the concerned authorities (Electrical Dept, Water Supply Board, Forest/Revenue, etc.,) for the preparation of estimates for the shifting of Obstruction Utilities as cited above. The list of utilities for the entire stretch will submit to your office in due course of time | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-3/6. Shifting of obstruction utilities 13.06.2017.pdf | Rehabilitation and Upgradation of Ghogaspargaon-Phulsangvi-Ukhandachakla-Dahiwandi-Shirur-Rakshasbhuvan-kholayachiwadi-Karegaon-Dongarkini-Chumbli-Patoda-Dighol Road (SH-62) Kharda. From KM 0+000 to KM 56+000 to two lanes with paved shoulders” (Project Length 55.937 KM) on EPC basis in the State of Maharashtra (Package — ¦) - Shifting of Obstruction Utilities | This has reference to the above mentioned subject and as per Contract Agreement Article No.9, Clause 9.2 of the EPC agreement, once again for your convenience as follows “The Contractor shall, in accordance with Applicable Laws and with assistance of the Authority, cause shifting of any utility {including electric lines, water pipes and telephone cable) to an appropriate location or alignment, if such utility or obstruction adversely affects the execution of the Works or Maintenance of the Project Highway. The actual cost of such shifting, as approved and communicated by the entity owning the utility, shall be paid by the Contractor and reimbursed by the Authority to the Contractor” Subjected to the provisions of the Clause 9.2, kindly send your recommended letter fo the concerned authorities (Electrical Dept, Water Supply Board, Foresi/Revenue, etc.) for the preparation of estimates for the shifting of Obstruction Utilities as cited above. The list of utilities for the entire stretch will submit to your office in due course of time. | FALSE | real_data
Utility shifting | Authority's Obligations; Contractor's Obligations; EoT | The contractor has made efforts to construct embankments with electrical posts in the middle, to migrate the delay, to some extent. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-3/18. Application of EOT or revision of milestone dates 14.06.2018.pdf | Application for extension of time/Revision of Mile Stone dates - Reg. | As the construction of project highway/structures could not proceed, as scheduled in the construction programme, submitted vide our letter no RCM PVR JV/MH PWD/2017-18/40, dated 02nd Jun 2018, we requested for the following. Annexure- i. Amendment of Appointment date (Please refer our letter no. RCM PVR JV/MH PWD/2018-19/151, date 30 Jan 2018) Annexure-I ii. Modification of date of milestone(s) by 120 days (Please refer our Letter no. RCM PVR JV/MH PWD/2018-19/165, date 10th Feb 2018) Annexure-III In your reply to our letter dated 10th Feb 2018 stated above, reference has been made to article/clause 10.1.3 We submit that a) as per terms of contract conditions, we submitted the original construction programme vide letter no. RCM PVR JV/MH PWD/2017-18/40, Dated 02nd Jun 2018 and Annexure-I b) the revised programme, as per article 10.1.3, vide letter no. RCM PVR JV/MH PWD/2018-19/235, date 02nd May 2018 guner regarding Appointed Date, in sl no. 3, you have stated that as the Appointed Date is declared, no EOT can be determined. We had a detailed discussion with the Team Leader on 03rd May 2018 and clarified the following. Schedule-A states that the site comprises of PROW width, which is the same as existing ROW, which implies that the land for 50.587 Km is already in possession of Authority. Please refer clause 5.2 (g) Annexure-V On good faith, The Appointed Date was accepted and encumbrances and existing utilities were recorded in Memorandum by Us. The statement is yet to be countersigned by Authority/Authority Engineer (Please refer our letter no. RCM PVR JV/MH PWD/2017-18/71, dated 10th August 2018). On commencement of works, we were intimated by revenue department of Maharashtra state (Tahsildar) that even the land on which the existing road is running is also not registered/alienated as a property/possession of PWD. Kindly refer our letter no. RCM PVR JV/MH PWD/2018-19/151, date 10th Jan 2018(Annexure-II). The reason for acceptance of Appointed Date was only good faith and the ground reality, when enlightened to Authority, the Authority commenced action for acquisition of entire land width. Kindly refer clause 5.2(h) regarding the commitment of Authority which is a warranty given by Authority Annexure-VI(a,b) The scope of the project {21.a) states that construction, as specified in schedule B & C. will conform to schedule D the technical specification. In order to achieve 80 Kmph in plain terrain & 40 kmph in hilly terrain (reference schedule B of 2.2 page 174) all the kinks, sharp Curves require geometric improvements. Hence, when the horizontal alignment gets changed/improved. deviating from the existing center line, such shifting of center line, results in additional land width requirement. Annexure-VII The assumption and decision of Authority/DPR consultants to procure land for major realignment (only for 5.35 Km) is absurd due to the reasons explained above. You have rightly stated in sl. No 4 referring to article 10.5.2/10.5.1 regarding the entitlement of extension of time by the contractor which is applicable as the works were affected and the Mile Stone could not be achieved. The details of programme of work achieved quantities etc are regularly furnished in all MPR's. The deficit in financial progress is also reflected in the S-Curve forming part of MPR. We reproduce the summary here under: SI.No. Targeted - Achieved Up to Sep 4.37 - 4.35 Oct 8.98 - 8.295 Nov 16.44 - 11.491 Dec 25.9 - 14.691 Jan 33.65 - 21.002 Feb 44.29 - 24.322 March 54.45 - 34.270 Please refer page 15 of MPR wherein a tabulation showing the affected length stretches are given in detail (copy enclosed all MPR) enable a proper evaluation of the time lost. | FALSE | real_data
Utility shifting | Authority's Obligations; Contractor's Obligations; EoT | This office is issuing NOTICE TO PROCEED WITH THE WORK for shifting of Electrical lines with assistance of the authority | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/17. Notice to Proceed with work Electrical pkg I pole & line shifting 22.05.2019.pdf | Rehabilitation & Upgradation of Paithan (Pategaon) - Mungi - Hadgaon - Bodhegaon - Ladjalgaon - Ghogaspargaon - Phulsangvi - Ukhandachakla - Dahiwandi - Shirur, NH752E to two lane with paved shoulder (Package -I) in the state of Maharashtra on EPC Mode. Regarding Electrical Pole & Line Shifting Estimate. | With reference to above cited subject, this office is issuing NOTICE TO PROCEED WITH THE WORK for shifting of Electrical lines with assistance of the authority, as per approved estimates from concerned department vide under reference no.4. R.O. MoRT& H, Navi Mumbai has approved the estimates with conditions as per reference letter no. 5 enclosed with this letter as follows. Sr. ¦ Approved by Division Section Chainage Modified No. Estimated Cost by RO, MoRT&H, Navi Mumbai 1 Executive Engineer, Pategaon Tal. 0+000 to 5+720 1,32,22,229 /- (O& M) Aurangabad R.I. Paithan div, Aurangabad 2 Executive Engineer, Tal Shevgaon 5+720 to 20+280 3,29,86,965/- MSEDCL, Rural Division Ahmednagar 3 Executive Engineer, Tal Shevgaon 20+280 to 37+400 4,60,48,489 /- MSEDCL, Rural Division Ahmednagar 4 Executive Engineer, Tal Pathardi 39+6710 to 43+550 & 2,64,48,876/- MSEDCL, Rural Division 45+960 to 49+400 Ahmednagar As per Article no. 09, Sub-Clause 9.2 of the agreement ‘The actual cost of such shifting.. shall be paid by the authorities to the contractor. Hereby you are directed to proceed the work shifting of water Supply Pipe line as per the rules, regulations and conditions laid down by the concerned department with proper caring and safety in all respects. For information and further action. | FALSE | real_data
Utility shifting | Authority's Obligations; Contractor's Obligations; EoT | A joint inspection of the project highway took place along with utility shifting contractor on 13.06.2019. It was identified and concluded by the Authority during the inspection that shifting of electrical poles can be taken up only after removal of encumbrances/ obstructions, as land was not available. Utility shifting is also interlinked with removal of encumbrance/ encroachments. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/40_07082019_Rescheduling of Project Milestones – Request for Extension of time.pdf | Rescheduling of Project Milestones - Request for Extension of time - Reg. | The Contract agreement for the above mentioned project was executed on 15.10.2018. The appointed date was fixed as 11.02.2019 and the same was communicated vide ref (3) cited above. The Copy of the same is herewith enclosed as Annexure 1. The Authority in its response vide ref (5) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. The copy of the same is enclosed as Annexure 3. The EPC contractor vide ref (6) cited above reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that still the condition remained the same and dismantling/ removal of structures fouling was not started and shifting of Electric pole and power line also not started. The impacted length due to encroachments and encumbrances was 12.18 Km which accounted to 33.77% of the project highway. The workable length available to the Contractor based on the impacted length was 66.23% of the Project Highway length. The EPC Contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of removal of encumbrance / encroachment / obstruction. The copy of ref (7) is herewith enclosed as Annexure 4. It is almost six months since the declaration of appointed date, removal/ dismantling of structures/encroachments have not been started. Also, the work of shifting of power line and electric pole of LT line and HT lines crossings have not been started yet. The following are some of the key contractual dates and events since the inception of the project to till date: 1. Total length of the project highway: 36.076 Km 2. Date of Signing of agreement: 152018 3. Submission of Performance BG as per Clause 7.1.1 of the Contract Agreement: 262018 4. Target date for preparation of Memorandum as per Clause 8.2.1 of the Contract Agreement: 142018 5. Actual date of signing of Memorandum of land handing over: 112019 6. Declaration of appointed date by the Authority: 112019 7. ROW to be handed over as on appointed date as per Clause 8.2.2 & Annexure II: 35.468 Km | FALSE | real_data
Utility shifting | Authority's Obligations; Contractor's Obligations; EoT | A strip chart showing the structures affected due to existence of utilities along the Project Highway is herewith enclosed as Annexure I. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20201119_SPK_AE_160_Contractor failure in achieving mile stone 1,2,&3.pdf | Six laning of Karaipcttai to Walajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - Contractor’s failure in achieving Project Mile Stone 1,2 & 3 applying of Damages vide Contract Article No. 10.3.2 & 10.3.3 - Reply made -Reg. | We are in receipt of your letter ref (26) cited above, our reply for the same is as follows: 1. The Contract Agreement for this Project was executed on 15.10.2018. The Appointed Date was fixed as 11.02.2019 and the same was communicated vide ref (2) cited above. 2. The Appointed date was declared as 11.02.2019 by the Authority taking into account the land handed over in terms of the available area without taking into consideration, the requirement of the Contract provision as per Clause 4.1.3 (a) of the EPC agreement which talks about the handing over of land only in terms of length of the Project Highway. The memorandum and appendix prepared in terms of area gave a deceptive / false picture about the availability of vacant access. Taking into consideration all the encumbrances, hindrances, utilities etc. the vacant access available on the appointed date declared was worked out and it was less than 90% and hence requested the Authority vide letter under ref (3) cited above for modification of the appointed date on which 90% of encumbrance free land would be made available to the Contractor. 3. The Authority in its response vide ref (4) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. 4. The EPC contractor vide ref (5) cited above in reply reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that the impacted length due to encroachments and encumbrances was 12.18 km which accounted to 33.77% of the project length. The workable length available to the contractor was only 66.23% of the project length. The EPC contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of encumbrance / encroachment / obstruction. | FALSE | real_data
Utility shifting | Authority's Obligations; Contractor's Obligations; EoT | Further, a meeting took place at NHAI HQ on 04.03.2020 and the status of the project was reviewed by Member (technical) wherein the issues faced by the EPC Contractor relating to non-handing over of ROW, delay in shifting of utilities, etc. were briefed. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20210416_SPK_AE_067_EOT request with Delay analysis.pdf | Six laning of Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V -EOT recommendation by the Authority for a period of 112 days not agreeable to the EPC Contractor — Request for considering EOT as discussed during the Review Meetings- reg | We are writing to express our concerns regarding the EOT recommendation by the Authority for a period of 112 days, which is not agreeable to the EPC Contractor. We request that the EOT be considered as discussed during the Review Meetings. The project involves six laning of the Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km 71+015 to km 107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase-V. We have referenced several documents and meetings in support of our request, and we hope for a favorable consideration. | FALSE | real_data
Utility shifting | Authority's Obligations; Contractor's Obligations; EoT | The Project Director informed that to take up the electrical works such as shifting of poles and any other tower lines an Agency called M/s.Sai Sri Enterprises was appointed on 19.07.2019. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/089_31082019_Minutes of Monthly Progress review meeting.pdf | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to 107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Minutes of Monthly Progress review meeting -Reg. | With respect to the above said reference please find enclosed herewith the minutes of meeting MoM -2 held on 27.08.2019. The venue and date for the next meeting will be intimated in due course of time. This is for your information and record. | FALSE | real_data
Utility shifting | Authority's Obligations; Contractor's Obligations; EoT | The Team leader informed that the shifting of electric poles was progressing Ch.Km 70 to 90 as planned. Project director instructed to expedite the same. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/119_01102019_Minutes of Monthly Progress review meeting Mom -3.pdf | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to 107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Minutes of Monthly Progress review meeting Mom -3 -Reg. | With respect to the above said reference please find enclosed herewith the minutes of meeting MoM -3 held on 25.09.2019. The venue and date for the next meeting will be intimated in due course of time. This is for your information and record. Assuring our best services at all times. | FALSE | real_data
Utility shifting | Authority's Obligations; Contractor's Obligations; EoT | The Contractor is not involved in the utility shifting, then too, in light of Clause 9.2,as stated that entitlement of Time Extension only beyond 180 days, Contractor is not entitled for the EOT for Milestone - 1 within 180 days from the Appointed Date, however thereafter Contractor is entitled for EOT on this ground. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/189_Rescheduling of Project Milestones - EOT - 1.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under BharatmalaPariyojana on EPC mode — Rescheduling of Project Mile Stone- Request for Extension of Time -Reg. | Having gone through your documents related to Rescheduling of Project Milestone-Request for Extension of Time EoT-1 please find enclosed herewith the Authority Engineers recommendations on the same subject. This is for your information and necessary action. | FALSE | real_data
Utility shifting | Authority's Obligations; Contractor's Obligations; EoT | The Contractor is not involved in the utility shifting, then too, in light of Clause 9.2,as stated that entitlement of Time Extension only beyond 180 days, Contractor is not entitled for the EOT for Milestone - 1 within 180 days from the Appointed Date, however thereafter Contractor is entitled for EOT on this ground. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/20191130_AE_PD_10451_Recommendation of EOT I for a period of 178 days.pdf | Application for EOT | This is with reference to the captioned subject and application for EOT received from the Contractor, in this regard, it is submitted that the Contract Agreement was signed between Contractor M/s SPK & Co. and the NHAI for Six Laning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km 71+015 to Km 107+091 in the State of Tamil Nadu under NHDP Phase - V. The following are the main contractual data ; Contract Seen Date : 15/10/2018 Length of the Project 36.076 Km Project Cost INR 533,36,67,000 Appointed Date : 11/02/2019 Construction Period : 730 days from Appointed Date Scheduled Completion Date: 09/02/2021 DLP Period : 4 years from the Provisional Certificate Project Milestone ~ Days from Project Milestone Appointed Date Milestone - -1 180 Days 09/08/2019 Not achieved 365 Days 10/02/2020 To be achieved 550 Days 13/08/2020 730 Days 09/02/2021 To be Achieved In view of the above, Authority's Engineer has scrutinized the EOT application and Authority's Engineer observations are being summarized hereunder in light of the Contract Agreement; Scheduled Date ¦ Status Procurement of the Site; As mentioned in the Clause 8.2.1 of the Contract Agreement, which reproduced herewith “the Authority Representative and the Contractor shall, within 30 days of the date of this Agreement, inspect the Site and prepare a memorandum containing an inventory of the site including the vacant and unencumbered land, buildings, structures, road works, trees and any other immovable property on or attached to the site. Subject to the provisions of Clause 8.2.3, such memorandum shall have appended thereto an appendix (the “Appendix”) specifying in reasonable detail those parts of the site to which vacant access and Right of Way has not been given to the Contractor. Signing of the memorandum, in two counterparts (each of which shall constitute an original), by the Authorized Representatives of the Parties shall be deemed to constitute a valid evidence of giving the Right of Way to the Contractor for discharging its obligations under and in accordance with the provisions of this Agreement and for no other purpose whatsoever.” | FALSE | real_data
Utility shifting | Authority's Obligations; Contractor's Obligations; EoT | The Contractor informed that one Number of Tower line Estimate has been received and another Estimate comprising 2 Nos. of Tower line is yet to receive. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/20191205_AE_NHAI_188_Minutes of Monthly Progress review meeting Mom-5.pdf | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to 107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Minutes of Monthly Progress review meeting Mom-5 -Reg. | With respect to the above said reference please find enclosed herewith the Minutes of Meeting Numbered as MoM-S held on 29.11.2019. The next meeting will be likely on 27.12.2019 at the Consultants office around 11.00 A.M in Kancheepuram. All the concerned are requested to attend with necessary documents. This is for your information and record. Assuring our best services at all times. | FALSE | real_data
Utility shifting | Authority's Obligations; Contractor's Obligations; EoT | However considering the balance in shifting of electrical utilities the EOT was recommended. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/20200827_AE_SPK_394_Delay in achieving of Project Milestones I and II.pdf | Delay in achieving of Project Milestones I and II - Reg | Dear Sir, In reference to the above-mentioned subject and Contractor letter refereed at (12) cited above, we would like to submit the following para wise reply: 1. Having gone through your disagreement with the approved for 112 days vide above said reference was reviewed and our comments was communicated through Ref. No.6. However, your contention for 324 vide above said No.4 by mentioning the points such as 1. Delay in handing over of ROW, 2. Delay in shifting of utilities, 3. Delay in Appointment of Authority Engineer 4. Delay in appointment of Proof & Safety Consultant & 5. Delay in procurement of Borrow earth was already addressed in our EoT recommendations letter. Hence, we stand by our earlier observations and reiterating the same issue is unprofitable. Further your request for 324 days and justifying yourself based on the above same grounds can’t be accepted. More ever, it should be noted that reasons submitted by the Contractor for delay, are nowhere concern with the delay in the works, such appointment of AE and the procurement of borrow earth, is the prime responsibility of the Contactor. He has to apply for such permits before the Appointed Date, but unfortunately, these permits applied very late by the Contractor. 2. The Extension of Time justifying for Mile Stone -1 based on the above said/suitable grounds was recommended vide C.C. CL. No. 10.5.1. & 2. Hence any delay in the Works effected due to the above reasons is already compensated in the EOT. However, mixing the same with WHOLE WORKS according Schedule “J” Point 6 is not accepted. This should also be noted that the progress of works is not appreciable even as on date. So, Contractor requested to please expedite the work progress instead of finding the reasons of delay. 3. Same as Point No.2 4. We reiterate that the approval of EoT for 112 days from the Competent Authority based on our recommendations and their own assessment. However, your disagreement on the same issue with the Authority is noted. 5. Same as point No.4. 6. Your contention for availability of land is deviating from the Joint Memorandum signed by both the parties. This issue was already addressed in the Point No.1. However, considering the balance in shifting of electrical utilities the EoT was recommended. But your contention to delay in achieving the Mile Stone due to non-shifting total electrical utilities is not acceptable. The AE do not agree the affected length as mentioned by the Contractor, however in case Contractor feels that encumbrances are not allowing him to proceed with the works, then Contractor may discuss with the Authority for the length not handed over in the Memorandum signed between the parties in light of Article 8 Right of Way of the Contract Agreement. 7. At no point of time the Authority Engineer has agreed to your contention of 324 days EoT. The AE opinion has been submitted while processing the EOT request. Presenting your grievances will not be accepted as approval of your contention for 324 days. It is requested to such one side conclusions shall not be accepted and they are beyond the good industry practice. Noted, but as mentioned in our letter as referenced No.9 and as on date the Project Mile Stone -3 has also lapsed where in which your stage payment certification should be 60% against which you achieved only 14.38%. This clear cut indicates in lack of progress at with in the available land itself. The delay in progress with specific points has already intimated to you vide our letter No’s SAICPL/Kar-Wal/TL/NH-48/TN/02B//71/2020/361, 367 & 380 Dated 10th July 2020, 23 July and 07th August 2020 respectively. Hence once again it is asked to mobilize your resources to achieve the required progress as per the scheduled completion date. | FALSE | real_data
Utility shifting | Authority's Obligations; Contractor's Obligations; EoT | The delay of 112 days mentioned towards shifting of scattered electrical utility lines /poles in some stretches of project highway appears to be delay on part of the Authority. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20200430_RO_PD_1461_Approval of 112 days for interim EOT I.pdf | NHAT, RO. Chennai ~ PIU, “Kancheepuram _ Six laning of Karaipettai to Walajapet section of NH4 (New NH-48) from km 71/015 to km 107/091 in the State of Tamil Nadu under N NHDP Phase V- rescheduling of Project Mile stone I | Please refer your letter cited at (1) on the above mentioned subject and esting for Extension of Time & Rescheduling of project Milestones. In this snection, in pursuance of the details and the report furnished in your letter dated 0 and the Authority Engineer(AE) letter at (2) under reference, the delay of 112 days mei ioned towards shifting of scattered electrical utility lines/poles in some ss retches of Project Highway appears to be delay on part of the Authority. Further, the j of 47 days delay due to excess rainfall from 15.10.2019 to 31.10.2019 : recom nended in your & AE’s letter is a overlap in the above mentioned period of 12 days. Accordingly, rescheduling of Milestone I only by 112 days without any change in the Scheduled Project Completion period stipulated in the Contract Agreement is approved. vee 2. As brought out in the AE’s letter cited under reference (2) the deployment of ma y ig not complete which indicates that the Contractor is not putting efforts to the pace, progress of the work and to complete the project. As such, for any ¦/ delay in achievement of progress beyond the rescheduled period of Mile Stone I and other Milestones the Contractor will be solely responsible for such delays. Hence, the Contractor shall be directed to make all out efforts to accelerate the progress, to achieve the prescribed milestones so that the work could be completed by the time . period stipulated in the Contract agree | FALSE | real_data
Utility shifting | Authority's Obligations; Contractor's Obligations; EoT | The consultant askeed the status of reerection of electrical towers and water pipeline shifting | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20201123_AE_SPK_480_Minutes of Monthly Progress review meeting Mom – 08.pdf | Consultancy services for Authority's Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode - Minutes of Monthly Progress review meeting Mom — 08 — Reg. | With respect to the above said reference please find enclosed herewith the Minutes of Meeting Numbered as MoM - 08 held on 21.11.2020 The next meeting will be likely on 23.12.2020 at the Consultants office around 11.00 A.M in Kancheepuram. All the concerned are requested to attend with necessary documents. This is for your information and record. Assuring our best services at all times. | FALSE | real_data
Utility shifting | Authority's Obligations; Contractor's Obligations; EoT | It may be noted that the estimates for various pipelines were approved 02.07.2020 to 07.07.2020.But after a lapse of 5 months,i.e on 02.12.2020,the Contractor has commenced the excavation works for shifting of pipe lines. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20201228_AE_SPK_506_Contractor’s failure in achieving Project Mile Stone 1, 2 & 3 applying of Damages vide Contract Article No. 10.3.2 & 10.3.3.pdf | Contractor’s failure in achieving Project Mile Stone 1, 2 & 3 applying of Damages vide Contract Article No. 10.3.2 & 10.3.3 - Reg. | In response to the reference letter no. 27, our replies are as follows, As per the Contractor's view point of 66.23% of available workable length, the Financial Progress of 6.62% on prorate basis is supposed to be achieved by the Contractor on the revised date of MS-¦ on 29.11.2019 including EOT of 112 days as approved by the Authority vide letter No NHAI/11019/17/2009/RO Chennai/1461 & NHAI/11036/4/2019/PIU. Kanchee/878 respectively dated 30.04.2020 & 07.05.2020. However, Contractor achieved a Financial Progress of 0.713% as on due date. Even, as on March 2020, the Financial Progress is about 5%. Hence it is clear indication of Contractor's failure, even if, we consider proportionate physical progress as per claimed 66.23% of land as by the Contractor, which is not line of the actual working land available at site and the memorandum signed between the parties. Further, it may be noted that the Estimates for various Pipelines were approved 02.07.2020 to 07.07.2020. But after a lapse of 5 months i.e. on 02.12.2020 the Contractor has commenced the excavation works for shifting of the Pipe lines. Hence, such land cannot be considered under hindrances/encumbrances, as shifting of water pipe lines are the responsibility of the Contractor, as per the Contract Article 9.2 of the Contract. In response to the Pt. No. 30, the Contractor is requested to produce a valid Document based on the discussions held in RO Meeting stating that the EOT is in consideration with RO, as any such information is not communicated to the Authority Engineer, hence cannot be cognizant. This is for your information and for necessary compliance. | FALSE | real_data
Utility shifting | Authority's Obligations; Contractor's Obligations; EoT | However,other affected length are overlapping with the other utilities,hence same is not being considered for completion of delay days.Therefore,it is submitted that based on the above total 25 days may be considered for EOT due to delay in shifting of electrical utilities. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210630_AE_PD_14484_Comprehensive EOT proposal.pdf | Extension of Time Comprehensive proposal- Reg. | With reference to the captioned subject and from the above mentioned chronology of correspondences, it can be understood that despite of approving an EoT for a period of 112 days for Mile Stone-1, the Contractor is disagreeing with the approval of the Authority and again highlighted the impediments adversely effected the First Mile Stone as well as other Milestone including the Scheduled Completion Date. The Contractor submitted the comprehensive proposal and requested for an extension of time. | FALSE | real_data
Utility shifting | EoT | The status of these water pipeline mentioned in the memorandum as mentioned Annexure 2.Also the relocation of these utilities from the site,provided as per the NHAI Dash board data mentioned herein above, are considered for extension of time on the basis of weightage delay days.The delay analysis annexed as Annexure 1. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210631_AE_PD_14484_Comprehensive EOT proposal.pdf | Extension of Time Comprehensive proposal- Reg. | With reference to the captioned subject and from the above mentioned chronology of correspondences, it can be understood that despite of approving an EoT for a period of 112 days for Mile Stone-1, the Contractor is disagreeing with the approval of the Authority and again highlighted the impediments adversely effected the First Mile Stone as well as other Milestone including the Scheduled Completion Date. The Contractor submitted the comprehensive proposal and requested for an extension of time. | FALSE | real_data
Utility shifting | EoT | In view of the above facts,delay of 194 days is attributable only on account of shifitng of electrical utilities assuming that expected date of utilitty shifting as 15.08.2021.Further,it is submitted that if the shifting of utilities get delayed at site beyond 15.08.2021,then further EOT may be considered.The detailed calculation is enclosed in Annexure II. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210709_PD_RO_1893_Comprehensive EOT recommendation.pdf | NHAI, PIU, Kancheepuram - Six laning of Karaipettai to Walajahpet section of NH-4 (Km 71/015 to Km 107/091) in the State of Tamil Nadu — Comprehensive Proposal / Revised Extension of Time & Rescheduling of Project Milestones upto 20.12.2022 -— Proposal submitted for approval - Reg. | I submit that, the Authority Engineer vide letter 1* cited above, recommended the Comprehensive Extension of Time Proposal for the period of 398 days i.e upto 13.03.2022 towards completion of the subject project. 2. In this regard, it is submitted that, the Regional Officer, NHAI, Chennai vide letter cited 9'8 above, approved the EoT for a period of 112 days for Milestone-1 against the contractor’s claim of 324 days. However, the contractor vide letter cited 8" above, requested the Authority for considering the EoT for a period of 324 days. 3. In this context, the Contractor was requested to submit the Comprehensive Extension of Time proposal for completion of work and the Contractor vide reference letter cited 4" and 5t above, submitted the Comprehensive EoT Proposal for a period of 678 days i.e., upto 20.12.2022 citing the delays in execution of work due to various reasons such as Covid-19 pandemic, delay in handing over of ROW, delay in Shifting of Utilities / Electrical Towers, delay in Appointment of Authority Engineer, delay in appointment of Proof & Safety Consultant, delay in Procurement of Barrow earth due to Vellore Constituency re-election etc. 4. In this regard, the Authority Engineer vide letter 15' cited above, recommended the Comprehensive Extension of Time Proposal for the period of 398 days i.e upto 13.03.2022 towards completion of the subject project as follows a) Authority Engineer Recommendation: “The AE would like to submit that as provision of Article 10.5.1 stated that “Without prejudice to any other provision of this Agreement for and in respect of Extension of Time, the Contractor shall be entitled to extension of time in the Project Mile Stone is or will be delayed by any of the following, namely: • Delay in providing the Right of Way, Environmental Clearance or Approval of railway Authorities specified in Article 4.1.1. • Any other cause or delay which entitles the Contractor to Extension of Time in accordance with the provisions of this Agreement. In view of the above, pursuant mentioned Article 10.5.1, Article 4.1.6 (a) & (e) of the Contract Agreement, the Authority Engineer opinion are being submitted herewith for further needful; i. Delay due to Force Majeure: Pandemic Coronavirus (COVID-19) As the COVID -19 Pandemic was started and its effect was falling on the project, the Contractor noticed the Authority and the AE through references mentioned as 25, 26 & 27.: In this regard the Contractor claimed total 270 days vide letter No. SPK/ KW/SAIC/ NH-48/2021/069 Dated 19.04.2021 mentioned as ref. No. 46 & 48. However, as per the guidelines issued by the MoRT & H and the Govt. of India, Under Atmanirbhar Bharat Scheme, the Authority Engineer has recommended the EoT under Atmanirbhar Bharat Scheme for a period of 6 months vide letter No. SAICPL/ Kar-IL | FALSE | real_data
Utility shifting | Authority's Obligations; Contractor's Obligations; EoT | Regarding shifting of Electrical Utilities, we wish to submit that the estimate approvals for shifting the utilities were accorded by the Competent Authority for Chandwad section in the month of May'24 and for Deola and Satana sections in the Month of June'24. Despite the delayed approvals from the authorities, we have completed the works for Chandwad section, and the works of Deola and Satana sections were started as soon as we have received the approvals, and the works are in progress. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-2/12. 20240728_564_Cont_AE_Progress of works.pdf | Rehabilitation and Upgradation of Satana to Mangrul (Chandwad) Section of NH 752 G Design Ch. KM 64+000 to KM 1014140 Two Lane with Paved Shoulder / Four Lane Configuration in the state of Maharashtra on EPC Mode. Reg. Progress of works. | We refer to your letter at ref. 2, wherein you have conveyed your observations on the progress of works in the above-mentioned project stretch. In this regard, please find our para-wise reply below: 1. Slow Progress of works It is mentioned in your letter that the work front of 11.4 Km from Km.64+000 to 75+400 is available to us. This is contrary to the actual site condition, the land available for works as on date is only 8.52 Km. The details of unavailable stretches are as follows: a) Km 65+000 to 66+490 (1.490 km) - Satana Market: Full width of the Right of Way (ROW) is not available as the encroachments have not been removed. Despite several meetings held with the Satana Tehsildar, Local MLA and the public, in the presence of the Authority and Authority’s Engineer (AE), the issue remains unresolved even as on date. b) Km 66+520 to 66+600 (LHS), 67+560 to 67+650 (LHS), 71+930 to 72+000 (LHS): Land Acquisition at the above locations is not yet completed by the Authority even as on date. c) Km 68+780 to 68+830 (LHS): Encroachments have not been removed, specifically a temple, which has not been removed by the Authority. d) Km 74+100 to 74+700 & 74+900 to 75+400 - Thengode-Lohner Market: Full width of the ROW is not available at these locations as the encroachments have not been removed even as on date. The status of completed works in the available stretch of 8.52 km is as below: ° PQC (Pavement Quality Concrete): 2.3 km (LHS) ° DLC (Dry Lean Concrete): 3.70 km (LHS) ° GSB (Granular Sub-base): 4.1 km (LHS) ° Subgrade: 4.6 km (LHS) ° Subgrade widening on RHS: km 69+000 to 74+600, i.e., 5.6 km. The works of minor bridges at Km. 67+710 and 68+800 could not be started due to the pending land acquisition issues which are yet to be cleared. Though the construction of Minor Bridge at km 71+910 was commenced in the last month, the same got halted due to heavy rains. To avoid idling, the manpower was shifted to other works and was again remobilized to the structure on 27.07.2024 and the work was resumed. The work on the slab drains at km 70+050 and km 70+100 is in progress and will be completed within a month. We assure you that all pipe culvert works from km 64+000 to 75+000 will be completed within a month. For the four-lane portion from km 64+000 to km 64+800, the scope of new Jersey-type divider is only of 590 meters, for which the PCC work is completed, balance work is in progress and will be completed at the earliest. The terminal slab work on one half of km 94+420 (RHS) is pending and will be completed after diversion of traffic movement onto LHS. 2. Shifting of Utilities Regarding shifting of Electrical Utilities, we wish to submit that the estimate approvals for shifting the utilities were accorded by the Competent Authority for Chandwad section in the month of May’24 and for Deola and Satana sections in the Month of June’24. Despite the delayed approvals from the authorities, we have completed the works for Chandwad section, and the works of Deola and Satana sections were started as soon as we have received the approvals, and the works are in progress. | FALSE | real_data
Utility shifting | Authority's Obligations; Contractor's Obligations; EoT | the EPC Contractor is requested to take necessary action to shift the MB water pipeline before taking up road works. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-2/18. 20241022_109_AE_Cont_Mission Bhageeratha pipeline shifting in siddipet Bypass-Reg.pdf | Widening to 2 Lane with paved shoulders of Medak - Siddipet section from Km 0/000 to Km 69/978 of NH-765DG in the state of Telangana under Annual plan 2021-22 on EPC Basis - Mission Bhageeratha pipeline shifting in Siddipet Bypass - Reg. | Please refer letter 2" cited above from the Executive Engineer, MB Grid Division Gajwel received from the Executive Engineer through E-mail dated 22.10.2024 regarding shifting of water pipeline. In this regard, the EPC Contractor is requested to take necessary action to shift the MB water pipeline before taking up road works. This is for your kind Information and necessary action please. | FALSE | real_data
Declaration of Appointed Date | Appointed Date; EoT | Hence it is requested to communicate appointed date for the project at the earliest | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/188_30012019_Procurement of Site Submission of Memorandum.pdf | NHAL, PIU ~ Krishnagiri - Six Laning of (New NH48) from km 71.015 to km 107.0 - Right-of-Way Procurement of the site Submission of Memorandum-Reg. | Kindly refer to the letter 24 cited wherein it is requested to submit joint memorandum signed by the Contractor along, with status of approval of GAD for ROBs, Environmental clearance as per clause 4.13 of Agreement and status of shifting of obstructing utilities and felling of trees as per cl 9.2 & 9.4 of Agreement. 2. The status report is submitted below: (i) Joint Signed copy of the Joint Memorandum submitted by the Contractor vide reference 1 is enclosed as Annexure. (ii) The status of Obligations of the Authority as per Article 4 is as below: (a) The Authority has to give Right of Way to the Contractor no less than 90% of the total length of the Project Highway. Accordingly, as per clause 62 the memorandum containing an inventory is prepared by the Contractor and Authority. As per Appendix to memorandum the percent of unencumbered and vacant area is coming out to 93.65% which is more than 90% as per cl 8.23 of contract and also as per clause 83.2 Schedule-A, Annex-II dates for providing right of way is more than 80% of the total length of the project on appointed date in compliance to clause 10.3 of agreement, hence fulfilled the obligation. (b) Approval of GAD from Railway Authorities to enable the contractor to construct ROBs. One No of 6 lane ROB is existing and only Repair/Rehabilitation is to be carried out no fresh approval of GAD is required from Railways, hence fulfilled the obligation. (c) Environmental clearance is required under cl 4.3 and shall be procured by Authority before issue of LOA. As per MOEF Notification S.O No 2559, 22.8.2013 Environmental clearance is required for the expansion of NHs greater than 100 Km involving additional right of way or land acquisition greater than 40m on existing alignments and 60m on realignments or by passes. In this case the length of project is only 36.076 Km and additional land acquired is less than 40m, hence no clearance is required from MOEF. (d) As per Article 9.2 of Agreement the status of shifting of obstructing Utilities are as below: (i) Balance Electrical Utilities are to be shifted. The subcontractor of the terminated Concessionaire has shifted the Electrical Utilities partially and the authority has decided to shift the balance utilities through the same agency at the old SOR rates. In this regard RO Chennai vide letter No 3921 dt 03.10.2018 has forwarded report to GM(T)-TN NHAI HQ Delhi. Approval is awaited. (ii) Tree cutting is already completed and few left out trees were identified and cutting is under progress. Hence it is requested to communicate appointed date for the project at the earliest. | FALSE | real_data
Declaration of Appointed Date | Appointed Date | Regarding declaration of Appointed Date | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/Lr.No.130404_08022019_ Declaration of Appointment Date.pdf | Six Laning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km. 71+015 to Km 107+091 on EPC Mode in the state of Tamil Nadu under NHDP Phase-V - Regarding declaration of Appointed Date. | This has reference to Joint Memorandum of Site Inventory signed jointly by PD, Krishnagiri and the EPC Contractor submitted vide your letter dated 01.02.2019 in terms of Clause 8.2.1 of Agreement regarding declaration of Appointed Date for the subject Project. By In this context, it is to convey that the Competent Authority has accorded approval to declare the Appointed Date as 11.02.2019, to commence the work. Further, it has also been directed to arrange handing over of balance ROW as per Clause 8.2.2 of Contract Agreement and to ensure that encumbrances due to Tree Cutting, removal of Structures, shifting of Electric Poles and Water Supply Lines etc., don’t hinder the construction of Project. This is for kind information and further necessary action, please. | FALSE | real_data
Declaration of Appointed Date | Appointed Date | Since the project site (including existing ROW which is more than 90% as indicated by the Executive Engineer (R&B) NH Division, Kalwakurthy) was handed over to you by the authorized representative of the Authority i.e., Executive Engineer (R&B) NH Division, Kalwakurthy as per Schedule-A and as per clause 8.2 of the agreement, therefore this day 24th of July 2021 is here by declared as the Appointed date for the project | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-2/1. 20210724_325_SE_Cont_Declaration of Appointed date.pdf | (R&B) NH Circle, Hyderabad — “Balance Works of Rehabilitation and Upgradation of Nakrekal to Nagarjunasagar section to 2L+PS/4L from Km 1.000 to Km 86.057 of NH-565 under NH(O) for the year 2020-21 in the State of Telangana on EPC Mode” — Declaration of Appointed date - Reg. | Adverting to the reference 1* cited, the contract agreement for the subject work has been concluded on 12.07.2021. The Executive Engineer vide reference 2" cited has informed that Joint inspection was conducted by the Executive Engineer (R&B) NH division, Kalwakurthy with Sri B. Venkat Reddy, M/s SLMI Infra Projects Private Limited, in terms of clause 8.2 of contract agreement on 22.07.2021. Subsequently, Handover memorandum of ROW, were signed by both the parties on 22.07.2021. The same is herewith enclosed. In the Handover memorandum of ROW, it is mentioned that ROW in a cumulative length of 83.245 Km (97.41%) out of the total project length of 85.451 Km is handed over to the contractor. Since the project site (including existing ROW which is more than 90% as indicated by the Executive Engineer (R&B) NH Division, Kalwakurthy) was handed over to you by the authorized representative of the Authority i.e., Executive Engineer (R&B) NH Division, Kalwakurthy as per Schedule-A and as per clause 8.2 of the agreement, therefore this day 24" of July 2021 is here by declared as the Appointed date for the project “Balance Works of Rehabilitation and Upgradation of Nakrekal to Nagarjunasagar section to 2L+PS/4L from Km 1.000 to Km 86.057 of NH-565 under NH(O) for the year 2020-21 in the State of Telangana on EPC Mode” in terms of article 3 and 8 of the contract agreement. | FALSE | real_data
Declaration of Appointed Date | EoT | With reference to the references 2nd &3rd cited, the competent authority in NHAI vide reference 1st cited has communicated approval to declare appointed date as 11.02.2019 to commence the works. | synthetic_template_20250913 | NHAIL, PIU - Krishnagiri - Six Laning of Karaipettai to Walajhapet section of NH-4 (New NH-48) from km.71.015 to km.107.091 in the State of Tamil Nadu under NHDP Phase-V under EPC Mode- M/s SPK é&Co -Declaration of Appointed Date—Reg. | With reference to the references 2nd & 3rd cited, the competent authority in NHAI vide reference 1st cited has communicated approval to declare appointed date as 11.02.2019 to commence the works. In view of the above, it is requested to submit the action taken on the following issues: (a) Status of obligations of the contractor as per Article 3 of agreement (b) Maintenance of the stretch during construction period as per clause 10.4 of Agreement for which the contractor is responsible for ensuring safe operation of Project Highway. (c) Status of obligations of the Contractor on Design and Construction of the Project Highway as per Article 10 of Agreement. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Declaration of Appointed Date | EoT | Hence it is requested to communicate appointed date for the project at the earliest | synthetic_template_20250913 | NHAL, PIU ~ Krishnagiri - Six Laning of (New NH48) from km 71.015 to km 107.0 - Right-of-Way Procurement of the site Submission of Memorandum-Reg. | Kindly refer to the letter 24 cited wherein it is requested to submit joint memorandum signed by the Contractor along, with status of approval of GAD for ROBs, Environmental clearance as per clause 4.13 of Agreement and status of shifting of obstructing utilities and felling of trees as per cl 9.2 & 9.4 of Agreement. 2. The status report is submitted below: (i) Joint Signed copy of the Joint Memorandum submitted by the Contractor vide reference 1 is enclosed as Annexure. (ii) The status of Obligations of the Authority as per Article 4 is as below: (a) The Authority has to give Right of Way to the Contractor no less than 90% of the total length of the Project Highway. Accordingly, as per clause 62 the memorandum containing an inventory is prepared by the Contractor and Authority. As per Appendix to memorandum the percent of unencumbered and vacant area is coming out to 93.65% which is more than 90% as per cl 8.23 of contract and also as per clause 83.2 Schedule-A, Annex-II dates for providing right of way is more than 80% of the total length of the project on appointed date in compliance to clause 10.3 of agreement, hence fulfilled the obligation. (b) Approval of GAD from Railway Authorities to enable the contractor to construct ROBs. One No of 6 lane ROB is existing and only Repair/Rehabilitation is to be carried out no fresh approval of GAD is required from Railways, hence fulfilled the obligation. (c) Environmental clearance is required under cl 4.3 and shall be procured by Authority before issue of LOA. As per MOEF Notification S.O No 2559, 22.8.2013 Environmental clearance is required for the expansion of NHs greater than 100 Km involving additional right of way or land acquisition greater than 40m on existing alignments and 60m on realignments or by passes. In this case the length of project is only 36.076 Km and additional land acquired is less than 40m, hence no clearance is required from MOEF. (d) As per Article 9.2 of Agreement the status of shifting of obstructing Utilities are as below: (i) Balance Electrical Utilities are to be shifted. The subcontractor of the terminated Concessionaire has shifted the Electrical Utilities partially and the authority has decided to shift the balance utilities through the same agency at the old SOR rates. In this regard RO Chennai vide letter No 3921 dt 03.10.2018 has forwarded report to GM(T)-TN NHAI HQ Delhi. Approval is awaited. (ii) Tree cutting is already completed and few left out trees were identified and cutting is under progress. Hence it is requested to communicate appointed date for the project at the earliest. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Declaration of Appointed Date | Appointed Date | Since the project site (including existing ROW which is more than 90% as indicated by the Executive Engineer (R&B) NH Division, Kalwakurthy) was handed over to you by the authorized representative of the Authority i.e., Executive Engineer (R&B) NH Division, Kalwakurthy as per Schedule-A and as per clause 8.2 of the agreement, therefore this day 24th of July 2021 is here by declared as the Appointed date for the project | synthetic_template_20250913 | (R&B) NH Circle, Hyderabad — “Balance Works of Rehabilitation and Upgradation of Nakrekal to Nagarjunasagar section to 2L+PS/4L from Km 1.000 to Km 86.057 of NH-565 under NH(O) for the year 2020-21 in the State of Telangana on EPC Mode” — Declaration of Appointed date - Reg. | Adverting to the reference 1* cited, the contract agreement for the subject work has been concluded on 12.07.2021. The Executive Engineer vide reference 2" cited has informed that Joint inspection was conducted by the Executive Engineer (R&B) NH division, Kalwakurthy with Sri B. Venkat Reddy, M/s SLMI Infra Projects Private Limited, in terms of clause 8.2 of contract agreement on 22.07.2021. Subsequently, Handover memorandum of ROW, were signed by both the parties on 22.07.2021. The same is herewith enclosed. In the Handover memorandum of ROW, it is mentioned that ROW in a cumulative length of 83.245 Km (97.41%) out of the total project length of 85.451 Km is handed over to the contractor. Since the project site (including existing ROW which is more than 90% as indicated by the Executive Engineer (R&B) NH Division, Kalwakurthy) was handed over to you by the authorized representative of the Authority i.e., Executive Engineer (R&B) NH Division, Kalwakurthy as per Schedule-A and as per clause 8.2 of the agreement, therefore this day 24" of July 2021 is here by declared as the Appointed date for the project “Balance Works of Rehabilitation and Upgradation of Nakrekal to Nagarjunasagar section to 2L+PS/4L from Km 1.000 to Km 86.057 of NH-565 under NH(O) for the year 2020-21 in the State of Telangana on EPC Mode” in terms of article 3 and 8 of the contract agreement. We await your further instructions. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Declaration of Appointed Date | Appointed Date | Hence it is requested to communicate appointed date for the project at the earliest | synthetic_template_20250913 | NHAL, PIU ~ Krishnagiri - Six Laning of (New NH48) from km 71.015 to km 107.0 - Right-of-Way Procurement of the site Submission of Memorandum-Reg. | We hereby confirm that Kindly refer to the letter 24 cited wherein it is requested to submit joint memorandum signed by the Contractor along, with status of approval of GAD for ROBs, Environmental clearance as per clause 4.13 of Agreement and status of shifting of obstructing utilities and felling of trees as per cl 9.2 & 9.4 of Agreement. 2. The status report is submitted below: (i) Joint Signed copy of the Joint Memorandum submitted by the Contractor vide reference 1 is enclosed as Annexure. (ii) The status of Obligations of the Authority as per Article 4 is as below: (a) The Authority has to give Right of Way to the Contractor no less than 90% of the total length of the Project Highway. Accordingly, as per clause 62 the memorandum containing an inventory is prepared by the Contractor and Authority. As per Appendix to memorandum the percent of unencumbered and vacant area is coming out to 93.65% which is more than 90% as per cl 8.23 of contract and also as per clause 83.2 Schedule-A, Annex-II dates for providing right of way is more than 80% of the total length of the project on appointed date in compliance to clause 10.3 of agreement, hence fulfilled the obligation. (b) Approval of GAD from Railway Authorities to enable the contractor to construct ROBs. One No of 6 lane ROB is existing and only Repair/Rehabilitation is to be carried out no fresh approval of GAD is required from Railways, hence fulfilled the obligation. (c) Environmental clearance is required under cl 4.3 and shall be procured by Authority before issue of LOA. As per MOEF Notification S.O No 2559, 22.8.2013 Environmental clearance is required for the expansion of NHs greater than 100 Km involving additional right of way or land acquisition greater than 40m on existing alignments and 60m on realignments or by passes. In this case the length of project is only 36.076 Km and additional land acquired is less than 40m, hence no clearance is required from MOEF. (d) As per Article 9.2 of Agreement the status of shifting of obstructing Utilities are as below: (i) Balance Electrical Utilities are to be shifted. The subcontractor of the terminated Concessionaire has shifted the Electrical Utilities partially and the authority has decided to shift the balance utilities through the same agency at the old SOR rates. In this regard RO Chennai vide letter No 3921 dt 03.10.2018 has forwarded report to GM(T)-TN NHAI HQ Delhi. Approval is awaited. (ii) Tree cutting is already completed and few left out trees were identified and cutting is under progress. Hence it is requested to communicate appointed date for the project at the earliest. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Submission of Applicable permits as per Schedule-F | Contractor's Obligations | Status of obligations of the Contractor as per Article 3 of Agreement | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/233_11022019_Declaration of Appointed Date.pdf | NHAIL, PIU - Krishnagiri - Six Laning of Karaipettai to Walajhapet section of NH-4 (New NH-48) from km.71.015 to km.107.091 in the State of Tamil Nadu under NHDP Phase-V under EPC Mode- M/s SPK é&Co -Declaration of Appointed Date—Reg. | With reference to the references 2nd & 3rd cited, the competent authority in NHAI vide reference 1st cited has communicated approval to declare appointed date as 11.02.2019 to commence the works. In view of the above, it is requested to submit the action taken on the following issues: (a) Status of obligations of the contractor as per Article 3 of agreement (b) Maintenance of the stretch during construction period as per clause 10.4 of Agreement for which the contractor is responsible for ensuring safe operation of Project Highway. (c) Status of obligations of the Contractor on Design and Construction of the Project Highway as per Article 10 of Agreement. | FALSE | real_data
Submission of Applicable permits as per Schedule-F | Contractor's Obligations | This has reference to your letter (2) cited above, we would like to intimate that the following are the status of applicable permits as per Schedule F of the Contract Agreement: | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LOT-10/132_25112019_ Status of Applicable permits.pdf | Status of applicable permits — Reg. | Dear Sir, This has reference to your letter (2) cited above, we would like to intimate that the following are the status of applicable permits as per Schedule F of the Contract Agreement: List of Applicable permits as per Schedule - F Status Permission of the State Government for extraction of boulders from quarry. It has been proposed to outsource aggregates from the private crushers. List of identified crushers are e Elan minerals Sun blues Argant JCS enterprises SRC Project Pvt. Ltd. Gopi Blue Metals NRM Sons Blue Metals Permission of Village Panchayat and Pollution Control board for installation of crushers. License for use of explosives. Permission of the State Government for drawing water from river / reservoir. The same is not applicable as the EPC contractor is not drawing water from river/reservoir. | FALSE | real_data
Submission of Applicable permits as per Schedule-F | Contractor's Obligations | This has reference to your letter (2) cited above, we would like to intimate that the following are the status of applicable permits as per Schedule F of the Contract Agreement: | synthetic_template_20250913 | Status of applicable permits — Reg. | Dear Sir, This has reference to your letter (2) cited above, we would like to intimate that the following are the status of applicable permits as per Schedule F of the Contract Agreement: List of Applicable permits as per Schedule - F Status Permission of the State Government for extraction of boulders from quarry. It has been proposed to outsource aggregates from the private crushers. List of identified crushers are e Elan minerals Sun blues Argant JCS enterprises SRC Project Pvt. Ltd. Gopi Blue Metals NRM Sons Blue Metals Permission of Village Panchayat and Pollution Control board for installation of crushers. License for use of explosives. Permission of the State Government for drawing water from river / reservoir. The same is not applicable as the EPC contractor is not drawing water from river/reservoir. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Submission of Applicable permits as per Schedule-F | Contractor's Obligations | This is being a Project of National Importance, it is requested your good self to provide us the requisite NOC for the establishment of Hot Mix Plant. | synthetic_template_20250913 | Requesting for Issuance of NOC for Establishment of Hot Mix Plant — Reg. | Dear Sir, This has reference to the subjected matter, we wish to bring your kind attention that; we have taken land on lease at RS No: 60, 57/1, 52/1A & 59/1 located at 712/A Anna Nagar, NH-48, Chennai - Bangalore National Highways, Kilambi Village, Krishnapuram Post, Kanchipuram Taluk & District, Pin - 631551. For the purpose of construction/execution of said National Highway project, we are intend to set up a Hot Mix plant within the above stated location. This is being a Project of National Importance, it is requested your good self to provide us the requisite NOC for the establishment of Hot Mix Plant. This is for your kind consideration and necessary approval, please. Yours faithfully, For SPK AND Managing Parther | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Submission of Applicable permits as per Schedule-F | Contractor's Obligations | Status of obligations of the Contractor as per Article 3 of Agreement | synthetic_template_20250913 | NHAIL, PIU - Krishnagiri - Six Laning of Karaipettai to Walajhapet section of NH-4 (New NH-48) from km.71.015 to km.107.091 in the State of Tamil Nadu under NHDP Phase-V under EPC Mode- M/s SPK é&Co -Declaration of Appointed Date—Reg. | With reference to the references 2nd & 3rd cited, the competent authority in NHAI vide reference 1st cited has communicated approval to declare appointed date as 11.02.2019 to commence the works. In view of the above, it is requested to submit the action taken on the following issues: (a) Status of obligations of the contractor as per Article 3 of agreement (b) Maintenance of the stretch during construction period as per clause 10.4 of Agreement for which the contractor is responsible for ensuring safe operation of Project Highway. (c) Status of obligations of the Contractor on Design and Construction of the Project Highway as per Article 10 of Agreement. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Submission of Applicable permits as per Schedule-F | Contractor's Obligations | Status of obligations of the Contractor as per Article 3 of Agreement | synthetic_template_20250913 | NHAIL, PIU - Krishnagiri - Six Laning of Karaipettai to Walajhapet section of NH-4 (New NH-48) from km.71.015 to km.107.091 in the State of Tamil Nadu under NHDP Phase-V under EPC Mode- M/s SPK é&Co -Declaration of Appointed Date—Reg. | With reference to the references 2nd & 3rd cited, the competent authority in NHAI vide reference 1st cited has communicated approval to declare appointed date as 11.02.2019 to commence the works. In view of the above, it is requested to submit the action taken on the following issues: (a) Status of obligations of the contractor as per Article 3 of agreement (b) Maintenance of the stretch during construction period as per clause 10.4 of Agreement for which the contractor is responsible for ensuring safe operation of Project Highway. (c) Status of obligations of the Contractor on Design and Construction of the Project Highway as per Article 10 of Agreement. Please confirm receipt of this correspondence. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Submission of Applicable permits as per Schedule-F | Contractor's Obligations | This is being a Project of National Importance, it is requested your good self to provide us the requisite NOC for the establishment of Hot Mix Plant. | synthetic_template_20250913 | Requesting for Issuance of NOC for Establishment of Hot Mix Plant — Reg. | We would like to inform you that Dear Sir, This has reference to the subjected matter, we wish to bring your kind attention that; we have taken land on lease at RS No: 60, 57/1, 52/1A & 59/1 located at 712/A Anna Nagar, NH-48, Chennai - Bangalore National Highways, Kilambi Village, Krishnapuram Post, Kanchipuram Taluk & District, Pin - 631551. For the purpose of construction/execution of said National Highway project, we are intend to set up a Hot Mix plant within the above stated location. This is being a Project of National Importance, it is requested your good self to provide us the requisite NOC for the establishment of Hot Mix Plant. This is for your kind consideration and necessary approval, please. Yours faithfully, For SPK AND Managing Parther | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Contractor's representative | Contractor's Obligations | It is observed that even-though sufficient time has been lapsed after commencing the above said Contract Agreement, till date there is no full time Project Manager has been deployed at site from your end. How-ever it is to note that Mr. G. Vijayakumar who is representing as Project Manager is attending the Co-ordination meetings & site inspections and rest of the time his presence at Project site is minimal. Hence it has been advised to arrange a full time Project Manager for proper co-ordination and effective management of site activities. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LOT-10/102_17092019_Presence of Project Manager at site.pdf | Presence of Project Manager at site: -Reg | Dear Sir, It is observed that even-though sufficient time has been lapsed after commencing the above said Contract Agreement, till date there is no full time Project Manager has been deployed at site from your end. How-ever it is to note that Mr. G. Vijayakumar who is representing as Project Manager Is attending the Co-ordination meetings & site inspections and rest of the time his presence at Project site is minimal. Hence it has been advised to arrange a full time Project Manager for proper co-ordination and effective management of site activities. Yours faithfully, CH Balakrishneé Team Leader cu XS¢ vor Hie Engineer, S.A. Infrastructure anis-P vt. Ltd., Kar-Wal, Six Lanning Project, Package-ll, Kancheepuram Copy to: * 1. The Project Director, NHAI, PIU — Kancheepuram. 2. H.O. S.A. Infrastructure Consultants Pvt. Ltd. Uttar Pradesh. INDIA. Tel. :+91-120-6148000 ¦ Tel./Fax: +91-120-6148090 | FALSE | real_data
Contractor's representative | Contractor's Obligations | It is observed that even-though sufficient time has been lapsed after commencing the above said Contract Agreement, till date there is no full time Project Manager has been deployed at site from your end. How-ever it is to note that Mr. G. Vijayakumar who is representing as Project Manager is attending the Co-ordination meetings & site inspections and rest of the time his presence at Project site is minimal. Hence it has been advised to arrange a full time Project Manager for proper co-ordination and effective management of site activities. | synthetic_template_20250913 | Presence of Project Manager at site: -Reg | Kindly be informed that Dear Sir, It is observed that even-though sufficient time has been lapsed after commencing the above said Contract Agreement, till date there is no full time Project Manager has been deployed at site from your end. How-ever it is to note that Mr. G. Vijayakumar who is representing as Project Manager Is attending the Co-ordination meetings & site inspections and rest of the time his presence at Project site is minimal. Hence it has been advised to arrange a full time Project Manager for proper co-ordination and effective management of site activities. Yours faithfully, CH Balakrishneé Team Leader cu XS¢ vor Hie Engineer, S.A. Infrastructure anis-P vt. Ltd., Kar-Wal, Six Lanning Project, Package-ll, Kancheepuram Copy to: * 1. The Project Director, NHAI, PIU — Kancheepuram. 2. H.O. S.A. Infrastructure Consultants Pvt. Ltd. Uttar Pradesh. INDIA. Tel. :+91-120-6148000 ¦ Tel./Fax: +91-120-6148090 | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Contractor's representative | Contractor's Obligations | It is observed that even-though sufficient time has been lapsed after commencing the above said Contract Agreement, till date there is no full time Project Manager has been deployed at site from your end. How-ever it is to note that Mr. G. Vijayakumar who is representing as Project Manager is attending the Co-ordination meetings & site inspections and rest of the time his presence at Project site is minimal. Hence it has been advised to arrange a full time Project Manager for proper co-ordination and effective management of site activities. | synthetic_template_20250913 | Presence of Project Manager at site: -Reg | Dear Sir, It is observed that even-though sufficient time has been lapsed after commencing the above said Contract Agreement, till date there is no full time Project Manager has been deployed at site from your end. How-ever it is to note that Mr. G. Vijayakumar who is representing as Project Manager Is attending the Co-ordination meetings & site inspections and rest of the time his presence at Project site is minimal. Hence it has been advised to arrange a full time Project Manager for proper co-ordination and effective management of site activities. Yours faithfully, CH Balakrishneé Team Leader cu XS¢ vor Hie Engineer, S.A. Infrastructure anis-P vt. Ltd., Kar-Wal, Six Lanning Project, Package-ll, Kancheepuram Copy to: * 1. The Project Director, NHAI, PIU — Kancheepuram. 2. H.O. S.A. Infrastructure Consultants Pvt. Ltd. Uttar Pradesh. INDIA. Tel. :+91-120-6148000 ¦ Tel./Fax: +91-120-6148090 | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Contractor's representative | Contractor's Obligations | (c) Status of obligations of the Contractor on Design and Construction of the Project Highway as per Article 10 of Agreement. | synthetic_template_20250913 | NHAIL, PIU - Krishnagiri - Six Laning of Karaipettai to Walajhapet section of NH-4 (New NH-48) from km.71.015 to km.107.091 in the State of Tamil Nadu under NHDP Phase-V under EPC Mode- M/s SPK é&Co -Declaration of Appointed Date—Reg. | Kindly be informed that With reference to the references 2nd & 3rd cited, the competent authority in NHAI vide reference 1st cited has communicated approval to declare appointed date as 11.02.2019 to commence the works. In view of the above, it is requested to submit the action taken on the following issues: (a) Status of obligations of the contractor as per Article 3 of agreement (b) Maintenance of the stretch during construction period as per clause 10.4 of Agreement for which the contractor is responsible for ensuring safe operation of Project Highway. (c) Status of obligations of the Contractor on Design and Construction of the Project Highway as per Article 10 of Agreement. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Contractor's representative | Contractor's Obligations | (c) Status of obligations of the Contractor on Design and Construction of the Project Highway as per Article 10 of Agreement. | synthetic_template_20250913 | NHAIL, PIU - Krishnagiri - Six Laning of Karaipettai to Walajhapet section of NH-4 (New NH-48) from km.71.015 to km.107.091 in the State of Tamil Nadu under NHDP Phase-V under EPC Mode- M/s SPK é&Co -Declaration of Appointed Date—Reg. | We hereby confirm that With reference to the references 2nd & 3rd cited, the competent authority in NHAI vide reference 1st cited has communicated approval to declare appointed date as 11.02.2019 to commence the works. In view of the above, it is requested to submit the action taken on the following issues: (a) Status of obligations of the contractor as per Article 3 of agreement (b) Maintenance of the stretch during construction period as per clause 10.4 of Agreement for which the contractor is responsible for ensuring safe operation of Project Highway. (c) Status of obligations of the Contractor on Design and Construction of the Project Highway as per Article 10 of Agreement. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Contractor's representative | Contractor's Obligations | (c) Status of obligations of the Contractor on Design and Construction of the Project Highway as per Article 10 of Agreement. | synthetic_template_20250913 | NHAIL, PIU - Krishnagiri - Six Laning of Karaipettai to Walajhapet section of NH-4 (New NH-48) from km.71.015 to km.107.091 in the State of Tamil Nadu under NHDP Phase-V under EPC Mode- M/s SPK é&Co -Declaration of Appointed Date—Reg. | With reference to the references 2nd & 3rd cited, the competent authority in NHAI vide reference 1st cited has communicated approval to declare appointed date as 11.02.2019 to commence the works. In view of the above, it is requested to submit the action taken on the following issues: (a) Status of obligations of the contractor as per Article 3 of agreement (b) Maintenance of the stretch during construction period as per clause 10.4 of Agreement for which the contractor is responsible for ensuring safe operation of Project Highway. (c) Status of obligations of the Contractor on Design and Construction of the Project Highway as per Article 10 of Agreement. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Appointment of Design Director | Contractor's Obligations | we have appointed Mr. Pattabiram Yegulla as "Design Director'' for the above mentioned project. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-1/1. Appointment of Design Director.pdf | Appointment of Design Director - Reg. | In pursuant to the article 10, clause 10.1.(B) of the Contract Agreement, we have appointed Mr. Pattabiram Yegulla as “Design Director” for the above mentioned project. This is for your kind information & Record please. | FALSE | real_data
Appointment of Design Director | Contractor's Obligations | (c) Status of obligations of the Contractor on Design and Construction of the Project Highway as per Article 10 of Agreement. | synthetic_template_20250913 | NHAIL, PIU - Krishnagiri - Six Laning of Karaipettai to Walajhapet section of NH-4 (New NH-48) from km.71.015 to km.107.091 in the State of Tamil Nadu under NHDP Phase-V under EPC Mode- M/s SPK é&Co -Declaration of Appointed Date—Reg. | With reference to the references 2nd & 3rd cited, the competent authority in NHAI vide reference 1st cited has communicated approval to declare appointed date as 11.02.2019 to commence the works. In view of the above, it is requested to submit the action taken on the following issues: (a) Status of obligations of the contractor as per Article 3 of agreement (b) Maintenance of the stretch during construction period as per clause 10.4 of Agreement for which the contractor is responsible for ensuring safe operation of Project Highway. (c) Status of obligations of the Contractor on Design and Construction of the Project Highway as per Article 10 of Agreement. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Appointment of Design Director | Contractor's Obligations | (c) Status of obligations of the Contractor on Design and Construction of the Project Highway as per Article 10 of Agreement. | synthetic_template_20250913 | NHAIL, PIU - Krishnagiri - Six Laning of Karaipettai to Walajhapet section of NH-4 (New NH-48) from km.71.015 to km.107.091 in the State of Tamil Nadu under NHDP Phase-V under EPC Mode- M/s SPK é&Co -Declaration of Appointed Date—Reg. | With reference to the references 2nd & 3rd cited, the competent authority in NHAI vide reference 1st cited has communicated approval to declare appointed date as 11.02.2019 to commence the works. In view of the above, it is requested to submit the action taken on the following issues: (a) Status of obligations of the contractor as per Article 3 of agreement (b) Maintenance of the stretch during construction period as per clause 10.4 of Agreement for which the contractor is responsible for ensuring safe operation of Project Highway. (c) Status of obligations of the Contractor on Design and Construction of the Project Highway as per Article 10 of Agreement. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Appointment of Design Director | Contractor's Obligations | we have appointed Mr. Pattabiram Yegulla as "Design Director'' for the above mentioned project. | synthetic_template_20250913 | Appointment of Design Director - Reg. | In pursuant to the article 10, clause 10.1.(B) of the Contract Agreement, we have appointed Mr. Pattabiram Yegulla as “Design Director” for the above mentioned project. This is for your kind information & Record please. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Appointment of Design Director | Contractor's Obligations | (c) Status of obligations of the Contractor on Design and Construction of the Project Highway as per Article 10 of Agreement. | synthetic_template_20250913 | NHAIL, PIU - Krishnagiri - Six Laning of Karaipettai to Walajhapet section of NH-4 (New NH-48) from km.71.015 to km.107.091 in the State of Tamil Nadu under NHDP Phase-V under EPC Mode- M/s SPK é&Co -Declaration of Appointed Date—Reg. | Please note that With reference to the references 2nd & 3rd cited, the competent authority in NHAI vide reference 1st cited has communicated approval to declare appointed date as 11.02.2019 to commence the works. In view of the above, it is requested to submit the action taken on the following issues: (a) Status of obligations of the contractor as per Article 3 of agreement (b) Maintenance of the stretch during construction period as per clause 10.4 of Agreement for which the contractor is responsible for ensuring safe operation of Project Highway. (c) Status of obligations of the Contractor on Design and Construction of the Project Highway as per Article 10 of Agreement. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Appointment of Design Director | Contractor's Obligations | (c) Status of obligations of the Contractor on Design and Construction of the Project Highway as per Article 10 of Agreement. | synthetic_template_20250913 | NHAIL, PIU - Krishnagiri - Six Laning of Karaipettai to Walajhapet section of NH-4 (New NH-48) from km.71.015 to km.107.091 in the State of Tamil Nadu under NHDP Phase-V under EPC Mode- M/s SPK é&Co -Declaration of Appointed Date—Reg. | With reference to the references 2nd & 3rd cited, the competent authority in NHAI vide reference 1st cited has communicated approval to declare appointed date as 11.02.2019 to commence the works. In view of the above, it is requested to submit the action taken on the following issues: (a) Status of obligations of the contractor as per Article 3 of agreement (b) Maintenance of the stretch during construction period as per clause 10.4 of Agreement for which the contractor is responsible for ensuring safe operation of Project Highway. (c) Status of obligations of the Contractor on Design and Construction of the Project Highway as per Article 10 of Agreement. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Modification of Appointed Date | Appointed Date; EoT; Dispute Resolution | The request of the Contractor to modify the appointed date is not eligible as per agreement due to the following reasons | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/972_03062019_Non acceptance of shifting of appointed date.pdf | NHAI, PIU - Krishnagiri — Six Laning of Karaipettai to Walajhapet section of NH+4 ( New NH~8) from km.71.015 to km.107.091 in the State of Tamil Nadu under NHDP Phase-V under EPC Mode- M's SPK &Co —Request for modification of Appointed date -Reg. | With reference to the letter 1* cited the following observations are made Para-I:- As per Annexure-II , Schedule-A dates for providing Right of Way the existing and proposed ROW is 60m at Plaza is 80m and is available as On appointed date . As per cl 8.2.2 the authority shall provide the Right of Way to the Contractor in respect of all land included in the Appendix by the date specified in Schedule-A for those parts of the site referred to therein, or no later than 90 days of the appointed date for those parts of the site which have not been specified in Schedule-A. From the above it is evident that the lands specified in Annexure-II, Schedule-A of agreement are available from the day one and as on appointed date, the existing and proposed ROW is same and no parts of the site is mentioned as not available in Schedule-A and joint memorandum signed on 11.01.2019 except for the lands for widening of plaza at Chennasamudram.Hence authority has fulfilled the obligation. ParaAs per cl 4.1.3 (a) — the authority shall provide to the contractor upon receiving the performance security under cl 7.1.] sthe right of way in accordance with the provisions of cl $.2 and 8.3 , within a period of 30 days from the date of this agreement , on no less than 90% of the total length of the project highway . As per joint memorandum signed by both the parties the length of project Highway covered is 36.076 Km _ on both sides and the total balance to be handed over ( length affected due to obstructions of structures and utilities ) is 6.35% ie 2.29 Km ( 36.076*6.35/100). Hence in length terms of the project highway also satisfied. It is a fact that the length affected due to structures and utility shifting for a length of 2.29 Km is not available to the contractor as on date. Para-4 — The joint memorandum signed by both the parties and as explained in para-3 the authority has taken action in shifting the Electrical utilities and dismantling of structures and the af! fected length is 2.29 Km out of total length of 36.076 Km. The unencumbered and vacant area available to the Contractor as per signed JM is 33.786 Km. Para-5 — From the strip map submitted the information regarding two types of encumbrances shown (Blue & Red Colour) and the Electrical poles the offset from centre line is not shown in the strip map. From the joint memorandum signed by both the parties the structures to be dismantled are almost at the edge of ROW and the length of highway affected is only 2.29 Km ,hence the encumbrance length handed over is coming out to 33.786 Km and hence the obligations are fulfilled by the authority as per cl 4.1.3 of agreement .Details is enclosed as Annexure-1. Para-6 — As per cl 10.1.2 of agreement the Authority has appointed the Authority Engineer M/s SA Infrastructure Consultants Pvt Ltd on 20.02.2019 and Mobilization is under progress .The Contractor has not submitted any designs for approval of AE. Para-7 — Mobilization of A E is under progress. ParaThe request of the Contractor to modify the appointed date is not eligible as per agreement due to the following reasons (i) As per cl 4.1.3, 8.2.1 & 8.2.2, 8.2.3-The agreement is signed on 15.10.2018 and the Joint memorandum is signed by both the parties on 30.01.2019 and appointed date is declared for the project on 11.2.2019 to commence the work. (it) As per cl 10.1.1 of agreement, the contractor has not submitted the details till date to the Authority. Further the Designs and Drawings as per cl 10.2.1 of agreement is not submitted for review of the Authority Engineer. (iii) The Camp Office and the laboratory of the Contractor is not yet established and Staff is not mobilized at site. (iv) The Contractor has not submitted the fulfilment of the obligations of the Contractor as per Article 3 of the agreement. | FALSE | real_data
Modification of Appointed Date | Appointed Date; EoT; Dispute Resolution | We now request you to expedite acquisition of land required for execution on priority and revise the day of Appointed Date as the date when 90% land is practically available. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-3/15. Revision of Appointed date 30.01.2018.pdf | Revision of Appointed Date - Reg. | The Appointed Date intimated vide letter no. NHD/Abad/TS-2/864, dated 05th May 2017 was on the assumptions that 90% of land/ROW is available to work. Please refer our letter no. RCM PVR JV/MH PWD/2017-18/71, dated 10th Aug 2017(Annexure-l). We submitted memorandum along with strip charts of each Km, which explicitly detailed encumbrances at site. Please refer page no 131 regarding definition of ROW, which should be free from encumbrances. Also please refer letter no RCM PVR JV/MH PWD/2017-18/71, dated 10th Aug 2017, stating that land for bus bay, Toll plaza, Truck lay bye also were not handed over(Annexure-ll). Later on, when we commenced work, we faced stiff resistance from property owners which was intimated vide letter no. RCM PVR JV/MH PWD/2018-19/70, dated 10th Aug 2017 and RCM PVR JV/MH PWD/2017-18/75, dated 23rd August 2017(Annexure-lll). Surprisingly, during the site visits of Tehsildars of Beed Taluka, Paithan Taluka, Sevgaon Taluka, Pathardi Taluka and Shirur Taluka, we were given to understand that PWD is not in possession of even a square inch of land even though NH752E is plying in these talukas. Thereafter the process of Land Acquisition started. Please refer our MPR's for all the months up to Dec17 for affected chainages (Annexure-IV). Even though the length of obstructed stretches was listed in the MPRs, contractually PWD, the Authority was not in possession of even 1% land. Hence, the date decided as 02nd Jun 2017 as Appointed Date without any ROW is contractually incorrect. Please refer Executive Engineer's letter no. NHD/Abad/1787. Dated 6th Sep 2017 last Para also (Annexure-V), in this connection. The 180 days from milestone —-I should be reckoned from the Appointed Date when 90% land is made available to the contractor to proceed with work. We understand from few correspondences (copies of 5 letters enclosed) (Annexure-Vi) that the commencement of joint survey to acquire land acquisition was from Dec17 and propagation on newspapers is yet to be made. Under these circumstances, we have been attempting to convince property owners to allow us to do work and the execution is being done in the limited land available at the mercy of land owners. This has resulted in idling of equipment/demobilization of plant & machinery due to disruption and the mobilization/un gainful deployment of equipment, delay in achieving milestones etc. The detailed financial impact will be intimated to you separately, since the above disadvantages are still ongoing. We now request you to expedite acquisition of land required for execution on priority and revise the day of Appointed Date as the date when 90% land is practically available. | FALSE | real_data
Modification of Appointed Date | Appointed Date; EoT; Dispute Resolution | Taking into consideration all these encumbrances, hindrances etc. the vacant access available on the appointed date declared was worked out and it was less than 90% and hence the Authority was requested to modify the appointed date on which 90% of encumbrance free highway would be made available to the EPC Contractor vide ref (4) cited above. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/40_07082019_Rescheduling of Project Milestones – Request for Extension of time.pdf | Rescheduling of Project Milestones - Request for Extension of time - Reg. | The Contract agreement for the above mentioned project was executed on 15.10.2018. The appointed date was fixed as 11.02.2019 and the same was communicated vide ref (3) cited above. The Copy of the same is herewith enclosed as Annexure 1. The Authority in its response vide ref (5) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. The copy of the same is enclosed as Annexure 3. The EPC contractor vide ref (6) cited above reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that still the condition remained the same and dismantling/ removal of structures fouling was not started and shifting of Electric pole and power line also not started. The impacted length due to encroachments and encumbrances was 12.18 Km which accounted to 33.77% of the project highway. The workable length available to the Contractor based on the impacted length was 66.23% of the Project Highway length. The EPC Contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of removal of encumbrance / encroachment / obstruction. The copy of ref (7) is herewith enclosed as Annexure 4. It is almost six months since the declaration of appointed date, removal/ dismantling of structures/encroachments have not been started. Also, the work of shifting of power line and electric pole of LT line and HT lines crossings have not been started yet. The following are some of the key contractual dates and events since the inception of the project to till date: 1. Total length of the project highway: 36.076 Km 2. Date of Signing of agreement: 152018 3. Submission of Performance BG as per Clause 7.1.1 of the Contract Agreement: 262018 4. Target date for preparation of Memorandum as per Clause 8.2.1 of the Contract Agreement: 142018 5. Actual date of signing of Memorandum of land handing over: 112019 6. Declaration of appointed date by the Authority: 112019 7. ROW to be handed over as on appointed date as per Clause 8.2.2 & Annexure II: 35.468 Km | FALSE | real_data
Modification of Appointed Date | Appointed Date; EoT; Dispute Resolution | The EPC Contractor vide his letter No. 49/SPK/Kar-wal/PD/NHAI dated 17.06.2019 requested the Authority to consider the ROW handed over in terms of length (as per Cl. 4.1.3 and not in terms of area ) and shift the Appointed Date based on the actual date of removal of encumbrance/encroachment/obstruction for which response is still awaited from the Authority | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20200129_SPK_AE_001_Reply on Rescheduling of Project Milestone - Request for EoT.pdf | Reply on Rescheduling of Project Milestones — Request for Extension of Time - Reg. | The Authority Engineer vide ref (3) cited above communicated his recommendation on the above captioned subject. The EPC Contractor would like to submit his observations which are as follows: 1. The EPC Contractor vide his letter No. 49 / SPK / Kar - Wal / PD / NHAI dated 17.06.2019 requested the Authority to consider the ROW handed over in terms of length (as per Cl. 4.1.3 and not in terms of area and shift the Appointed Date based on the actual date of removal of encumbrance / encroachment / obstruction for which response is still awaited from the Authority. Further, it is worth mentioning that the AE also reiterated our stand wherein it was mentioned in Authority Engineer recommendation that “It is also worth mentioning that this memorandum was signed based on the % of area of the project ROW, in place of % of length, as mentioned in the Clause 4.1.3 (a).” 2. The assessment of hindrance length by the EPC contractor is correct as irrespective of hindrance available on one side, the same has to be considered for entire six laning width. In this regard it is hereby requested that the definition of ROW as per Article 28 shall be referred for further clarity. Further a working strip of at least 3 m wide shall be available parallel from the toe of the embankment pursuant to Clause 8.3.1 of the Contract Agreement. Authority Engineer has not based on this provision. 3. We totally deny with the observation of the Authority Engineer in not considering delay in handing over of land by the Authority pursuant to 4.1.3 (a) and 8.3.2 of the Contract Agreement. It is worth mentioning that even as on date 90% of encumbrance free land is yet to be handed over which is against the provisions of the Contract Agreement as 90% of land should have been handed over within 30 days of the execution of the agreement as per 4.1.3 (a) i.e on or before 15/11 / 2019. The joint inspection done on 24.10.2019 and on which the Authority Engineer’s representative signed would prove that only 62.51% of length was available on that day. Even today the Authority Engineer may carry out a joint inspection and will find that hardly 70% of the length is available for work front if imparted length is considered. 4. The EPC Contractor is obligated to comply only with the provisions of the Contract Agreement and not bound by any internal circular of the Authority as mentioned in AE recommendation. Hence, we disagree with the contention of the Authority Engineer that the EPC Contractor is not entitled for EOT in light of the circular issued by the Authority dated 16.08.2019. 5. It has been explicitly mentioned in Authority Engineer’s recommendation that shifting of utilities was being taken care by the Authority. Further the Contract Agreement between the Authority and Utility shifting agency was executed only on 19.07.2019. It is evident that shifting of utilities was not taken up till 19.07.2019, i.e 158 days from the declaration of Appointed Date by the Authority. Since the Authority is taking care of utility shifting and the agency appointed by the Authority commenced the works only after 180 days of the Appointed Date, period of 180 days mentioned in Clause 9.2is has no relevance. Hence, we deny with the contention of the Authority Engineer that the Contractor is entitled for time extension only beyond 180 days. The project duration is only 24 months and first 6 months are very crucial for the EPC contractor to progress the works based on his targeted programme. The Authority Engineer is also reiterating our concern wherein it has been mentioned that, ’The shifting of Utilities is important for this project, as the project is a Toll road and considering this, the Contractor submitted Construction Methodology, stating that first service road is to be constructed and after diverting the traffic over there, Main carriageway would be constructed ” . Utility shifting work is also not progressing as the encumbrances have not been removed and space is not made available for relocating the utility. 6. We would like to submit that as per Cl. 6 of Schedule-J , the Extension of Time recommendation is for Scheduled Project Completion Date and not confined to Milestone I. Based on the EOT recommended, all the milestones get automatically rescheduled accordingly. Hence, we do not agree with the contention of the Authority Engineer that the Extension of Time for Project. | FALSE | real_data
Modification of Appointed Date | Appointed Date; EoT; Dispute Resolution | Taking into consideration all these encumbrances, hindrances etc. the vacant access available on the appointed date declared was worked out and it was less than 90% and hence requested the Authority vide letter under ref (3) cited above for modification of the appointed date on which 90% encumbrance free land would be made available to the Contractor. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20201119_SPK_AE_160_Contractor failure in achieving mile stone 1,2,&3.pdf | Six laning of Karaipcttai to Walajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - Contractor’s failure in achieving Project Mile Stone 1,2 & 3 applying of Damages vide Contract Article No. 10.3.2 & 10.3.3 - Reply made -Reg. | We are in receipt of your letter ref (26) cited above, our reply for the same is as follows: 1. The Contract Agreement for this Project was executed on 15.10.2018. The Appointed Date was fixed as 11.02.2019 and the same was communicated vide ref (2) cited above. 2. The Appointed date was declared as 11.02.2019 by the Authority taking into account the land handed over in terms of the available area without taking into consideration, the requirement of the Contract provision as per Clause 4.1.3 (a) of the EPC agreement which talks about the handing over of land only in terms of length of the Project Highway. The memorandum and appendix prepared in terms of area gave a deceptive / false picture about the availability of vacant access. Taking into consideration all the encumbrances, hindrances, utilities etc. the vacant access available on the appointed date declared was worked out and it was less than 90% and hence requested the Authority vide letter under ref (3) cited above for modification of the appointed date on which 90% of encumbrance free land would be made available to the Contractor. 3. The Authority in its response vide ref (4) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. 4. The EPC contractor vide ref (5) cited above in reply reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that the impacted length due to encroachments and encumbrances was 12.18 km which accounted to 33.77% of the project length. The workable length available to the contractor was only 66.23% of the project length. The EPC contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of encumbrance / encroachment / obstruction. | FALSE | real_data
Modification of Appointed Date | Appointed Date; EoT; Dispute Resolution | Taking into consideration all these encumbrances, hindrances etc. the vacant access available on the appointed date declared was worked out and it was less than 90% and hence the Authority was requested to modify the appointed date on which 90% encumbrance free highway would be made available to the EPC Contractor vide ref(5) cited above. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20210416_SPK_AE_067_EOT request with Delay analysis.pdf | Six laning of Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V -EOT recommendation by the Authority for a period of 112 days not agreeable to the EPC Contractor — Request for considering EOT as discussed during the Review Meetings- reg | We are writing to express our concerns regarding the EOT recommendation by the Authority for a period of 112 days, which is not agreeable to the EPC Contractor. We request that the EOT be considered as discussed during the Review Meetings. The project involves six laning of the Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km 71+015 to km 107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase-V. We have referenced several documents and meetings in support of our request, and we hope for a favorable consideration. | FALSE | real_data
Modification of Appointed Date | Appointed Date; EoT; Dispute Resolution | Further, it is submitted that the Joint memorandum was signed on 1 1.01.2019 & the appointment date is declared as 11.02.2019. The Contractor has requested the Authority for modifying the Appointment date based on the length of Project Highway handed over, vide letter No.HAI/ Dated 13.05.2019. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/264_18022020_Rescheduling of Project Milestones – Request for Extension of Time.pdf | Rescheduling of Project Milestones — Request for Extension of Time -Reg. | In reference to the above-mentioned subject and Contractor letter No. SPK/KW/SAIC/NH-48/2020/001 dated 29.01.2020 regarding the rescheduling of Project Milestone, in this regard, it is submitted that AE has computed the 176 days for extension of time in Milestones I and II. The same was recommended vide AE letter No. SAICPL/Kar-Wal/H.O./NH-48/TN/2019/10451 dated 30.11.2019 to the Authority for their acceptance and further needful. However, the Contractor submitted his reservations on the computation of the nos. of delay days and requested for rescheduling of Project Milestones for a period of 324 days instead of recommended 176 nos. of days. In this regard, AE is hereby submitted point wise reply of your raised observations for your ready reference and record, please; 4. Modification of Appointed date and Handing Over in % of area. The appointed date was communicated by the Authority letter No. NHAI/PIU.K.giri/NH-4/SPK/PS/2019/972 Dated 03.06.2019. it is also submitted that as per cl 8.2.2 the authority shall provide the Right of Way to the Contractor in respect of all land included in the Appendix by the date specified in Schedule-A for those parts of the site referred to therein, or no later than 90 days of the appointed date for those parts of the site which have not been specified in Schedule-A. It is well evident that the lands specified in Annexure-II, Schedule-A of agreement are available from the day one and as on appointed date, the existing and proposed ROW is same and no parts of the site is mentioned as not available in Schedule-A and joint memorandum signed on 11.01.2019 except for the lands for widening of plaza at Chennasamudram. Hence authority has fulfilled the obligation. This was informed vide Authority letter No. NHAI/PIU.K.giri/NH-4/SPK/PS/2019/972 Dated 03.06.2019. In view of above, the request of the Contractor to modify the appointed date is not eligible as per agreement due to the following reasons (i) As per cl 4.1.3, 8.2.1 & 8.2.2, 8.2.3 — The agreement is signed on 15.10.2018 and the Joint memorandum is signed by both the parties on 30.01.2019 and appointed date is declared for the project on 11.02.2019 to commence the work. (i) The Authority Engineer vide Letter No. SAICPL/Kar-Wal/H.O./NH-48/TN/2019/10451 Dated 30.11.2019. informed that the contractor consciously agreed and signed the Joint memorandum and aware that the unencumbered and the vacant land available after joint inspection is 93.65%. (iii) Further, it is submitted that the Joint memorandum was signed on 11.01.2019 & the appointment date is declared as 11.02.2019. The Contractor has requested the Authority for modifying the Appointment date based on the length of Project Highway handed over, vide letter No. 29/SPK/Kar-Wal/PD/NHAI/ Dated 13.05.2019. On this account and in view of clause 8.3.2 of the Contract Agreement, the Contractor cited reason of land not handed over pursuant to Clause 4.1.3 (a) is not acceptable and cannot be considered for Entitlement for EOT. 2. Assessment of Hindrance length. The assessment of hindrance length is already enumerated in Point No. 01 above. It is to remind the contractor that the Joint memorandum was signed by both the parties on 30.01.2019 as per the provisions of the Contract Agreement. The AE hereby like to reiterate the clause 8.2.1. “The Authority Representative and the Contractor shall, within 30 (thirty) days of the date of this Agreement, inspect the Site and prepare a memorandum containing an inventory of the Site including the vacant and unencumbered land, buildings, structures, road works, trees and any other immovable property on or attached to the Site. Subject to the provisions of Clause 8.2.3, such memorandum shall have appended thereto an appendix (the “Appendix”) specifying in reasonable detail those parts of the Site to which vacant access and Right of Way has not been given to the Contractor. Signing of the memorandum, in two counterparts (each of which shall constitute an original), by the authorized representatives of the Parties shall be deemed to constitute a valid evidence of giving the Right of Way to the Contractor for discharging its obligations under and in accordance with the provisions of this Agreement and for no other purpose whatsoever’. AE would like to further clarify that cl. 8.3.1 last para stating that “For the avoidance of doubt, the Parties expressly agree that the Damages specified hereunder and the Time Extension specified in Clause 10.5 shall be restricted only to failure of the Authority to provide the Right of Way for and in respect of the width of the roadway, its embankment and a parallel working strip at least 3 (three) meters wide”. The width of the roadway can be treated as one side of the road since it is neither mentioned “Total width nor Full width’. Hence the Authority Engineer has done the analysis of Hindrance free length is clear with the above illustrated iteration. | FALSE | real_data
Providing Right of Way as per Schedule A | Authority's Obligations; EoT; Dispute Resolution | From the above it is evident that the lands specified in Annexure-Il, Schedule-A of agreement are available from the day one and as on appointed date, the existing and proposed ROW is same and no parts of the site is mentioned as not available in Schedule-A and joint memorandum signed on 11.01-2019 except for the lands for widening of plaza at Chennasamudram. Hence authority has fulfilled the obligation. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/972_03062019_Non acceptance of shifting of appointed date.pdf | NHAI, PIU - Krishnagiri — Six Laning of Karaipettai to Walajhapet section of NH+4 ( New NH~8) from km.71.015 to km.107.091 in the State of Tamil Nadu under NHDP Phase-V under EPC Mode- M's SPK &Co —Request for modification of Appointed date -Reg. | With reference to the letter 1* cited the following observations are made Para-I:- As per Annexure-II , Schedule-A dates for providing Right of Way the existing and proposed ROW is 60m at Plaza is 80m and is available as On appointed date . As per cl 8.2.2 the authority shall provide the Right of Way to the Contractor in respect of all land included in the Appendix by the date specified in Schedule-A for those parts of the site referred to therein, or no later than 90 days of the appointed date for those parts of the site which have not been specified in Schedule-A. From the above it is evident that the lands specified in Annexure-II, Schedule-A of agreement are available from the day one and as on appointed date, the existing and proposed ROW is same and no parts of the site is mentioned as not available in Schedule-A and joint memorandum signed on 11.01.2019 except for the lands for widening of plaza at Chennasamudram.Hence authority has fulfilled the obligation. ParaAs per cl 4.1.3 (a) — the authority shall provide to the contractor upon receiving the performance security under cl 7.1.] sthe right of way in accordance with the provisions of cl $.2 and 8.3 , within a period of 30 days from the date of this agreement , on no less than 90% of the total length of the project highway . As per joint memorandum signed by both the parties the length of project Highway covered is 36.076 Km _ on both sides and the total balance to be handed over ( length affected due to obstructions of structures and utilities ) is 6.35% ie 2.29 Km ( 36.076*6.35/100). Hence in length terms of the project highway also satisfied. It is a fact that the length affected due to structures and utility shifting for a length of 2.29 Km is not available to the contractor as on date. Para-4 — The joint memorandum signed by both the parties and as explained in para-3 the authority has taken action in shifting the Electrical utilities and dismantling of structures and the af! fected length is 2.29 Km out of total length of 36.076 Km. The unencumbered and vacant area available to the Contractor as per signed JM is 33.786 Km. Para-5 — From the strip map submitted the information regarding two types of encumbrances shown (Blue & Red Colour) and the Electrical poles the offset from centre line is not shown in the strip map. From the joint memorandum signed by both the parties the structures to be dismantled are almost at the edge of ROW and the length of highway affected is only 2.29 Km ,hence the encumbrance length handed over is coming out to 33.786 Km and hence the obligations are fulfilled by the authority as per cl 4.1.3 of agreement .Details is enclosed as Annexure-1. Para-6 — As per cl 10.1.2 of agreement the Authority has appointed the Authority Engineer M/s SA Infrastructure Consultants Pvt Ltd on 20.02.2019 and Mobilization is under progress .The Contractor has not submitted any designs for approval of AE. Para-7 — Mobilization of A E is under progress. ParaThe request of the Contractor to modify the appointed date is not eligible as per agreement due to the following reasons (i) As per cl 4.1.3, 8.2.1 & 8.2.2, 8.2.3-The agreement is signed on 15.10.2018 and the Joint memorandum is signed by both the parties on 30.01.2019 and appointed date is declared for the project on 11.2.2019 to commence the work. (it) As per cl 10.1.1 of agreement, the contractor has not submitted the details till date to the Authority. Further the Designs and Drawings as per cl 10.2.1 of agreement is not submitted for review of the Authority Engineer. (iii) The Camp Office and the laboratory of the Contractor is not yet established and Staff is not mobilized at site. (iv) The Contractor has not submitted the fulfilment of the obligations of the Contractor as per Article 3 of the agreement. | FALSE | real_data
Providing Right of Way as per Schedule A | Authority's Obligations; EoT; Dispute Resolution | The unencumbered and vacant area available to the Contractor based on the impacted length is 66.23%. The affected length is 12.18 Km out of total length of 36.076 Km. The details of existing encumbrances along the project highway is herewith enclosed as Annexure-1. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/49_17062019_ Modification of Appointed Date.pdf | Request for modification of appointed date - Reply made - reg. | from _all encroachments and encumbrances, and free access thereto for the execution of this agreement.” Even today, ROW handed over is not free from all encroachments and encumbrances. There are structures which are fouling within ROW which are to be dismantled. No action has been taken on this issue by the 2. It is also submitted that the following structures couldn’t be taken up due to encumbrances/ obstructions as given in the remark’s column in the table below. Bund, Buildi d_ shifti f electri 82/566 ¦ vup ¦ Hs ¦ Buildings, Hut and shifting of electric pole. 85/874 ¦ LvuP ¦ BHS ¦ Pylon ~ 2 Nos. (RHS) & Pond Bund (LHS). ¦S {93/115 ¦ vup ¦ Bris —¦ Buildings to be eno ¦ 6 ¦ 98/423 ¦ Vup ¦ BES _¦ Buildings to be removed. ¦ LHS ¦ Building and temporary shed to be removed. RHS Boundary wall, building, water tank and temporary structure. above mentioned structures is one year. The same is also endorsed in policy circular — Policy matters — Technical ( 195/2016) dated 19. 1.2016 of the Authority while determining Extension of Time. event for extension of time if required. However, it has been three weeks since model code of conduct has been lifted and work of removal of encumbrance/ obstruction has not been started. As per the discussion had with the appointed entity for utility shifting, it was identified and concluded that shifting of electrical poles in the already encumbered portion can be taken up only after removal of encumbrances/ obstructions as land was not available. Utility shifting is also interlinked with removal of encumbrance/encroachments. Hence i requested to remove the encumbrance and provide vacant acc Clause 8.1 of the Contract Agreement. | FALSE | real_data
Providing Right of Way as per Schedule A | Authority's Obligations; EoT; Dispute Resolution | Authority's primary obligation is to provide the 90% length of ROW within 30 days from the date of Agreement. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-1/8. Request to grant an Extension of Time under Clause 10.5 of the Contract Agreement..pdf | Request to grant an Extension of Time under Clause 10.5 of the Contract Agreement | 1. This is with reference to our various representations/submissions regarding various events on delay which has adversely affected the construction activities of Project and are still persisting at site resulting delay in completion of construction works as per scope envisaged under Contract Agreement. 2. We take this opportunity to summarize the facts chronologically as below giving rise to the claim for an Extension of Time (“EOT”) in accordance with the provisions of this Agreement on account of various delay events. Contract Particulars: Development Corporation Limited Authority Engineer Accepted Contract Price Construction Period Appointed Date 26.11.2021 Stipulated Completion Date ¦ 19.05.2023 Request for EOT by this 135 days Cl 01.10.2023 Revised Completion Date Background Facts: 3. The National Highway & Infrastructure Development Corporation Limited (“Authority”) had issued the LOA dated 02.09.2021 (Ref#01) in favor of B.R Goyal Infrastructure Limited (“Contractor"). The formal Contract Agreement was signed on 08.10.2021. In pursuant to the conditions of LOA, we had submitted the Performance Security and Additional Performance Security in the form of Bank Guarantees (PBG and APBG) vide our letters dated 28.09.2021 and 02.11.2021 (Ref #2 & 4 above). It is in place to mention that the Contractor have discharged its prime obligation i.e. submission of Performance Security and Additional Performance Security, well within time limit. To ensure the start of construction activities immediate after declaration of Appointed Date, Contractor has mobilized the adequate manpower & machinery resources at site after receiving of LOA. In pursuant to the provisions of the Contract Agreement, Authority’s primary obligation is to provide the 90% length of ROW within 30 days from the date of Agreement. However, after signing of CA, both the parties visited the site and it | FALSE | real_data
Providing Right of Way as per Schedule A | Authority's Obligations; EoT; Dispute Resolution | Pursuant to Clause 82.2 and 8.2.3 of the EPC Agreement, the Authority should have provided Right of way for 100% length of the project highway on appointed date plus 90 days, i.e. 11.05.2019. As apparent from the above table, it is brought to your notice that this requirement has not been fulfilled by the Authority even as on date. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/40_07082019_Rescheduling of Project Milestones – Request for Extension of time.pdf | Rescheduling of Project Milestones - Request for Extension of time - Reg. | The Contract agreement for the above mentioned project was executed on 15.10.2018. The appointed date was fixed as 11.02.2019 and the same was communicated vide ref (3) cited above. The Copy of the same is herewith enclosed as Annexure 1. The Authority in its response vide ref (5) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. The copy of the same is enclosed as Annexure 3. The EPC contractor vide ref (6) cited above reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that still the condition remained the same and dismantling/ removal of structures fouling was not started and shifting of Electric pole and power line also not started. The impacted length due to encroachments and encumbrances was 12.18 Km which accounted to 33.77% of the project highway. The workable length available to the Contractor based on the impacted length was 66.23% of the Project Highway length. The EPC Contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of removal of encumbrance / encroachment / obstruction. The copy of ref (7) is herewith enclosed as Annexure 4. It is almost six months since the declaration of appointed date, removal/ dismantling of structures/encroachments have not been started. Also, the work of shifting of power line and electric pole of LT line and HT lines crossings have not been started yet. The following are some of the key contractual dates and events since the inception of the project to till date: 1. Total length of the project highway: 36.076 Km 2. Date of Signing of agreement: 152018 3. Submission of Performance BG as per Clause 7.1.1 of the Contract Agreement: 262018 4. Target date for preparation of Memorandum as per Clause 8.2.1 of the Contract Agreement: 142018 5. Actual date of signing of Memorandum of land handing over: 112019 6. Declaration of appointed date by the Authority: 112019 7. ROW to be handed over as on appointed date as per Clause 8.2.2 & Annexure II: 35.468 Km | FALSE | real_data
Providing Right of Way as per Schedule A | Authority's Obligations; EoT; Dispute Resolution | It is worth mentioning that even as on date 90% of encumbrance free land is yet to be handed over which is against the provisions of the Contract Agreement as 90% of land should have been handed over within 30 days of the execution of the agreement as per 4.1.3 (a) i.e. on or before 15/11/2019. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20200129_SPK_AE_001_Reply on Rescheduling of Project Milestone - Request for EoT.pdf | Reply on Rescheduling of Project Milestones — Request for Extension of Time - Reg. | The Authority Engineer vide ref (3) cited above communicated his recommendation on the above captioned subject. The EPC Contractor would like to submit his observations which are as follows: 1. The EPC Contractor vide his letter No. 49 / SPK / Kar - Wal / PD / NHAI dated 17.06.2019 requested the Authority to consider the ROW handed over in terms of length (as per Cl. 4.1.3 and not in terms of area and shift the Appointed Date based on the actual date of removal of encumbrance / encroachment / obstruction for which response is still awaited from the Authority. Further, it is worth mentioning that the AE also reiterated our stand wherein it was mentioned in Authority Engineer recommendation that “It is also worth mentioning that this memorandum was signed based on the % of area of the project ROW, in place of % of length, as mentioned in the Clause 4.1.3 (a).” 2. The assessment of hindrance length by the EPC contractor is correct as irrespective of hindrance available on one side, the same has to be considered for entire six laning width. In this regard it is hereby requested that the definition of ROW as per Article 28 shall be referred for further clarity. Further a working strip of at least 3 m wide shall be available parallel from the toe of the embankment pursuant to Clause 8.3.1 of the Contract Agreement. Authority Engineer has not based on this provision. 3. We totally deny with the observation of the Authority Engineer in not considering delay in handing over of land by the Authority pursuant to 4.1.3 (a) and 8.3.2 of the Contract Agreement. It is worth mentioning that even as on date 90% of encumbrance free land is yet to be handed over which is against the provisions of the Contract Agreement as 90% of land should have been handed over within 30 days of the execution of the agreement as per 4.1.3 (a) i.e on or before 15/11 / 2019. The joint inspection done on 24.10.2019 and on which the Authority Engineer’s representative signed would prove that only 62.51% of length was available on that day. Even today the Authority Engineer may carry out a joint inspection and will find that hardly 70% of the length is available for work front if imparted length is considered. 4. The EPC Contractor is obligated to comply only with the provisions of the Contract Agreement and not bound by any internal circular of the Authority as mentioned in AE recommendation. Hence, we disagree with the contention of the Authority Engineer that the EPC Contractor is not entitled for EOT in light of the circular issued by the Authority dated 16.08.2019. 5. It has been explicitly mentioned in Authority Engineer’s recommendation that shifting of utilities was being taken care by the Authority. Further the Contract Agreement between the Authority and Utility shifting agency was executed only on 19.07.2019. It is evident that shifting of utilities was not taken up till 19.07.2019, i.e 158 days from the declaration of Appointed Date by the Authority. Since the Authority is taking care of utility shifting and the agency appointed by the Authority commenced the works only after 180 days of the Appointed Date, period of 180 days mentioned in Clause 9.2is has no relevance. Hence, we deny with the contention of the Authority Engineer that the Contractor is entitled for time extension only beyond 180 days. The project duration is only 24 months and first 6 months are very crucial for the EPC contractor to progress the works based on his targeted programme. The Authority Engineer is also reiterating our concern wherein it has been mentioned that, ’The shifting of Utilities is important for this project, as the project is a Toll road and considering this, the Contractor submitted Construction Methodology, stating that first service road is to be constructed and after diverting the traffic over there, Main carriageway would be constructed ” . Utility shifting work is also not progressing as the encumbrances have not been removed and space is not made available for relocating the utility. 6. We would like to submit that as per Cl. 6 of Schedule-J , the Extension of Time recommendation is for Scheduled Project Completion Date and not confined to Milestone I. Based on the EOT recommended, all the milestones get automatically rescheduled accordingly. Hence, we do not agree with the contention of the Authority Engineer that the Extension of Time for Project. | FALSE | real_data
Providing Right of Way as per Schedule A | Authority's Obligations; EoT; Dispute Resolution | The Authority is yet to fulfil the obligations relating to handing over of ROW as per Sub Clause 8.2 of the Contract Agreement. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20200713_SPK_RO_42_Reminder - Request for revisiting the EOT already recommended - Rev2.pdf | Extension of Time and Rescheduling of Project Milestones - EOT granted for 112 days not acceptable to the EPC contractor - Request for revisiting the EOT recommended - Reminder sent - Reg. | 1. This is with respect to the Extension of Time(EOT} approved by the Authority for. a period of 112 days for Project Milestone-I without effecting changes in Scheduled Project Completion Period vide ref (3) cited above.The EPC Contrator disagrees and does not accept the grant of EOT approval for 112 days, the reasons for disgreeement of this approval are elaborated in our submission to the Authority Engineer vide ref (4) cited above. 2. The EPC contractor requested the Authority/NHAI to revisit the EOT determined/approved and communicate 324 days as interim Extension of time vide ref (5) cited above but, we are yet to receive response in this regard. Copy of the same is herewith enclosed as Annexure 1. 3. The Authority is yet to fulfil the obligations relating to handing over of ROW as per Sub Clause 8.2 of the Contract Agreement. Copy of the newspaper publication regarding LA status / notification for acquiring land for the Project Highway (Kanchipuram District} is herewith enclosed as Annexure 2. By not fulfilling the obligations as per the provisions of the Contract Agreement, the Authority committed a material default pursuant to Sub clause 23.2.1 (a) of the Contract Agreement. 4. The electrical pole/Transformer shifting is yet to be completed by the Authority even as on date and following are the Chainages whether shifting is required to be carried out: No.of Transformers In addition to the above, following locations listed below where shifting of High Tension(HT) Towerlines are required to be carried out: No. of HT Towers Status All Material mobilized at site. Due to Lockdown Estimate Approved on 22.02.2020. Electrical Contractor engaged by EPC Contractor on 20.03.2020 for shifting works. Due to Lockdown work yet to be taken-up. Estimate yet to be approved. Estimate yet to be approved. | FALSE | real_data
Providing Right of Way as per Schedule A | Authority's Obligations; EoT; Dispute Resolution | From the above table it can be understood that even on 04.03.2020, i.e. after 13 months from Appointed Date, 90% of the Project Highway length was not made available and condition precedent was not fulfilled by the Authority. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20201119_SPK_AE_160_Contractor failure in achieving mile stone 1,2,&3.pdf | Six laning of Karaipcttai to Walajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - Contractor’s failure in achieving Project Mile Stone 1,2 & 3 applying of Damages vide Contract Article No. 10.3.2 & 10.3.3 - Reply made -Reg. | We are in receipt of your letter ref (26) cited above, our reply for the same is as follows: 1. The Contract Agreement for this Project was executed on 15.10.2018. The Appointed Date was fixed as 11.02.2019 and the same was communicated vide ref (2) cited above. 2. The Appointed date was declared as 11.02.2019 by the Authority taking into account the land handed over in terms of the available area without taking into consideration, the requirement of the Contract provision as per Clause 4.1.3 (a) of the EPC agreement which talks about the handing over of land only in terms of length of the Project Highway. The memorandum and appendix prepared in terms of area gave a deceptive / false picture about the availability of vacant access. Taking into consideration all the encumbrances, hindrances, utilities etc. the vacant access available on the appointed date declared was worked out and it was less than 90% and hence requested the Authority vide letter under ref (3) cited above for modification of the appointed date on which 90% of encumbrance free land would be made available to the Contractor. 3. The Authority in its response vide ref (4) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. 4. The EPC contractor vide ref (5) cited above in reply reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that the impacted length due to encroachments and encumbrances was 12.18 km which accounted to 33.77% of the project length. The workable length available to the contractor was only 66.23% of the project length. The EPC contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of encumbrance / encroachment / obstruction. | FALSE | real_data
Providing Right of Way as per Schedule A | Authority's Obligations; EoT; Dispute Resolution | It is well evident that the lands specified in Annexure-Il, Schedule-A of agreement are available from the day one and as on appointed date, the existing and proposed ROW is same and no parts of the site is mentioned as not available in Schedule-A and joint memorandum signed on 1 1.01.2019 except for the lands for widening of plaza at Chennasamudram. Hence authority has fulfilled the obligation. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/264_18022020_Rescheduling of Project Milestones – Request for Extension of Time.pdf | Rescheduling of Project Milestones — Request for Extension of Time -Reg. | In reference to the above-mentioned subject and Contractor letter No. SPK/KW/SAIC/NH-48/2020/001 dated 29.01.2020 regarding the rescheduling of Project Milestone, in this regard, it is submitted that AE has computed the 176 days for extension of time in Milestones I and II. The same was recommended vide AE letter No. SAICPL/Kar-Wal/H.O./NH-48/TN/2019/10451 dated 30.11.2019 to the Authority for their acceptance and further needful. However, the Contractor submitted his reservations on the computation of the nos. of delay days and requested for rescheduling of Project Milestones for a period of 324 days instead of recommended 176 nos. of days. In this regard, AE is hereby submitted point wise reply of your raised observations for your ready reference and record, please; 4. Modification of Appointed date and Handing Over in % of area. The appointed date was communicated by the Authority letter No. NHAI/PIU.K.giri/NH-4/SPK/PS/2019/972 Dated 03.06.2019. it is also submitted that as per cl 8.2.2 the authority shall provide the Right of Way to the Contractor in respect of all land included in the Appendix by the date specified in Schedule-A for those parts of the site referred to therein, or no later than 90 days of the appointed date for those parts of the site which have not been specified in Schedule-A. It is well evident that the lands specified in Annexure-II, Schedule-A of agreement are available from the day one and as on appointed date, the existing and proposed ROW is same and no parts of the site is mentioned as not available in Schedule-A and joint memorandum signed on 11.01.2019 except for the lands for widening of plaza at Chennasamudram. Hence authority has fulfilled the obligation. This was informed vide Authority letter No. NHAI/PIU.K.giri/NH-4/SPK/PS/2019/972 Dated 03.06.2019. In view of above, the request of the Contractor to modify the appointed date is not eligible as per agreement due to the following reasons (i) As per cl 4.1.3, 8.2.1 & 8.2.2, 8.2.3 — The agreement is signed on 15.10.2018 and the Joint memorandum is signed by both the parties on 30.01.2019 and appointed date is declared for the project on 11.02.2019 to commence the work. (i) The Authority Engineer vide Letter No. SAICPL/Kar-Wal/H.O./NH-48/TN/2019/10451 Dated 30.11.2019. informed that the contractor consciously agreed and signed the Joint memorandum and aware that the unencumbered and the vacant land available after joint inspection is 93.65%. (iii) Further, it is submitted that the Joint memorandum was signed on 11.01.2019 & the appointment date is declared as 11.02.2019. The Contractor has requested the Authority for modifying the Appointment date based on the length of Project Highway handed over, vide letter No. 29/SPK/Kar-Wal/PD/NHAI/ Dated 13.05.2019. On this account and in view of clause 8.3.2 of the Contract Agreement, the Contractor cited reason of land not handed over pursuant to Clause 4.1.3 (a) is not acceptable and cannot be considered for Entitlement for EOT. 2. Assessment of Hindrance length. The assessment of hindrance length is already enumerated in Point No. 01 above. It is to remind the contractor that the Joint memorandum was signed by both the parties on 30.01.2019 as per the provisions of the Contract Agreement. The AE hereby like to reiterate the clause 8.2.1. “The Authority Representative and the Contractor shall, within 30 (thirty) days of the date of this Agreement, inspect the Site and prepare a memorandum containing an inventory of the Site including the vacant and unencumbered land, buildings, structures, road works, trees and any other immovable property on or attached to the Site. Subject to the provisions of Clause 8.2.3, such memorandum shall have appended thereto an appendix (the “Appendix”) specifying in reasonable detail those parts of the Site to which vacant access and Right of Way has not been given to the Contractor. Signing of the memorandum, in two counterparts (each of which shall constitute an original), by the authorized representatives of the Parties shall be deemed to constitute a valid evidence of giving the Right of Way to the Contractor for discharging its obligations under and in accordance with the provisions of this Agreement and for no other purpose whatsoever’. AE would like to further clarify that cl. 8.3.1 last para stating that “For the avoidance of doubt, the Parties expressly agree that the Damages specified hereunder and the Time Extension specified in Clause 10.5 shall be restricted only to failure of the Authority to provide the Right of Way for and in respect of the width of the roadway, its embankment and a parallel working strip at least 3 (three) meters wide”. The width of the roadway can be treated as one side of the road since it is neither mentioned “Total width nor Full width’. Hence the Authority Engineer has done the analysis of Hindrance free length is clear with the above illustrated iteration. | FALSE | real_data
Model code of conduct | EoT | We agree that model code of conduct was being in force and many activities were affected. Hence, we request the Authority to take this it into consideration as an event for extension of time if required. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/49_17062019_ Modification of Appointed Date.pdf | Request for modification of appointed date - Reply made - reg. | from _all encroachments and encumbrances, and free access thereto for the execution of this agreement.” Even today, ROW handed over is not free from all encroachments and encumbrances. There are structures which are fouling within ROW which are to be dismantled. No action has been taken on this issue by the 2. It is also submitted that the following structures couldn’t be taken up due to encumbrances/ obstructions as given in the remark’s column in the table below. Bund, Buildi d_ shifti f electri 82/566 ¦ vup ¦ Hs ¦ Buildings, Hut and shifting of electric pole. 85/874 ¦ LvuP ¦ BHS ¦ Pylon ~ 2 Nos. (RHS) & Pond Bund (LHS). ¦S {93/115 ¦ vup ¦ Bris —¦ Buildings to be eno ¦ 6 ¦ 98/423 ¦ Vup ¦ BES _¦ Buildings to be removed. ¦ LHS ¦ Building and temporary shed to be removed. RHS Boundary wall, building, water tank and temporary structure. above mentioned structures is one year. The same is also endorsed in policy circular — Policy matters — Technical ( 195/2016) dated 19. 1.2016 of the Authority while determining Extension of Time. event for extension of time if required. However, it has been three weeks since model code of conduct has been lifted and work of removal of encumbrance/ obstruction has not been started. As per the discussion had with the appointed entity for utility shifting, it was identified and concluded that shifting of electrical poles in the already encumbered portion can be taken up only after removal of encumbrances/ obstructions as land was not available. Utility shifting is also interlinked with removal of encumbrance/encroachments. Hence i requested to remove the encumbrance and provide vacant acc Clause 8.1 of the Contract Agreement. | FALSE | real_data
Model code of conduct | EoT | The length affected due to structures and Utility shifting for a length 2.29 Km could not be taken up due to model code of conduct | synthetic_template_20250913 | NHAI, PIU - Krishnagiri — Six Laning of Karaipettai to Walajhapet section of NH+4 ( New NH~8) from km.71.015 to km.107.091 in the State of Tamil Nadu under NHDP Phase-V under EPC Mode- M's SPK &Co —Request for modification of Appointed date -Reg. | This is to notify you that With reference to the letter 1* cited the following observations are made Para-I:- As per Annexure-II , Schedule-A dates for providing Right of Way the existing and proposed ROW is 60m at Plaza is 80m and is available as On appointed date . As per cl 8.2.2 the authority shall provide the Right of Way to the Contractor in respect of all land included in the Appendix by the date specified in Schedule-A for those parts of the site referred to therein, or no later than 90 days of the appointed date for those parts of the site which have not been specified in Schedule-A. From the above it is evident that the lands specified in Annexure-II, Schedule-A of agreement are available from the day one and as on appointed date, the existing and proposed ROW is same and no parts of the site is mentioned as not available in Schedule-A and joint memorandum signed on 11.01.2019 except for the lands for widening of plaza at Chennasamudram.Hence authority has fulfilled the obligation. ParaAs per cl 4.1.3 (a) — the authority shall provide to the contractor upon receiving the performance security under cl 7.1.] sthe right of way in accordance with the provisions of cl $.2 and 8.3 , within a period of 30 days from the date of this agreement , on no less than 90% of the total length of the project highway . As per joint memorandum signed by both the parties the length of project Highway covered is 36.076 Km _ on both sides and the total balance to be handed over ( length affected due to obstructions of structures and utilities ) is 6.35% ie 2.29 Km ( 36.076*6.35/100). Hence in length terms of the project highway also satisfied. It is a fact that the length affected due to structures and utility shifting for a length of 2.29 Km is not available to the contractor as on date. Para-4 — The joint memorandum signed by both the parties and as explained in para-3 the authority has taken action in shifting the Electrical utilities and dismantling of structures and the af! fected length is 2.29 Km out of total length of 36.076 Km. The unencumbered and vacant area available to the Contractor as per signed JM is 33.786 Km. Para-5 — From the strip map submitted the information regarding two types of encumbrances shown (Blue & Red Colour) and the Electrical poles the offset from centre line is not shown in the strip map. From the joint memorandum signed by both the parties the structures to be dismantled are almost at the edge of ROW and the length of highway affected is only 2.29 Km ,hence the encumbrance length handed over is coming out to 33.786 Km and hence the obligations are fulfilled by the authority as per cl 4.1.3 of agreement .Details is enclosed as Annexure-1. Para-6 — As per cl 10.1.2 of agreement the Authority has appointed the Authority Engineer M/s SA Infrastructure Consultants Pvt Ltd on 20.02.2019 and Mobilization is under progress .The Contractor has not submitted any designs for approval of AE. Para-7 — Mobilization of A E is under progress. ParaThe request of the Contractor to modify the appointed date is not eligible as per agreement due to the following reasons (i) As per cl 4.1.3, 8.2.1 & 8.2.2, 8.2.3-The agreement is signed on 15.10.2018 and the Joint memorandum is signed by both the parties on 30.01.2019 and appointed date is declared for the project on 11.2.2019 to commence the work. (it) As per cl 10.1.1 of agreement, the contractor has not submitted the details till date to the Authority. Further the Designs and Drawings as per cl 10.2.1 of agreement is not submitted for review of the Authority Engineer. (iii) The Camp Office and the laboratory of the Contractor is not yet established and Staff is not mobilized at site. (iv) The Contractor has not submitted the fulfilment of the obligations of the Contractor as per Article 3 of the agreement. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Model code of conduct | EoT | We agree that model code of conduct was being in force and many activities were affected. Hence, we request the Authority to take this it into consideration as an event for extension of time if required. | synthetic_template_20250913 | Request for modification of appointed date - Reply made - reg. | from _all encroachments and encumbrances, and free access thereto for the execution of this agreement.” Even today, ROW handed over is not free from all encroachments and encumbrances. There are structures which are fouling within ROW which are to be dismantled. No action has been taken on this issue by the 2. It is also submitted that the following structures couldn’t be taken up due to encumbrances/ obstructions as given in the remark’s column in the table below. Bund, Buildi d_ shifti f electri 82/566 ¦ vup ¦ Hs ¦ Buildings, Hut and shifting of electric pole. 85/874 ¦ LvuP ¦ BHS ¦ Pylon ~ 2 Nos. (RHS) & Pond Bund (LHS). ¦S {93/115 ¦ vup ¦ Bris —¦ Buildings to be eno ¦ 6 ¦ 98/423 ¦ Vup ¦ BES _¦ Buildings to be removed. ¦ LHS ¦ Building and temporary shed to be removed. RHS Boundary wall, building, water tank and temporary structure. above mentioned structures is one year. The same is also endorsed in policy circular — Policy matters — Technical ( 195/2016) dated 19. 1.2016 of the Authority while determining Extension of Time. event for extension of time if required. However, it has been three weeks since model code of conduct has been lifted and work of removal of encumbrance/ obstruction has not been started. As per the discussion had with the appointed entity for utility shifting, it was identified and concluded that shifting of electrical poles in the already encumbered portion can be taken up only after removal of encumbrances/ obstructions as land was not available. Utility shifting is also interlinked with removal of encumbrance/encroachments. Hence i requested to remove the encumbrance and provide vacant acc Clause 8.1 of the Contract Agreement. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Model code of conduct | EoT | The length affected due to structures and Utility shifting for a length 2.29 Km could not be taken up due to model code of conduct | synthetic_template_20250913 | NHAI, PIU - Krishnagiri — Six Laning of Karaipettai to Walajhapet section of NH+4 ( New NH~8) from km.71.015 to km.107.091 in the State of Tamil Nadu under NHDP Phase-V under EPC Mode- M's SPK &Co —Request for modification of Appointed date -Reg. | With reference to the letter 1* cited the following observations are made Para-I:- As per Annexure-II , Schedule-A dates for providing Right of Way the existing and proposed ROW is 60m at Plaza is 80m and is available as On appointed date . As per cl 8.2.2 the authority shall provide the Right of Way to the Contractor in respect of all land included in the Appendix by the date specified in Schedule-A for those parts of the site referred to therein, or no later than 90 days of the appointed date for those parts of the site which have not been specified in Schedule-A. From the above it is evident that the lands specified in Annexure-II, Schedule-A of agreement are available from the day one and as on appointed date, the existing and proposed ROW is same and no parts of the site is mentioned as not available in Schedule-A and joint memorandum signed on 11.01.2019 except for the lands for widening of plaza at Chennasamudram.Hence authority has fulfilled the obligation. ParaAs per cl 4.1.3 (a) — the authority shall provide to the contractor upon receiving the performance security under cl 7.1.] sthe right of way in accordance with the provisions of cl $.2 and 8.3 , within a period of 30 days from the date of this agreement , on no less than 90% of the total length of the project highway . As per joint memorandum signed by both the parties the length of project Highway covered is 36.076 Km _ on both sides and the total balance to be handed over ( length affected due to obstructions of structures and utilities ) is 6.35% ie 2.29 Km ( 36.076*6.35/100). Hence in length terms of the project highway also satisfied. It is a fact that the length affected due to structures and utility shifting for a length of 2.29 Km is not available to the contractor as on date. Para-4 — The joint memorandum signed by both the parties and as explained in para-3 the authority has taken action in shifting the Electrical utilities and dismantling of structures and the af! fected length is 2.29 Km out of total length of 36.076 Km. The unencumbered and vacant area available to the Contractor as per signed JM is 33.786 Km. Para-5 — From the strip map submitted the information regarding two types of encumbrances shown (Blue & Red Colour) and the Electrical poles the offset from centre line is not shown in the strip map. From the joint memorandum signed by both the parties the structures to be dismantled are almost at the edge of ROW and the length of highway affected is only 2.29 Km ,hence the encumbrance length handed over is coming out to 33.786 Km and hence the obligations are fulfilled by the authority as per cl 4.1.3 of agreement .Details is enclosed as Annexure-1. Para-6 — As per cl 10.1.2 of agreement the Authority has appointed the Authority Engineer M/s SA Infrastructure Consultants Pvt Ltd on 20.02.2019 and Mobilization is under progress .The Contractor has not submitted any designs for approval of AE. Para-7 — Mobilization of A E is under progress. ParaThe request of the Contractor to modify the appointed date is not eligible as per agreement due to the following reasons (i) As per cl 4.1.3, 8.2.1 & 8.2.2, 8.2.3-The agreement is signed on 15.10.2018 and the Joint memorandum is signed by both the parties on 30.01.2019 and appointed date is declared for the project on 11.2.2019 to commence the work. (it) As per cl 10.1.1 of agreement, the contractor has not submitted the details till date to the Authority. Further the Designs and Drawings as per cl 10.2.1 of agreement is not submitted for review of the Authority Engineer. (iii) The Camp Office and the laboratory of the Contractor is not yet established and Staff is not mobilized at site. (iv) The Contractor has not submitted the fulfilment of the obligations of the Contractor as per Article 3 of the agreement. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Model code of conduct | EoT | The length affected due to structures and Utility shifting for a length 2.29 Km could not be taken up due to model code of conduct | synthetic_template_20250913 | NHAI, PIU - Krishnagiri — Six Laning of Karaipettai to Walajhapet section of NH+4 ( New NH~8) from km.71.015 to km.107.091 in the State of Tamil Nadu under NHDP Phase-V under EPC Mode- M's SPK &Co —Request for modification of Appointed date -Reg. | With reference to the letter 1* cited the following observations are made Para-I:- As per Annexure-II , Schedule-A dates for providing Right of Way the existing and proposed ROW is 60m at Plaza is 80m and is available as On appointed date . As per cl 8.2.2 the authority shall provide the Right of Way to the Contractor in respect of all land included in the Appendix by the date specified in Schedule-A for those parts of the site referred to therein, or no later than 90 days of the appointed date for those parts of the site which have not been specified in Schedule-A. From the above it is evident that the lands specified in Annexure-II, Schedule-A of agreement are available from the day one and as on appointed date, the existing and proposed ROW is same and no parts of the site is mentioned as not available in Schedule-A and joint memorandum signed on 11.01.2019 except for the lands for widening of plaza at Chennasamudram.Hence authority has fulfilled the obligation. ParaAs per cl 4.1.3 (a) — the authority shall provide to the contractor upon receiving the performance security under cl 7.1.] sthe right of way in accordance with the provisions of cl $.2 and 8.3 , within a period of 30 days from the date of this agreement , on no less than 90% of the total length of the project highway . As per joint memorandum signed by both the parties the length of project Highway covered is 36.076 Km _ on both sides and the total balance to be handed over ( length affected due to obstructions of structures and utilities ) is 6.35% ie 2.29 Km ( 36.076*6.35/100). Hence in length terms of the project highway also satisfied. It is a fact that the length affected due to structures and utility shifting for a length of 2.29 Km is not available to the contractor as on date. Para-4 — The joint memorandum signed by both the parties and as explained in para-3 the authority has taken action in shifting the Electrical utilities and dismantling of structures and the af! fected length is 2.29 Km out of total length of 36.076 Km. The unencumbered and vacant area available to the Contractor as per signed JM is 33.786 Km. Para-5 — From the strip map submitted the information regarding two types of encumbrances shown (Blue & Red Colour) and the Electrical poles the offset from centre line is not shown in the strip map. From the joint memorandum signed by both the parties the structures to be dismantled are almost at the edge of ROW and the length of highway affected is only 2.29 Km ,hence the encumbrance length handed over is coming out to 33.786 Km and hence the obligations are fulfilled by the authority as per cl 4.1.3 of agreement .Details is enclosed as Annexure-1. Para-6 — As per cl 10.1.2 of agreement the Authority has appointed the Authority Engineer M/s SA Infrastructure Consultants Pvt Ltd on 20.02.2019 and Mobilization is under progress .The Contractor has not submitted any designs for approval of AE. Para-7 — Mobilization of A E is under progress. ParaThe request of the Contractor to modify the appointed date is not eligible as per agreement due to the following reasons (i) As per cl 4.1.3, 8.2.1 & 8.2.2, 8.2.3-The agreement is signed on 15.10.2018 and the Joint memorandum is signed by both the parties on 30.01.2019 and appointed date is declared for the project on 11.2.2019 to commence the work. (it) As per cl 10.1.1 of agreement, the contractor has not submitted the details till date to the Authority. Further the Designs and Drawings as per cl 10.2.1 of agreement is not submitted for review of the Authority Engineer. (iii) The Camp Office and the laboratory of the Contractor is not yet established and Staff is not mobilized at site. (iv) The Contractor has not submitted the fulfilment of the obligations of the Contractor as per Article 3 of the agreement. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Model code of conduct | EoT | We agree that model code of conduct was being in force and many activities were affected. Hence, we request the Authority to take this it into consideration as an event for extension of time if required. | synthetic_template_20250913 | Request for modification of appointed date - Reply made - reg. | from _all encroachments and encumbrances, and free access thereto for the execution of this agreement.” Even today, ROW handed over is not free from all encroachments and encumbrances. There are structures which are fouling within ROW which are to be dismantled. No action has been taken on this issue by the 2. It is also submitted that the following structures couldn’t be taken up due to encumbrances/ obstructions as given in the remark’s column in the table below. Bund, Buildi d_ shifti f electri 82/566 ¦ vup ¦ Hs ¦ Buildings, Hut and shifting of electric pole. 85/874 ¦ LvuP ¦ BHS ¦ Pylon ~ 2 Nos. (RHS) & Pond Bund (LHS). ¦S {93/115 ¦ vup ¦ Bris —¦ Buildings to be eno ¦ 6 ¦ 98/423 ¦ Vup ¦ BES _¦ Buildings to be removed. ¦ LHS ¦ Building and temporary shed to be removed. RHS Boundary wall, building, water tank and temporary structure. above mentioned structures is one year. The same is also endorsed in policy circular — Policy matters — Technical ( 195/2016) dated 19. 1.2016 of the Authority while determining Extension of Time. event for extension of time if required. However, it has been three weeks since model code of conduct has been lifted and work of removal of encumbrance/ obstruction has not been started. As per the discussion had with the appointed entity for utility shifting, it was identified and concluded that shifting of electrical poles in the already encumbered portion can be taken up only after removal of encumbrances/ obstructions as land was not available. Utility shifting is also interlinked with removal of encumbrance/encroachments. Hence i requested to remove the encumbrance and provide vacant acc Clause 8.1 of the Contract Agreement. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Dismantling of structures | Authority's Obligations; EoT; Payments | and action is being taken to dismantle the structures affected . | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/972_03062019_Non acceptance of shifting of appointed date.pdf | NHAI, PIU - Krishnagiri — Six Laning of Karaipettai to Walajhapet section of NH+4 ( New NH~8) from km.71.015 to km.107.091 in the State of Tamil Nadu under NHDP Phase-V under EPC Mode- M's SPK &Co —Request for modification of Appointed date -Reg. | With reference to the letter 1* cited the following observations are made Para-I:- As per Annexure-II , Schedule-A dates for providing Right of Way the existing and proposed ROW is 60m at Plaza is 80m and is available as On appointed date . As per cl 8.2.2 the authority shall provide the Right of Way to the Contractor in respect of all land included in the Appendix by the date specified in Schedule-A for those parts of the site referred to therein, or no later than 90 days of the appointed date for those parts of the site which have not been specified in Schedule-A. From the above it is evident that the lands specified in Annexure-II, Schedule-A of agreement are available from the day one and as on appointed date, the existing and proposed ROW is same and no parts of the site is mentioned as not available in Schedule-A and joint memorandum signed on 11.01.2019 except for the lands for widening of plaza at Chennasamudram.Hence authority has fulfilled the obligation. ParaAs per cl 4.1.3 (a) — the authority shall provide to the contractor upon receiving the performance security under cl 7.1.] sthe right of way in accordance with the provisions of cl $.2 and 8.3 , within a period of 30 days from the date of this agreement , on no less than 90% of the total length of the project highway . As per joint memorandum signed by both the parties the length of project Highway covered is 36.076 Km _ on both sides and the total balance to be handed over ( length affected due to obstructions of structures and utilities ) is 6.35% ie 2.29 Km ( 36.076*6.35/100). Hence in length terms of the project highway also satisfied. It is a fact that the length affected due to structures and utility shifting for a length of 2.29 Km is not available to the contractor as on date. Para-4 — The joint memorandum signed by both the parties and as explained in para-3 the authority has taken action in shifting the Electrical utilities and dismantling of structures and the af! fected length is 2.29 Km out of total length of 36.076 Km. The unencumbered and vacant area available to the Contractor as per signed JM is 33.786 Km. Para-5 — From the strip map submitted the information regarding two types of encumbrances shown (Blue & Red Colour) and the Electrical poles the offset from centre line is not shown in the strip map. From the joint memorandum signed by both the parties the structures to be dismantled are almost at the edge of ROW and the length of highway affected is only 2.29 Km ,hence the encumbrance length handed over is coming out to 33.786 Km and hence the obligations are fulfilled by the authority as per cl 4.1.3 of agreement .Details is enclosed as Annexure-1. Para-6 — As per cl 10.1.2 of agreement the Authority has appointed the Authority Engineer M/s SA Infrastructure Consultants Pvt Ltd on 20.02.2019 and Mobilization is under progress .The Contractor has not submitted any designs for approval of AE. Para-7 — Mobilization of A E is under progress. ParaThe request of the Contractor to modify the appointed date is not eligible as per agreement due to the following reasons (i) As per cl 4.1.3, 8.2.1 & 8.2.2, 8.2.3-The agreement is signed on 15.10.2018 and the Joint memorandum is signed by both the parties on 30.01.2019 and appointed date is declared for the project on 11.2.2019 to commence the work. (it) As per cl 10.1.1 of agreement, the contractor has not submitted the details till date to the Authority. Further the Designs and Drawings as per cl 10.2.1 of agreement is not submitted for review of the Authority Engineer. (iii) The Camp Office and the laboratory of the Contractor is not yet established and Staff is not mobilized at site. (iv) The Contractor has not submitted the fulfilment of the obligations of the Contractor as per Article 3 of the agreement. | FALSE | real_data
Dismantling of structures | Authority's Obligations; EoT; Payments | We request your good self to arrange for removal of the structures and statues and provide encumbrance free land as per Clause 8.1, Article 8 of the EPC Agreement | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-1/9. Removal of religious and political statues.pdf | Removal of Religious and Political statues- Reg. | We would like to bring to your kind notice that, there are few religious structures and political statues which are existing within the construction zone and are obstructing the construction activities. In this context, we request your good self to arrange for removal of the structures and statues and provide encumbrance free land as per Clause 8.1, Article 8 of the EPC Agreement, so as to enable us to proceed with the construction activities. The photographs along with chainage and location reference details of the structures / statues are enclosed for your ready reference. Thanking & assuring our best services always, | FALSE | real_data
Dismantling of structures | Authority's Obligations; EoT; Payments | It is to remind that the debris of the dismantled structures within the NHAI boundary at villages ocheri,kaveripakkam,sumaithangi,Kadaperi,Avalur & near the toll plaza is still lying there itself instead of removing and commencing your construction activities. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20201128_AE_SPK_485_Clearance of within the NHAI boundary occupied Structures dismantled debris and Misc works.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode — Clearance of within the NHAI boundary occupied Structures dismantled debris and Misc works - Reg. | In continuation to the discussion’s held in the Progress Review Meeting and based on the subsequent site visit made by Project Director PIU NHAI Kancheepuram on 26.11.2020, it is to remind that the debris of the dismantled structures with in the NHAI boundary at villages Ocheri, Kaveripakkam, Sumaithangi, Kadaperi, Avalur & near the Toll Plaza is still lying there itself instead of removing and commencing your construction activities. However, it is to ncte that except Drain construction activity at Kaveripakkam & Ocheri villages no other works had commenced by occupying the vacated land. Hence it is resulting in again occupying the premises by the near by residents and commencing their business establishments. Please note that any delay from your end in this regard may lead to further complications. Hence it has been asked to commence your construction activities at the vacated locations on priority. I hope the Local Management will initiate appropriate steps in this regard immediately. | FALSE | real_data
Dismantling of structures | EoT | We request your good self to arrange for removal of the structures and statues and provide encumbrance free land as per Clause 8.1, Article 8 of the EPC Agreement | synthetic_template_20250913 | Removal of Religious and Political statues- Reg. | It is brought to your attention that We would like to bring to your kind notice that, there are few religious structures and political statues which are existing within the construction zone and are obstructing the construction activities. In this context, we request your good self to arrange for removal of the structures and statues and provide encumbrance free land as per Clause 8.1, Article 8 of the EPC Agreement, so as to enable us to proceed with the construction activities. The photographs along with chainage and location reference details of the structures / statues are enclosed for your ready reference. Thanking & assuring our best services always, | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Dismantling of structures | EoT | and action is being taken to dismantle the structures affected . | synthetic_template_20250913 | NHAI, PIU - Krishnagiri — Six Laning of Karaipettai to Walajhapet section of NH+4 ( New NH~8) from km.71.015 to km.107.091 in the State of Tamil Nadu under NHDP Phase-V under EPC Mode- M's SPK &Co —Request for modification of Appointed date -Reg. | With reference to the letter 1* cited the following observations are made Para-I:- As per Annexure-II , Schedule-A dates for providing Right of Way the existing and proposed ROW is 60m at Plaza is 80m and is available as On appointed date . As per cl 8.2.2 the authority shall provide the Right of Way to the Contractor in respect of all land included in the Appendix by the date specified in Schedule-A for those parts of the site referred to therein, or no later than 90 days of the appointed date for those parts of the site which have not been specified in Schedule-A. From the above it is evident that the lands specified in Annexure-II, Schedule-A of agreement are available from the day one and as on appointed date, the existing and proposed ROW is same and no parts of the site is mentioned as not available in Schedule-A and joint memorandum signed on 11.01.2019 except for the lands for widening of plaza at Chennasamudram.Hence authority has fulfilled the obligation. ParaAs per cl 4.1.3 (a) — the authority shall provide to the contractor upon receiving the performance security under cl 7.1.] sthe right of way in accordance with the provisions of cl $.2 and 8.3 , within a period of 30 days from the date of this agreement , on no less than 90% of the total length of the project highway . As per joint memorandum signed by both the parties the length of project Highway covered is 36.076 Km _ on both sides and the total balance to be handed over ( length affected due to obstructions of structures and utilities ) is 6.35% ie 2.29 Km ( 36.076*6.35/100). Hence in length terms of the project highway also satisfied. It is a fact that the length affected due to structures and utility shifting for a length of 2.29 Km is not available to the contractor as on date. Para-4 — The joint memorandum signed by both the parties and as explained in para-3 the authority has taken action in shifting the Electrical utilities and dismantling of structures and the af! fected length is 2.29 Km out of total length of 36.076 Km. The unencumbered and vacant area available to the Contractor as per signed JM is 33.786 Km. Para-5 — From the strip map submitted the information regarding two types of encumbrances shown (Blue & Red Colour) and the Electrical poles the offset from centre line is not shown in the strip map. From the joint memorandum signed by both the parties the structures to be dismantled are almost at the edge of ROW and the length of highway affected is only 2.29 Km ,hence the encumbrance length handed over is coming out to 33.786 Km and hence the obligations are fulfilled by the authority as per cl 4.1.3 of agreement .Details is enclosed as Annexure-1. Para-6 — As per cl 10.1.2 of agreement the Authority has appointed the Authority Engineer M/s SA Infrastructure Consultants Pvt Ltd on 20.02.2019 and Mobilization is under progress .The Contractor has not submitted any designs for approval of AE. Para-7 — Mobilization of A E is under progress. ParaThe request of the Contractor to modify the appointed date is not eligible as per agreement due to the following reasons (i) As per cl 4.1.3, 8.2.1 & 8.2.2, 8.2.3-The agreement is signed on 15.10.2018 and the Joint memorandum is signed by both the parties on 30.01.2019 and appointed date is declared for the project on 11.2.2019 to commence the work. (it) As per cl 10.1.1 of agreement, the contractor has not submitted the details till date to the Authority. Further the Designs and Drawings as per cl 10.2.1 of agreement is not submitted for review of the Authority Engineer. (iii) The Camp Office and the laboratory of the Contractor is not yet established and Staff is not mobilized at site. (iv) The Contractor has not submitted the fulfilment of the obligations of the Contractor as per Article 3 of the agreement. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Dismantling of structures | Authority's Obligations | substantial length is affected due to existing buildings which are to be dismantled. The Authority has not started dismantling buildings at any location. The stretches passing through the villages are badly affected. | synthetic_template_20250913 | Modifying the Appointed Date based on the length of project highway handed over in pursuant to Article 8 of EPC agreement - reg | 1. Pursuant to Clause 8.2.2 and 8.2.3 of the EPC Agreement, the Authority should have provided Right of way for 100% length of the project highway on appointed date plus 90 days, i.e. 11.05.2019. It is brought to your notice that this requirement has not been fulfilled by the Authority. 2. We also bring to your kind notice that the memorandum and appendix jointly signed on 11.01.2019 and submitted vide ref (3) cited above was prepared based on the available area without taking into consideration, the requirement of the contract provision as per Clause 4.1.3 (a) of the EPC agreement which talks about the handing over of land only in terms of length of the Project Highway. 3. When we started assessing the stretches affected in terms of length, we come to know that substantial length is affected due to existing buildings which are to be dismantled. The Authority has not started dismantling buildings at any location. The stretches passing through the villages are badly affected. 4. The memorandum and appendix prepared in terms of area is giving a deceptive/false picture about the availability of the vacant access. Power line and HT lines are still to be shifted and this work has not been started by the utility. 5. We have prepared a strip chart showing the existing encumbrance already enumerated in the Joint memorandum and appendix which is giving a clear picture of the percentage of length of project highway available on Appointed Date. As per this strip chart, only 63.26% of encumbrance free length has been made available. The minimum requirement of handing over of 90% of length of Project Highway as per Cl. 4.1.3 is not fulfilled for declaration of the Appointed Date. 6. Similarly, as per Clause 10.1.2 and Clause 18.1.2 of EPC agreement, the Authority Engineer should have been mobilised within 30 days from the date of signing of Agreement which was due on 14.11.2018. Even after seven months (from the date of signing of Agreement), the Authority Engineer has not been mobilised which is having its impact on the approvals of program, design and materials. 7. The Authority vide its recent circular — NHAI / Policy Guidelines / COS / 2019 / No.9.2.24 / 2019 dated 29.04.2019 has categorically mentioned that any Change of Scope / Reduction in Scope shall be finalised within a maximum period of 6 months from the Appointed Date. Hence the appointment of Authority Engineer is very crucial in deciding the COS / RIS and any further delay in appointment of Authority Engineer will have its impact on the as per the programme submitted by us as some crucial decisions and reviews are affected. Already three months have elapsed in the duration of six months given by the Authority. 8. In view of the above circumstances, we request you to kindly take a practical view and modify the Appointed Date already declared as 11.02.2019. This may be kindly modified to a date on which 90% of encumbrance free length of the Project Highway is made available to us. 9. Strip chart along with some photographs of the buildings to be dismantled, HT tower etc. are enclosed with this letter for your ready reference. This is for your information and further necessary action. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Dismantling of structures | Authority's Obligations | We request your good self to arrange for removal of the structures and statues and provide encumbrance free land as per Clause 8.1, Article 8 of the EPC Agreement | synthetic_template_20250913 | Removal of Religious and Political statues- Reg. | We would like to bring to your kind notice that, there are few religious structures and political statues which are existing within the construction zone and are obstructing the construction activities. In this context, we request your good self to arrange for removal of the structures and statues and provide encumbrance free land as per Clause 8.1, Article 8 of the EPC Agreement, so as to enable us to proceed with the construction activities. The photographs along with chainage and location reference details of the structures / statues are enclosed for your ready reference. Thanking & assuring our best services always, | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Dismantling of structures | Payments | substantial length is affected due to existing buildings which are to be dismantled. The Authority has not started dismantling buildings at any location. The stretches passing through the villages are badly affected. | synthetic_template_20250913 | Modifying the Appointed Date based on the length of project highway handed over in pursuant to Article 8 of EPC agreement - reg | 1. Pursuant to Clause 8.2.2 and 8.2.3 of the EPC Agreement, the Authority should have provided Right of way for 100% length of the project highway on appointed date plus 90 days, i.e. 11.05.2019. It is brought to your notice that this requirement has not been fulfilled by the Authority. 2. We also bring to your kind notice that the memorandum and appendix jointly signed on 11.01.2019 and submitted vide ref (3) cited above was prepared based on the available area without taking into consideration, the requirement of the contract provision as per Clause 4.1.3 (a) of the EPC agreement which talks about the handing over of land only in terms of length of the Project Highway. 3. When we started assessing the stretches affected in terms of length, we come to know that substantial length is affected due to existing buildings which are to be dismantled. The Authority has not started dismantling buildings at any location. The stretches passing through the villages are badly affected. 4. The memorandum and appendix prepared in terms of area is giving a deceptive/false picture about the availability of the vacant access. Power line and HT lines are still to be shifted and this work has not been started by the utility. 5. We have prepared a strip chart showing the existing encumbrance already enumerated in the Joint memorandum and appendix which is giving a clear picture of the percentage of length of project highway available on Appointed Date. As per this strip chart, only 63.26% of encumbrance free length has been made available. The minimum requirement of handing over of 90% of length of Project Highway as per Cl. 4.1.3 is not fulfilled for declaration of the Appointed Date. 6. Similarly, as per Clause 10.1.2 and Clause 18.1.2 of EPC agreement, the Authority Engineer should have been mobilised within 30 days from the date of signing of Agreement which was due on 14.11.2018. Even after seven months (from the date of signing of Agreement), the Authority Engineer has not been mobilised which is having its impact on the approvals of program, design and materials. 7. The Authority vide its recent circular — NHAI / Policy Guidelines / COS / 2019 / No.9.2.24 / 2019 dated 29.04.2019 has categorically mentioned that any Change of Scope / Reduction in Scope shall be finalised within a maximum period of 6 months from the Appointed Date. Hence the appointment of Authority Engineer is very crucial in deciding the COS / RIS and any further delay in appointment of Authority Engineer will have its impact on the as per the programme submitted by us as some crucial decisions and reviews are affected. Already three months have elapsed in the duration of six months given by the Authority. 8. In view of the above circumstances, we request you to kindly take a practical view and modify the Appointed Date already declared as 11.02.2019. This may be kindly modified to a date on which 90% of encumbrance free length of the Project Highway is made available to us. 9. Strip chart along with some photographs of the buildings to be dismantled, HT tower etc. are enclosed with this letter for your ready reference. This is for your information and further necessary action. Thank you for your attention to this matter. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Mobilisation of Authority Engineer | Authority's Obligations | Para-6 — As per cl 10.1.2 of agreement the Authority has appointed the Authority Engineer M/S SA Infrastructure Consultants Pvt Ltd on 20.02.2019 and Mobilization is under progress . | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/972_03062019_Non acceptance of shifting of appointed date.pdf | NHAI, PIU - Krishnagiri — Six Laning of Karaipettai to Walajhapet section of NH+4 ( New NH~8) from km.71.015 to km.107.091 in the State of Tamil Nadu under NHDP Phase-V under EPC Mode- M's SPK &Co —Request for modification of Appointed date -Reg. | With reference to the letter 1* cited the following observations are made Para-I:- As per Annexure-II , Schedule-A dates for providing Right of Way the existing and proposed ROW is 60m at Plaza is 80m and is available as On appointed date . As per cl 8.2.2 the authority shall provide the Right of Way to the Contractor in respect of all land included in the Appendix by the date specified in Schedule-A for those parts of the site referred to therein, or no later than 90 days of the appointed date for those parts of the site which have not been specified in Schedule-A. From the above it is evident that the lands specified in Annexure-II, Schedule-A of agreement are available from the day one and as on appointed date, the existing and proposed ROW is same and no parts of the site is mentioned as not available in Schedule-A and joint memorandum signed on 11.01.2019 except for the lands for widening of plaza at Chennasamudram.Hence authority has fulfilled the obligation. ParaAs per cl 4.1.3 (a) — the authority shall provide to the contractor upon receiving the performance security under cl 7.1.] sthe right of way in accordance with the provisions of cl $.2 and 8.3 , within a period of 30 days from the date of this agreement , on no less than 90% of the total length of the project highway . As per joint memorandum signed by both the parties the length of project Highway covered is 36.076 Km _ on both sides and the total balance to be handed over ( length affected due to obstructions of structures and utilities ) is 6.35% ie 2.29 Km ( 36.076*6.35/100). Hence in length terms of the project highway also satisfied. It is a fact that the length affected due to structures and utility shifting for a length of 2.29 Km is not available to the contractor as on date. Para-4 — The joint memorandum signed by both the parties and as explained in para-3 the authority has taken action in shifting the Electrical utilities and dismantling of structures and the af! fected length is 2.29 Km out of total length of 36.076 Km. The unencumbered and vacant area available to the Contractor as per signed JM is 33.786 Km. Para-5 — From the strip map submitted the information regarding two types of encumbrances shown (Blue & Red Colour) and the Electrical poles the offset from centre line is not shown in the strip map. From the joint memorandum signed by both the parties the structures to be dismantled are almost at the edge of ROW and the length of highway affected is only 2.29 Km ,hence the encumbrance length handed over is coming out to 33.786 Km and hence the obligations are fulfilled by the authority as per cl 4.1.3 of agreement .Details is enclosed as Annexure-1. Para-6 — As per cl 10.1.2 of agreement the Authority has appointed the Authority Engineer M/s SA Infrastructure Consultants Pvt Ltd on 20.02.2019 and Mobilization is under progress .The Contractor has not submitted any designs for approval of AE. Para-7 — Mobilization of A E is under progress. ParaThe request of the Contractor to modify the appointed date is not eligible as per agreement due to the following reasons (i) As per cl 4.1.3, 8.2.1 & 8.2.2, 8.2.3-The agreement is signed on 15.10.2018 and the Joint memorandum is signed by both the parties on 30.01.2019 and appointed date is declared for the project on 11.2.2019 to commence the work. (it) As per cl 10.1.1 of agreement, the contractor has not submitted the details till date to the Authority. Further the Designs and Drawings as per cl 10.2.1 of agreement is not submitted for review of the Authority Engineer. (iii) The Camp Office and the laboratory of the Contractor is not yet established and Staff is not mobilized at site. (iv) The Contractor has not submitted the fulfilment of the obligations of the Contractor as per Article 3 of the agreement. | FALSE | real_data
Mobilisation of Authority Engineer | Authority's Obligations | Similarly, as per Clause 10.1.2 and Clause 18.1.2 of EPC agreement, the Authority Engineer should have been mobilised within 30 days from the date of signing of Agreement which was due on 14.11.2018. Even after seven months (from the date of signing of Agreement), the Authority Engineer has not been mobilised which is having its impact on the approvals of program, design and materials. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/29_13052019_ Modifying the Appointed Date.pdf | Modifying the Appointed Date based on the length of project highway handed over in pursuant to Article 8 of EPC agreement - reg | 1. Pursuant to Clause 8.2.2 and 8.2.3 of the EPC Agreement, the Authority should have provided Right of way for 100% length of the project highway on appointed date plus 90 days, i.e. 11.05.2019. It is brought to your notice that this requirement has not been fulfilled by the Authority. 2. We also bring to your kind notice that the memorandum and appendix jointly signed on 11.01.2019 and submitted vide ref (3) cited above was prepared based on the available area without taking into consideration, the requirement of the contract provision as per Clause 4.1.3 (a) of the EPC agreement which talks about the handing over of land only in terms of length of the Project Highway. 3. When we started assessing the stretches affected in terms of length, we come to know that substantial length is affected due to existing buildings which are to be dismantled. The Authority has not started dismantling buildings at any location. The stretches passing through the villages are badly affected. 4. The memorandum and appendix prepared in terms of area is giving a deceptive/false picture about the availability of the vacant access. Power line and HT lines are still to be shifted and this work has not been started by the utility. 5. We have prepared a strip chart showing the existing encumbrance already enumerated in the Joint memorandum and appendix which is giving a clear picture of the percentage of length of project highway available on Appointed Date. As per this strip chart, only 63.26% of encumbrance free length has been made available. The minimum requirement of handing over of 90% of length of Project Highway as per Cl. 4.1.3 is not fulfilled for declaration of the Appointed Date. 6. Similarly, as per Clause 10.1.2 and Clause 18.1.2 of EPC agreement, the Authority Engineer should have been mobilised within 30 days from the date of signing of Agreement which was due on 14.11.2018. Even after seven months (from the date of signing of Agreement), the Authority Engineer has not been mobilised which is having its impact on the approvals of program, design and materials. 7. The Authority vide its recent circular — NHAI / Policy Guidelines / COS / 2019 / No.9.2.24 / 2019 dated 29.04.2019 has categorically mentioned that any Change of Scope / Reduction in Scope shall be finalised within a maximum period of 6 months from the Appointed Date. Hence the appointment of Authority Engineer is very crucial in deciding the COS / RIS and any further delay in appointment of Authority Engineer will have its impact on the as per the programme submitted by us as some crucial decisions and reviews are affected. Already three months have elapsed in the duration of six months given by the Authority. 8. In view of the above circumstances, we request you to kindly take a practical view and modify the Appointed Date already declared as 11.02.2019. This may be kindly modified to a date on which 90% of encumbrance free length of the Project Highway is made available to us. 9. Strip chart along with some photographs of the buildings to be dismantled, HT tower etc. are enclosed with this letter for your ready reference. This is for your information and further necessary action. | FALSE | real_data
Mobilisation of Authority Engineer | Authority's Obligations | As all activities relating to surveys and investigations are in progress, we hereby request you to communicate the details of Authority's Engineer and instruct them to supervise the ongoing works to avoid ambiguities and disputes in future. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/Lr.No.7 Appointment of Authority Engineer.pdf | Intimation regarding appointment of Authority Engineer | With reference to above referred contract your kind attention is drawn to Article 10.1.2 wherein it is stated “The Authority shall, within 30 (thirty) days of the date of this Agreement, appoint an engineer (the “Authority’s Engineer”) to discharge the functions and duties specified in this Agreement, and shall notify to the Contractor the name, address and the date of appointment of the Authority’s Engineer forthwith’. Please note the contract agreement was entered on 15.10.2018. As on date we have not received the details of Authority’s Engineer appointment and their contact details. As all activities relating to surveys and investigations are in progress, we hereby request you to communicate the details of Authority’s Engineer and instruct them to supervise the ongoing works to avoid ambiguities and disputes in future. | FALSE | real_data
Mobilisation of Authority Engineer | Authority's Obligations | As no communication is received on mobilization of the Authority Engineer fill date, it is requested to mobilize the staff at Site under intimation to this office for performing the duties of Authority Engineer. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LOT-10/Lr.No.694_24042019 To SA_Mobilization of Site_Review of Programme.pdf | NHALI PIU - Krishnagiri - Consultancy services for Authority Engineer for supervision of Six laning of Karaipettai to Walajahpet section of NH-48 (old NH-4) from km.71+015 to km.107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase V- Mobilization at Site ~ Reg. | As you know that your firm has been appointed as Authority Engineer for the ee work and the contract agreement for civil work is signed on 15.10.2018 and appointed date is: declared as 11.2.2019 and the contractor has started the work and is in progress. 2.AS a part of contract agreement the contractor has submitted programme for the works as per clause 10.1.3 of agreement and Plan & Profile drawings and requesting for approvals. 3.As per para- 4 ,Annex-I ,Schedule-N of agreement ,the Authority Engineer shall review the programme for the works submitted by the contractor as per cl 10.1.3 of agreement and shall convey its comments to the contractor within a stipulated period of time. 4. As no communication is received on mobilisation of the Authority Engineer till date, it is requested to mobilise the staff at site under intimation to this office immediately for performing the duties of Authority Engineer. | FALSE | real_data
Mobilisation of Authority Engineer | Authority's Obligations | Pursuant to Clause 10.1.2 and 18.1.2 of Contract Agreement, the Authority Engineer should have been mobilised within 30 days from the date of signing of agreement which was due on 14.11.2018. But the Authority Engineer was mobilised at site only on 22.06.2019 which is almost 7 1/2 months from the date of agreement. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/40_07082019_Rescheduling of Project Milestones – Request for Extension of time.pdf | Rescheduling of Project Milestones - Request for Extension of time - Reg. | The Contract agreement for the above mentioned project was executed on 15.10.2018. The appointed date was fixed as 11.02.2019 and the same was communicated vide ref (3) cited above. The Copy of the same is herewith enclosed as Annexure 1. The Authority in its response vide ref (5) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. The copy of the same is enclosed as Annexure 3. The EPC contractor vide ref (6) cited above reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that still the condition remained the same and dismantling/ removal of structures fouling was not started and shifting of Electric pole and power line also not started. The impacted length due to encroachments and encumbrances was 12.18 Km which accounted to 33.77% of the project highway. The workable length available to the Contractor based on the impacted length was 66.23% of the Project Highway length. The EPC Contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of removal of encumbrance / encroachment / obstruction. The copy of ref (7) is herewith enclosed as Annexure 4. It is almost six months since the declaration of appointed date, removal/ dismantling of structures/encroachments have not been started. Also, the work of shifting of power line and electric pole of LT line and HT lines crossings have not been started yet. The following are some of the key contractual dates and events since the inception of the project to till date: 1. Total length of the project highway: 36.076 Km 2. Date of Signing of agreement: 152018 3. Submission of Performance BG as per Clause 7.1.1 of the Contract Agreement: 262018 4. Target date for preparation of Memorandum as per Clause 8.2.1 of the Contract Agreement: 142018 5. Actual date of signing of Memorandum of land handing over: 112019 6. Declaration of appointed date by the Authority: 112019 7. ROW to be handed over as on appointed date as per Clause 8.2.2 & Annexure II: 35.468 Km | FALSE | real_data
Mobilisation of Authority Engineer | Authority's Obligations | Beside that the Authority has communicated the appointment of Authority Engineer and the Mobilization of Authority Engineer vide reference cited (14). | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/189_Rescheduling of Project Milestones - EOT - 1.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under BharatmalaPariyojana on EPC mode — Rescheduling of Project Mile Stone- Request for Extension of Time -Reg. | Having gone through your documents related to Rescheduling of Project Milestone-Request for Extension of Time EoT-1 please find enclosed herewith the Authority Engineers recommendations on the same subject. This is for your information and necessary action. | FALSE | real_data
Mobilisation of Authority Engineer | Authority's Obligations | In response to the Contractor cited reasons of delay in mobilization of Authority Engineer. It is to inform that the source approval for different types of material have been submitted to PD, NHAI, Krishnagiri (PIU), since 26.04.2019 through different correspondences. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/20191130_AE_PD_10451_Recommendation of EOT I for a period of 178 days.pdf | Application for EOT | This is with reference to the captioned subject and application for EOT received from the Contractor, in this regard, it is submitted that the Contract Agreement was signed between Contractor M/s SPK & Co. and the NHAI for Six Laning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km 71+015 to Km 107+091 in the State of Tamil Nadu under NHDP Phase - V. The following are the main contractual data ; Contract Seen Date : 15/10/2018 Length of the Project 36.076 Km Project Cost INR 533,36,67,000 Appointed Date : 11/02/2019 Construction Period : 730 days from Appointed Date Scheduled Completion Date: 09/02/2021 DLP Period : 4 years from the Provisional Certificate Project Milestone ~ Days from Project Milestone Appointed Date Milestone - -1 180 Days 09/08/2019 Not achieved 365 Days 10/02/2020 To be achieved 550 Days 13/08/2020 730 Days 09/02/2021 To be Achieved In view of the above, Authority's Engineer has scrutinized the EOT application and Authority's Engineer observations are being summarized hereunder in light of the Contract Agreement; Scheduled Date ¦ Status Procurement of the Site; As mentioned in the Clause 8.2.1 of the Contract Agreement, which reproduced herewith “the Authority Representative and the Contractor shall, within 30 days of the date of this Agreement, inspect the Site and prepare a memorandum containing an inventory of the site including the vacant and unencumbered land, buildings, structures, road works, trees and any other immovable property on or attached to the site. Subject to the provisions of Clause 8.2.3, such memorandum shall have appended thereto an appendix (the “Appendix”) specifying in reasonable detail those parts of the site to which vacant access and Right of Way has not been given to the Contractor. Signing of the memorandum, in two counterparts (each of which shall constitute an original), by the Authorized Representatives of the Parties shall be deemed to constitute a valid evidence of giving the Right of Way to the Contractor for discharging its obligations under and in accordance with the provisions of this Agreement and for no other purpose whatsoever.” | FALSE | real_data
Mobilisation of Authority Engineer | Authority's Obligations | Impact on account of delay in mobilisation of Authority Engineer is pointless and not considered for the EOT | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210630_AE_PD_14484_Comprehensive EOT proposal.pdf | Extension of Time Comprehensive proposal- Reg. | With reference to the captioned subject and from the above mentioned chronology of correspondences, it can be understood that despite of approving an EoT for a period of 112 days for Mile Stone-1, the Contractor is disagreeing with the approval of the Authority and again highlighted the impediments adversely effected the First Mile Stone as well as other Milestone including the Scheduled Completion Date. The Contractor submitted the comprehensive proposal and requested for an extension of time. | FALSE | real_data
Submission of Plan & Profile | Contractor's Obligations | The EPC contractor has already submitted plan and profile for a length of 10 Km from Km.71/015 to Km.81/OOO vide Lr.No.20/SPK/Kar - Wal/PD/NHA1 dated 03.04.2019. Hence, we disagree with the contention of the Authority that the EPC contractor has not submitted any designs for approval by Authority Engineer. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/49_17062019_ Modification of Appointed Date.pdf | Request for modification of appointed date - Reply made - reg. | from _all encroachments and encumbrances, and free access thereto for the execution of this agreement.” Even today, ROW handed over is not free from all encroachments and encumbrances. There are structures which are fouling within ROW which are to be dismantled. No action has been taken on this issue by the 2. It is also submitted that the following structures couldn’t be taken up due to encumbrances/ obstructions as given in the remark’s column in the table below. Bund, Buildi d_ shifti f electri 82/566 ¦ vup ¦ Hs ¦ Buildings, Hut and shifting of electric pole. 85/874 ¦ LvuP ¦ BHS ¦ Pylon ~ 2 Nos. (RHS) & Pond Bund (LHS). ¦S {93/115 ¦ vup ¦ Bris —¦ Buildings to be eno ¦ 6 ¦ 98/423 ¦ Vup ¦ BES _¦ Buildings to be removed. ¦ LHS ¦ Building and temporary shed to be removed. RHS Boundary wall, building, water tank and temporary structure. above mentioned structures is one year. The same is also endorsed in policy circular — Policy matters — Technical ( 195/2016) dated 19. 1.2016 of the Authority while determining Extension of Time. event for extension of time if required. However, it has been three weeks since model code of conduct has been lifted and work of removal of encumbrance/ obstruction has not been started. As per the discussion had with the appointed entity for utility shifting, it was identified and concluded that shifting of electrical poles in the already encumbered portion can be taken up only after removal of encumbrances/ obstructions as land was not available. Utility shifting is also interlinked with removal of encumbrance/encroachments. Hence i requested to remove the encumbrance and provide vacant acc Clause 8.1 of the Contract Agreement. | FALSE | real_data
Submission of Plan & Profile | Contractor's Obligations | we have submitted initial Plan & Profile for a length of 34 Km | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-3/5. Delay in start of work 13.06.2017.pdf | Rehabilitation and Upgradation of Ghogaspargaon-Phulsangvi-Ukhandachakla-Dahiwandi-Shirur-Rakshasbhuvan-Kholayachiwadi-Karegaon-Dongarkini-Chumbli-Patoda-Dighol Road (SH-62) Kharda. From KM 0+000 to KM 56+000 to two lanes with paved shoulders” (Project Length 55.937 KM) on EPC basis in the State of Maharashtra (Package — I) — Delay in start of work | We are planned fo start the execution of the project from 14th June 2017 as intimated to you verbally and as per the construction programme submitted to you to complete the project execution in stipulated period. Based on this, we have submitted initial Plan & Profile for a length of 34 Km, starting from Ch: 0+000 to Ch: 34+000 and also at the same time, we have mobilized rigs for carrying out soil investigation work of the bridges. , So far, we have completed detailed survey including establishment of bench marks for a length of 56 km. We are planning to submit the balance Plan & Profile of 22 Km by this weekend. Initially, we have submitted the Plan & Profile in oe copy for your review. Please go through it and suggest for 5 a modifications if any. (amr aT igre wera PUT ty, we are establishing centre line marking on the existing road and will be completed by s. In mean time, we have placed order to procure the lab equipment required for this project e€ are expecting. the delivery of the material by this weekend and we are establishing the NM temporary laboratory at the camp location and can be utilized for the time being till the camp construction completes. As per the discussions we had earlier with the Department, we are forced to take appointed date as 30.05.17, We are mobilizing our equipment to start preliminary works like Clearing and Grubbing and base compaction of the existing ground making suitable for embankment construction. But you L have given instruction not to start the work due to the various reasons which are known to you. This delay will cause slippage in achievement of milestones & completion of the project. Hence we would like to bring to your notice that, if any delay occurs due to any reason and circumstances which are beyond our control in achieving the milestone would not be considered as a failure from our side. So please permit us to start the work at the earliest. | FALSE | real_data
Submission of Plan & Profile | Contractor's Obligations | The EPC contractor has already submitted plan and profile for a length of 10 Km from Km.71/015 to Km.81/OOO vide Lr.No.20/SPK/Kar - Wal/PD/NHA1 dated 03.04.2019. Hence, we disagree with the contention of the Authority that the EPC contractor has not submitted any designs for approval by Authority Engineer. | synthetic_template_20250913 | Request for modification of appointed date - Reply made - reg. | Please note that from _all encroachments and encumbrances, and free access thereto for the execution of this agreement.” Even today, ROW handed over is not free from all encroachments and encumbrances. There are structures which are fouling within ROW which are to be dismantled. No action has been taken on this issue by the 2. It is also submitted that the following structures couldn’t be taken up due to encumbrances/ obstructions as given in the remark’s column in the table below. Bund, Buildi d_ shifti f electri 82/566 ¦ vup ¦ Hs ¦ Buildings, Hut and shifting of electric pole. 85/874 ¦ LvuP ¦ BHS ¦ Pylon ~ 2 Nos. (RHS) & Pond Bund (LHS). ¦S {93/115 ¦ vup ¦ Bris —¦ Buildings to be eno ¦ 6 ¦ 98/423 ¦ Vup ¦ BES _¦ Buildings to be removed. ¦ LHS ¦ Building and temporary shed to be removed. RHS Boundary wall, building, water tank and temporary structure. above mentioned structures is one year. The same is also endorsed in policy circular — Policy matters — Technical ( 195/2016) dated 19. 1.2016 of the Authority while determining Extension of Time. event for extension of time if required. However, it has been three weeks since model code of conduct has been lifted and work of removal of encumbrance/ obstruction has not been started. As per the discussion had with the appointed entity for utility shifting, it was identified and concluded that shifting of electrical poles in the already encumbered portion can be taken up only after removal of encumbrances/ obstructions as land was not available. Utility shifting is also interlinked with removal of encumbrance/encroachments. Hence i requested to remove the encumbrance and provide vacant acc Clause 8.1 of the Contract Agreement. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Submission of Plan & Profile | Contractor's Obligations | we have submitted initial Plan & Profile for a length of 34 Km | synthetic_template_20250913 | Rehabilitation and Upgradation of Ghogaspargaon-Phulsangvi-Ukhandachakla-Dahiwandi-Shirur-Rakshasbhuvan-Kholayachiwadi-Karegaon-Dongarkini-Chumbli-Patoda-Dighol Road (SH-62) Kharda. From KM 0+000 to KM 56+000 to two lanes with paved shoulders” (Project Length 55.937 KM) on EPC basis in the State of Maharashtra (Package — I) — Delay in start of work | Kindly be informed that We are planned fo start the execution of the project from 14th June 2017 as intimated to you verbally and as per the construction programme submitted to you to complete the project execution in stipulated period. Based on this, we have submitted initial Plan & Profile for a length of 34 Km, starting from Ch: 0+000 to Ch: 34+000 and also at the same time, we have mobilized rigs for carrying out soil investigation work of the bridges. , So far, we have completed detailed survey including establishment of bench marks for a length of 56 km. We are planning to submit the balance Plan & Profile of 22 Km by this weekend. Initially, we have submitted the Plan & Profile in oe copy for your review. Please go through it and suggest for 5 a modifications if any. (amr aT igre wera PUT ty, we are establishing centre line marking on the existing road and will be completed by s. In mean time, we have placed order to procure the lab equipment required for this project e€ are expecting. the delivery of the material by this weekend and we are establishing the NM temporary laboratory at the camp location and can be utilized for the time being till the camp construction completes. As per the discussions we had earlier with the Department, we are forced to take appointed date as 30.05.17, We are mobilizing our equipment to start preliminary works like Clearing and Grubbing and base compaction of the existing ground making suitable for embankment construction. But you L have given instruction not to start the work due to the various reasons which are known to you. This delay will cause slippage in achievement of milestones & completion of the project. Hence we would like to bring to your notice that, if any delay occurs due to any reason and circumstances which are beyond our control in achieving the milestone would not be considered as a failure from our side. So please permit us to start the work at the earliest. Thank you for your attention to this matter. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Submission of Plan & Profile | Contractor's Obligations | The EPC contractor has already submitted plan and profile for a length of 10 Km from Km.71/015 to Km.81/OOO vide Lr.No.20/SPK/Kar - Wal/PD/NHA1 dated 03.04.2019. Hence, we disagree with the contention of the Authority that the EPC contractor has not submitted any designs for approval by Authority Engineer. | synthetic_template_20250913 | Request for modification of appointed date - Reply made - reg. | from _all encroachments and encumbrances, and free access thereto for the execution of this agreement.” Even today, ROW handed over is not free from all encroachments and encumbrances. There are structures which are fouling within ROW which are to be dismantled. No action has been taken on this issue by the 2. It is also submitted that the following structures couldn’t be taken up due to encumbrances/ obstructions as given in the remark’s column in the table below. Bund, Buildi d_ shifti f electri 82/566 ¦ vup ¦ Hs ¦ Buildings, Hut and shifting of electric pole. 85/874 ¦ LvuP ¦ BHS ¦ Pylon ~ 2 Nos. (RHS) & Pond Bund (LHS). ¦S {93/115 ¦ vup ¦ Bris —¦ Buildings to be eno ¦ 6 ¦ 98/423 ¦ Vup ¦ BES _¦ Buildings to be removed. ¦ LHS ¦ Building and temporary shed to be removed. RHS Boundary wall, building, water tank and temporary structure. above mentioned structures is one year. The same is also endorsed in policy circular — Policy matters — Technical ( 195/2016) dated 19. 1.2016 of the Authority while determining Extension of Time. event for extension of time if required. However, it has been three weeks since model code of conduct has been lifted and work of removal of encumbrance/ obstruction has not been started. As per the discussion had with the appointed entity for utility shifting, it was identified and concluded that shifting of electrical poles in the already encumbered portion can be taken up only after removal of encumbrances/ obstructions as land was not available. Utility shifting is also interlinked with removal of encumbrance/encroachments. Hence i requested to remove the encumbrance and provide vacant acc Clause 8.1 of the Contract Agreement. Please confirm receipt of this correspondence. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Submission of Plan & Profile | Contractor's Obligations | Contractor has submitted the program for the works as per Clause 10.3 of agreement and plan & Profile drawings and requesting for approval | synthetic_template_20250913 | NHALI PIU - Krishnagiri - Consultancy services for Authority Engineer for supervision of Six laning of Karaipettai to Walajahpet section of NH-48 (old NH-4) from km.71+015 to km.107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase V- Mobilization at Site ~ Reg. | As you know that your firm has been appointed as Authority Engineer for the ee work and the contract agreement for civil work is signed on 15.10.2018 and appointed date is: declared as 11.2.2019 and the contractor has started the work and is in progress. 2.AS a part of contract agreement the contractor has submitted programme for the works as per clause 10.1.3 of agreement and Plan & Profile drawings and requesting for approvals. 3.As per para- 4 ,Annex-I ,Schedule-N of agreement ,the Authority Engineer shall review the programme for the works submitted by the contractor as per cl 10.1.3 of agreement and shall convey its comments to the contractor within a stipulated period of time. 4. As no communication is received on mobilisation of the Authority Engineer till date, it is requested to mobilise the staff at site under intimation to this office immediately for performing the duties of Authority Engineer. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Submission of Plan & Profile | Contractor's Obligations | The EPC contractor has already submitted plan and profile for a length of 10 Km from Km.71/015 to Km.81/OOO vide Lr.No.20/SPK/Kar - Wal/PD/NHA1 dated 03.04.2019. Hence, we disagree with the contention of the Authority that the EPC contractor has not submitted any designs for approval by Authority Engineer. | synthetic_template_20250913 | Request for modification of appointed date - Reply made - reg. | from _all encroachments and encumbrances, and free access thereto for the execution of this agreement.” Even today, ROW handed over is not free from all encroachments and encumbrances. There are structures which are fouling within ROW which are to be dismantled. No action has been taken on this issue by the 2. It is also submitted that the following structures couldn’t be taken up due to encumbrances/ obstructions as given in the remark’s column in the table below. Bund, Buildi d_ shifti f electri 82/566 ¦ vup ¦ Hs ¦ Buildings, Hut and shifting of electric pole. 85/874 ¦ LvuP ¦ BHS ¦ Pylon ~ 2 Nos. (RHS) & Pond Bund (LHS). ¦S {93/115 ¦ vup ¦ Bris —¦ Buildings to be eno ¦ 6 ¦ 98/423 ¦ Vup ¦ BES _¦ Buildings to be removed. ¦ LHS ¦ Building and temporary shed to be removed. RHS Boundary wall, building, water tank and temporary structure. above mentioned structures is one year. The same is also endorsed in policy circular — Policy matters — Technical ( 195/2016) dated 19. 1.2016 of the Authority while determining Extension of Time. event for extension of time if required. However, it has been three weeks since model code of conduct has been lifted and work of removal of encumbrance/ obstruction has not been started. As per the discussion had with the appointed entity for utility shifting, it was identified and concluded that shifting of electrical poles in the already encumbered portion can be taken up only after removal of encumbrances/ obstructions as land was not available. Utility shifting is also interlinked with removal of encumbrance/encroachments. Hence i requested to remove the encumbrance and provide vacant acc Clause 8.1 of the Contract Agreement. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Removal of Encumbrances and Encroachments from the ROW | EoT; Authority's Obligations | However, it has been three weeks since model code of conduct has been lifted and work of removal of encumbrance/ obstruction has not been started | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/49_17062019_ Modification of Appointed Date.pdf | Request for modification of appointed date - Reply made - reg. | from _all encroachments and encumbrances, and free access thereto for the execution of this agreement.” Even today, ROW handed over is not free from all encroachments and encumbrances. There are structures which are fouling within ROW which are to be dismantled. No action has been taken on this issue by the 2. It is also submitted that the following structures couldn’t be taken up due to encumbrances/ obstructions as given in the remark’s column in the table below. Bund, Buildi d_ shifti f electri 82/566 ¦ vup ¦ Hs ¦ Buildings, Hut and shifting of electric pole. 85/874 ¦ LvuP ¦ BHS ¦ Pylon ~ 2 Nos. (RHS) & Pond Bund (LHS). ¦S {93/115 ¦ vup ¦ Bris —¦ Buildings to be eno ¦ 6 ¦ 98/423 ¦ Vup ¦ BES _¦ Buildings to be removed. ¦ LHS ¦ Building and temporary shed to be removed. RHS Boundary wall, building, water tank and temporary structure. above mentioned structures is one year. The same is also endorsed in policy circular — Policy matters — Technical ( 195/2016) dated 19. 1.2016 of the Authority while determining Extension of Time. event for extension of time if required. However, it has been three weeks since model code of conduct has been lifted and work of removal of encumbrance/ obstruction has not been started. As per the discussion had with the appointed entity for utility shifting, it was identified and concluded that shifting of electrical poles in the already encumbered portion can be taken up only after removal of encumbrances/ obstructions as land was not available. Utility shifting is also interlinked with removal of encumbrance/encroachments. Hence i requested to remove the encumbrance and provide vacant acc Clause 8.1 of the Contract Agreement. | FALSE | real_data
Removal of Encumbrances and Encroachments from the ROW | EoT; Authority's Obligations | The impacted length due to encroachments and encumbrances was 12.18 km which accounted to 33.77% of the project highway. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/40_07082019_Rescheduling of Project Milestones – Request for Extension of time.pdf | Rescheduling of Project Milestones - Request for Extension of time - Reg. | The Contract agreement for the above mentioned project was executed on 15.10.2018. The appointed date was fixed as 11.02.2019 and the same was communicated vide ref (3) cited above. The Copy of the same is herewith enclosed as Annexure 1. The Authority in its response vide ref (5) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. The copy of the same is enclosed as Annexure 3. The EPC contractor vide ref (6) cited above reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that still the condition remained the same and dismantling/ removal of structures fouling was not started and shifting of Electric pole and power line also not started. The impacted length due to encroachments and encumbrances was 12.18 Km which accounted to 33.77% of the project highway. The workable length available to the Contractor based on the impacted length was 66.23% of the Project Highway length. The EPC Contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of removal of encumbrance / encroachment / obstruction. The copy of ref (7) is herewith enclosed as Annexure 4. It is almost six months since the declaration of appointed date, removal/ dismantling of structures/encroachments have not been started. Also, the work of shifting of power line and electric pole of LT line and HT lines crossings have not been started yet. The following are some of the key contractual dates and events since the inception of the project to till date: 1. Total length of the project highway: 36.076 Km 2. Date of Signing of agreement: 152018 3. Submission of Performance BG as per Clause 7.1.1 of the Contract Agreement: 262018 4. Target date for preparation of Memorandum as per Clause 8.2.1 of the Contract Agreement: 142018 5. Actual date of signing of Memorandum of land handing over: 112019 6. Declaration of appointed date by the Authority: 112019 7. ROW to be handed over as on appointed date as per Clause 8.2.2 & Annexure II: 35.468 Km | FALSE | real_data
Removal of Encumbrances and Encroachments from the ROW | EoT; Authority's Obligations | The EPC Contractor vide his letter No. 49/SPK/Kar-wal/PD/NHAI dated 17.06.2019 requested the Authority to consider the ROW handed over in terms of length (as per Cl. 4.1.3 and not in terms of area ) and shift the Appointed Date based on the actual date of removal of encumbrance/encroachment/obstruction for which response is still awaited from the Authority | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20200129_SPK_AE_001_Reply on Rescheduling of Project Milestone - Request for EoT.pdf | Reply on Rescheduling of Project Milestones — Request for Extension of Time - Reg. | The Authority Engineer vide ref (3) cited above communicated his recommendation on the above captioned subject. The EPC Contractor would like to submit his observations which are as follows: 1. The EPC Contractor vide his letter No. 49 / SPK / Kar - Wal / PD / NHAI dated 17.06.2019 requested the Authority to consider the ROW handed over in terms of length (as per Cl. 4.1.3 and not in terms of area and shift the Appointed Date based on the actual date of removal of encumbrance / encroachment / obstruction for which response is still awaited from the Authority. Further, it is worth mentioning that the AE also reiterated our stand wherein it was mentioned in Authority Engineer recommendation that “It is also worth mentioning that this memorandum was signed based on the % of area of the project ROW, in place of % of length, as mentioned in the Clause 4.1.3 (a).” 2. The assessment of hindrance length by the EPC contractor is correct as irrespective of hindrance available on one side, the same has to be considered for entire six laning width. In this regard it is hereby requested that the definition of ROW as per Article 28 shall be referred for further clarity. Further a working strip of at least 3 m wide shall be available parallel from the toe of the embankment pursuant to Clause 8.3.1 of the Contract Agreement. Authority Engineer has not based on this provision. 3. We totally deny with the observation of the Authority Engineer in not considering delay in handing over of land by the Authority pursuant to 4.1.3 (a) and 8.3.2 of the Contract Agreement. It is worth mentioning that even as on date 90% of encumbrance free land is yet to be handed over which is against the provisions of the Contract Agreement as 90% of land should have been handed over within 30 days of the execution of the agreement as per 4.1.3 (a) i.e on or before 15/11 / 2019. The joint inspection done on 24.10.2019 and on which the Authority Engineer’s representative signed would prove that only 62.51% of length was available on that day. Even today the Authority Engineer may carry out a joint inspection and will find that hardly 70% of the length is available for work front if imparted length is considered. 4. The EPC Contractor is obligated to comply only with the provisions of the Contract Agreement and not bound by any internal circular of the Authority as mentioned in AE recommendation. Hence, we disagree with the contention of the Authority Engineer that the EPC Contractor is not entitled for EOT in light of the circular issued by the Authority dated 16.08.2019. 5. It has been explicitly mentioned in Authority Engineer’s recommendation that shifting of utilities was being taken care by the Authority. Further the Contract Agreement between the Authority and Utility shifting agency was executed only on 19.07.2019. It is evident that shifting of utilities was not taken up till 19.07.2019, i.e 158 days from the declaration of Appointed Date by the Authority. Since the Authority is taking care of utility shifting and the agency appointed by the Authority commenced the works only after 180 days of the Appointed Date, period of 180 days mentioned in Clause 9.2is has no relevance. Hence, we deny with the contention of the Authority Engineer that the Contractor is entitled for time extension only beyond 180 days. The project duration is only 24 months and first 6 months are very crucial for the EPC contractor to progress the works based on his targeted programme. The Authority Engineer is also reiterating our concern wherein it has been mentioned that, ’The shifting of Utilities is important for this project, as the project is a Toll road and considering this, the Contractor submitted Construction Methodology, stating that first service road is to be constructed and after diverting the traffic over there, Main carriageway would be constructed ” . Utility shifting work is also not progressing as the encumbrances have not been removed and space is not made available for relocating the utility. 6. We would like to submit that as per Cl. 6 of Schedule-J , the Extension of Time recommendation is for Scheduled Project Completion Date and not confined to Milestone I. Based on the EOT recommended, all the milestones get automatically rescheduled accordingly. Hence, we do not agree with the contention of the Authority Engineer that the Extension of Time for Project. | FALSE | real_data
Removal of Encumbrances and Encroachments from the ROW | EoT; Authority's Obligations | This is with reference to the subject matter; we would like to bring to your kind attention that (i) Police Booth is located in the existing island in the proposed service road section (ii) High Mast light and some electrical utilities in junction improvement section in LHS of project alignment which has to be removed/shifted for diverting the traffic for construction of the vehicular underpass with RE wall at Km 76+846. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20200804_SPK_AE_120_Intimation of Hindrance at Km. 76+846 _1.pdf | Intimation of Existence of various hindrances for taking up construction of VUP & Junction Improvement at Km. 76+846 (Kilambi Junction) — Reg. | This is with refererice to the subject matter; we would like to bring your kind attention that, (i) Police Booth is located in the existing Island in the Proposed Service Road section (ii) High Mast Light and some Electrical Utilities in Junction Improvement section in LHS of Project Alignment which has to be removed/shifted for diverting the Traffic for construction of the Vehicular Underpass with RE wall at Km. 76+846. Plan showing the proposed Junction location is enclosed as Annexure - I. In this regard, we hereby request your goodself to intimate the same to the Authority in order to take up the clearing of above said hindrances at the earliest. This is for your kind information & necessary action, please. | FALSE | real_data
Removal of Encumbrances and Encroachments from the ROW | EoT; Authority's Obligations | The EPC contractor vide ref (5) cited above in reply reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that the impacted length due to encroachments and encumbrances was 12.18 km which accounted to 33.77% of the project length. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20201119_SPK_AE_160_Contractor failure in achieving mile stone 1,2,&3.pdf | Six laning of Karaipcttai to Walajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - Contractor’s failure in achieving Project Mile Stone 1,2 & 3 applying of Damages vide Contract Article No. 10.3.2 & 10.3.3 - Reply made -Reg. | We are in receipt of your letter ref (26) cited above, our reply for the same is as follows: 1. The Contract Agreement for this Project was executed on 15.10.2018. The Appointed Date was fixed as 11.02.2019 and the same was communicated vide ref (2) cited above. 2. The Appointed date was declared as 11.02.2019 by the Authority taking into account the land handed over in terms of the available area without taking into consideration, the requirement of the Contract provision as per Clause 4.1.3 (a) of the EPC agreement which talks about the handing over of land only in terms of length of the Project Highway. The memorandum and appendix prepared in terms of area gave a deceptive / false picture about the availability of vacant access. Taking into consideration all the encumbrances, hindrances, utilities etc. the vacant access available on the appointed date declared was worked out and it was less than 90% and hence requested the Authority vide letter under ref (3) cited above for modification of the appointed date on which 90% of encumbrance free land would be made available to the Contractor. 3. The Authority in its response vide ref (4) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. 4. The EPC contractor vide ref (5) cited above in reply reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that the impacted length due to encroachments and encumbrances was 12.18 km which accounted to 33.77% of the project length. The workable length available to the contractor was only 66.23% of the project length. The EPC contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of encumbrance / encroachment / obstruction. | FALSE | real_data
Removal of Encumbrances and Encroachments from the ROW | EoT; Authority's Obligations | Even as on date 100% of unencumbered land is not made available by the Authority and only 79.69% of unencumbered land is available. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20210416_SPK_AE_067_EOT request with Delay analysis.pdf | Six laning of Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V -EOT recommendation by the Authority for a period of 112 days not agreeable to the EPC Contractor — Request for considering EOT as discussed during the Review Meetings- reg | We are writing to express our concerns regarding the EOT recommendation by the Authority for a period of 112 days, which is not agreeable to the EPC Contractor. We request that the EOT be considered as discussed during the Review Meetings. The project involves six laning of the Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km 71+015 to km 107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase-V. We have referenced several documents and meetings in support of our request, and we hope for a favorable consideration. | FALSE | real_data
Removal of Encumbrances and Encroachments from the ROW | EoT; Authority's Obligations | 1. we have been objected by local public to dismantle the existing CC drain at Nizampet village 2. the encroachment needs to be cleared. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-2/3. 20231220_169_Cont_AE_Existing CC drain_from KM 30+830 to 31+550 on RHS.pdf | Existing CC drain @ Nizampet Village from KM 30+830 to 31+550 on RHS - Reg. | With reference to the above subject, we would like to inform your good office that, we have been objected by local public to dismantle the existing CC drain at Nizampet Village. The existing drain location is from km 30+850 to 31+550 on RHS and it is currently connected with the household usage water. Please note that we have to construct the RCC drain from 30+750 to 31+550 on RHS as per CA and we have completed the drain construction from 30+750 to 30+815 on RHS. To continue further, the encroachment needs to be cleared. Photographs of the said location are enclosed herewith for your ready reference. Hence, we request your good office to clear the encroachment at the earliest to enable us to complete the RCC drain construction at the said location. | FALSE | real_data
Removal of Encumbrances and Encroachments from the ROW | EoT; Authority's Obligations | Encroachments have not been removed, specifically a temple, which has not been removed by the Authority. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-2/12. 20240728_564_Cont_AE_Progress of works.pdf | Rehabilitation and Upgradation of Satana to Mangrul (Chandwad) Section of NH 752 G Design Ch. KM 64+000 to KM 1014140 Two Lane with Paved Shoulder / Four Lane Configuration in the state of Maharashtra on EPC Mode. Reg. Progress of works. | We refer to your letter at ref. 2, wherein you have conveyed your observations on the progress of works in the above-mentioned project stretch. In this regard, please find our para-wise reply below: 1. Slow Progress of works It is mentioned in your letter that the work front of 11.4 Km from Km.64+000 to 75+400 is available to us. This is contrary to the actual site condition, the land available for works as on date is only 8.52 Km. The details of unavailable stretches are as follows: a) Km 65+000 to 66+490 (1.490 km) - Satana Market: Full width of the Right of Way (ROW) is not available as the encroachments have not been removed. Despite several meetings held with the Satana Tehsildar, Local MLA and the public, in the presence of the Authority and Authority’s Engineer (AE), the issue remains unresolved even as on date. b) Km 66+520 to 66+600 (LHS), 67+560 to 67+650 (LHS), 71+930 to 72+000 (LHS): Land Acquisition at the above locations is not yet completed by the Authority even as on date. c) Km 68+780 to 68+830 (LHS): Encroachments have not been removed, specifically a temple, which has not been removed by the Authority. d) Km 74+100 to 74+700 & 74+900 to 75+400 - Thengode-Lohner Market: Full width of the ROW is not available at these locations as the encroachments have not been removed even as on date. The status of completed works in the available stretch of 8.52 km is as below: ° PQC (Pavement Quality Concrete): 2.3 km (LHS) ° DLC (Dry Lean Concrete): 3.70 km (LHS) ° GSB (Granular Sub-base): 4.1 km (LHS) ° Subgrade: 4.6 km (LHS) ° Subgrade widening on RHS: km 69+000 to 74+600, i.e., 5.6 km. The works of minor bridges at Km. 67+710 and 68+800 could not be started due to the pending land acquisition issues which are yet to be cleared. Though the construction of Minor Bridge at km 71+910 was commenced in the last month, the same got halted due to heavy rains. To avoid idling, the manpower was shifted to other works and was again remobilized to the structure on 27.07.2024 and the work was resumed. The work on the slab drains at km 70+050 and km 70+100 is in progress and will be completed within a month. We assure you that all pipe culvert works from km 64+000 to 75+000 will be completed within a month. For the four-lane portion from km 64+000 to km 64+800, the scope of new Jersey-type divider is only of 590 meters, for which the PCC work is completed, balance work is in progress and will be completed at the earliest. The terminal slab work on one half of km 94+420 (RHS) is pending and will be completed after diversion of traffic movement onto LHS. 2. Shifting of Utilities Regarding shifting of Electrical Utilities, we wish to submit that the estimate approvals for shifting the utilities were accorded by the Competent Authority for Chandwad section in the month of May’24 and for Deola and Satana sections in the Month of June’24. Despite the delayed approvals from the authorities, we have completed the works for Chandwad section, and the works of Deola and Satana sections were started as soon as we have received the approvals, and the works are in progress. | FALSE | real_data
Providing Right of Way in terms of length of Project Highway | Authority's Obligations; Appointed Date | We once again request you to consider the ROW handed over in terms of length and not in terms of area and shift the Appointed Date based on the actual date of removal of encumbrance/ encroachment/ obstruction. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/49_17062019_ Modification of Appointed Date.pdf | Request for modification of appointed date - Reply made - reg. | from _all encroachments and encumbrances, and free access thereto for the execution of this agreement.” Even today, ROW handed over is not free from all encroachments and encumbrances. There are structures which are fouling within ROW which are to be dismantled. No action has been taken on this issue by the 2. It is also submitted that the following structures couldn’t be taken up due to encumbrances/ obstructions as given in the remark’s column in the table below. Bund, Buildi d_ shifti f electri 82/566 ¦ vup ¦ Hs ¦ Buildings, Hut and shifting of electric pole. 85/874 ¦ LvuP ¦ BHS ¦ Pylon ~ 2 Nos. (RHS) & Pond Bund (LHS). ¦S {93/115 ¦ vup ¦ Bris —¦ Buildings to be eno ¦ 6 ¦ 98/423 ¦ Vup ¦ BES _¦ Buildings to be removed. ¦ LHS ¦ Building and temporary shed to be removed. RHS Boundary wall, building, water tank and temporary structure. above mentioned structures is one year. The same is also endorsed in policy circular — Policy matters — Technical ( 195/2016) dated 19. 1.2016 of the Authority while determining Extension of Time. event for extension of time if required. However, it has been three weeks since model code of conduct has been lifted and work of removal of encumbrance/ obstruction has not been started. As per the discussion had with the appointed entity for utility shifting, it was identified and concluded that shifting of electrical poles in the already encumbered portion can be taken up only after removal of encumbrances/ obstructions as land was not available. Utility shifting is also interlinked with removal of encumbrance/encroachments. Hence i requested to remove the encumbrance and provide vacant acc Clause 8.1 of the Contract Agreement. | FALSE | real_data
Providing Right of Way in terms of length of Project Highway | Authority's Obligations; Appointed Date | The EPC Contractor vide his letter No. 49/SPK/Kar-wal/PD/NHAI dated 17.06.2019 requested the Authority to consider the ROW handed over in terms of length (as per Cl. 4.1.3 and not in terms of area ) and shift the Appointed Date based on the actual date of removal of encumbrance/encroachment/obstruction for which response is still awaited from the Authority | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20200129_SPK_AE_001_Reply on Rescheduling of Project Milestone - Request for EoT.pdf | Reply on Rescheduling of Project Milestones — Request for Extension of Time - Reg. | The Authority Engineer vide ref (3) cited above communicated his recommendation on the above captioned subject. The EPC Contractor would like to submit his observations which are as follows: 1. The EPC Contractor vide his letter No. 49 / SPK / Kar - Wal / PD / NHAI dated 17.06.2019 requested the Authority to consider the ROW handed over in terms of length (as per Cl. 4.1.3 and not in terms of area and shift the Appointed Date based on the actual date of removal of encumbrance / encroachment / obstruction for which response is still awaited from the Authority. Further, it is worth mentioning that the AE also reiterated our stand wherein it was mentioned in Authority Engineer recommendation that “It is also worth mentioning that this memorandum was signed based on the % of area of the project ROW, in place of % of length, as mentioned in the Clause 4.1.3 (a).” 2. The assessment of hindrance length by the EPC contractor is correct as irrespective of hindrance available on one side, the same has to be considered for entire six laning width. In this regard it is hereby requested that the definition of ROW as per Article 28 shall be referred for further clarity. Further a working strip of at least 3 m wide shall be available parallel from the toe of the embankment pursuant to Clause 8.3.1 of the Contract Agreement. Authority Engineer has not based on this provision. 3. We totally deny with the observation of the Authority Engineer in not considering delay in handing over of land by the Authority pursuant to 4.1.3 (a) and 8.3.2 of the Contract Agreement. It is worth mentioning that even as on date 90% of encumbrance free land is yet to be handed over which is against the provisions of the Contract Agreement as 90% of land should have been handed over within 30 days of the execution of the agreement as per 4.1.3 (a) i.e on or before 15/11 / 2019. The joint inspection done on 24.10.2019 and on which the Authority Engineer’s representative signed would prove that only 62.51% of length was available on that day. Even today the Authority Engineer may carry out a joint inspection and will find that hardly 70% of the length is available for work front if imparted length is considered. 4. The EPC Contractor is obligated to comply only with the provisions of the Contract Agreement and not bound by any internal circular of the Authority as mentioned in AE recommendation. Hence, we disagree with the contention of the Authority Engineer that the EPC Contractor is not entitled for EOT in light of the circular issued by the Authority dated 16.08.2019. 5. It has been explicitly mentioned in Authority Engineer’s recommendation that shifting of utilities was being taken care by the Authority. Further the Contract Agreement between the Authority and Utility shifting agency was executed only on 19.07.2019. It is evident that shifting of utilities was not taken up till 19.07.2019, i.e 158 days from the declaration of Appointed Date by the Authority. Since the Authority is taking care of utility shifting and the agency appointed by the Authority commenced the works only after 180 days of the Appointed Date, period of 180 days mentioned in Clause 9.2is has no relevance. Hence, we deny with the contention of the Authority Engineer that the Contractor is entitled for time extension only beyond 180 days. The project duration is only 24 months and first 6 months are very crucial for the EPC contractor to progress the works based on his targeted programme. The Authority Engineer is also reiterating our concern wherein it has been mentioned that, ’The shifting of Utilities is important for this project, as the project is a Toll road and considering this, the Contractor submitted Construction Methodology, stating that first service road is to be constructed and after diverting the traffic over there, Main carriageway would be constructed ” . Utility shifting work is also not progressing as the encumbrances have not been removed and space is not made available for relocating the utility. 6. We would like to submit that as per Cl. 6 of Schedule-J , the Extension of Time recommendation is for Scheduled Project Completion Date and not confined to Milestone I. Based on the EOT recommended, all the milestones get automatically rescheduled accordingly. Hence, we do not agree with the contention of the Authority Engineer that the Extension of Time for Project. | FALSE | real_data
Providing Right of Way in terms of length of Project Highway | Authority's Obligations; Appointed Date | The appointed date was declared as 11.02.2019 by the Authority taking into account the land handed over in terms of the available area without taking into consideration, the requirement of the Contract provision as per Clause 4.1.3 (a) of the EPC agreement which talks about the handing over of land only in terms of length of the Project Highway. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20201119_SPK_AE_160_Contractor failure in achieving mile stone 1,2,&3.pdf | Six laning of Karaipcttai to Walajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - Contractor’s failure in achieving Project Mile Stone 1,2 & 3 applying of Damages vide Contract Article No. 10.3.2 & 10.3.3 - Reply made -Reg. | We are in receipt of your letter ref (26) cited above, our reply for the same is as follows: 1. The Contract Agreement for this Project was executed on 15.10.2018. The Appointed Date was fixed as 11.02.2019 and the same was communicated vide ref (2) cited above. 2. The Appointed date was declared as 11.02.2019 by the Authority taking into account the land handed over in terms of the available area without taking into consideration, the requirement of the Contract provision as per Clause 4.1.3 (a) of the EPC agreement which talks about the handing over of land only in terms of length of the Project Highway. The memorandum and appendix prepared in terms of area gave a deceptive / false picture about the availability of vacant access. Taking into consideration all the encumbrances, hindrances, utilities etc. the vacant access available on the appointed date declared was worked out and it was less than 90% and hence requested the Authority vide letter under ref (3) cited above for modification of the appointed date on which 90% of encumbrance free land would be made available to the Contractor. 3. The Authority in its response vide ref (4) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. 4. The EPC contractor vide ref (5) cited above in reply reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that the impacted length due to encroachments and encumbrances was 12.18 km which accounted to 33.77% of the project length. The workable length available to the contractor was only 66.23% of the project length. The EPC contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of encumbrance / encroachment / obstruction. | FALSE | real_data
Providing Right of Way in terms of length of Project Highway | Authority's Obligations; Appointed Date | The appointed date was declared as 11.02.2019 by the Authority considering the land handed over in terms of area in lieu of the linear length, which was not conforming to the requirement as per Clause 4.1.3 (a) of the EPC agreement. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20210416_SPK_AE_067_EOT request with Delay analysis.pdf | Six laning of Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V -EOT recommendation by the Authority for a period of 112 days not agreeable to the EPC Contractor — Request for considering EOT as discussed during the Review Meetings- reg | We are writing to express our concerns regarding the EOT recommendation by the Authority for a period of 112 days, which is not agreeable to the EPC Contractor. We request that the EOT be considered as discussed during the Review Meetings. The project involves six laning of the Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km 71+015 to km 107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase-V. We have referenced several documents and meetings in support of our request, and we hope for a favorable consideration. | FALSE | real_data
Providing Right of Way in terms of length of Project Highway | Authority's Obligations; Appointed Date | The Contractor has arrived the percentage/ length of encumbrances as considering the "impacted length" due to encumbrances clubbing hindrance length at both sides irrespective of hindrance available on single side. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/189_Rescheduling of Project Milestones - EOT - 1.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under BharatmalaPariyojana on EPC mode — Rescheduling of Project Mile Stone- Request for Extension of Time -Reg. | Having gone through your documents related to Rescheduling of Project Milestone-Request for Extension of Time EoT-1 please find enclosed herewith the Authority Engineers recommendations on the same subject. This is for your information and necessary action. | FALSE | real_data
Providing Right of Way in terms of length of Project Highway | Authority's Obligations; Appointed Date | The Authority Engineer will not agree with the percentage of calculation of available length. The contractor has adopted additional length before and after the hindrance for his working front. Moreover, the hindrance length calculated will not be considered since it is calculated as impacted length considering width of Road way on Both the sides. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/264_18022020_Rescheduling of Project Milestones – Request for Extension of Time.pdf | Rescheduling of Project Milestones — Request for Extension of Time -Reg. | In reference to the above-mentioned subject and Contractor letter No. SPK/KW/SAIC/NH-48/2020/001 dated 29.01.2020 regarding the rescheduling of Project Milestone, in this regard, it is submitted that AE has computed the 176 days for extension of time in Milestones I and II. The same was recommended vide AE letter No. SAICPL/Kar-Wal/H.O./NH-48/TN/2019/10451 dated 30.11.2019 to the Authority for their acceptance and further needful. However, the Contractor submitted his reservations on the computation of the nos. of delay days and requested for rescheduling of Project Milestones for a period of 324 days instead of recommended 176 nos. of days. In this regard, AE is hereby submitted point wise reply of your raised observations for your ready reference and record, please; 4. Modification of Appointed date and Handing Over in % of area. The appointed date was communicated by the Authority letter No. NHAI/PIU.K.giri/NH-4/SPK/PS/2019/972 Dated 03.06.2019. it is also submitted that as per cl 8.2.2 the authority shall provide the Right of Way to the Contractor in respect of all land included in the Appendix by the date specified in Schedule-A for those parts of the site referred to therein, or no later than 90 days of the appointed date for those parts of the site which have not been specified in Schedule-A. It is well evident that the lands specified in Annexure-II, Schedule-A of agreement are available from the day one and as on appointed date, the existing and proposed ROW is same and no parts of the site is mentioned as not available in Schedule-A and joint memorandum signed on 11.01.2019 except for the lands for widening of plaza at Chennasamudram. Hence authority has fulfilled the obligation. This was informed vide Authority letter No. NHAI/PIU.K.giri/NH-4/SPK/PS/2019/972 Dated 03.06.2019. In view of above, the request of the Contractor to modify the appointed date is not eligible as per agreement due to the following reasons (i) As per cl 4.1.3, 8.2.1 & 8.2.2, 8.2.3 — The agreement is signed on 15.10.2018 and the Joint memorandum is signed by both the parties on 30.01.2019 and appointed date is declared for the project on 11.02.2019 to commence the work. (i) The Authority Engineer vide Letter No. SAICPL/Kar-Wal/H.O./NH-48/TN/2019/10451 Dated 30.11.2019. informed that the contractor consciously agreed and signed the Joint memorandum and aware that the unencumbered and the vacant land available after joint inspection is 93.65%. (iii) Further, it is submitted that the Joint memorandum was signed on 11.01.2019 & the appointment date is declared as 11.02.2019. The Contractor has requested the Authority for modifying the Appointment date based on the length of Project Highway handed over, vide letter No. 29/SPK/Kar-Wal/PD/NHAI/ Dated 13.05.2019. On this account and in view of clause 8.3.2 of the Contract Agreement, the Contractor cited reason of land not handed over pursuant to Clause 4.1.3 (a) is not acceptable and cannot be considered for Entitlement for EOT. 2. Assessment of Hindrance length. The assessment of hindrance length is already enumerated in Point No. 01 above. It is to remind the contractor that the Joint memorandum was signed by both the parties on 30.01.2019 as per the provisions of the Contract Agreement. The AE hereby like to reiterate the clause 8.2.1. “The Authority Representative and the Contractor shall, within 30 (thirty) days of the date of this Agreement, inspect the Site and prepare a memorandum containing an inventory of the Site including the vacant and unencumbered land, buildings, structures, road works, trees and any other immovable property on or attached to the Site. Subject to the provisions of Clause 8.2.3, such memorandum shall have appended thereto an appendix (the “Appendix”) specifying in reasonable detail those parts of the Site to which vacant access and Right of Way has not been given to the Contractor. Signing of the memorandum, in two counterparts (each of which shall constitute an original), by the authorized representatives of the Parties shall be deemed to constitute a valid evidence of giving the Right of Way to the Contractor for discharging its obligations under and in accordance with the provisions of this Agreement and for no other purpose whatsoever’. AE would like to further clarify that cl. 8.3.1 last para stating that “For the avoidance of doubt, the Parties expressly agree that the Damages specified hereunder and the Time Extension specified in Clause 10.5 shall be restricted only to failure of the Authority to provide the Right of Way for and in respect of the width of the roadway, its embankment and a parallel working strip at least 3 (three) meters wide”. The width of the roadway can be treated as one side of the road since it is neither mentioned “Total width nor Full width’. Hence the Authority Engineer has done the analysis of Hindrance free length is clear with the above illustrated iteration. | FALSE | real_data
Providing Right of Way in terms of length of Project Highway | Authority's Obligations; Appointed Date | The way the Contractor assessed the un-encumbrance length and percentage is impractical and cannot be justified. Practically the encumbrance length can be assessed side wise as per how the execution will be carried out and not considering the total width of Row as per TCS. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/20191130_AE_PD_10451_Recommendation of EOT I for a period of 178 days.pdf | Application for EOT | This is with reference to the captioned subject and application for EOT received from the Contractor, in this regard, it is submitted that the Contract Agreement was signed between Contractor M/s SPK & Co. and the NHAI for Six Laning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km 71+015 to Km 107+091 in the State of Tamil Nadu under NHDP Phase - V. The following are the main contractual data ; Contract Seen Date : 15/10/2018 Length of the Project 36.076 Km Project Cost INR 533,36,67,000 Appointed Date : 11/02/2019 Construction Period : 730 days from Appointed Date Scheduled Completion Date: 09/02/2021 DLP Period : 4 years from the Provisional Certificate Project Milestone ~ Days from Project Milestone Appointed Date Milestone - -1 180 Days 09/08/2019 Not achieved 365 Days 10/02/2020 To be achieved 550 Days 13/08/2020 730 Days 09/02/2021 To be Achieved In view of the above, Authority's Engineer has scrutinized the EOT application and Authority's Engineer observations are being summarized hereunder in light of the Contract Agreement; Scheduled Date ¦ Status Procurement of the Site; As mentioned in the Clause 8.2.1 of the Contract Agreement, which reproduced herewith “the Authority Representative and the Contractor shall, within 30 days of the date of this Agreement, inspect the Site and prepare a memorandum containing an inventory of the site including the vacant and unencumbered land, buildings, structures, road works, trees and any other immovable property on or attached to the site. Subject to the provisions of Clause 8.2.3, such memorandum shall have appended thereto an appendix (the “Appendix”) specifying in reasonable detail those parts of the site to which vacant access and Right of Way has not been given to the Contractor. Signing of the memorandum, in two counterparts (each of which shall constitute an original), by the Authorized Representatives of the Parties shall be deemed to constitute a valid evidence of giving the Right of Way to the Contractor for discharging its obligations under and in accordance with the provisions of this Agreement and for no other purpose whatsoever.” | FALSE | real_data
Labour License | Contractor's Obligations | Regarding issuance of Form V to EPC Contractor M/s SPK AND CO, for obtaining Labour License | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/34_13052019_ Request for Issuance of Form V.pdf | Regarding Issuance of Form V to EPC Contractor M/s SPK AND CO,,. for Obtaining Labour License. | This has reference to the subjected matter, we hereby request you to kindly issue Form-V Certificate in the name of EPC Contractor “M/s SPK AND CO” for obtaining registration/permission for Contract labour license from District Labour Commissioner under the Contract Labour Act 1970. | FALSE | real_data
Labour License | Contractor's Obligations | 1.EPC Mode in the state of Tamil Nadu under NHDP Phase-V is strictly fulfilling the wages norms of the Govt. of India policies / MORTH / Govt. of Tamil Nadu for all the construction labours utilized in the above said project. 2.In future if any discrepancies arise in regarding the wages of the Labours utilized in the subjected project, we M/s.SPK AND Co., will be solely responsible. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LOT-10/20230223_Declaration of Undertaking.pdf | Declaration of Undertaking for the wages of Labours utilized - Reg. | It is to hereby declare that M/s.SPK AND Co., who is executing the Six Laning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km.71+015 (Existing Km 71/000) to Km 107+091 (Existing Km 107/068) on EPC Mode in the state of Tamil Nadu under NHDP Phase-V is strictly fulfilling the wages norms of the Govt. of India policies / MORTH / Govt. of Tamil Nadu for all the construction labours utilized in the above said project. In future if any discrepancies arise in regarding the wages of the Labours utilized in the subjected project, we M/s.SPK AND Co., will be solely responsible. Thanking you and always assuring of the best services. Yours faithfully, For SPK AND CoO., Managing Partner GST : 33ABXFS5510P1ZG | FALSE | real_data
Labour License | Contractor's Obligations | Regarding issuance of Form V to EPC Contractor M/s SPK AND CO, for obtaining Labour License | synthetic_template_20250913 | Regarding Issuance of Form V to EPC Contractor M/s SPK AND CO,,. for Obtaining Labour License. | This has reference to the subjected matter, we hereby request you to kindly issue Form-V Certificate in the name of EPC Contractor “M/s SPK AND CO” for obtaining registration/permission for Contract labour license from District Labour Commissioner under the Contract Labour Act 1970. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Labour License | Contractor's Obligations | The engagement of contract labour in the above said work is not prohibited under sub section (1) of section 10 of the Contract Labour (Regulation and Abolition) Act, 1970 (37 of 1970). | synthetic_template_20250913 | Form of Certificate of Principal Employer | We would like to inform you that Certified that National Highways Authority of India (NHAI), a body corporate under the Ministry of Road Transport & Highways, Government of India having its Corporate office at Plot G - 5 & 6, Sector -10, Dwaraka, New Delhi 100 075 through Project Implementation Unit, Kancheepuram have engaged M/s. S.P.K. & Co, Reg. Off 2/67, R.C. Middle Street, Keelamudimannarkottai, Kamuthi Taluk, Ramnad District 623 603 as contractor in this establishment for the work of “Six laning of karaipettai to Walajapet section of NH4 (New NH-48) from Km 71+015 to Km 107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase V” to be carried out from 11.02.2019 to 10.02.2021 for a period of two year. NHAI undertake to be bound by the provisions of the Contract Labour (Regulation and Abolition) Act 1970 (37 of 1970) and Contract Labour (Regulation and Abolition) Central Rules 1971, in so far as the Provisions are applicable to NHAI in respect of the Employment of Contract Labour by M/s. S.P.K. & CO in this establishment. The engagement of contract labour in the above said work is not prohibited under sub section (1) of section 10 of the Contract Labour (Regulation and Abolition) Act, 1970 (37 of 1970). | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Labour License | Others | The engagement of contract labour in the above said work is not prohibited under sub section (1) of section 10 of the Contract Labour (Regulation and Abolition) Act, 1970 (37 of 1970). | synthetic_template_20250913 | Form of Certificate of Principal Employer | Certified that National Highways Authority of India (NHAI), a body corporate under the Ministry of Road Transport & Highways, Government of India having its Corporate office at Plot G - 5 & 6, Sector -10, Dwaraka, New Delhi 100 075 through Project Implementation Unit, Kancheepuram have engaged M/s. S.P.K. & Co, Reg. Off 2/67, R.C. Middle Street, Keelamudimannarkottai, Kamuthi Taluk, Ramnad District 623 603 as contractor in this establishment for the work of “Six laning of karaipettai to Walajapet section of NH4 (New NH-48) from Km 71+015 to Km 107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase V” to be carried out from 11.02.2019 to 10.02.2021 for a period of two year. NHAI undertake to be bound by the provisions of the Contract Labour (Regulation and Abolition) Act 1970 (37 of 1970) and Contract Labour (Regulation and Abolition) Central Rules 1971, in so far as the Provisions are applicable to NHAI in respect of the Employment of Contract Labour by M/s. S.P.K. & CO in this establishment. The engagement of contract labour in the above said work is not prohibited under sub section (1) of section 10 of the Contract Labour (Regulation and Abolition) Act, 1970 (37 of 1970). We look forward to your response. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Labour License | Others | Regarding issuance of Form V to EPC Contractor M/s SPK AND CO, for obtaining Labour License | synthetic_template_20250913 | Regarding Issuance of Form V to EPC Contractor M/s SPK AND CO,,. for Obtaining Labour License. | This has reference to the subjected matter, we hereby request you to kindly issue Form-V Certificate in the name of EPC Contractor “M/s SPK AND CO” for obtaining registration/permission for Contract labour license from District Labour Commissioner under the Contract Labour Act 1970. We appreciate your cooperation in this regard. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Approval for Proof Consultant conveyed | Contractor's Obligations | Proof Consultant by the Contractor M/S. S.P.K & Co., approval is hereby conveyed to the firm M/S. Professional Civil Infra Pvt. Ltd., as a Proof Consultant for the above project. | synthetic_template_20250913 | Six laning of Karaipettai to Walajahpet section of NH-48 (old NH-4) from km.71+015 to km.107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase V-Appointment of Proof Consultant- Approval -Reg. | Apropos your letter cited under reference seeking approval for engaging Proof Consultant by the Contractor M/s. S.P.K & Co., approval is hereby conveyed to the firm M/s. Professional Civil Infra Pvt. Ltd., as a Proof Consultant for the above project. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Approval for Proof Consultant conveyed | Contractor's Obligations | Proof Consultant by the Contractor M/S. S.P.K & Co., approval is hereby conveyed to the firm M/S. Professional Civil Infra Pvt. Ltd., as a Proof Consultant for the above project. | synthetic_template_20250913 | Six laning of Karaipettai to Walajahpet section of NH-48 (old NH-4) from km.71+015 to km.107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase V-Appointment of Proof Consultant- Approval -Reg. | Apropos your letter cited under reference seeking approval for engaging Proof Consultant by the Contractor M/s. S.P.K & Co., approval is hereby conveyed to the firm M/s. Professional Civil Infra Pvt. Ltd., as a Proof Consultant for the above project. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Approval for Proof Consultant conveyed | Contractor's Obligations | Proof Consultant by the Contractor M/S. S.P.K & Co., approval is hereby conveyed to the firm M/S. Professional Civil Infra Pvt. Ltd., as a Proof Consultant for the above project. | synthetic_template_20250913 | Six laning of Karaipettai to Walajahpet section of NH-48 (old NH-4) from km.71+015 to km.107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase V-Appointment of Proof Consultant- Approval -Reg. | Apropos your letter cited under reference seeking approval for engaging Proof Consultant by the Contractor M/s. S.P.K & Co., approval is hereby conveyed to the firm M/s. Professional Civil Infra Pvt. Ltd., as a Proof Consultant for the above project. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Approval for Proof Consultant conveyed | Contractor's Obligations | Proof Consultant by the Contractor M/S. S.P.K & Co., approval is hereby conveyed to the firm M/S. Professional Civil Infra Pvt. Ltd., as a Proof Consultant for the above project. | synthetic_template_20250913 | Six laning of Karaipettai to Walajahpet section of NH-48 (old NH-4) from km.71+015 to km.107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase V-Appointment of Proof Consultant- Approval -Reg. | Apropos your letter cited under reference seeking approval for engaging Proof Consultant by the Contractor M/s. S.P.K & Co., approval is hereby conveyed to the firm M/s. Professional Civil Infra Pvt. Ltd., as a Proof Consultant for the above project. Thank you for your attention to this matter. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Approval for Proof Consultant conveyed | Contractor's Obligations | Proof Consultant by the Contractor M/S. S.P.K & Co., approval is hereby conveyed to the firm M/S. Professional Civil Infra Pvt. Ltd., as a Proof Consultant for the above project. | synthetic_template_20250913 | Six laning of Karaipettai to Walajahpet section of NH-48 (old NH-4) from km.71+015 to km.107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase V-Appointment of Proof Consultant- Approval -Reg. | Apropos your letter cited under reference seeking approval for engaging Proof Consultant by the Contractor M/s. S.P.K & Co., approval is hereby conveyed to the firm M/s. Professional Civil Infra Pvt. Ltd., as a Proof Consultant for the above project. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Letter of Award issued by the Authority | Authority's Obligations; Others | Letter of Award | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/124648A_05102018_LOA with acceptance.pdf | Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km. 71+015 to Km 107+091 on EPC Mode in the state of Tamil Nadu under NHDP Phase-V- Letter of Award-Reg. | This is to notify that your bid submitted for the project of “Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km. 71+015 to Km 107+091 on EPC Mode in the state of Tamil Nadu”, is hereby accepted by NHAI for the contract price of Rs. 533,36,67,000/- (Rupees Five Hundred Thirty Three Crore Thirty Six Lakh and Sixty Seven Thousand Only) and declaring you a “Selected Bidder”. 2. In accordance with the Clause 3.3.4 of the RFP document (Volume-l), you are requested to sign the duplicate copy of the LOA and return the same as your acknowledgement within 7 (Seven) days of the receipt of LOA. It is requested to deliver a legal opinion from your legal counsel with respect to your authority to enter into Contract Agreement and the enforceability of the provision thereof, within 10 (Ten) days of issue of this LOA. 3. Further, as per RFP documents, the Contractor for due and faithful performance of its obligations during the Construction Period as well as Defects Liability Period required to furnish a Performance Security by way of an irrevocable and unconditional Bank Guarantee of Rs. 26,66,83,350/- (Rupees Twenty Six Crore Sixty Six Lakhs Eighty Three Thousand Three Hundred and Fifty Only) within 10 days from the date of signing of the Contract Agreement. The Performance Security shall be valid until 60 (sixty) days after the Defects Liability Period. (refer Clauses of Article-7 of EPC Agreement). 4. You are requested to Comply with the above and all the terms and conditions set forth in the RFP documents. In case of any default on your part, you shall be liable for action as stated in the RFP Document. | FALSE | real_data
Letter of Award issued by the Authority | Authority's Obligations | Letter of Award | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km. 71+015 to Km 107+091 on EPC Mode in the state of Tamil Nadu under NHDP Phase-V- Letter of Award-Reg. | This is to notify you that This is to notify that your bid submitted for the project of “Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km. 71+015 to Km 107+091 on EPC Mode in the state of Tamil Nadu”, is hereby accepted by NHAI for the contract price of Rs. 533,36,67,000/- (Rupees Five Hundred Thirty Three Crore Thirty Six Lakh and Sixty Seven Thousand Only) and declaring you a “Selected Bidder”. 2. In accordance with the Clause 3.3.4 of the RFP document (Volume-l), you are requested to sign the duplicate copy of the LOA and return the same as your acknowledgement within 7 (Seven) days of the receipt of LOA. It is requested to deliver a legal opinion from your legal counsel with respect to your authority to enter into Contract Agreement and the enforceability of the provision thereof, within 10 (Ten) days of issue of this LOA. 3. Further, as per RFP documents, the Contractor for due and faithful performance of its obligations during the Construction Period as well as Defects Liability Period required to furnish a Performance Security by way of an irrevocable and unconditional Bank Guarantee of Rs. 26,66,83,350/- (Rupees Twenty Six Crore Sixty Six Lakhs Eighty Three Thousand Three Hundred and Fifty Only) within 10 days from the date of signing of the Contract Agreement. The Performance Security shall be valid until 60 (sixty) days after the Defects Liability Period. (refer Clauses of Article-7 of EPC Agreement). 4. You are requested to Comply with the above and all the terms and conditions set forth in the RFP documents. In case of any default on your part, you shall be liable for action as stated in the RFP Document. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Letter of Award issued by the Authority | Others | Letter of Award | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km. 71+015 to Km 107+091 on EPC Mode in the state of Tamil Nadu under NHDP Phase-V- Letter of Award-Reg. | It is brought to your attention that This is to notify that your bid submitted for the project of “Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km. 71+015 to Km 107+091 on EPC Mode in the state of Tamil Nadu”, is hereby accepted by NHAI for the contract price of Rs. 533,36,67,000/- (Rupees Five Hundred Thirty Three Crore Thirty Six Lakh and Sixty Seven Thousand Only) and declaring you a “Selected Bidder”. 2. In accordance with the Clause 3.3.4 of the RFP document (Volume-l), you are requested to sign the duplicate copy of the LOA and return the same as your acknowledgement within 7 (Seven) days of the receipt of LOA. It is requested to deliver a legal opinion from your legal counsel with respect to your authority to enter into Contract Agreement and the enforceability of the provision thereof, within 10 (Ten) days of issue of this LOA. 3. Further, as per RFP documents, the Contractor for due and faithful performance of its obligations during the Construction Period as well as Defects Liability Period required to furnish a Performance Security by way of an irrevocable and unconditional Bank Guarantee of Rs. 26,66,83,350/- (Rupees Twenty Six Crore Sixty Six Lakhs Eighty Three Thousand Three Hundred and Fifty Only) within 10 days from the date of signing of the Contract Agreement. The Performance Security shall be valid until 60 (sixty) days after the Defects Liability Period. (refer Clauses of Article-7 of EPC Agreement). 4. You are requested to Comply with the above and all the terms and conditions set forth in the RFP documents. In case of any default on your part, you shall be liable for action as stated in the RFP Document. Thank you for your attention to this matter. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Letter of Award issued by the Authority | Others | Letter of Award | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km. 71+015 to Km 107+091 on EPC Mode in the state of Tamil Nadu under NHDP Phase-V- Letter of Award-Reg. | This is to notify that your bid submitted for the project of “Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km. 71+015 to Km 107+091 on EPC Mode in the state of Tamil Nadu”, is hereby accepted by NHAI for the contract price of Rs. 533,36,67,000/- (Rupees Five Hundred Thirty Three Crore Thirty Six Lakh and Sixty Seven Thousand Only) and declaring you a “Selected Bidder”. 2. In accordance with the Clause 3.3.4 of the RFP document (Volume-l), you are requested to sign the duplicate copy of the LOA and return the same as your acknowledgement within 7 (Seven) days of the receipt of LOA. It is requested to deliver a legal opinion from your legal counsel with respect to your authority to enter into Contract Agreement and the enforceability of the provision thereof, within 10 (Ten) days of issue of this LOA. 3. Further, as per RFP documents, the Contractor for due and faithful performance of its obligations during the Construction Period as well as Defects Liability Period required to furnish a Performance Security by way of an irrevocable and unconditional Bank Guarantee of Rs. 26,66,83,350/- (Rupees Twenty Six Crore Sixty Six Lakhs Eighty Three Thousand Three Hundred and Fifty Only) within 10 days from the date of signing of the Contract Agreement. The Performance Security shall be valid until 60 (sixty) days after the Defects Liability Period. (refer Clauses of Article-7 of EPC Agreement). 4. You are requested to Comply with the above and all the terms and conditions set forth in the RFP documents. In case of any default on your part, you shall be liable for action as stated in the RFP Document. We appreciate your cooperation in this regard. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
BG's for Performance Security and Additional Performance Security | Contractor's Obligations | 1. We had submitted the Performance Security and Additional Performance Security in the form of Bank Guarantees (PBG and APBG) vide our letters dated 28.09.2021 and 02.11.2021. 2. Contractor have discharged its prime obligation i.e. submission of Performance Security and Additional Performance Security, well within time limit. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-1/8. Request to grant an Extension of Time under Clause 10.5 of the Contract Agreement..pdf | Request to grant an Extension of Time under Clause 10.5 of the Contract Agreement | 1. This is with reference to our various representations/submissions regarding various events on delay which has adversely affected the construction activities of Project and are still persisting at site resulting delay in completion of construction works as per scope envisaged under Contract Agreement. 2. We take this opportunity to summarize the facts chronologically as below giving rise to the claim for an Extension of Time (“EOT”) in accordance with the provisions of this Agreement on account of various delay events. Contract Particulars: Development Corporation Limited Authority Engineer Accepted Contract Price Construction Period Appointed Date 26.11.2021 Stipulated Completion Date ¦ 19.05.2023 Request for EOT by this 135 days Cl 01.10.2023 Revised Completion Date Background Facts: 3. The National Highway & Infrastructure Development Corporation Limited (“Authority”) had issued the LOA dated 02.09.2021 (Ref#01) in favor of B.R Goyal Infrastructure Limited (“Contractor"). The formal Contract Agreement was signed on 08.10.2021. In pursuant to the conditions of LOA, we had submitted the Performance Security and Additional Performance Security in the form of Bank Guarantees (PBG and APBG) vide our letters dated 28.09.2021 and 02.11.2021 (Ref #2 & 4 above). It is in place to mention that the Contractor have discharged its prime obligation i.e. submission of Performance Security and Additional Performance Security, well within time limit. To ensure the start of construction activities immediate after declaration of Appointed Date, Contractor has mobilized the adequate manpower & machinery resources at site after receiving of LOA. In pursuant to the provisions of the Contract Agreement, Authority’s primary obligation is to provide the 90% length of ROW within 30 days from the date of Agreement. However, after signing of CA, both the parties visited the site and it | FALSE | real_data
BG's for Performance Security and Additional Performance Security | Contractor's Obligations | performance of its obligations during the Construction Period as well as Defects Liability Period required to furnish a Performance Security by way of an irrevocable and unconditional Bank Guarantee of Rs. 26,66,83,350/- (Rupees Twenty Six Crore Sixty Six Lakhs Eighty Three Thousand Three Hundred and Fifty Only) within 10 days from the date of signing of the Contract Agreement. The Performance Security shall be valid until 60 (sixty) days after the Defects Liability Period. (refer Clauses of Article-7 of EPC Agreement | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km. 71+015 to Km 107+091 on EPC Mode in the state of Tamil Nadu under NHDP Phase-V- Letter of Award-Reg. | This is to notify that your bid submitted for the project of “Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km. 71+015 to Km 107+091 on EPC Mode in the state of Tamil Nadu”, is hereby accepted by NHAI for the contract price of Rs. 533,36,67,000/- (Rupees Five Hundred Thirty Three Crore Thirty Six Lakh and Sixty Seven Thousand Only) and declaring you a “Selected Bidder”. 2. In accordance with the Clause 3.3.4 of the RFP document (Volume-l), you are requested to sign the duplicate copy of the LOA and return the same as your acknowledgement within 7 (Seven) days of the receipt of LOA. It is requested to deliver a legal opinion from your legal counsel with respect to your authority to enter into Contract Agreement and the enforceability of the provision thereof, within 10 (Ten) days of issue of this LOA. 3. Further, as per RFP documents, the Contractor for due and faithful performance of its obligations during the Construction Period as well as Defects Liability Period required to furnish a Performance Security by way of an irrevocable and unconditional Bank Guarantee of Rs. 26,66,83,350/- (Rupees Twenty Six Crore Sixty Six Lakhs Eighty Three Thousand Three Hundred and Fifty Only) within 10 days from the date of signing of the Contract Agreement. The Performance Security shall be valid until 60 (sixty) days after the Defects Liability Period. (refer Clauses of Article-7 of EPC Agreement). 4. You are requested to Comply with the above and all the terms and conditions set forth in the RFP documents. In case of any default on your part, you shall be liable for action as stated in the RFP Document. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
BG's for Performance Security and Additional Performance Security | Contractor's Obligations | performance of its obligations during the Construction Period as well as Defects Liability Period required to furnish a Performance Security by way of an irrevocable and unconditional Bank Guarantee of Rs. 26,66,83,350/- (Rupees Twenty Six Crore Sixty Six Lakhs Eighty Three Thousand Three Hundred and Fifty Only) within 10 days from the date of signing of the Contract Agreement. The Performance Security shall be valid until 60 (sixty) days after the Defects Liability Period. (refer Clauses of Article-7 of EPC Agreement | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km. 71+015 to Km 107+091 on EPC Mode in the state of Tamil Nadu under NHDP Phase-V- Letter of Award-Reg. | This is to notify that your bid submitted for the project of “Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km. 71+015 to Km 107+091 on EPC Mode in the state of Tamil Nadu”, is hereby accepted by NHAI for the contract price of Rs. 533,36,67,000/- (Rupees Five Hundred Thirty Three Crore Thirty Six Lakh and Sixty Seven Thousand Only) and declaring you a “Selected Bidder”. 2. In accordance with the Clause 3.3.4 of the RFP document (Volume-l), you are requested to sign the duplicate copy of the LOA and return the same as your acknowledgement within 7 (Seven) days of the receipt of LOA. It is requested to deliver a legal opinion from your legal counsel with respect to your authority to enter into Contract Agreement and the enforceability of the provision thereof, within 10 (Ten) days of issue of this LOA. 3. Further, as per RFP documents, the Contractor for due and faithful performance of its obligations during the Construction Period as well as Defects Liability Period required to furnish a Performance Security by way of an irrevocable and unconditional Bank Guarantee of Rs. 26,66,83,350/- (Rupees Twenty Six Crore Sixty Six Lakhs Eighty Three Thousand Three Hundred and Fifty Only) within 10 days from the date of signing of the Contract Agreement. The Performance Security shall be valid until 60 (sixty) days after the Defects Liability Period. (refer Clauses of Article-7 of EPC Agreement). 4. You are requested to Comply with the above and all the terms and conditions set forth in the RFP documents. In case of any default on your part, you shall be liable for action as stated in the RFP Document. We await your further instructions. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
BG's for Performance Security and Additional Performance Security | Contractor's Obligations | 1. We had submitted the Performance Security and Additional Performance Security in the form of Bank Guarantees (PBG and APBG) vide our letters dated 28.09.2021 and 02.11.2021. 2. Contractor have discharged its prime obligation i.e. submission of Performance Security and Additional Performance Security, well within time limit. | synthetic_template_20250913 | Request to grant an Extension of Time under Clause 10.5 of the Contract Agreement | 1. This is with reference to our various representations/submissions regarding various events on delay which has adversely affected the construction activities of Project and are still persisting at site resulting delay in completion of construction works as per scope envisaged under Contract Agreement. 2. We take this opportunity to summarize the facts chronologically as below giving rise to the claim for an Extension of Time (“EOT”) in accordance with the provisions of this Agreement on account of various delay events. Contract Particulars: Development Corporation Limited Authority Engineer Accepted Contract Price Construction Period Appointed Date 26.11.2021 Stipulated Completion Date ¦ 19.05.2023 Request for EOT by this 135 days Cl 01.10.2023 Revised Completion Date Background Facts: 3. The National Highway & Infrastructure Development Corporation Limited (“Authority”) had issued the LOA dated 02.09.2021 (Ref#01) in favor of B.R Goyal Infrastructure Limited (“Contractor"). The formal Contract Agreement was signed on 08.10.2021. In pursuant to the conditions of LOA, we had submitted the Performance Security and Additional Performance Security in the form of Bank Guarantees (PBG and APBG) vide our letters dated 28.09.2021 and 02.11.2021 (Ref #2 & 4 above). It is in place to mention that the Contractor have discharged its prime obligation i.e. submission of Performance Security and Additional Performance Security, well within time limit. To ensure the start of construction activities immediate after declaration of Appointed Date, Contractor has mobilized the adequate manpower & machinery resources at site after receiving of LOA. In pursuant to the provisions of the Contract Agreement, Authority’s primary obligation is to provide the 90% length of ROW within 30 days from the date of Agreement. However, after signing of CA, both the parties visited the site and it Please confirm receipt of this correspondence. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
BG's for Performance Security and Additional Performance Security | Contractor's Obligations | performance of its obligations during the Construction Period as well as Defects Liability Period required to furnish a Performance Security by way of an irrevocable and unconditional Bank Guarantee of Rs. 26,66,83,350/- (Rupees Twenty Six Crore Sixty Six Lakhs Eighty Three Thousand Three Hundred and Fifty Only) within 10 days from the date of signing of the Contract Agreement. The Performance Security shall be valid until 60 (sixty) days after the Defects Liability Period. (refer Clauses of Article-7 of EPC Agreement | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km. 71+015 to Km 107+091 on EPC Mode in the state of Tamil Nadu under NHDP Phase-V- Letter of Award-Reg. | This is to notify that your bid submitted for the project of “Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km. 71+015 to Km 107+091 on EPC Mode in the state of Tamil Nadu”, is hereby accepted by NHAI for the contract price of Rs. 533,36,67,000/- (Rupees Five Hundred Thirty Three Crore Thirty Six Lakh and Sixty Seven Thousand Only) and declaring you a “Selected Bidder”. 2. In accordance with the Clause 3.3.4 of the RFP document (Volume-l), you are requested to sign the duplicate copy of the LOA and return the same as your acknowledgement within 7 (Seven) days of the receipt of LOA. It is requested to deliver a legal opinion from your legal counsel with respect to your authority to enter into Contract Agreement and the enforceability of the provision thereof, within 10 (Ten) days of issue of this LOA. 3. Further, as per RFP documents, the Contractor for due and faithful performance of its obligations during the Construction Period as well as Defects Liability Period required to furnish a Performance Security by way of an irrevocable and unconditional Bank Guarantee of Rs. 26,66,83,350/- (Rupees Twenty Six Crore Sixty Six Lakhs Eighty Three Thousand Three Hundred and Fifty Only) within 10 days from the date of signing of the Contract Agreement. The Performance Security shall be valid until 60 (sixty) days after the Defects Liability Period. (refer Clauses of Article-7 of EPC Agreement). 4. You are requested to Comply with the above and all the terms and conditions set forth in the RFP documents. In case of any default on your part, you shall be liable for action as stated in the RFP Document. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
BG's for Performance Security and Additional Performance Security | Contractor's Obligations | 1. We had submitted the Performance Security and Additional Performance Security in the form of Bank Guarantees (PBG and APBG) vide our letters dated 28.09.2021 and 02.11.2021. 2. Contractor have discharged its prime obligation i.e. submission of Performance Security and Additional Performance Security, well within time limit. | synthetic_template_20250913 | Request to grant an Extension of Time under Clause 10.5 of the Contract Agreement | 1. This is with reference to our various representations/submissions regarding various events on delay which has adversely affected the construction activities of Project and are still persisting at site resulting delay in completion of construction works as per scope envisaged under Contract Agreement. 2. We take this opportunity to summarize the facts chronologically as below giving rise to the claim for an Extension of Time (“EOT”) in accordance with the provisions of this Agreement on account of various delay events. Contract Particulars: Development Corporation Limited Authority Engineer Accepted Contract Price Construction Period Appointed Date 26.11.2021 Stipulated Completion Date ¦ 19.05.2023 Request for EOT by this 135 days Cl 01.10.2023 Revised Completion Date Background Facts: 3. The National Highway & Infrastructure Development Corporation Limited (“Authority”) had issued the LOA dated 02.09.2021 (Ref#01) in favor of B.R Goyal Infrastructure Limited (“Contractor"). The formal Contract Agreement was signed on 08.10.2021. In pursuant to the conditions of LOA, we had submitted the Performance Security and Additional Performance Security in the form of Bank Guarantees (PBG and APBG) vide our letters dated 28.09.2021 and 02.11.2021 (Ref #2 & 4 above). It is in place to mention that the Contractor have discharged its prime obligation i.e. submission of Performance Security and Additional Performance Security, well within time limit. To ensure the start of construction activities immediate after declaration of Appointed Date, Contractor has mobilized the adequate manpower & machinery resources at site after receiving of LOA. In pursuant to the provisions of the Contract Agreement, Authority’s primary obligation is to provide the 90% length of ROW within 30 days from the date of Agreement. However, after signing of CA, both the parties visited the site and it Thank you for your attention to this matter. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Fly ash supply | Others; EoT; Payments; Contractor's Obligations | In this regard your attention is invited to the MoEF notification S.O. 254(E) dated 25th January 2016 wherein it was directed to use fly ash in construction of road or flyover embankments within a radius of 300 Km of a thermal power plant and the relevant paragraph are as follows: | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/20201215_PD_NTCEL_ 4053_Supply of pond ash.pdf | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet Section of NH - 4 (New NH-48) from Km. 71+015 to km. 107+091 in the State of Tamil Nadu under NHDP (Phase V) under Bharatmala Pariyojana on EPC Mode - Supply of Fly Ash by NTECL - Reg. | This is with reference to the meeting held with the undersigned by AGM, NTECL on 07.01.2020 at NHAI Office at Tambaram, it is informed that the contractor vide letter 1 cited above, requested this office to request NTECL to supply fly ash (approx. 13 lakh MT) for the said project. In this regard your attention is invited to the MoEF notification S.0. 254(E) dated 25th January 2016 wherein it was directed to use fly ash in construction of road or flyover embankments within a radius of 300 Km of a thermal power plant and the relevant paragraph are as follows: “10. The cost of transportation of ash for road construction projects or for manufacturing of ash based products or use as soil conditioner in agriculture activity within a radius of hundred kilometers from a coal or lignite based thermal power plant shall be borne by such coal or lignite based thermal power plant and the cost of transportation beyond the radius of hundred kilometers and up to three hundred kilometers shall be shared equally between the user and the coal or lignite based thermal power plant. The present road stretch mentioned in the subject is within 300 Km from the power plant. In view of the above, it is requested to take necessary action to supply fly ash to the site as requested by the contractor at the earliest after following procedure in vogue. | FALSE | real_data
Fly ash supply | Others; EoT; Payments; Contractor's Obligations | In view of the above and considering the necessity to complete the project within the prescribed period, it is requested to take necessary action to supply fly ash to the site as requested by the contractor (approx. 14 Lakh MT) at the earliest after following procedure in vogue. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/20210211_PD_NTEC_501 - Supply of Fly ash.pdf | NHAI, PIU, Kancheepuram — Six Laning of Karaipettai to Walajahpet Section of NH - 4 (New NH-48) from Km. 71+015 to km. 107+091 in the State of Tamil Nadu under NHDP (Phase V) under Bharatmala Pariyojana on EPC Mode - Supply of Fly Ash by NTECL - Reg. | This has reference to this office letter cited in reference (1), wherein it was requested to take necessary action to supply fly ash to the project site as requested by the EPC Contractor for the above subject Six Laning Project at the earliest after following procedure in Vogue. Further, your attention is invited to the MoEF notification S.O. 254(E) dated 25th January 2016 wherein it was directed to use fly ash in construction of road or flyover embankments within a radius of 300 Km of a thermal power plant and it was submitted that the present road stretch mentioned in the subject is within 300 Km from the Power Plant. In this context, your attention is invited to Order of Hon’ble High Court of Madras W.P.No.33323 of 2019 (Suo Motu PIL) dated 22.01.2021, wherein the progress of works between Maduravoyal to Walajahpet is being discussed, and it has been pointed out that the delay has been caused on account of the involvement of various Stakeholders and in the light of the difficulties faced by NHAI, there is a delay in completion of the six-laning project and hence, the Court may pass appropriate orders, which may expedite the six-laning of the road. The relevant paragraph are as follows: “The learned Assistant Solicitor General of India, appearing for NHAI, has drawn the attention of this Court to the order dated 21.02.2020, especially to Para No.4 of the said order, wherein, it has been pointed out that the delay has been caused on account of the involvement of various Stakeholders and request has been made to the State Government to put in place a Single Window Agency comprising of various Stakeholders, so that all necessary clearances can be obtained without any loss of time, so as to enable the NHAI to complete the project on time, and would submit that, in the light of the difficulties faced by NHAI, there is a delay in completion of the six-laning project. Mr.R.Viiayakumar, learned Additional Government Pleader, representing the officials of the State Government would submit that, if the concerned officials of NHAI approach them, the needful would be done. In response to the said submission, the learned Assistant Solicitor General of India, appearing for NHAI, would submit that the presence of the following officials/ entities is necessary, and prays for leave to file a petition for impleadment for impleading them as parties. For Karaipettai to Walajahpet Section of NH-4: 1. The District Collector, Ranipet District, Ranipet 2. The Special District Revenue Officer, LA-NH, Kancheepuram and Vellore 3. Tamil Nadu Generation & Distribution Corporation Limited [TANGEDCO], Kancheepuram South, Sholingar and Walajahpet Divisions. 4. Tamil Nadu Transmission Corporation Limited (TANTRANSCO), Thiruvalam 5. Tamil Nadu Water Supply and Drainage Board (TWAD), Ranipet Division 6. The Commissioner, Kancheepuram Municipality, Kancheepuram. 7. The Assistant Director of Town Panchayats, Ranipet 8. The Chief Executive Officer, M/s.NTEC, Vallur Thermal Power Projects,Vellivoyal Chavadi, Ponneri Taluk, Thiruvallur District-600 103. 9. The Superintendent of Police, Ranipet District, Ranipet 10. M/s SPK & Co, 63/7, SPK Complex, Ananthapuri Nagar, 2nd Street, Madurai Road, Aruppukkottai-626 101. 11. The Commissioner of Geology & Mining, Guindy, Chennat” Since this Court has taken this matter purely in public interest, the difficulties faced by NHAI in coordinating with the various Stakeholders can be taken note of and may pass appropriate orders, which may expedite the six-laning of the road.” | FALSE | real_data
Fly ash supply | Others; EoT; Payments; Contractor's Obligations | Supply of Fly Ash | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/20210628_PD_AE_1753_Utilisation of Fly ash_Counter Affidavit by NTPC,Vallur.pdf | NHAI, PIU, Kancheepuram —- Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from km. 71/015 to km 107/091 in the State of Tamil Nadu — Supply of Flyash - Reg. | This has reference to the DGM (EMG), NTECL letter cited above, wherein the counter affidavit filed on behalf of NTECL in Hon’ble High Court of Madras vide W.P No. 33323 of 2019 has been communicated. In this regard, it is to inform that since the contractor - M/s. S.P.K & Co is also impleaded in W.P No. 33323 of 2019; the same affidavit would have already been communicated by their Advocate / Legal Counsel. However, the copy of the same has been enclosed herewith for your information and further necessary action. | FALSE | real_data
Fly ash supply | Others; EoT; Payments; Contractor's Obligations | this office vide letters dated 15.12.2020 and 11.02.2021 requested the nearby Thermal plant M/s NTECL (NTPC Tamilnadu Energy Company Limited) to supply Fly ash to the site | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/20210904_PD_SPK_2597_Coordination with NTPC for flyash procurement.pdf | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet section of NH-4 from Km 71/015 to Km 107/091 in the State of Tamilnadu under residual NHDP (Phase — V) under Bharathmala Pariyojana on EPC Mode - Proposal for Utilization of Fly Ash from M/s. NTECL Vallur Thermal Power Projects - Reg. | This has reference to the letter cited 01st above, where in the Contractor has requested this office to obtain in principle approval from the nearby Thermal Power Plant M/s. NTECL Vallur Thermal Power Project for utilization of Pond ash for Construction of Road embankments. In this regard, as per Article 3.1.7 (Obligations of the Contractor) of the EPC Contract agreement, “The Contactor shall, at its own cost and expense, in addition to and not in derogation of its obligations elsewhere set out in this Agreement: (b) procure, as required, the appropriate proprietary rights, licenses, agreements and permissions for Materials, methods, processes and systems used or incorporated into the Project Highway”. From the above clause, it is clear that it is the responsibility of the contractor for the procurement of the materials, obtaining necessary permissions for materials etc. However, based on the request of the EPC Contractor - M/s. S.P.K & Co vide letter dated 07.12.2020, this office vide letters dated 15.12.2020 and 11.02.2021 requested the nearby Thermal Plant M/s. NTECL (NTPC Tamilnadu Energy Company Limited) to supply Fly ash to the site as per the MoEF notification S.O. 254 (E) dated 25th January 2016. Further, this office vide letter dated 28.06.2021, communicated the counter affidavit filed on behalf of M/s. NTECL in Hon’ble High Court of Madras in W.P No.33323 of 2019, wherein the current status and the availability of Fly ash has been submitted by M/s. NTECL. In view of the above, it is requested to coordinate with the Fly ash supplying agency M/s. NTECL and to facilitate the supply of Fly ash to the Project site. | FALSE | real_data
Fly ash supply | Others; EoT; Payments; Contractor's Obligations | In view of the above, it is requested to coordinate with the Fly ash supplying agency M/S. NTECL and to facilitate the supply of Fly ash to the Project site. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/20210904_PD_SPK_2597_Coordination with NTPC for flyash procurement.pdf | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet section of NH-4 from Km 71/015 to Km 107/091 in the State of Tamilnadu under residual NHDP (Phase — V) under Bharathmala Pariyojana on EPC Mode - Proposal for Utilization of Fly Ash from M/s. NTECL Vallur Thermal Power Projects - Reg. | This has reference to the letter cited 01st above, where in the Contractor has requested this office to obtain in principle approval from the nearby Thermal Power Plant M/s. NTECL Vallur Thermal Power Project for utilization of Pond ash for Construction of Road embankments. In this regard, as per Article 3.1.7 (Obligations of the Contractor) of the EPC Contract agreement, “The Contactor shall, at its own cost and expense, in addition to and not in derogation of its obligations elsewhere set out in this Agreement: (b) procure, as required, the appropriate proprietary rights, licenses, agreements and permissions for Materials, methods, processes and systems used or incorporated into the Project Highway”. From the above clause, it is clear that it is the responsibility of the contractor for the procurement of the materials, obtaining necessary permissions for materials etc. However, based on the request of the EPC Contractor - M/s. S.P.K & Co vide letter dated 07.12.2020, this office vide letters dated 15.12.2020 and 11.02.2021 requested the nearby Thermal Plant M/s. NTECL (NTPC Tamilnadu Energy Company Limited) to supply Fly ash to the site as per the MoEF notification S.O. 254 (E) dated 25th January 2016. Further, this office vide letter dated 28.06.2021, communicated the counter affidavit filed on behalf of M/s. NTECL in Hon’ble High Court of Madras in W.P No.33323 of 2019, wherein the current status and the availability of Fly ash has been submitted by M/s. NTECL. In view of the above, it is requested to coordinate with the Fly ash supplying agency M/s. NTECL and to facilitate the supply of Fly ash to the Project site. | FALSE | real_data
Fly ash supply | Others; EoT; Payments; Contractor's Obligations | In this regard, as per Article 3.1.7 (Obligations of the Contractor) of the EPC Contract agreement, "The Contactor shall, at its own cost and expense, in addition to and not in derogation of its obligations elsewhere set out in this Agreement: | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/20210904_PD_SPK_2597_Coordination with NTPC for flyash procurement.pdf | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet section of NH-4 from Km 71/015 to Km 107/091 in the State of Tamilnadu under residual NHDP (Phase — V) under Bharathmala Pariyojana on EPC Mode - Proposal for Utilization of Fly Ash from M/s. NTECL Vallur Thermal Power Projects - Reg. | This has reference to the letter cited 01st above, where in the Contractor has requested this office to obtain in principle approval from the nearby Thermal Power Plant M/s. NTECL Vallur Thermal Power Project for utilization of Pond ash for Construction of Road embankments. In this regard, as per Article 3.1.7 (Obligations of the Contractor) of the EPC Contract agreement, “The Contactor shall, at its own cost and expense, in addition to and not in derogation of its obligations elsewhere set out in this Agreement: (b) procure, as required, the appropriate proprietary rights, licenses, agreements and permissions for Materials, methods, processes and systems used or incorporated into the Project Highway”. From the above clause, it is clear that it is the responsibility of the contractor for the procurement of the materials, obtaining necessary permissions for materials etc. However, based on the request of the EPC Contractor - M/s. S.P.K & Co vide letter dated 07.12.2020, this office vide letters dated 15.12.2020 and 11.02.2021 requested the nearby Thermal Plant M/s. NTECL (NTPC Tamilnadu Energy Company Limited) to supply Fly ash to the site as per the MoEF notification S.O. 254 (E) dated 25th January 2016. Further, this office vide letter dated 28.06.2021, communicated the counter affidavit filed on behalf of M/s. NTECL in Hon’ble High Court of Madras in W.P No.33323 of 2019, wherein the current status and the availability of Fly ash has been submitted by M/s. NTECL. In view of the above, it is requested to coordinate with the Fly ash supplying agency M/s. NTECL and to facilitate the supply of Fly ash to the Project site. | FALSE | real_data
Fly ash supply | Others; EoT; Payments; Contractor's Obligations | In this regard, as per Article 3.1.7 (Obligations of the Contractor) of the EPC Contract agreement, "The Contactor shall, at its own cost and expense, in addition to and not in derogation of its obligations elsewhere set out in this Agreement: | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/20210904_PD_SPK_2597_Coordination with NTPC for flyash procurement.pdf | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet section of NH-4 from Km 71/015 to Km 107/091 in the State of Tamilnadu under residual NHDP (Phase — V) under Bharathmala Pariyojana on EPC Mode - Proposal for Utilization of Fly Ash from M/s. NTECL Vallur Thermal Power Projects - Reg. | This has reference to the letter cited 01st above, where in the Contractor has requested this office to obtain in principle approval from the nearby Thermal Power Plant M/s. NTECL Vallur Thermal Power Project for utilization of Pond ash for Construction of Road embankments. In this regard, as per Article 3.1.7 (Obligations of the Contractor) of the EPC Contract agreement, “The Contactor shall, at its own cost and expense, in addition to and not in derogation of its obligations elsewhere set out in this Agreement: (b) procure, as required, the appropriate proprietary rights, licenses, agreements and permissions for Materials, methods, processes and systems used or incorporated into the Project Highway”. From the above clause, it is clear that it is the responsibility of the contractor for the procurement of the materials, obtaining necessary permissions for materials etc. However, based on the request of the EPC Contractor - M/s. S.P.K & Co vide letter dated 07.12.2020, this office vide letters dated 15.12.2020 and 11.02.2021 requested the nearby Thermal Plant M/s. NTECL (NTPC Tamilnadu Energy Company Limited) to supply Fly ash to the site as per the MoEF notification S.O. 254 (E) dated 25th January 2016. Further, this office vide letter dated 28.06.2021, communicated the counter affidavit filed on behalf of M/s. NTECL in Hon’ble High Court of Madras in W.P No.33323 of 2019, wherein the current status and the availability of Fly ash has been submitted by M/s. NTECL. In view of the above, it is requested to coordinate with the Fly ash supplying agency M/s. NTECL and to facilitate the supply of Fly ash to the Project site. | FALSE | real_data
Fly ash supply | Others; EoT; Payments; Contractor's Obligations | However, the Contractor never made any direct correspondence with the agencies till date and not at all participated in the bidding/ auction towards procurement of fly ash. As such it is clearly evident that not even minimum efforts have been made by the Contractor till date regarding procurement of fly ash. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/20221108_PD_SPK_3511_Procurement of Ash from Thermal Power plant.pdf | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet section of NH-4 from Km 71/015 to Km 107/091 in the State of Tamilnadu — Procurement of Fly ash from Thermal Power Plant - Reg. | This has reference to the letter cited above, wherein the EPC Contractor requesting for the Authority support towards procurement of fly ash from the ash supplying agencies. In this regard, as per Article 3 (Obligations of the Contractor) of the Contract agreement, it is the responsibility of the contractor for the procurement of the materials, obtaining necessary permissions for materials etc. Further as per Article 6.1.1 of CA, the Contractor has to visit the site and made independent evaluation of RFP and scope of the project before submission of bid. As such procurement of materials involved in this regard is solely the contractor’s responsibility only. In this regard, the Plan & Profile / GAD has approved during July 2019 & March 2020 itself for structures i.e.,VUP/SVUP/flyover with filling materials for approaches as Soil only. As per the statement furnished by the Authority Engineer as on 10.10.2022, the total borrow earth quantity required is 20 Lakh Cum. However, the contractor has applied borrow earth permission for about 4.7 lakhs Cum and obtained permission for 3.41 lakh Cum which are now filled with water ie., lake area. Further, from the records available at PIU office, it is observed that the contractor M/s.SPK & Co, requesting only NHAI to obtain approval & support for supply of fly ash from the ash supplying agencies and the contractor never made any direct correspondence with the agencies till date regarding supply of fly ash, even though procurement of material is contractor obligation as per CA. As such the Contractor has made correspondence to NHAI only on 25.11.2019, 05.12.2020, 07.12.2020 & 20.08.2021 and after August 2021, no request has been received from the Concessionaire regarding Fly Ash. The Deputy Secretary to Govt. of India, Ministry of Power vide circular no. 9/7/2011-S.Th (Vol.IV) dated 22.09.2021, informed the following: The power plants shall provide the Fly Ash to end users through a transparent bidding process only. If after bidding/ auction some quantity of Fly Ash still remains un-utilized, then only, as one of the options, it could be considered to be given free of cost on first come first served basis if the user agency is willing to bear transportation cost. If ash remains unutilized even after the steps taken in Paras 2.1 and 2.2 above. TPP shall bear the transportation of fly ash to be provided free to eligible projects. The end users shall be obligated to source the fly ash from the nearest TPPs to reduce the cost of fly ash transportation. If the nearest TPP refuses to do so, the end user project shall approach Ministry of Power for appropriate directions. The fly ash will be offered to the end users on the competing demand basis, i.e the end users who offer the highest price for fly ash and seek minimum support for transportation cost will be offered the same fly ash on priority. This will reduce the tariff of electricity and burden on the consumers. However, the Contractor never made any direct correspondence with the agencies till date and not at all participated in the bidding/auction towards procurement of fly ash. As such it is clearly evident that not even minimum efforts have been made by the Contractor till date regarding procurement of fly ash. In this context, this office letter no.2597 dated 04.09.2021 also, it was already requested to coordinate with the Fly ash supplying agency to facilitate the supply of fly ash to the project site. Subsequently, based on the Review Meeting conducted by Chairperson, NHAI on 18.08.2022, it was instructed that “the contractor to apply for entire quantity of borrow earth permission immediately”. However, after Chairperson NHAI meeting held in Chennai on 18.08.2022. | FALSE | real_data
Fly ash supply | Others; EoT; Payments; Contractor's Obligations | In this regard, it is evident that instead of applying borrow earth for entire quantity, the contractor suddenly requested for fly ash which concludes that the contractor taking evasive measures to delay the project. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/20221108_PD_SPK_3511_Procurement of Ash from Thermal Power plant.pdf | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet section of NH-4 from Km 71/015 to Km 107/091 in the State of Tamilnadu — Procurement of Fly ash from Thermal Power Plant - Reg. | This has reference to the letter cited above, wherein the EPC Contractor requesting for the Authority support towards procurement of fly ash from the ash supplying agencies. In this regard, as per Article 3 (Obligations of the Contractor) of the Contract agreement, it is the responsibility of the contractor for the procurement of the materials, obtaining necessary permissions for materials etc. Further as per Article 6.1.1 of CA, the Contractor has to visit the site and made independent evaluation of RFP and scope of the project before submission of bid. As such procurement of materials involved in this regard is solely the contractor’s responsibility only. In this regard, the Plan & Profile / GAD has approved during July 2019 & March 2020 itself for structures i.e.,VUP/SVUP/flyover with filling materials for approaches as Soil only. As per the statement furnished by the Authority Engineer as on 10.10.2022, the total borrow earth quantity required is 20 Lakh Cum. However, the contractor has applied borrow earth permission for about 4.7 lakhs Cum and obtained permission for 3.41 lakh Cum which are now filled with water ie., lake area. Further, from the records available at PIU office, it is observed that the contractor M/s.SPK & Co, requesting only NHAI to obtain approval & support for supply of fly ash from the ash supplying agencies and the contractor never made any direct correspondence with the agencies till date regarding supply of fly ash, even though procurement of material is contractor obligation as per CA. As such the Contractor has made correspondence to NHAI only on 25.11.2019, 05.12.2020, 07.12.2020 & 20.08.2021 and after August 2021, no request has been received from the Concessionaire regarding Fly Ash. The Deputy Secretary to Govt. of India, Ministry of Power vide circular no. 9/7/2011-S.Th (Vol.IV) dated 22.09.2021, informed the following: The power plants shall provide the Fly Ash to end users through a transparent bidding process only. If after bidding/ auction some quantity of Fly Ash still remains un-utilized, then only, as one of the options, it could be considered to be given free of cost on first come first served basis if the user agency is willing to bear transportation cost. If ash remains unutilized even after the steps taken in Paras 2.1 and 2.2 above. TPP shall bear the transportation of fly ash to be provided free to eligible projects. The end users shall be obligated to source the fly ash from the nearest TPPs to reduce the cost of fly ash transportation. If the nearest TPP refuses to do so, the end user project shall approach Ministry of Power for appropriate directions. The fly ash will be offered to the end users on the competing demand basis, i.e the end users who offer the highest price for fly ash and seek minimum support for transportation cost will be offered the same fly ash on priority. This will reduce the tariff of electricity and burden on the consumers. However, the Contractor never made any direct correspondence with the agencies till date and not at all participated in the bidding/auction towards procurement of fly ash. As such it is clearly evident that not even minimum efforts have been made by the Contractor till date regarding procurement of fly ash. In this context, this office letter no.2597 dated 04.09.2021 also, it was already requested to coordinate with the Fly ash supplying agency to facilitate the supply of fly ash to the project site. Subsequently, based on the Review Meeting conducted by Chairperson, NHAI on 18.08.2022, it was instructed that “the contractor to apply for entire quantity of borrow earth permission immediately”. However, after Chairperson NHAI meeting held in Chennai on 18.08.2022. | FALSE | real_data
Fly ash supply | Others; EoT; Payments; Contractor's Obligations | We hereby request your good self to obtain in principle approval from the nearby Thermal power Station at Ennore for utilizing the available unutilized Pond ash to enable us to use the same for construction of road embankments. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/20191125_SPK_PD_.66 Request for Extraction of Fly Ash.pdf | Request for approval of extraction of Fly Ash | We, M/s. SPK and Co had bagged the above mentioned project work through competitive bidding to be executed on EPC (Engineering Procurement Contract) mode and accordingly contract agreement executed with the employer M/s. National Highways Authority of India on 15.10.2018. The project has a requirement of approximately 12, 20,000 cum of embankment and subgrade filling. In order to complete the project on time bound manner, we require enormous quantities of filling material and due to paucity of natural soil, we would like to utilize Fly ash as alternate medium which is recommended by MoRTH and MoEF &CC of Govt. of India for construction of road embankments. In this regard, vide reference (2) cited, the Director General (Road Development) & SS, MoRTH Govt. of India has stressed for bulk utilization of the Pond ash as far as possible in the field of civil engineering applivalion, especially construction of road embankments. Further, Ministry of Environment Forests and Climate Change (MoEF & CC) has issued various notifications for Pond ash utilization. The principal notification was issued on 14.09.1999, which was subsequently amended vide notifications dated 27.08.2003, 03.11.2009 and 25.01.2016. As per the notification of MoEF & CC, it is mandatory to use Fly-ash in the construction of road or flyover embankments within a radius of 300 km of a thermal power plant. Further, the relevant content of the notification dated 25.01.2016 of MoEF & CC regarding road/ flyover embankment construc rien s under; Para 10: The cost of transportation of ash for road construction projects or for manufacturing of ash based products or use as soil conditioner in agriculture activity within a radius of hundred kilometres from a coal or lignite based thermal power plant shall be borne by such coal or lignite based thermal power plant and the cost of transportation beyond the radius of hundred kilometres and up to three hundred kilometres shall be shared equally between the user and the coal or lignite based thermal power plant. We hereby request your goodself to obtain in principle approval from the nearby Thermal power Station at Ennore for utilizing the available unutilized Pond ash to enable us to use the same for construction of road embankments: | FALSE | real_data
Fly ash supply | Others; EoT; Payments; Contractor's Obligations | We hereby request your good self to obtain in principle approval from the nearby Thermal power Station M/S. NTCEL Vallur Power Projects - Thiruvallur for utilizing the available unutilized Pond ash to enable us to use the same for construction of road embankments. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/20201207_SPK_NHAI_075_Request for approval of extraction of Fly ash (1).pdf | Request for approval of extraction of Fly Ash -Reg. | Dear Sir, In continuation to our letter (3) cited above under subject matter and as mentioned vide our letter (4); due to paucity of natural soil we proposed to utilize Pondash in the approaches of VUP/LVUP/Flyover as a filling material and which is recommended by MoRTH and MoEF &CC of Govt. of India for construction of road embankments. In this regard, vide reference (2) cited, the Director General (Road Development) & SS, MoRTH Govt. of India has stressed for bulk utilization of the Fly ash as far as possible in the field of civil engineering application, especially construction of road embankments. We once again reiterate that, Ministry of Environment Forests and Climate Change (MoEF & CC) has issued various notifications for Pond ash utilization. The principal notification was issued on 14.09.1999, which was subsequently amended vide notifications dated 27.08.2003, 03.11.2009 and 25.01.2016. As per the notification of MoEF & CC, it is mandatory to use Fly-ash in the construction of road embankments within a radius of 300 km of a thermal power plant. Further, the relevant content of the notification dated 25.01.2016 of MoEF & CC regarding road/flyover embankment construction are as under: Para 10: The cost of transportation of ash for road construction projects or for manufacturing of ash based products or use as soil conditioner in agriculture activity within a radius of hundred kilometres from a coal or lignite based thermal power plant shall be borne by such coal or lignite based thermal power plant and the cost of transportation beyond the radius of hundred kilometres and up to three hundred kilometres shall be shared equally between the user and the coal or lignite based thermal power plant. In this connection, we wish to mention that the approximate requirement of pond ash was 14 lakh MT for our project. Also, monthwise requirement of Pondash is enclosed as Annexure - I. We hereby request your goodself to obtain in principle approval from the nearby Thermal power Station M/s. NTCEL Vallur Power Projects - Thiruvallur for utilizing the available unutilized Pond ash to enable us to use the same for construction of road embankments. | FALSE | real_data
Fly ash supply | Others; EoT; Payments; Contractor's Obligations | We hereby request your good office to obtain in principle approval from the nearby Thermal power Station M/S. NTCEL Vallur Power Projects Thiruvallur for utilizing the available unutilized Pond ash to enable us to use the same for construction of road embankments. The distance from M/s.NTECL to our project location at Km.87 is falling in within the radius of 100Km | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/20210820_SPK_PD_054_Request for approval of extraction of Fly Ash – Reg..pdf | Request for approval of extraction of Fly Ash - Reg. | Dear Sir, This is with reference to the subject matter, in continuation to our letters cited above; due to paucity of natural soil we proposed to utilize Pondash in the approaches of VUP/LVUP/Flyover as a filling material and which is recommended by MoRTH and MoEF' & CC of Govt. of India for construction of road embankments. In this regard, vide reference (2) cited, the Director General (Road Development) & SS, MoRTH Govt. of India has stressed for bulk utilization of the Fly ash as far as possible in the field of civil engineering application, especially construction of road embankments. We once again reiterate that; Ministry of Environment Forests and Climate Change (MoEF & CC) has issued various notifications fddatPondash............ utilization. The principal notification was issued on 14.09.1999, which was subsequently amended vide notifications dated 27.08.2003, 03.11.2009 and 25.01.2016. As per the notification of MoEF & CC, it is mandatory to use Fly-ash in the construction of road embankments within a radius of 300 km of a thermal power plant. Further, the relevant content of the notification dated 25.01.2016 of MoEF & CC regarding road/flyover embankment construction are as under Para 10: The cost of transportation of ash for road construction projects or for manufacturing of ash based products or use as soil conditioner in agriculture activity within a radius of hundred kilometres from a coal or lignite based thermal power plant shall be borne by such coal or lignite based thermal power plant and the cost of transportation beyond the radius of hundred kilometres and up to three hundred kilometres shall be shared equally between the user and the coal or lignite based thermal power plant. In this connection, the Project Director PIU Kancheepuram vide letter referenced at (6),(7) & (8) has requested the Chief Executive Officer, M/s NTECL Vallur Thermal Power Projects to supply necessary fly ash to the site as requested by the Contractor and despite approaching in person the supply of Fly ash by M/s NTECL has not materialised till date. We hereby request your good office to obtain in principle approval from the nearby Thermal power Station M/s. NTCEL Vallur Power Projects - Thiruvallur for utilizing the available unutilized Pond ash to enable us to use the same for construction of road embankments. The distance from M/s.NTECL to our project location at Km.87 is falling in within the radius of 100km. For information as we are aware that the permission for borrow earth is badly delayed and due to the scarcity of the same and due to unseasonal rainfall and second wave of COVID-19 Pandemic, the progress of our work is slow and severely hampered. | FALSE | real_data
Pond ash supply | Others; EoT; Payments; Contractor's Obligations | In view of the above, it is requested to take necessary action to supply fly ash to the site as requested by the contractor at the earliest after following procedure in vogue. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/20201215_PD_NTCEL_ 4053_Supply of pond ash.pdf | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet Section of NH - 4 (New NH-48) from Km. 71+015 to km. 107+091 in the State of Tamil Nadu under NHDP (Phase V) under Bharatmala Pariyojana on EPC Mode - Supply of Fly Ash by NTECL - Reg. | This is with reference to the meeting held with the undersigned by AGM, NTECL on 07.01.2020 at NHAI Office at Tambaram, it is informed that the contractor vide letter 1 cited above, requested this office to request NTECL to supply fly ash (approx. 13 lakh MT) for the said project. In this regard your attention is invited to the MoEF notification S.0. 254(E) dated 25th January 2016 wherein it was directed to use fly ash in construction of road or flyover embankments within a radius of 300 Km of a thermal power plant and the relevant paragraph are as follows: “10. The cost of transportation of ash for road construction projects or for manufacturing of ash based products or use as soil conditioner in agriculture activity within a radius of hundred kilometers from a coal or lignite based thermal power plant shall be borne by such coal or lignite based thermal power plant and the cost of transportation beyond the radius of hundred kilometers and up to three hundred kilometers shall be shared equally between the user and the coal or lignite based thermal power plant. The present road stretch mentioned in the subject is within 300 Km from the power plant. In view of the above, it is requested to take necessary action to supply fly ash to the site as requested by the contractor at the earliest after following procedure in vogue. | FALSE | real_data
Pond ash supply | EoT | In view of the above, it is requested to take necessary action to supply fly ash to the site as requested by the contractor at the earliest after following procedure in vogue. | synthetic_template_20250913 | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet Section of NH - 4 (New NH-48) from Km. 71+015 to km. 107+091 in the State of Tamil Nadu under NHDP (Phase V) under Bharatmala Pariyojana on EPC Mode - Supply of Fly Ash by NTECL - Reg. | This is with reference to the meeting held with the undersigned by AGM, NTECL on 07.01.2020 at NHAI Office at Tambaram, it is informed that the contractor vide letter 1 cited above, requested this office to request NTECL to supply fly ash (approx. 13 lakh MT) for the said project. In this regard your attention is invited to the MoEF notification S.0. 254(E) dated 25th January 2016 wherein it was directed to use fly ash in construction of road or flyover embankments within a radius of 300 Km of a thermal power plant and the relevant paragraph are as follows: “10. The cost of transportation of ash for road construction projects or for manufacturing of ash based products or use as soil conditioner in agriculture activity within a radius of hundred kilometers from a coal or lignite based thermal power plant shall be borne by such coal or lignite based thermal power plant and the cost of transportation beyond the radius of hundred kilometers and up to three hundred kilometers shall be shared equally between the user and the coal or lignite based thermal power plant. The present road stretch mentioned in the subject is within 300 Km from the power plant. In view of the above, it is requested to take necessary action to supply fly ash to the site as requested by the contractor at the earliest after following procedure in vogue. We appreciate your cooperation in this regard. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Pond ash supply | EoT | In view of the above, it is requested to take necessary action to supply fly ash to the site as requested by the contractor at the earliest after following procedure in vogue. | synthetic_template_20250913 | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet Section of NH - 4 (New NH-48) from Km. 71+015 to km. 107+091 in the State of Tamil Nadu under NHDP (Phase V) under Bharatmala Pariyojana on EPC Mode - Supply of Fly Ash by NTECL - Reg. | This is to notify you that This is with reference to the meeting held with the undersigned by AGM, NTECL on 07.01.2020 at NHAI Office at Tambaram, it is informed that the contractor vide letter 1 cited above, requested this office to request NTECL to supply fly ash (approx. 13 lakh MT) for the said project. In this regard your attention is invited to the MoEF notification S.0. 254(E) dated 25th January 2016 wherein it was directed to use fly ash in construction of road or flyover embankments within a radius of 300 Km of a thermal power plant and the relevant paragraph are as follows: “10. The cost of transportation of ash for road construction projects or for manufacturing of ash based products or use as soil conditioner in agriculture activity within a radius of hundred kilometers from a coal or lignite based thermal power plant shall be borne by such coal or lignite based thermal power plant and the cost of transportation beyond the radius of hundred kilometers and up to three hundred kilometers shall be shared equally between the user and the coal or lignite based thermal power plant. The present road stretch mentioned in the subject is within 300 Km from the power plant. In view of the above, it is requested to take necessary action to supply fly ash to the site as requested by the contractor at the earliest after following procedure in vogue. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Pond ash supply | Contractor's Obligations | In view of the above, it is requested to take necessary action to supply fly ash to the site as requested by the contractor at the earliest after following procedure in vogue. | synthetic_template_20250913 | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet Section of NH - 4 (New NH-48) from Km. 71+015 to km. 107+091 in the State of Tamil Nadu under NHDP (Phase V) under Bharatmala Pariyojana on EPC Mode - Supply of Fly Ash by NTECL - Reg. | This is with reference to the meeting held with the undersigned by AGM, NTECL on 07.01.2020 at NHAI Office at Tambaram, it is informed that the contractor vide letter 1 cited above, requested this office to request NTECL to supply fly ash (approx. 13 lakh MT) for the said project. In this regard your attention is invited to the MoEF notification S.0. 254(E) dated 25th January 2016 wherein it was directed to use fly ash in construction of road or flyover embankments within a radius of 300 Km of a thermal power plant and the relevant paragraph are as follows: “10. The cost of transportation of ash for road construction projects or for manufacturing of ash based products or use as soil conditioner in agriculture activity within a radius of hundred kilometers from a coal or lignite based thermal power plant shall be borne by such coal or lignite based thermal power plant and the cost of transportation beyond the radius of hundred kilometers and up to three hundred kilometers shall be shared equally between the user and the coal or lignite based thermal power plant. The present road stretch mentioned in the subject is within 300 Km from the power plant. In view of the above, it is requested to take necessary action to supply fly ash to the site as requested by the contractor at the earliest after following procedure in vogue. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Pond ash supply | Contractor's Obligations | In view of the above, it is requested to take necessary action to supply fly ash to the site as requested by the contractor at the earliest after following procedure in vogue. | synthetic_template_20250913 | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet Section of NH - 4 (New NH-48) from Km. 71+015 to km. 107+091 in the State of Tamil Nadu under NHDP (Phase V) under Bharatmala Pariyojana on EPC Mode - Supply of Fly Ash by NTECL - Reg. | This is with reference to the meeting held with the undersigned by AGM, NTECL on 07.01.2020 at NHAI Office at Tambaram, it is informed that the contractor vide letter 1 cited above, requested this office to request NTECL to supply fly ash (approx. 13 lakh MT) for the said project. In this regard your attention is invited to the MoEF notification S.0. 254(E) dated 25th January 2016 wherein it was directed to use fly ash in construction of road or flyover embankments within a radius of 300 Km of a thermal power plant and the relevant paragraph are as follows: “10. The cost of transportation of ash for road construction projects or for manufacturing of ash based products or use as soil conditioner in agriculture activity within a radius of hundred kilometers from a coal or lignite based thermal power plant shall be borne by such coal or lignite based thermal power plant and the cost of transportation beyond the radius of hundred kilometers and up to three hundred kilometers shall be shared equally between the user and the coal or lignite based thermal power plant. The present road stretch mentioned in the subject is within 300 Km from the power plant. In view of the above, it is requested to take necessary action to supply fly ash to the site as requested by the contractor at the earliest after following procedure in vogue. We await your further instructions. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Pond ash supply | Payments | In view of the above, it is requested to take necessary action to supply fly ash to the site as requested by the contractor at the earliest after following procedure in vogue. | synthetic_template_20250913 | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet Section of NH - 4 (New NH-48) from Km. 71+015 to km. 107+091 in the State of Tamil Nadu under NHDP (Phase V) under Bharatmala Pariyojana on EPC Mode - Supply of Fly Ash by NTECL - Reg. | This is with reference to the meeting held with the undersigned by AGM, NTECL on 07.01.2020 at NHAI Office at Tambaram, it is informed that the contractor vide letter 1 cited above, requested this office to request NTECL to supply fly ash (approx. 13 lakh MT) for the said project. In this regard your attention is invited to the MoEF notification S.0. 254(E) dated 25th January 2016 wherein it was directed to use fly ash in construction of road or flyover embankments within a radius of 300 Km of a thermal power plant and the relevant paragraph are as follows: “10. The cost of transportation of ash for road construction projects or for manufacturing of ash based products or use as soil conditioner in agriculture activity within a radius of hundred kilometers from a coal or lignite based thermal power plant shall be borne by such coal or lignite based thermal power plant and the cost of transportation beyond the radius of hundred kilometers and up to three hundred kilometers shall be shared equally between the user and the coal or lignite based thermal power plant. The present road stretch mentioned in the subject is within 300 Km from the power plant. In view of the above, it is requested to take necessary action to supply fly ash to the site as requested by the contractor at the earliest after following procedure in vogue. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Pond ash supply | Payments | In view of the above, it is requested to take necessary action to supply fly ash to the site as requested by the contractor at the earliest after following procedure in vogue. | synthetic_template_20250913 | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet Section of NH - 4 (New NH-48) from Km. 71+015 to km. 107+091 in the State of Tamil Nadu under NHDP (Phase V) under Bharatmala Pariyojana on EPC Mode - Supply of Fly Ash by NTECL - Reg. | Please note that This is with reference to the meeting held with the undersigned by AGM, NTECL on 07.01.2020 at NHAI Office at Tambaram, it is informed that the contractor vide letter 1 cited above, requested this office to request NTECL to supply fly ash (approx. 13 lakh MT) for the said project. In this regard your attention is invited to the MoEF notification S.0. 254(E) dated 25th January 2016 wherein it was directed to use fly ash in construction of road or flyover embankments within a radius of 300 Km of a thermal power plant and the relevant paragraph are as follows: “10. The cost of transportation of ash for road construction projects or for manufacturing of ash based products or use as soil conditioner in agriculture activity within a radius of hundred kilometers from a coal or lignite based thermal power plant shall be borne by such coal or lignite based thermal power plant and the cost of transportation beyond the radius of hundred kilometers and up to three hundred kilometers shall be shared equally between the user and the coal or lignite based thermal power plant. The present road stretch mentioned in the subject is within 300 Km from the power plant. In view of the above, it is requested to take necessary action to supply fly ash to the site as requested by the contractor at the earliest after following procedure in vogue. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Pond ash supply | Others | In view of the above, it is requested to take necessary action to supply fly ash to the site as requested by the contractor at the earliest after following procedure in vogue. | synthetic_template_20250913 | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet Section of NH - 4 (New NH-48) from Km. 71+015 to km. 107+091 in the State of Tamil Nadu under NHDP (Phase V) under Bharatmala Pariyojana on EPC Mode - Supply of Fly Ash by NTECL - Reg. | We would like to inform you that This is with reference to the meeting held with the undersigned by AGM, NTECL on 07.01.2020 at NHAI Office at Tambaram, it is informed that the contractor vide letter 1 cited above, requested this office to request NTECL to supply fly ash (approx. 13 lakh MT) for the said project. In this regard your attention is invited to the MoEF notification S.0. 254(E) dated 25th January 2016 wherein it was directed to use fly ash in construction of road or flyover embankments within a radius of 300 Km of a thermal power plant and the relevant paragraph are as follows: “10. The cost of transportation of ash for road construction projects or for manufacturing of ash based products or use as soil conditioner in agriculture activity within a radius of hundred kilometers from a coal or lignite based thermal power plant shall be borne by such coal or lignite based thermal power plant and the cost of transportation beyond the radius of hundred kilometers and up to three hundred kilometers shall be shared equally between the user and the coal or lignite based thermal power plant. The present road stretch mentioned in the subject is within 300 Km from the power plant. In view of the above, it is requested to take necessary action to supply fly ash to the site as requested by the contractor at the earliest after following procedure in vogue. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Filing of affidavit | Others | counter affidavit file on behalf of M/s NTECL in Hon'ble High Court of Madras | synthetic_template_20250913 | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet section of NH-4 from Km 71/015 to Km 107/091 in the State of Tamilnadu under residual NHDP (Phase — V) under Bharathmala Pariyojana on EPC Mode - Proposal for Utilization of Fly Ash from M/s. NTECL Vallur Thermal Power Projects - Reg. | This is to notify you that This has reference to the letter cited 01st above, where in the Contractor has requested this office to obtain in principle approval from the nearby Thermal Power Plant M/s. NTECL Vallur Thermal Power Project for utilization of Pond ash for Construction of Road embankments. In this regard, as per Article 3.1.7 (Obligations of the Contractor) of the EPC Contract agreement, “The Contactor shall, at its own cost and expense, in addition to and not in derogation of its obligations elsewhere set out in this Agreement: (b) procure, as required, the appropriate proprietary rights, licenses, agreements and permissions for Materials, methods, processes and systems used or incorporated into the Project Highway”. From the above clause, it is clear that it is the responsibility of the contractor for the procurement of the materials, obtaining necessary permissions for materials etc. However, based on the request of the EPC Contractor - M/s. S.P.K & Co vide letter dated 07.12.2020, this office vide letters dated 15.12.2020 and 11.02.2021 requested the nearby Thermal Plant M/s. NTECL (NTPC Tamilnadu Energy Company Limited) to supply Fly ash to the site as per the MoEF notification S.O. 254 (E) dated 25th January 2016. Further, this office vide letter dated 28.06.2021, communicated the counter affidavit filed on behalf of M/s. NTECL in Hon’ble High Court of Madras in W.P No.33323 of 2019, wherein the current status and the availability of Fly ash has been submitted by M/s. NTECL. In view of the above, it is requested to coordinate with the Fly ash supplying agency M/s. NTECL and to facilitate the supply of Fly ash to the Project site. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Filing of affidavit | Others | counter affidavit file on behalf of M/s NTECL in Hon'ble High Court of Madras | synthetic_template_20250913 | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet section of NH-4 from Km 71/015 to Km 107/091 in the State of Tamilnadu under residual NHDP (Phase — V) under Bharathmala Pariyojana on EPC Mode - Proposal for Utilization of Fly Ash from M/s. NTECL Vallur Thermal Power Projects - Reg. | This has reference to the letter cited 01st above, where in the Contractor has requested this office to obtain in principle approval from the nearby Thermal Power Plant M/s. NTECL Vallur Thermal Power Project for utilization of Pond ash for Construction of Road embankments. In this regard, as per Article 3.1.7 (Obligations of the Contractor) of the EPC Contract agreement, “The Contactor shall, at its own cost and expense, in addition to and not in derogation of its obligations elsewhere set out in this Agreement: (b) procure, as required, the appropriate proprietary rights, licenses, agreements and permissions for Materials, methods, processes and systems used or incorporated into the Project Highway”. From the above clause, it is clear that it is the responsibility of the contractor for the procurement of the materials, obtaining necessary permissions for materials etc. However, based on the request of the EPC Contractor - M/s. S.P.K & Co vide letter dated 07.12.2020, this office vide letters dated 15.12.2020 and 11.02.2021 requested the nearby Thermal Plant M/s. NTECL (NTPC Tamilnadu Energy Company Limited) to supply Fly ash to the site as per the MoEF notification S.O. 254 (E) dated 25th January 2016. Further, this office vide letter dated 28.06.2021, communicated the counter affidavit filed on behalf of M/s. NTECL in Hon’ble High Court of Madras in W.P No.33323 of 2019, wherein the current status and the availability of Fly ash has been submitted by M/s. NTECL. In view of the above, it is requested to coordinate with the Fly ash supplying agency M/s. NTECL and to facilitate the supply of Fly ash to the Project site. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Filing of affidavit | Others | counter affidavit file on behalf of M/s NTECL in Hon'ble High Court of Madras | synthetic_template_20250913 | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet section of NH-4 from Km 71/015 to Km 107/091 in the State of Tamilnadu under residual NHDP (Phase — V) under Bharathmala Pariyojana on EPC Mode - Proposal for Utilization of Fly Ash from M/s. NTECL Vallur Thermal Power Projects - Reg. | This has reference to the letter cited 01st above, where in the Contractor has requested this office to obtain in principle approval from the nearby Thermal Power Plant M/s. NTECL Vallur Thermal Power Project for utilization of Pond ash for Construction of Road embankments. In this regard, as per Article 3.1.7 (Obligations of the Contractor) of the EPC Contract agreement, “The Contactor shall, at its own cost and expense, in addition to and not in derogation of its obligations elsewhere set out in this Agreement: (b) procure, as required, the appropriate proprietary rights, licenses, agreements and permissions for Materials, methods, processes and systems used or incorporated into the Project Highway”. From the above clause, it is clear that it is the responsibility of the contractor for the procurement of the materials, obtaining necessary permissions for materials etc. However, based on the request of the EPC Contractor - M/s. S.P.K & Co vide letter dated 07.12.2020, this office vide letters dated 15.12.2020 and 11.02.2021 requested the nearby Thermal Plant M/s. NTECL (NTPC Tamilnadu Energy Company Limited) to supply Fly ash to the site as per the MoEF notification S.O. 254 (E) dated 25th January 2016. Further, this office vide letter dated 28.06.2021, communicated the counter affidavit filed on behalf of M/s. NTECL in Hon’ble High Court of Madras in W.P No.33323 of 2019, wherein the current status and the availability of Fly ash has been submitted by M/s. NTECL. In view of the above, it is requested to coordinate with the Fly ash supplying agency M/s. NTECL and to facilitate the supply of Fly ash to the Project site. Please confirm receipt of this correspondence. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Filing of affidavit | Others | counter affidavit file on behalf of M/s NTECL in Hon'ble High Court of Madras | synthetic_template_20250913 | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet section of NH-4 from Km 71/015 to Km 107/091 in the State of Tamilnadu under residual NHDP (Phase — V) under Bharathmala Pariyojana on EPC Mode - Proposal for Utilization of Fly Ash from M/s. NTECL Vallur Thermal Power Projects - Reg. | This has reference to the letter cited 01st above, where in the Contractor has requested this office to obtain in principle approval from the nearby Thermal Power Plant M/s. NTECL Vallur Thermal Power Project for utilization of Pond ash for Construction of Road embankments. In this regard, as per Article 3.1.7 (Obligations of the Contractor) of the EPC Contract agreement, “The Contactor shall, at its own cost and expense, in addition to and not in derogation of its obligations elsewhere set out in this Agreement: (b) procure, as required, the appropriate proprietary rights, licenses, agreements and permissions for Materials, methods, processes and systems used or incorporated into the Project Highway”. From the above clause, it is clear that it is the responsibility of the contractor for the procurement of the materials, obtaining necessary permissions for materials etc. However, based on the request of the EPC Contractor - M/s. S.P.K & Co vide letter dated 07.12.2020, this office vide letters dated 15.12.2020 and 11.02.2021 requested the nearby Thermal Plant M/s. NTECL (NTPC Tamilnadu Energy Company Limited) to supply Fly ash to the site as per the MoEF notification S.O. 254 (E) dated 25th January 2016. Further, this office vide letter dated 28.06.2021, communicated the counter affidavit filed on behalf of M/s. NTECL in Hon’ble High Court of Madras in W.P No.33323 of 2019, wherein the current status and the availability of Fly ash has been submitted by M/s. NTECL. In view of the above, it is requested to coordinate with the Fly ash supplying agency M/s. NTECL and to facilitate the supply of Fly ash to the Project site. We appreciate your cooperation in this regard. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Filing of affidavit | Others | counter affidavit file on behalf of M/s NTECL in Hon'ble High Court of Madras | synthetic_template_20250913 | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet section of NH-4 from Km 71/015 to Km 107/091 in the State of Tamilnadu under residual NHDP (Phase — V) under Bharathmala Pariyojana on EPC Mode - Proposal for Utilization of Fly Ash from M/s. NTECL Vallur Thermal Power Projects - Reg. | This has reference to the letter cited 01st above, where in the Contractor has requested this office to obtain in principle approval from the nearby Thermal Power Plant M/s. NTECL Vallur Thermal Power Project for utilization of Pond ash for Construction of Road embankments. In this regard, as per Article 3.1.7 (Obligations of the Contractor) of the EPC Contract agreement, “The Contactor shall, at its own cost and expense, in addition to and not in derogation of its obligations elsewhere set out in this Agreement: (b) procure, as required, the appropriate proprietary rights, licenses, agreements and permissions for Materials, methods, processes and systems used or incorporated into the Project Highway”. From the above clause, it is clear that it is the responsibility of the contractor for the procurement of the materials, obtaining necessary permissions for materials etc. However, based on the request of the EPC Contractor - M/s. S.P.K & Co vide letter dated 07.12.2020, this office vide letters dated 15.12.2020 and 11.02.2021 requested the nearby Thermal Plant M/s. NTECL (NTPC Tamilnadu Energy Company Limited) to supply Fly ash to the site as per the MoEF notification S.O. 254 (E) dated 25th January 2016. Further, this office vide letter dated 28.06.2021, communicated the counter affidavit filed on behalf of M/s. NTECL in Hon’ble High Court of Madras in W.P No.33323 of 2019, wherein the current status and the availability of Fly ash has been submitted by M/s. NTECL. In view of the above, it is requested to coordinate with the Fly ash supplying agency M/s. NTECL and to facilitate the supply of Fly ash to the Project site. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Tree cutting | EoT | It is requested to accord permission for felling of existing trees in the Govt. (NHAI) lands at the earliest | synthetic_template_20250913 | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet section of NH-4 from Km 71/015 to Km 107/091 (36.076 Km) in the State of Tamil Nadu - Felling of Trees in NHAI Lands - Reg. | This has reference to the Six laning of Karaipettai to Walajahpet section of NH-4 from Km 71/015 to Km 107/091 in the State of Tamil Nadu. In this regard, it is submitted that The Project Stretch from Km 85/910 to Km 107/091 passes through Ranipet District in the state of Tamil Nadu. Authority executed the Contract Agreement with M/s.S.P.K & Co., on 15.10.2018 and the appointed date has been declared with effect from 11.02.2019. The contractor for the project M/s.S.P.K & Co., has submitted report on the existing trees on Govt. (NHAI) in the Chennasamudram User Fee Plaza in the Ranipet District. As per the report, total 15 no. of trees in Govt. (NHAI) lands falling under Ranipet District which are needed to be felled towards the ongoing six lanning works and for the formation of the New User Fee Plaza at Chennasamudram. These trees had been planted by NHAI itself in the Public funded User Fee Plaza at Chennasamudram at Km 104/900 during the Four laning of Kanchipuram to Walajahpet Section (NH4) from Km 70/200 to Km 106/400 which was completed on 23rd Mar 2004 under Golden Quadrilateral Programme. Further, as a part of compensatory planting at 1:10 ration, ie., 150 No.s of trees shall be planted. The contractor has to do Median Plantation, Avenue Plantation and Landscaping at Toll Plaza as pr the Contract Agreement. Further, the Contractor has already completed the Median Plantation for a length of 12.00 Km. The details of the trees are given below; As per the G.O. issued by the Environmental, Climate Change and Forest (FR.13) dated 02.07.2021, permission of the Green Committee is required for felling of trees so that encumbrance free land can be provided to the contractor for commencement of New User Fee Plaza at Chennasamudram. In view of the above, it is requested to accord permission for felling of existing trees in the Govt. (NHAI) lands at the earliest. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Tree cutting | EoT | It is requested to accord permission for felling of existing trees in the Govt. (NHAI) lands at the earliest | synthetic_template_20250913 | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet section of NH-4 from Km 71/015 to Km 107/091 (36.076 Km) in the State of Tamil Nadu - Felling of Trees in NHAI Lands - Reg. | This has reference to the Six laning of Karaipettai to Walajahpet section of NH-4 from Km 71/015 to Km 107/091 in the State of Tamil Nadu. In this regard, it is submitted that The Project Stretch from Km 85/910 to Km 107/091 passes through Ranipet District in the state of Tamil Nadu. Authority executed the Contract Agreement with M/s.S.P.K & Co., on 15.10.2018 and the appointed date has been declared with effect from 11.02.2019. The contractor for the project M/s.S.P.K & Co., has submitted report on the existing trees on Govt. (NHAI) in the Chennasamudram User Fee Plaza in the Ranipet District. As per the report, total 15 no. of trees in Govt. (NHAI) lands falling under Ranipet District which are needed to be felled towards the ongoing six lanning works and for the formation of the New User Fee Plaza at Chennasamudram. These trees had been planted by NHAI itself in the Public funded User Fee Plaza at Chennasamudram at Km 104/900 during the Four laning of Kanchipuram to Walajahpet Section (NH4) from Km 70/200 to Km 106/400 which was completed on 23rd Mar 2004 under Golden Quadrilateral Programme. Further, as a part of compensatory planting at 1:10 ration, ie., 150 No.s of trees shall be planted. The contractor has to do Median Plantation, Avenue Plantation and Landscaping at Toll Plaza as pr the Contract Agreement. Further, the Contractor has already completed the Median Plantation for a length of 12.00 Km. The details of the trees are given below; As per the G.O. issued by the Environmental, Climate Change and Forest (FR.13) dated 02.07.2021, permission of the Green Committee is required for felling of trees so that encumbrance free land can be provided to the contractor for commencement of New User Fee Plaza at Chennasamudram. In view of the above, it is requested to accord permission for felling of existing trees in the Govt. (NHAI) lands at the earliest. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Tree cutting | Authority's Obligations | It is requested to accord permission for felling of existing trees in the Govt. (NHAI) lands at the earliest | synthetic_template_20250913 | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet section of NH-4 from Km 71/015 to Km 107/091 (36.076 Km) in the State of Tamil Nadu - Felling of Trees in NHAI Lands - Reg. | This has reference to the Six laning of Karaipettai to Walajahpet section of NH-4 from Km 71/015 to Km 107/091 in the State of Tamil Nadu. In this regard, it is submitted that The Project Stretch from Km 85/910 to Km 107/091 passes through Ranipet District in the state of Tamil Nadu. Authority executed the Contract Agreement with M/s.S.P.K & Co., on 15.10.2018 and the appointed date has been declared with effect from 11.02.2019. The contractor for the project M/s.S.P.K & Co., has submitted report on the existing trees on Govt. (NHAI) in the Chennasamudram User Fee Plaza in the Ranipet District. As per the report, total 15 no. of trees in Govt. (NHAI) lands falling under Ranipet District which are needed to be felled towards the ongoing six lanning works and for the formation of the New User Fee Plaza at Chennasamudram. These trees had been planted by NHAI itself in the Public funded User Fee Plaza at Chennasamudram at Km 104/900 during the Four laning of Kanchipuram to Walajahpet Section (NH4) from Km 70/200 to Km 106/400 which was completed on 23rd Mar 2004 under Golden Quadrilateral Programme. Further, as a part of compensatory planting at 1:10 ration, ie., 150 No.s of trees shall be planted. The contractor has to do Median Plantation, Avenue Plantation and Landscaping at Toll Plaza as pr the Contract Agreement. Further, the Contractor has already completed the Median Plantation for a length of 12.00 Km. The details of the trees are given below; As per the G.O. issued by the Environmental, Climate Change and Forest (FR.13) dated 02.07.2021, permission of the Green Committee is required for felling of trees so that encumbrance free land can be provided to the contractor for commencement of New User Fee Plaza at Chennasamudram. In view of the above, it is requested to accord permission for felling of existing trees in the Govt. (NHAI) lands at the earliest. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Tree cutting | Authority's Obligations | It is requested to accord permission for felling of existing trees in the Govt. (NHAI) lands at the earliest | synthetic_template_20250913 | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet section of NH-4 from Km 71/015 to Km 107/091 (36.076 Km) in the State of Tamil Nadu - Felling of Trees in NHAI Lands - Reg. | This has reference to the Six laning of Karaipettai to Walajahpet section of NH-4 from Km 71/015 to Km 107/091 in the State of Tamil Nadu. In this regard, it is submitted that The Project Stretch from Km 85/910 to Km 107/091 passes through Ranipet District in the state of Tamil Nadu. Authority executed the Contract Agreement with M/s.S.P.K & Co., on 15.10.2018 and the appointed date has been declared with effect from 11.02.2019. The contractor for the project M/s.S.P.K & Co., has submitted report on the existing trees on Govt. (NHAI) in the Chennasamudram User Fee Plaza in the Ranipet District. As per the report, total 15 no. of trees in Govt. (NHAI) lands falling under Ranipet District which are needed to be felled towards the ongoing six lanning works and for the formation of the New User Fee Plaza at Chennasamudram. These trees had been planted by NHAI itself in the Public funded User Fee Plaza at Chennasamudram at Km 104/900 during the Four laning of Kanchipuram to Walajahpet Section (NH4) from Km 70/200 to Km 106/400 which was completed on 23rd Mar 2004 under Golden Quadrilateral Programme. Further, as a part of compensatory planting at 1:10 ration, ie., 150 No.s of trees shall be planted. The contractor has to do Median Plantation, Avenue Plantation and Landscaping at Toll Plaza as pr the Contract Agreement. Further, the Contractor has already completed the Median Plantation for a length of 12.00 Km. The details of the trees are given below; As per the G.O. issued by the Environmental, Climate Change and Forest (FR.13) dated 02.07.2021, permission of the Green Committee is required for felling of trees so that encumbrance free land can be provided to the contractor for commencement of New User Fee Plaza at Chennasamudram. In view of the above, it is requested to accord permission for felling of existing trees in the Govt. (NHAI) lands at the earliest. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Tree cutting | Contractor's Obligations | It is requested to accord permission for felling of existing trees in the Govt. (NHAI) lands at the earliest | synthetic_template_20250913 | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet section of NH-4 from Km 71/015 to Km 107/091 (36.076 Km) in the State of Tamil Nadu - Felling of Trees in NHAI Lands - Reg. | This has reference to the Six laning of Karaipettai to Walajahpet section of NH-4 from Km 71/015 to Km 107/091 in the State of Tamil Nadu. In this regard, it is submitted that The Project Stretch from Km 85/910 to Km 107/091 passes through Ranipet District in the state of Tamil Nadu. Authority executed the Contract Agreement with M/s.S.P.K & Co., on 15.10.2018 and the appointed date has been declared with effect from 11.02.2019. The contractor for the project M/s.S.P.K & Co., has submitted report on the existing trees on Govt. (NHAI) in the Chennasamudram User Fee Plaza in the Ranipet District. As per the report, total 15 no. of trees in Govt. (NHAI) lands falling under Ranipet District which are needed to be felled towards the ongoing six lanning works and for the formation of the New User Fee Plaza at Chennasamudram. These trees had been planted by NHAI itself in the Public funded User Fee Plaza at Chennasamudram at Km 104/900 during the Four laning of Kanchipuram to Walajahpet Section (NH4) from Km 70/200 to Km 106/400 which was completed on 23rd Mar 2004 under Golden Quadrilateral Programme. Further, as a part of compensatory planting at 1:10 ration, ie., 150 No.s of trees shall be planted. The contractor has to do Median Plantation, Avenue Plantation and Landscaping at Toll Plaza as pr the Contract Agreement. Further, the Contractor has already completed the Median Plantation for a length of 12.00 Km. The details of the trees are given below; As per the G.O. issued by the Environmental, Climate Change and Forest (FR.13) dated 02.07.2021, permission of the Green Committee is required for felling of trees so that encumbrance free land can be provided to the contractor for commencement of New User Fee Plaza at Chennasamudram. In view of the above, it is requested to accord permission for felling of existing trees in the Govt. (NHAI) lands at the earliest. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Tree cutting | Contractor's Obligations | It is requested to accord permission for felling of existing trees in the Govt. (NHAI) lands at the earliest | synthetic_template_20250913 | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet section of NH-4 from Km 71/015 to Km 107/091 (36.076 Km) in the State of Tamil Nadu - Felling of Trees in NHAI Lands - Reg. | It is brought to your attention that This has reference to the Six laning of Karaipettai to Walajahpet section of NH-4 from Km 71/015 to Km 107/091 in the State of Tamil Nadu. In this regard, it is submitted that The Project Stretch from Km 85/910 to Km 107/091 passes through Ranipet District in the state of Tamil Nadu. Authority executed the Contract Agreement with M/s.S.P.K & Co., on 15.10.2018 and the appointed date has been declared with effect from 11.02.2019. The contractor for the project M/s.S.P.K & Co., has submitted report on the existing trees on Govt. (NHAI) in the Chennasamudram User Fee Plaza in the Ranipet District. As per the report, total 15 no. of trees in Govt. (NHAI) lands falling under Ranipet District which are needed to be felled towards the ongoing six lanning works and for the formation of the New User Fee Plaza at Chennasamudram. These trees had been planted by NHAI itself in the Public funded User Fee Plaza at Chennasamudram at Km 104/900 during the Four laning of Kanchipuram to Walajahpet Section (NH4) from Km 70/200 to Km 106/400 which was completed on 23rd Mar 2004 under Golden Quadrilateral Programme. Further, as a part of compensatory planting at 1:10 ration, ie., 150 No.s of trees shall be planted. The contractor has to do Median Plantation, Avenue Plantation and Landscaping at Toll Plaza as pr the Contract Agreement. Further, the Contractor has already completed the Median Plantation for a length of 12.00 Km. The details of the trees are given below; As per the G.O. issued by the Environmental, Climate Change and Forest (FR.13) dated 02.07.2021, permission of the Green Committee is required for felling of trees so that encumbrance free land can be provided to the contractor for commencement of New User Fee Plaza at Chennasamudram. In view of the above, it is requested to accord permission for felling of existing trees in the Govt. (NHAI) lands at the earliest. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Appointment of Safety & Proof Consultants | Contractor's Obligations | It is requested to submit the proposal of CV duly mentioning the Date of Birth and Signed for Safety Consultant in complete shape | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/Lr.No.565_CV For The Safety Consultant.pdf | NHAI, PIU - Krishnagiri - Six laning of Karaipettai to Walajahpet section of NH-48 (old NH-4) from km.71+015 to km.107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase V- CV for the Safety Consultant - Reg. | With reference to the letter cited above, wherein the Contractor M/s. SP.K & Co., has submitted Proposal of proposed the following Safety Consulting firms with their key professionals for the captioned subject. 1. M/s. RODES Infra Consultancy Services LLP. 2. M/s. Hivistra Projects Private Limited, 3. M/s. MNJ Consulting Engineers, In this regard, it is inform that the above proposal for Safety Consulting firms is examined and the following observations are made. In view of the above, it is requested to submit the proposal of CVs duly mentioning Date of Birth and Signed for the Safety Consultant in complete shape at the earliest for taking further necessary action. | FALSE | real_data
Appointment of Safety & Proof Consultants | Contractor's Obligations | Contractor's Obligations | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LOT-10/16_02042019_CV for Safety Consultant.pdf | Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km.71+015 (Existing Km 71/000) to Km 107+091 (Existing Km 107/068) on EPC Mode in the state of Tamil Nadu under NHDP Phase-V - CV for Safety Consultant - Reg. | Dear Sir, With reference to your letter dated 30.03.2019 in regard to CVs for proposed key persons for safety consultant, we wish to state that as per the discussion with the proposed firms it is learnt that the following key persons were proposed by the firms to act as key professionals in the above stated project. Road Safety Auditor cum Sr. Highway Engineer: Mr. Goganna Gandi (Transportation) M/s. RODES Infra Consultancy Services LLP Sr. Structures Design Engineer: Mr. Subbarao Kakumanu Traffic Expert: Mr. Ramesh Darukumalli M/s. Hivista Projects Private Limited Road Safety Engineer cum Coordinator: Mr. Dinesh Kumar Yadav (Construction Technology and Management) M/s. MNJ Pavement Consulting Engineers Highway Engineer: Mr. Rammohan Rao Accordingly, signed copies of the CVs of proposed key professionals are enclosed herewith for your necessary further action. Kindly note CVs of the persons proposed to work in the project is only enclosed as the CVs of all persons working in the firm may not be relevant. | FALSE | real_data
Appointment of Safety & Proof Consultants | Contractor's Obligations | 1.We have proposed three names of experienced firms to act as Proof and Safety consultants and we have not received any reasons from the Authority for non-acceptance of the firms proposed by us. However, it is further to inform you that Govt. of India, Ministry of Road Transport and Highways (MORTH) vide its Circular No.RW/NH-34054/2/2011-S&R(B) dated 14.08.2018 discontinued empanelment of consultants. Copy of the circular is attached herewith for your kind reference. Therefore, as on date there is no firm empaneled under MORTH. Therefore by considering the experience of the firms and qualification and experience of the key persons proposed the firms can be selected. 2.Therefore, we hereby request you to give the consent for the proof and safety consultants. The Proof and safety consultants appointed by the contractor is as follows: | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LOT-10/38_24052019_ Appointment of Proof and safety Consultant.pdf | Six Lanning of Karaipcttai to Walajapet Section of NH-4 (New NH-48) from Km.71+015 (Existing Km 71/000) to Km 107+091 (Existing Km 107/068) on EPC Mode in the state of Tamil Nadu under NHDP Phase-V — Appointment of Proof and Safety Consultant - reg. | With reference to your email dated 23.05.2019 with regard to appointment of Proof and Safety Consultant we would like to draw your kind attention to the following clauses of the Contract. to be the Safety Consultant. Provided, however, that if the panel is not acceptable to the Authority and the reasons for the same are furnished to the Contractor, the Contractor shall Propose to the Authority a revised panel of three names from the firms empanelled as Safety consultants by the Ministry of Road Transport and Highways for obtaining the consent of the Authority.....” ~ — GST: 33ABXFS5510P1ZG Meo esa yr ipuliel Tin No ; 33665521308 CST No : 516750 Dt: 25.02.2008 S.P.K. AND Co.., Area Code : 283 Reg. Off. 2/67, R.C. Middle Street, Keelamudimannarkottai, Kamuthi Taluk, Ramnad District - 623 603 Branch. Off. 1-1-63/7, S.P.K. Complex, Ananthapuri Nagar 2nd Street, Madurai Road, Aruppukottai - 626 101. pate. 2415 ¦14.... Clause 10.2.2 - “The Contractor shall appoint Proof Check Consultant (the “Proof Check Consultant”) after proposing to the Authority a panel of three names of qualified and experienced firms from whom the Authority may choose one to be the Proof Consultant. Provided, however, that if the panel is not acceptable to the Authority and the reasons for the same are furnished to the Contractor, the Contractor shall propose to the Authority a revised panel of three names from the firms empanelled as proof consultants by the Ministry of Road Transport and Highways for obtaining the consent of the Authority. The Contractor shall also obtain the consent of the Authority for two key personnel of the Proof Consultant who shall have adequate experience and qualifications in highways and bridges respectively.” From the above clauses it is clear and evident that Contractor has to propose three names to qualify experienced firms for Safety and Proof Check Consultants. If the panel is not acceptable to the Authority and the reasons for the same are furnished to the Contractor, the Contractor shall further submit three names from the firms | FALSE | real_data
Appointment of Safety & Proof Consultants | Contractor's Obligations | Pursuant to Contract clause No. 10.1.1 (b) of the Contract, we hereby propose to appoint M/S. RUKY Projects Private Ltd situated at Flat No.205 & 207, 2nd Floor, Hemadurga Plaza, Above ICICI Bank, Allwyn Colony 'X' Road, Hyderabad as our Design Consultant for the said project. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LOT-10/Lr.No.1 Appointmet of Design Consultant.pdf | Appointment of Design Consultant/ Director - Reg. | Dear Sir, Pursuant to Contract clause No.10.1.1 (b) of the Contract, we hereby propose to appoint M/s. RUKY Projects Private Ltd situated at Flat No.205 & 207, 2.4 Floor, Hemadurga Plaza, Above ICICI Bank, Allwyn Colony ’ Road, Hyderabad as our Design Consultant for the said project. The details of key design team of M/s. RUKY Project Private limited are as under: 1, G.Praveen Yadav, Sr. Design Engineer (Highways) 2. G.Venkatesh, Sr. Design Engineer (Structures) Mr. G.Praveen Yadav, who is Post graduated in M.Tech (Transportation) having more than 12 years of experience in relevant field shall head the design unit to act as Design Director. The CV of proposed Design Director Mr. G. Praveen Yadav of M/s.Rucky Projects Pvt Ltd and company profile of proposed Design Consultant is submitted herewith for your kind information and record under the provisions of the contract. Thanking you, Yours faithfully, For SPK And Co.., | FALSE | real_data
Appointment of Safety & Proof Consultants | Contractor's Obligations | As per the provisions of clause 10.2.2 of the Contract "The contractor shall appoint the Proof consultant ('The Proof Consultant') after proposing to the authority a panel of three names of qualified and firms from whom the authority may choose one to be the Proof Consultant. ' Accordingly, we hereby propose the following three firms for appointment as Proof Consultants: | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LOT-10/Lr.No.2 Appointment of Proof Consultant.pdf | Request for Appointment of Proof Consultants - Reg. | Dear Sir, As per the provisions of clause 10.2.2 of the Contract “The contractor shall appoint the Proof check consultant (“The Proof Consultant”) after proposing to the authority a panel of three names of qualified and experienced firms from whom the authority may choose one to be the Proof Consultant. ” Accordingly, we hereby propose the following three firms for appointment as Proof Consultants: 1. M/s. Vax Consultants Pvt Limited. 2. M/s. RODES Infra Consultancy Services LLP 3. M/s. Professional Civil Infra Pvt. Ltd The profiles of above stated three firms are enclosed herewith. Therefore, we hereby request you to choose one of the above firms and communicate to us the selected Proof Consultant name to proceed further to appoint them. Thanking you, For SPK An / Cz Managing Partner VAN Encl: Proffle of the above § ies. Va | FALSE | real_data
Appointment of Safety & Proof Consultants | Contractor's Obligations | Therefore, we hereby request you to choose one of the above firms and communicate to us the selected Safety Consultant name to proceed further to appoint them. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LOT-10/Lr.No.3 Appointment of Safety Consultant.pdf | Request for Appointment of Safety Consultants - Reg. | Dear Sir, As per the provisions of clause 10.1.5 of the Contract “The contractor shall appoint the Safety Consultant (“The Safety Consultant”) to carry out safety audit at the design stage of the project highway in accordance with the applicable law and good industry practice. The Safety Consultant shall be appointed after proposing to the authority a panel of three names of qualified and experienced firms from whom the authority may choose one to be the Safety Consultant...”. Accordingly, we hereby propose the following three firms for appointment as Safety Consultant. 1. M/s. RODES Infra Consultancy Services LLP Mr. Goganna Gandi has 16 years of experience in Highways and Safety. 2. M/s. Smart Safety Services Mr. S.A.Prabhakar has 12 years of experience in Highways and Safety. 3. M/s. Vax Consultants Pvt Limited. The profiles of above stated three firms are enclosed herewith. Therefore, we hereby request you to choose one of the above firms and communicate to us the selected Safety Consultant name to proceed further to appoint them. Thanking you, | FALSE | real_data
Appointment of Safety & Proof Consultants | Contractor's Obligations | The approval of Safety and Proof Consultant should have been given by the Authority within 15 days of the submission of proposal by the EPC contractor i.e. on or before 05.01.2019. But the approval was given only in the month of June 2019. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/40_07082019_Rescheduling of Project Milestones – Request for Extension of time.pdf | Rescheduling of Project Milestones - Request for Extension of time - Reg. | The Contract agreement for the above mentioned project was executed on 15.10.2018. The appointed date was fixed as 11.02.2019 and the same was communicated vide ref (3) cited above. The Copy of the same is herewith enclosed as Annexure 1. The Authority in its response vide ref (5) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. The copy of the same is enclosed as Annexure 3. The EPC contractor vide ref (6) cited above reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that still the condition remained the same and dismantling/ removal of structures fouling was not started and shifting of Electric pole and power line also not started. The impacted length due to encroachments and encumbrances was 12.18 Km which accounted to 33.77% of the project highway. The workable length available to the Contractor based on the impacted length was 66.23% of the Project Highway length. The EPC Contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of removal of encumbrance / encroachment / obstruction. The copy of ref (7) is herewith enclosed as Annexure 4. It is almost six months since the declaration of appointed date, removal/ dismantling of structures/encroachments have not been started. Also, the work of shifting of power line and electric pole of LT line and HT lines crossings have not been started yet. The following are some of the key contractual dates and events since the inception of the project to till date: 1. Total length of the project highway: 36.076 Km 2. Date of Signing of agreement: 152018 3. Submission of Performance BG as per Clause 7.1.1 of the Contract Agreement: 262018 4. Target date for preparation of Memorandum as per Clause 8.2.1 of the Contract Agreement: 142018 5. Actual date of signing of Memorandum of land handing over: 112019 6. Declaration of appointed date by the Authority: 112019 7. ROW to be handed over as on appointed date as per Clause 8.2.2 & Annexure II: 35.468 Km | FALSE | real_data
Appointment of Safety & Proof Consultants | Contractor's Obligations | The Contractor has no impact on the preparation and approval of design and drawings due to delay in approval of proof and safety consultant.Therefore, the ground for EOT is not being considered herewith. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210630_AE_PD_14484_Comprehensive EOT proposal.pdf | Extension of Time Comprehensive proposal- Reg. | With reference to the captioned subject and from the above mentioned chronology of correspondences, it can be understood that despite of approving an EoT for a period of 112 days for Mile Stone-1, the Contractor is disagreeing with the approval of the Authority and again highlighted the impediments adversely effected the First Mile Stone as well as other Milestone including the Scheduled Completion Date. The Contractor submitted the comprehensive proposal and requested for an extension of time. | FALSE | real_data
Memorandum and Appendix | Contractor's Obligations | be available for joint inspection for preparation of memorandum from 1st January, 2019 to January, 2019. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km.71+015 (Existing Km 71/000) to Km 107+091 (Existing Km 107/068) on EPC Mode in the state of Tamil Nadu under NHDP Phase-V - Joint inspection for preparation of Memorandum - reg. | With reference to your request for joint inspection and preparation of Joint Memorandum vide letter dated S1.No.2 cited above, we would like to inform you that our team will be available for joint inspection for preparation of memorandum from 1% January, 2019 to 3 January, 2019. Kindly confirm your convenience to make necessary arrangements. We look forward to your response. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Memorandum and Appendix | Contractor's Obligations | be available for joint inspection for preparation of memorandum from 1st January, 2019 to January, 2019. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km.71+015 (Existing Km 71/000) to Km 107+091 (Existing Km 107/068) on EPC Mode in the state of Tamil Nadu under NHDP Phase-V - Joint inspection for preparation of Memorandum - reg. | With reference to your request for joint inspection and preparation of Joint Memorandum vide letter dated S1.No.2 cited above, we would like to inform you that our team will be available for joint inspection for preparation of memorandum from 1% January, 2019 to 3 January, 2019. Kindly confirm your convenience to make necessary arrangements. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Memorandum and Appendix | Authority's Obligations | be available for joint inspection for preparation of memorandum from 1st January, 2019 to January, 2019. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km.71+015 (Existing Km 71/000) to Km 107+091 (Existing Km 107/068) on EPC Mode in the state of Tamil Nadu under NHDP Phase-V - Joint inspection for preparation of Memorandum - reg. | With reference to your request for joint inspection and preparation of Joint Memorandum vide letter dated S1.No.2 cited above, we would like to inform you that our team will be available for joint inspection for preparation of memorandum from 1% January, 2019 to 3 January, 2019. Kindly confirm your convenience to make necessary arrangements. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Memorandum and Appendix | Authority's Obligations | be available for joint inspection for preparation of memorandum from 1st January, 2019 to January, 2019. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km.71+015 (Existing Km 71/000) to Km 107+091 (Existing Km 107/068) on EPC Mode in the state of Tamil Nadu under NHDP Phase-V - Joint inspection for preparation of Memorandum - reg. | Please note that With reference to your request for joint inspection and preparation of Joint Memorandum vide letter dated S1.No.2 cited above, we would like to inform you that our team will be available for joint inspection for preparation of memorandum from 1% January, 2019 to 3 January, 2019. Kindly confirm your convenience to make necessary arrangements. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Memorandum and Appendix | Appointed Date | be available for joint inspection for preparation of memorandum from 1st January, 2019 to January, 2019. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km.71+015 (Existing Km 71/000) to Km 107+091 (Existing Km 107/068) on EPC Mode in the state of Tamil Nadu under NHDP Phase-V - Joint inspection for preparation of Memorandum - reg. | With reference to your request for joint inspection and preparation of Joint Memorandum vide letter dated S1.No.2 cited above, we would like to inform you that our team will be available for joint inspection for preparation of memorandum from 1% January, 2019 to 3 January, 2019. Kindly confirm your convenience to make necessary arrangements. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Memorandum and Appendix | Appointed Date | be available for joint inspection for preparation of memorandum from 1st January, 2019 to January, 2019. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km.71+015 (Existing Km 71/000) to Km 107+091 (Existing Km 107/068) on EPC Mode in the state of Tamil Nadu under NHDP Phase-V - Joint inspection for preparation of Memorandum - reg. | We hereby confirm that With reference to your request for joint inspection and preparation of Joint Memorandum vide letter dated S1.No.2 cited above, we would like to inform you that our team will be available for joint inspection for preparation of memorandum from 1% January, 2019 to 3 January, 2019. Kindly confirm your convenience to make necessary arrangements. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Change of scope proposal | Change of Scope; EoT; Dispute Resolution; Payments | In view of the above, as per the NHAI Policy guidelines and based on the heavy vehicular traffic volume between the two metropolitan cities like Chennai & Bangaluru, considering a separate lane and all aspects Authority Engineer has an opinion to construct minimum 14 numbers of new toll lanes as per the above said circulate is required at toll plaza location and Change of Scope (COS) may be submitted by the Contractor as per the provisions of Contract Agreement. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/Lot-11/20220217_AE_SPK_883-Construction of Toll Plaza at Chennasamudram Village Ch. Km. 104+917.pdf | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajapet from km 71.015 to107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode. - Construction of Toll Plaza at Chennasamudram Village Ch. Km. 104+917 - Reg. | This has reference to the meeting held in NHAI Regional Office, Chennai regarding construction of number of lanes at toll plaza location wherein the discussion held under the Chairmanship of Chief General Manager cum Regional Officer, Chennai, in this regards. “After the implementation of 100% ETC and upcoming parallel road of Bangalore - Chennai Expressway 24 number of lanes at toll plaza may not be required. Therefore, RO shall analyze the actual requirement of toll lanes and retrofit the same with in ROW. If, required staggered toll plaza may be proposed to avoid further land acquisition”. As per the directions provided by the Competent Authority, Authority Engineer has calculated required number of toll lanes to be constructed as toll per location as accordance to the NHAI Policy Circular no. 17.5.82 dated 24.05.2021 and submits our comments/recommendations for concurrence/approvals. Authority Engineer is considered two traffic reports i.e. One is Traffic survey report prepared/submitted by the Contractor and other one is traffic count report received from the existing toll plaza for calculating number of lanes at toll plaza location. Authority Engineer is calculated number of toll lanes in accordance to the NHAI Policy Circular No. 17.5.82 dated 24.05.2021 for projected traffic of 10 years and submits to the Competent Authority. (A) Number of lanes at toll plaza as per traffic survey report provided by the Contractor: The Contractor has conducted three days traffic survey from 03.09.2019 to 06.09.2019 and on the basis of traffic survey Average Daily Traffic (ADT) count is 21,244 numbers. | FALSE | real_data
Change of scope proposal | Change of Scope; EoT; Dispute Resolution; Payments | In view of the above, the Authority Engineer hereby recommends the Change of Scope-02 construction of 14 lane Toll Plaza in place of 24 Lane Toll plaza as per NHAI Circular No.17.5.82 dated 24.05.2021, amounting to Rs.(-)39,40,20,433/-. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/Lot-11/20220831_AE_PD_19060_Change of Scope proposal no 2 for Chennasamudram toll plaza @ Km.104956.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode — Change of Scope No. 02 proposal for Toll Plaza at km 104+956 - Reg. | Dear Sir, In reference to the above noted subject and letter under reference (26), Contractor submitted the Change of Scope proposal with drawing for construction of 14(7+7) lane Toll plaza in place of 24 lane toll plaza due to land issue at proposed Toll plaza location at Km 104+917, amounting to Rs. (-)4,98,20,340/- for review and recommendation to the Authority Engineer. According to the above, it is submitted that Contract Agreement vide ANNEXURE-1, SCHEDULE —C Project Facilities Para 2.1 “As per NHAI policy matter the number of Toll Lanes four times the number of lanes for which the highway has been designed accordingly existing Toll Plaza shall be modified/ widened to 24-Lane Toll Plaza. Other facilities on Toll Plaza shall be constructed as per Specifications mentioned in Scheduled —D. the Toll Plaza shall be provided with fencing for adequate length on all four sides for the safety and access control”. It is well aware that the required land for construction of 12+12 lane Toll Plaza is not available at the location. Hence, NHAI initiated the process for acquiring additional land to accommodate the proposed toll plaza. But the land acquisition process stuck in Hon’ble High Court, thus acquisition procedure was got delayed. Meanwhile, in light of NHAI Policy Circular no. 15.5.82 dated 24% May 2021. 14 lanes Toll Plaza as per available ROW is proposed by the contractor. This 14 lane Toll Plaza is sufficient as per peak hour traffic. Accordingly, Contractor’s proposed for the Negative Change of Scope-2 towards the reduction of works in Toll plaza. The same was reviewed by Authority’s Engineer and following is being submitted herewith; As per schedule C Clause 2.1 of Contract Agreement, 24 lanes Toll Plaza with fencing on all four side is provisioned. However, due to land issue and to follow the NHAI Policy Circular no. 15.5.82 dated 24" May 2021, 14 lanes Toll Plaza is proposed by the contractor. As per the traffic projection, 14 lane (7+7) Toll Plaza suffice the traffic requirement as per the policy guidelines. It is submitted that the 10 lane Toll Plaza is existed with flexible pavement. However, Contractor consider rehabilitation/strengthening of existing Bituminous surface and proposed PQC/DLC in widening portion. However, as per schedule C Clause 2.1 of Contract Agreement, existing Toll Plaza shall be modified/widened to 24 lanes and also as per Schedule B clause 6.9, Rigid pavement at Toll plaza is provisioned from Km 104+230 to km 105+630, that is for 1400m length. Accordingly, widening of GSB and Subgrade and full width DILC and PQC is being considered in this COS. | FALSE | real_data
Change of scope proposal | Change of Scope | It is hereby informed that COS proposals has to be submitted without any delay for scrutiny | /Users/hareeshkb/GenAIWork/krishna/NewCategories/Lot-11/20221124_AE_SPK_1194_Change of Scope No.2 proposal for Toll Plaza at Chennasamudram – Confirmation of (8+8) Total 16 Toll lanes requested.pdf | Change of Scope No.2 proposal for Toll Plaza at Chennasamudram — Confirmation of (8+8) Total 16 Toll lanes requested- Reg. | Dear Sir, W.r.t the above said references regarding” Change of Scope No.2 proposal for Toll Plaza at Chennasamudram — Confirmation of (8+8) Total 16 Toll lanes requested” our observations/comments are as under: 4. As mentioned vide point No.3 vide above said reference No.3 in the office of the RO Chennai it was discussed and opted to-look in to the possibilities of 8+8 Toll lane constructions at the Chennasamudram Toll Plaza by the RO Chennai & PD Kancheeepuram in the meeting itself with in the availability of land and asked to submit the revised cost estimate by 02.11.2022. 2. Based on the discussions a line diagram with 8+8 lane possibility was checked there itself (In RO Chennai Office) and planned to plot the same at site for confirmation purpose along with finalizing of quantities for COS proposals scrutiny. 3. A broad marking of the TP was done and the same was inspected (in presence of your Project Manager & the under signed) by the RO Chennai at site on 09.11.2022 along with the PD Kancheepuram 4. Since the new proposal was suiting with in the available land RO Chennai has expressed his pleasure and asked to submit the COS proposals & commence the works accordingly considering the reduction in Scope of Works as compared to the CA. 5. But it is unfortunate to receive a communication from your end after a lapse of 10 days for confirmation of “Number of Toll Lanes” through an email on 19.11.2022 at 06.06 PM which is nothing but prolonging the issue instead of submission of COS proposals as directed by the RO Chennai. Further it may be noted that till date this office has not received any Hard Copy of the said communicaticn. | FALSE | real_data
Change of scope proposal | Change of Scope; EoT; Dispute Resolution; Payments | These proposals were discussed in length at several meetings and asked to submit the proposals. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-6/20200526_AE_SPK_322_Extension of continuous service roads and Underpasses in Ranipet and Kanchipuram Districts Zone.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode — Extension of continuous service roads and Underpasses in Ranipet and Kanchipuram Districts Zone - Reg. | With reference to the above-mentioned correspondences relating to references/requests from Hon'ble Member of Parliament Shri G. Selvam, Ranipet & Kanchipuram District Collector's and Local Residents from Damal Lake to provide additional facilities in the ongoing package Works which were reproduced as below, the necessary proposals are yet to be received from your end. Shri G. Selvam Hon'ble Member of Parliament: Provision of making an underpass along with fly over at Thiruppukuzhi and Musaravakkam considering local people movement to other side of the Carriage way for regular activities such as Schools, Hospital and Temple District Collector Ranipet: Requesting to make a continuous service road provision in the Ranipet District stretch of the package road. Further it is requested to provide three underpasses at Villages namely Avalur, Sirukarumbur & Bhagavali to avoid any accident. District collector Kanchipuram: The Kanchipuram district Collector made a request to make a continuous provision for service road. This will help in distributing the traffic between Main Carriageway and Service roads which will avoid accidents. Damal Lake village residents: Vide their representation the Damal lake villagers has requested to provide an underpass to cross the highway for Agricultural activity purpose and to reach the Burial ground. These proposals were discussed in length at several meetings and asked to submit the proposals. During the review meeting with Member (Technical), NHAI in New Delhi on March 04, 2020, the same proposals were discussed and asked to submit with in fifteen days. Further to the above the Project Director during his site visits on 15" & 22°° of this month again reviewed the status/requirement of the said Works. As considerable time has been lapsed, you are hereby once again asked to submit the proposals at the earliest for verification and onward processing. Delay in this regard, would be considered in the part of the Contractor. Your early action is appreciated. | FALSE | real_data
Change of scope proposal | Change of Scope; EoT; Dispute Resolution; Payments | Considerable time has been elapsed, you are hereby once again asked to submit the proposal at the earliest | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-6/20200526_AE_SPK_322_Extension of continuous service roads and Underpasses in Ranipet and Kanchipuram Districts Zone.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode — Extension of continuous service roads and Underpasses in Ranipet and Kanchipuram Districts Zone - Reg. | With reference to the above-mentioned correspondences relating to references/requests from Hon'ble Member of Parliament Shri G. Selvam, Ranipet & Kanchipuram District Collector's and Local Residents from Damal Lake to provide additional facilities in the ongoing package Works which were reproduced as below, the necessary proposals are yet to be received from your end. Shri G. Selvam Hon'ble Member of Parliament: Provision of making an underpass along with fly over at Thiruppukuzhi and Musaravakkam considering local people movement to other side of the Carriage way for regular activities such as Schools, Hospital and Temple District Collector Ranipet: Requesting to make a continuous service road provision in the Ranipet District stretch of the package road. Further it is requested to provide three underpasses at Villages namely Avalur, Sirukarumbur & Bhagavali to avoid any accident. District collector Kanchipuram: The Kanchipuram district Collector made a request to make a continuous provision for service road. This will help in distributing the traffic between Main Carriageway and Service roads which will avoid accidents. Damal Lake village residents: Vide their representation the Damal lake villagers has requested to provide an underpass to cross the highway for Agricultural activity purpose and to reach the Burial ground. These proposals were discussed in length at several meetings and asked to submit the proposals. During the review meeting with Member (Technical), NHAI in New Delhi on March 04, 2020, the same proposals were discussed and asked to submit with in fifteen days. Further to the above the Project Director during his site visits on 15" & 22°° of this month again reviewed the status/requirement of the said Works. As considerable time has been lapsed, you are hereby once again asked to submit the proposals at the earliest for verification and onward processing. Delay in this regard, would be considered in the part of the Contractor. Your early action is appreciated. | FALSE | real_data
Change of scope proposal | Change of Scope; EoT; Dispute Resolution; Payments | We are herewith submitting the Tentative Quantity (BOQ) and Cost estimate proposals along with drawings under COS as per Sub Clause 13.1.1 of article 13 of Contract Agreement | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-6/20200703_SPK_IE_94_Submission of CoS Proposal.pdf | Submission of Change of Scope Proposal as per Article 13 of Contract Agreement - Reg. | This is in reference to the discussions with your goodself and the various requests received vide above cited letters from District Collectors of Kanchipuram & Ranipet Districts, Hon’ble Member of Parliament, Residents of Dhamal Village of Kanchipuram district and residents of Avalur Village Sirukarumbur Village & Bagaveli Village of Ranipet district for additional works i.e. Service Road and underpasses in various locations on the Project Highway. The additional works requested as above for the Project Highway are given below: a) Additional Service Road for Kanchipuram District & Ranipet District stretch: The above said project stretch covers a length of 29.786Km of Service Road (BHS) out of total project length of 36.076Km. As per requests of District Administration of Kanchipuram & Ranipet district for continuous service road, the details of Additional Service Road are as follows. Kanchipuram District 1. Km 75+580 to Km 76+240 (Length-660m) 2. Km 77+400 to Km 78+100 (Length-700m) 3. Km 83+340 to Km 84+600 (Length -1260m) Total Length - 2.62 Km Ranipet District 1. Km 88+160 to Km 88+560 (Length -400m) 2. Km 90+700 to Km 91+660 (Length -960m) 3. Km 91+660 to Km 92+350 (Length -690m) 4. Km 94+640 to Km 94+860 (Length -220m) Total Length - 2.27 Km In the above provision of SR, the existing cross drainage works shall also to be widened. b) Providing Underpass i. Km. 80+060 (Thirupukuzhi - Blackspot Location) Shri. G.Selvam Hon’ble Member of Parliament submitted request to Shri. Nitin Gatkari — Hon’ble Minister of Road Transport and Highways for providing underpass along with flyover at Musaravakkam Ch. 79+860 and Thirupukuzhi Ch. 80+060 considering the local people movement to other side of the carriageway for regular activities such as Schools, Hospital and Temple. In addition to the above, it is pertinent to note that Thirupukuzhi Junction falls under MoRT&H identified Black spot location. ii. Km. 84+032 (Dhamal West) Residents of Dhamal Village located on the LHS of the MCW submitted their request to provide a underpass at Km. 84+050 to cross the project highway from Dhamal village to burial ground on RHS of Project Corridor and also, for the purpose of their daily agricultural activities. iii, Km. 89+1324(Avalur village), Km. 94+090(Sirukarumbur village), Km.102+134 (Bagaveli) of Ranipet district Ranipet District Calligeior & local pubge requested to jsxomlels Salettosrel Deere ss Highway. | FALSE | real_data
Change of scope proposal | Change of Scope; EoT; Dispute Resolution; Payments | Further we would like to intimate that since the construction of above mentioned works under positive change of scope, the execution of the same requires time extension and the same shall be taken into account | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-6/20200703_SPK_IE_94_Submission of CoS Proposal.pdf | Submission of Change of Scope Proposal as per Article 13 of Contract Agreement - Reg. | This is in reference to the discussions with your goodself and the various requests received vide above cited letters from District Collectors of Kanchipuram & Ranipet Districts, Hon’ble Member of Parliament, Residents of Dhamal Village of Kanchipuram district and residents of Avalur Village Sirukarumbur Village & Bagaveli Village of Ranipet district for additional works i.e. Service Road and underpasses in various locations on the Project Highway. The additional works requested as above for the Project Highway are given below: a) Additional Service Road for Kanchipuram District & Ranipet District stretch: The above said project stretch covers a length of 29.786Km of Service Road (BHS) out of total project length of 36.076Km. As per requests of District Administration of Kanchipuram & Ranipet district for continuous service road, the details of Additional Service Road are as follows. Kanchipuram District 1. Km 75+580 to Km 76+240 (Length-660m) 2. Km 77+400 to Km 78+100 (Length-700m) 3. Km 83+340 to Km 84+600 (Length -1260m) Total Length - 2.62 Km Ranipet District 1. Km 88+160 to Km 88+560 (Length -400m) 2. Km 90+700 to Km 91+660 (Length -960m) 3. Km 91+660 to Km 92+350 (Length -690m) 4. Km 94+640 to Km 94+860 (Length -220m) Total Length - 2.27 Km In the above provision of SR, the existing cross drainage works shall also to be widened. b) Providing Underpass i. Km. 80+060 (Thirupukuzhi - Blackspot Location) Shri. G.Selvam Hon’ble Member of Parliament submitted request to Shri. Nitin Gatkari — Hon’ble Minister of Road Transport and Highways for providing underpass along with flyover at Musaravakkam Ch. 79+860 and Thirupukuzhi Ch. 80+060 considering the local people movement to other side of the carriageway for regular activities such as Schools, Hospital and Temple. In addition to the above, it is pertinent to note that Thirupukuzhi Junction falls under MoRT&H identified Black spot location. ii. Km. 84+032 (Dhamal West) Residents of Dhamal Village located on the LHS of the MCW submitted their request to provide a underpass at Km. 84+050 to cross the project highway from Dhamal village to burial ground on RHS of Project Corridor and also, for the purpose of their daily agricultural activities. iii, Km. 89+1324(Avalur village), Km. 94+090(Sirukarumbur village), Km.102+134 (Bagaveli) of Ranipet district Ranipet District Calligeior & local pubge requested to jsxomlels Salettosrel Deere ss Highway. | FALSE | real_data
Change of scope proposal | Change of Scope; EoT; Dispute Resolution; Payments | We are herewith submitting the Tentative Quantity (BOQ) and Cost estimate proposals along with drawings under COS as per Sub Clause 13.1.1 of article 13 of Contract Agreement | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-6/20200703_SPK_IE_94_Submission of CoS Proposal.pdf | Submission of Change of Scope Proposal as per Article 13 of Contract Agreement - Reg. | This is in reference to the discussions with your goodself and the various requests received vide above cited letters from District Collectors of Kanchipuram & Ranipet Districts, Hon’ble Member of Parliament, Residents of Dhamal Village of Kanchipuram district and residents of Avalur Village Sirukarumbur Village & Bagaveli Village of Ranipet district for additional works i.e. Service Road and underpasses in various locations on the Project Highway. The additional works requested as above for the Project Highway are given below: a) Additional Service Road for Kanchipuram District & Ranipet District stretch: The above said project stretch covers a length of 29.786Km of Service Road (BHS) out of total project length of 36.076Km. As per requests of District Administration of Kanchipuram & Ranipet district for continuous service road, the details of Additional Service Road are as follows. Kanchipuram District 1. Km 75+580 to Km 76+240 (Length-660m) 2. Km 77+400 to Km 78+100 (Length-700m) 3. Km 83+340 to Km 84+600 (Length -1260m) Total Length - 2.62 Km Ranipet District 1. Km 88+160 to Km 88+560 (Length -400m) 2. Km 90+700 to Km 91+660 (Length -960m) 3. Km 91+660 to Km 92+350 (Length -690m) 4. Km 94+640 to Km 94+860 (Length -220m) Total Length - 2.27 Km In the above provision of SR, the existing cross drainage works shall also to be widened. b) Providing Underpass i. Km. 80+060 (Thirupukuzhi - Blackspot Location) Shri. G.Selvam Hon’ble Member of Parliament submitted request to Shri. Nitin Gatkari — Hon’ble Minister of Road Transport and Highways for providing underpass along with flyover at Musaravakkam Ch. 79+860 and Thirupukuzhi Ch. 80+060 considering the local people movement to other side of the carriageway for regular activities such as Schools, Hospital and Temple. In addition to the above, it is pertinent to note that Thirupukuzhi Junction falls under MoRT&H identified Black spot location. ii. Km. 84+032 (Dhamal West) Residents of Dhamal Village located on the LHS of the MCW submitted their request to provide a underpass at Km. 84+050 to cross the project highway from Dhamal village to burial ground on RHS of Project Corridor and also, for the purpose of their daily agricultural activities. iii, Km. 89+1324(Avalur village), Km. 94+090(Sirukarumbur village), Km.102+134 (Bagaveli) of Ranipet district Ranipet District Calligeior & local pubge requested to jsxomlels Salettosrel Deere ss Highway. | FALSE | real_data
Change of scope proposal | Change of Scope; EoT; Dispute Resolution; Payments | Considering the change in scope of work you are hereby asked to submit the proposal with necessary change in quantum of work & cost | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-6/20200722_AE_SPK_364 - Submission of Toll Plaza Lay out.pdf | Submission of Toll Plaza Lay out - Reg. | Having gone through the above said Reference relating to the construction of Toll Plaza, our comments are as under for your compliance: 1. Considering the land constraint as discussed with the Authority, the submitted 16 ETC lanes (8+8) at toll plaza reviewed by the A.E. within the ROW is found O.K. 2. The plan and drawing of toll Plaza as well as the Pavement Crust composition are found as per the codal provisions and these 16 ETC lanes are sufficient for the Peak hour traffic to a design period of 20 years. 3. However as per the Contract Agreement, 24 lane Toll Plaza is to be provided. Hence considering the change in scope of work you are hereby asked to submit the proposal with necessary changes in quantum of work & cost for obtaining proper approvals from the Competent Authority. This is for your information and necessary action at the earliest. | FALSE | real_data
Change of scope proposal | Change of Scope; EoT; Dispute Resolution; Payments | We are hereby re-submitting herewith revised COS (Change of Scope) proposal as per Article-13. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-6/20210623_SPK_AE_084_Submission of proposal for COS works.pdf | Re-Submission of Change of Scope Proposal as per Article -13 of Contract Agreement - Reg. | This is in reference to your letters (6), (7) and (8) we are herewith re-submitting the revised COS (Change of scope) Proposal as per Article-13 of Contract Agreement incorporating all the observations referred as per the letter cited at (10); which are as follows: The additional works requested as above for the Project Highway are given below: a) Additional Service Road for Kanchipuram District & Ranipet District stretch (1.980 Km): The above said project stretch covers a length of 29.786Km of Service Road (BHS) out of total project length of 36.076Km. As per the requests of District Administration of Kanchipuram & Ranipet district for continuous service road, the details of Additional Service Road are as follows: Kanchipuram District 1. Km 75+580 to Km 76+240 (Length-660m) 2. Km 77+400 to Km 78+100 (Length-700m) Total Length - 1.360 Km Ranipet District 1. Km 88+160 to Km 88+560 (Length -400m) 2. Km 94+640 to Km 94+860 (Length -220m) Total Length - 0.620 Km Additional works due to provision of additional Service Road as mentioned above, the existing cross drainage works like Pipe Culverts (11 Nos.), Box Culverts (3 Nos.) has to be widened and the same quantities considered in CoS. b) Providing Underpass i. Km. 80+060 (Thirupukuzhi - Blackspot Location Id. No TN(O2) -146) Shri. G.Selvam Hon’ble Member of Parliament submitted request to Shri. Nitin Gadkari — Hon’ble Minister of Road Transport and Highways for providing underpass along with flyover at Musaravakkam Ch. 79+860 and Thirupukuzhi Ch. 80+060 considering the local people movement to other side of the carriageway for regular activities such as Schools, Hospital and Temple. In addition to the above, it is pertinent to note that Thirupukuzhi Junction falls under MoRT&H identified Black spot location. As per the survey conducted, accidents occur frequently at this location. Local people used to cross the Road frequently, since there is village Thirupukuzhi. | FALSE | real_data
Change of scope proposal | Change of Scope; EoT; Dispute Resolution; Payments | Further we would like to intimate that since the construction of above mentioned works under positive change of scope, the execution of the same requires time extension and the same shall be taken into account | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-6/20210623_SPK_AE_084_Submission of proposal for COS works.pdf | Re-Submission of Change of Scope Proposal as per Article -13 of Contract Agreement - Reg. | This is in reference to your letters (6), (7) and (8) we are herewith re-submitting the revised COS (Change of scope) Proposal as per Article-13 of Contract Agreement incorporating all the observations referred as per the letter cited at (10); which are as follows: The additional works requested as above for the Project Highway are given below: a) Additional Service Road for Kanchipuram District & Ranipet District stretch (1.980 Km): The above said project stretch covers a length of 29.786Km of Service Road (BHS) out of total project length of 36.076Km. As per the requests of District Administration of Kanchipuram & Ranipet district for continuous service road, the details of Additional Service Road are as follows: Kanchipuram District 1. Km 75+580 to Km 76+240 (Length-660m) 2. Km 77+400 to Km 78+100 (Length-700m) Total Length - 1.360 Km Ranipet District 1. Km 88+160 to Km 88+560 (Length -400m) 2. Km 94+640 to Km 94+860 (Length -220m) Total Length - 0.620 Km Additional works due to provision of additional Service Road as mentioned above, the existing cross drainage works like Pipe Culverts (11 Nos.), Box Culverts (3 Nos.) has to be widened and the same quantities considered in CoS. b) Providing Underpass i. Km. 80+060 (Thirupukuzhi - Blackspot Location Id. No TN(O2) -146) Shri. G.Selvam Hon’ble Member of Parliament submitted request to Shri. Nitin Gadkari — Hon’ble Minister of Road Transport and Highways for providing underpass along with flyover at Musaravakkam Ch. 79+860 and Thirupukuzhi Ch. 80+060 considering the local people movement to other side of the carriageway for regular activities such as Schools, Hospital and Temple. In addition to the above, it is pertinent to note that Thirupukuzhi Junction falls under MoRT&H identified Black spot location. As per the survey conducted, accidents occur frequently at this location. Local people used to cross the Road frequently, since there is village Thirupukuzhi. | FALSE | real_data
Change of scope proposal | Change of Scope; EoT; Dispute Resolution; Payments | We are herewith submitting the revised cost estimate for user fee Toll Plaza with 16 Lanes | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-6/20230529_SPK_AE_268_Submission of Revised Cost Estimates for TOLL PLAZA 16 lanes.pdf | Submission of Revised Cost Estimate for Proposed Toll Plaza/User Fee plaza - Request for early COS Approval of Proposed Toll /User Fee Plaza with 16 lanes at Km.104+981 - Reg. | Dear Sir, In continuation of our letter cited at ref (10) & from ref (11 to 18) above, we are herewith submitting the revised cost estimate for User Fee Plaza with 16 lanes at Km.104+981 based on the review and concurrence of the drawings by the Authority Engineer. Detailed revised cost estimates are herewith enclosed as Annexures. We hereby request your good self to review and recommend the cost estimate for approval by the Competent Authority. | FALSE | real_data
Change of scope proposal | Change of Scope; Dispute Resolution; Payments | As the original proposal which was consented is for 1.5m width and current proposal is for 2.5m width, thus the Contractor is now requested to issue a COS notice to proceed with the works. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/Lot-12/20220915-AE_PD_ storm water drain having width of 2.5m in lieu of 1.5 m from Km 98+214 to 98+374 (160m) on LHS- Diversion of the storm water in to the PWD Canal – request to issue as COS (+) for t.pdf | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajapet from km 71.015 to107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode— Mandatory requirement of storm water drain having width of 2.5m in lieu of 1.5 m from Km 98+214 to 98+374 (160m) on LHS- Diversion of the storm water in to the PWD Canal - request to issue as COS (+) for this additional scope of Work in accordance with Sub Clause 13.2.1 of Article 13 of Contract Agreement -Reg. | From the above references, it can be understood that the Contractor is progressing the works of Service Road, Culvert & Darin in between Ch. Km. 98+196 to 98+373. In this regard, our submission is as follows. As per CA, there are two existing slab culverts at Km 98.196 & Km 98.373 which were proposed to be reconstructed. i) Upstream and downstream of these culverts are RHS and LHS respectively. ii) The storm water which is collecting on RHS side of 98+373 culvert is passing to the LHS and continued to a length of 158m in the form of a kaccha drain in the proposed LSR road alignment. Then the flow will deviate to the ROW @ 98+215 and merging with the drain iii) Hence the existing drain is passing from Ch. Km. 98+373 to Km 98.215 which was owned by State PWD, to cater the water from slab culvert, is necessary to shift the kaccha drain beyond the Project Works (Service Road +drain) or beyond the NHAI ROW. The same was informed vide our letter no 976 dated 27.04.2022. iv) The Contractor vide its letter cited 1st had submitted covered drain in this location i.e. collecting the water from highway and dispersion/merging the same with the drain @ 98+215 in parallel to the proposed service road alignment. v) As proposed by the Contractor, the existing kaccha drain can easily be shifted away from the covered drain so that there will not be problem with the water accumulated from outside of ROW on LHS. vi) After verifying the Contractor's proposals as there is no ambiguity and the quantum of discharge is maintained through the project drain without any hindrance or accumulation of water the same is being intimated to the Authority vide our letter No. 976 dated 27th April 2022. vii) Accordingly, the Contractor had commenced covered drain & service road works. However, the Contractor reported that during the execution of works, the PWD Asst. Engineer visited the site and informed to stop the works stating that an NOC is to be obtained from the PWD depot. The Contractor staff approached the higher level PWD officials and it is suggested by the PWD to construct a 2.5m width drain instead of 1.5m drain for which they will not insist for NOC or else instructed orally to stop the works. viii) As the Works are getting delayed the Contractor had accepted to construct a drain having 2.5m width as per PWD’s instruction and accordingly proposed to construct a drain having width of 2.5 m in this location. As the original proposal which was consented is for 1.5 m width and current proposal is for 2.5 m width, thus the Contractor is now requested to issue a COS notice to proceed with the works. ix) Based the hydrology, we have already consented the drain with a width of 1.50 m vide our letter No. 976 dated 27th July2022. x) But, the request of PWD involves financial implication which burdens the Authority, we request the Authority to convey its decision under Clause 13.1.3 of the Agreement. This is for your information and necessary actions. | FALSE | real_data
Change of scope proposal | Change of Scope; EoT; Dispute Resolution; Payments | the following observations after having the discussion with TL of Consultant on 12.04.2021. In view of the above, it is requested to submit the compliance at the earliest. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/Lot-12/20230628_RO_CGM_1866_Approval of COS 2 Toll plaza.pdf | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet Section of NH-4 from Km 71/015 to Km 107/091 in the State of Tamilnadu under residual NHDP (Phase - V) under Bharathmala Pariyojana on EPC Mode-Change of Scope Proposal 02 - Reg. | This has reference to the PD letter cited 5"cited, thereby submitting the Change of Scope Proposal towards User Fee Plaza with 16 lanes Chennasamudram User Fee Plaza at Km104+981. The work of Six laning of Karaipettai to Walajahpet section of NH-4 from Km 71/015 to Km 107/091 in the State of Tamil Nadu under NHDP Phase -V. has been awarded to M/S SPK & Co. The Salient features of the contract is as below: - Total Length Date of Agreement 15.10.2018 Mode of Implementation EPC Duration of Contract ¦ Construction Period 24 Months (730 Days) O&M Period/DLP Period 48 Months (DLP Period) ‘Appointed Date Schedule date of Construction Settlement Agreement signed on 07.01.2023 Date of completion as per Settlement agreement Progress as on 23.6.2023 64.70% Ss NHAI HQs vide letter cited 2"“above, accorded In-Principle approval for the Change of Scope Proposal for an amount of Rs.39,85,58,903/-for certain additional works. The Final CoS for the same (including the effect of GST 18% revision) has been finalized for Rs.41,07,41,491/- by RO. There is an existing User Fee Plaza at Chennasamudram at Km 104+917 with 10 lanes and is functional. As per the EPC Contract Agreement, the Contractor is supposed to Construct 24 lanes (12+12) User Fee Plaza. However, NHAI HQ’s has issued Policy Guidelines vide Policy Guideline No. NHAI/Policy Guidelines/Management_ of Plaza/2021/Policy Circular No.17.5.82 dated 24.05.2021; on the Amendments in the Provisions of Toll Plaza consequent upon implementation of Electronic Toll Collection (ETC)/FASTag on all lanes, wherein it was mentioned that “In cases where construction of Toll Plaza has not yet started, the Toll Plaza be re-planned as per the above guidelines through COS and the land already acquired be explored for effective utilization”. Subsequently, the Competent Authority, NHAI HQs_ vide letter NHAI/Tech/TN/11012/Kar-Wal/EPC/03/2018/E.101723/2944 dated 24.09.2021 while according approval for Extension of time for the subject project upto 19.12.2022, stated that; “Due to implementation of 100% ETC and upcoming parallel road of Bangalore - Chennai Expressway 24 number of lanes at toll plaza may not be required. Therefore, RO shall analyze the actual requirement of toll lanes and retrofit the same with in ROW. If, required staggered toll plaza may be proposed to avoid further land acquisition”. In this context, the Contractor was requested to explore the feasibility of providing 16 lanes (8+8) within the available ROW at Chennasamudram User Fee Plaza at Km 104+917. Accordingly, the EPC Contractor vide reference cited 3" above, submitted the Change of Scope Proposal at Km 104+981 (Staggered Plaza) amounting to Rs.3,81,82,081/- there by considering the positive and negative scope of work due to the Change in User Fee Plaza Lane configuration. PD has reviewed the proposal in consultation with IE and accordingly has submitted (-) CoS for Rs (-) 6,33,73,571/- incorporating the following scope of works. (a) Toll Plaza. Construction of 8+8 lane (7 ETC+1Manual) staggered toll lane system with Foot over Bridge as per provisions of NHAI Guidelines 17.5.82 dated 24.05.2021 at Km 104+981. Relevant drawings is enclosed. The existing Toll Plaza at Km 104+917 will be dismantled. The cost effect of construction of new toll plaza, dismantling are considered as (+) CoS and the provisions in the CA for construction of 24 lane toll plaza has been considered as (-) CoS. Service Road.According to Original Scope, 24 lane Toll plaza is to be constructed from Km. 104+230 to 105+630 (1400 mtr) and service roads provision is not made therein. But, due to modification of Toll Lanes to 8+8 system with staggered toll lane system, the proposed Toll Plaza starts at | FALSE | real_data
Change of scope proposal | Change of Scope; EoT; Dispute Resolution; Payments | The respective EPC Contractors were not deployed the Cranes, Route Patrolling vehicles, Ambulances saying that such provision is not existing as per the Agreements during construction period. In view of the above approval for competent Authority for the following is requested. (i) Approval for Change of Scope to the respective EPC Contractors for the said two stretches from Km.107.091 to Km.71.015 & from Km.71.015 to Km.37.000 for providing incidental Management Vehicles | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/Lot-12/941 _27052019_Non maintenance of route patrolling vehicles.pdf | NHAI, PIU - Krishnagiri - Six Laning of Karaipettai to Walajhapet section of NH-4 (New NH-48) from km.71.015 to km.107.091 & Karaipettai to Sriperumbudur Section from Km 71.015 to Km 37.000 in the State of Tamil Nadu under NHDP Phase-V under EPC Mode-Maintenance during Construction period as per cl 10.4 -Non Mainteance of Route Patrolling Vehicles, Ambulances and Cranes by the EPC Contractors -Reg. | It is to submit that agreements vide reference 3rd & 4th cited is entered for Six Laning of Karaipettai to Walajhapet section of NH-4 (New NH-48) from km.71.015 to km.107.091 & Karaipettai to Sriperumbudur Section from Km 71.015 to Km 37.000 in the State of Tamil Nadu under NHDP Phase-V under EPC Mode. As per Contract Agreements cl 10.4 Maintenance of the stretch during construction period the contractor is responsible for ensuring safe operation of Project Highway - Accordingly the respective EPC Contractors vide reference 1st & 2nd cited were requested to deploy Pick and carry cranes, Route Patrolling vehicles, Ambulances to ensure O&M of the stretch. The respective EPC Contractors were not deployed the Cranes, Route Patrolling vehicles, Ambulances saying that such Provision is not existing as per the Agreements during construction period. NHAI vide Policy circular No 12.19 Dt 20.3.2018 has issued Guidelines on strengthening of Incident Management services being provided across existing Concessions and on not covered stretches. As per Para 5 (d) of the policy guidelines “on the stretches of National Highways which are under construction /under implementation. Further as per para 5(e) of the policy guidelines ” for all other stretches, which are under operation and maintenance by O&M Agencies and no such facility exist in their contract agreement. The similar facilities to be provided @ 50 Km by the O&M agency by providing them a change of scope for which RO are authorised. As per para 5(f) “the new facility to be provided strictly as per the specifications and colour schemes given in Annexure-I by the ROs under OPEX or service model /Rent basis contract usually made for two years. In view of the above, approval of competent authority for the following is requested: (i) Approval of change of scope to the respective EPC Contractors for the said two stretches from Km 107.091 to Km 71.015 & from Km 71.015 to Km 37.000 for providing Incident Management Vehicles duly fitted with GPS/VTS system for two years or till the completion of the project. (ii) The balance stretch from Km 37.000 to Km 13.800 is under DPR for six laning under PIU-Kanchipuram and as the stretch is under tolling and no maintenance contractor is in force and NHAI has the obligation to maintain Incident Management Vehicles. As the stretch is only 23.2 Km and as per Guidelines the Incident Management Vehicles are to be provided at 50 Km length, the respective EPC Contractors may be directed to maintain the Incident Management Vehicles within the limits of 46.5 Km each to avoid separate Incident Management Vehicles as the total length of stretch is only 93 Km including this stretch of 23.5 Km for this stretch under change of scope. Vide Lr No NHAI/11015/181-A/2009/RO Chennai/844 dt 11.3.2019 the RO, Chennai has instructed the PD Krishnagiri to take action on Operation and Maintenance including Incident Management of the stretch from 71.015 to Km 37.000 of NH-4 for a period of 3 months only as per the powers delegated to PD vide NHAI Policy Matters No 9.4.21/2016 dt 28.11.2016. In view of the above request of approval, if the Incident Management Vehicles are approved on change of scope basis to the respective EPC Contractors, this office will take up the emergency works like cleaning of carriageway, filling of potholes, watering of plantation etc in the stretch from Km 37.000 to Km 13.800 under powers delegated to PD. | FALSE | real_data
Change of scope proposal | Change of Scope; EoT; Dispute Resolution; Payments | The Contractor informed that they will send their compliance in a short period | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20201123_AE_SPK_480_Minutes of Monthly Progress review meeting Mom – 08.pdf | Consultancy services for Authority's Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode - Minutes of Monthly Progress review meeting Mom — 08 — Reg. | With respect to the above said reference please find enclosed herewith the Minutes of Meeting Numbered as MoM - 08 held on 21.11.2020 The next meeting will be likely on 23.12.2020 at the Consultants office around 11.00 A.M in Kancheepuram. All the concerned are requested to attend with necessary documents. This is for your information and record. Assuring our best services at all times. | FALSE | real_data
Change of scope proposal | Change of Scope; EoT; Dispute Resolution; Payments | The Consultatnt askd to submit the COS proposals to the propose subway at 106 Km as requeste by the locals for scrutiny and verification. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210302_AE_SPK_569-Minutes of Monthly Progress review meeting Mom – 09.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode. - Minutes of Monthly Progress review meeting Mom — 09 — Reg. | With respect to the above said reference please find enclosed herewith the Minutes of Meeting Numbered as MoM - 09 held on 26.02.2021 The next meeting will be likely on 19 March 2021 at Team Leader office around 11.00 A.M in Kancheepuram. All the concerned are requested to attend with necessary documents. This is for your information and record. Assuring our best services at all times. | FALSE | real_data
Change of scope proposals clarifications | Change of Scope; Dispute Resolution; Payments | despite of asking several times to comply with the observations made on your submittal for the COS proposals. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/Lot-11/20201017_AE_SPK_445-Observations made on Change of Scope proposal submitted as per Article No. 13 of Contract Agreement and Compliance.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode — Observations made on Change of Scope proposal submitted as per Article No. 13 of Contract Agreement and Compliance - Reg. | Dear Sir, It is very unfortunate to note that despite of asking several times to comply the observations made on your submittal for the COS proposals vide above said Ref. No’s 7 & 8 till date there is no response from your end. You are aware that the Project completion date is fast approaching and the submissions relating to COS are getting delayed from your end which is alarming. Hence it has been advised to submit the same for proper verification and for obtaining the necessary approvals from Competent Authority well in advance. This is for your information and necessary action. € ultants Pvt. Ltd., Kar-Wal, Six Lanning Project, Package-ll, Kancheepuram Copy to: 1. The Project Director, NHAI, PIU —- Kancheepuram. 2. H.O.S.A. Infrastructure Consultants Pvt. Ltd. ot No. 7A/1, Sector 142, Noida 201301, +91-120-6148090 www.sainfra.com | FALSE | real_data
Change of scope proposals clarifications | Change of Scope; Dispute Resolution; Payments | During scrutinizing it is observed that the Analysis of Rates has been done based on old edition of MORTH Standard Data Book. There is an error on the calculation of lead for various materials. You are advised to resubmit the Change of Scope duly incorporating the above said observations. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/Lot-11/20201118_AE_SPK_474_Submission of Revised Change of Scope Proposal- Comments.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode — Submission of Revised Change of Scope Proposal- Comments - Reg. | Dear Sir, With regards to the subject cited and reference letter, the revised Change of Scope submitted by you has been verifying at our end. During scrutinizing it is observed that the Analysis of Rates has been done based on old edition of MORTH Standard Data Book. But the MORTH Standard Data Book IInd Edition 2019 being the latest has to be followed for the preparation of Cost Estimate for the Change of Scope. It is also observed that there is an error in the calculation of Lead for various materials. Further the Negative Change of Scope items like Earthen Shoulder, Side Slopes & Earthen Drain, etc. has to be included. Hence you are advised to resubmit the Change of Scope duly incorporating the above said observations. With Regards, Yours faithfull CH Balakrishra Team Leader et ‘Highway Engineer, S.A. Infrastructure Gers utfants Pvt. Ltd., Kar-Wal, Six Lanning Prick Package-ll, Kancheepuram | FALSE | real_data
Change of scope proposals clarifications | Change of Scope; EoT; Dispute Resolution; Payments; Contractor's Obligations | the following observations after having the discussion with TL of Consultant on 12.04.2021. In view of the above, it is requested to submit the compliance at the earliest. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/Lot-11/20210423_PD_AE_1221_Change of Scope Proposal 02.pdf | NHAI - PIU, Kancheepuram - Six laning of Karaipettai to Walajahpet Section of NH-4 from Km 71/015 to Km 107/091 in the State of Tamil Nadu under residual NHDP (Phase — V) under Bharatmala Pariyojana on EPC Mode — Change of Scope Proposal 02 - reg. | With reference to the above, the Deputy General Manager (T), Regional Office, NHAI, Chennai on 23.04.2021 made the following observations after having the discussion with TL of Consultant on 12.04.2021: a) Details of location wise structures proposed in a tabulated manner including details and cost of (-)ve CoS due to the proposals. Format given to AE TL. b) Rate analysis modifications by incorporating the correct labour, machinery inputs (Explained to TL). c) Copies of all correspondences from State Adminstration, PD. d) Detailed plan, profile and drawings of the proposals. e) Time schedule / effect for the proposed CoS. f) Quantities of sub grade, soulder to be rechecked. g) Savings on the items due to the CoS be accounted. 2. In view of the above, it is requested to submit the compliance at the earliest. | FALSE | real_data
Change of scope proposals clarifications | Payments; Dispute Resolution; Change of Scope; EoT | Further, vide letter cited 02nd above, the Contractor raised certain clarifications on the Cost Estimate prepared for In-Principle Approval of change of scope works. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/Lot-11/20211020_PD_AE_3079_Cost estimate for COS review of the same.pdf | NHAI, PIU, Kancheepuram — Six laning of Karaipettai to Walajahpet section of NH-4 (Km 71/015 to Km 107/091) in the State of Tamil Nadu — Clarification sought on the Cost Estimate Prepared for in-Principal Approval of COS - Reg. | This has reference to the letter cited 01st above, where in the Contractor requested for revisiting the approval of Change of Scope works without considering the deduction towards discount of 9.66% and issue a revised COS order. 2. Further, vide letter cited 024 above, the Contractor raised certain clarifications on the Cost Estimate prepared for In-Principle Approval of Change of Scope works. 3. In this regard, the Authority Engineer is requested to examine the above request and to submit a detailed report to this office at the earliest to proceed further. | FALSE | real_data
Change of scope proposals clarifications | Change of Scope; Contractor's Obligations; Dispute Resolution | It is observed in the submitted proposals there is neither technical back up nor any data in finalisation of toll lanes. Hence, based on the above circumstances and considering the discussions held at site, it is hereby requested to resubmit the proper as per IRC 10.5 SP 87 2013. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/Lot-11/20220127_AE_SPK_838-Construction of Toll Plaza at Chennasamudram Village Ch. Km. 104+917.pdf | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajapet from km 71.015 to107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Construction of Toll Plaza at Chennasamudram Village Ch. Km. 104+917 - Reg. | Sir, According to the Contract Agreement vide Annexure — ¦ Schedule “C” para 2.1 Page No. 161 Toll Plaza with 24 lanes has to be constructed at Ch. Km. 104+917 near a village called Chennasamudram. However, considering the up gradation of tolling system through ETC / FASTag Hence the Contractor was communicated accordingly vide above said Ref. No. 7. However, the Contractor through Ref. No. 6 (A hard copy with 8+8 lane system) & Ref. No. 3 (Through e mail dated 13.08.202 with 6+6 lane system) submitted different proposals. It is observed in the submitted Hence based on the above circumstances and considering the discussions held at ste, it is hereby This is for your information and necessary actions please. Thanking You. U iol Kar-Wa + an Rrnior? Six Lane Project : haz "2 fai nvSenior- ghway Engineer, S.A. Infrastructure Consultants Pvt. Ltd., Kar-Wal, Six Lanning Project, Package-ll, Kancheepuram Copy to: 1. The Project Director, NHAI, PIU — Kancheepuram. 2. H.O. S.A. Infrastructure Consultants Pvt. Ltd. | FALSE | real_data
Change of scope proposals clarifications | Change of Scope; Dispute Resolution; Payments; Contractor's Obligations | AE has reviewed the drawings submitted vide Letter No.67 dated 17.03.2022 and the following observations were communicated for compliance. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/Lot-11/20220513_AE_SPK_990_Submission of Toll Plaza Layout Plan.pdf | Consultancy services for Authority's Engineer for Supervision of Six Lanning of Karaipettai to Walajapet from km 71.015 to107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode. - Submission of Toll Plaza Layout Plan - Reg. | Dear Sir,\n\nThrough above said Ref. No.3 AE has sought the in-principle approvals/concurrence for a 7+7 lane Toll Plaza @ Chennasamudram from the Competent Authority. While scrutinizing the proposals the RO NHAI office has asked to submit the cost estimate of the proposals for consideration of cos. Based on that, the cost estimate sent by you through e-mails dated 21.04.2022, 26.04.2022 & 28.04.2022 are found to be incomplete due to lack of required data. Meanwhile AE has reviewed the drawings submitted vide Letter No. 67 dated 17.03.2022 and the following observations were communicated for compliance.\n\n1. Toll Plaza layout.\n\ne Number of Toll Plaza Lane is found in order.\n\ne Location of Static Weigh Bridge (SWB) shall be provided.\n\ne Separate toilet facilities under Swachch Bharat shall be provided near Toll Plaza location along with parking facilities for road users.\n\ne Toll Plaza drainage plan shall be provided.\n\ne Boundary wall shall be provided to cover complete toll plaza complex.\n\ne Contractor shall ensure the width of island i.e., 0.6m is sufficient to install TMS island equipment.\n\n2. Toll Plaza administration building. | FALSE | real_data
Change of scope proposals clarifications | Change of Scope; Dispute Resolution; Payments | Submission of Change of Scope with latest SOR and MORTH, the same has been verified in detail by AE and observations are as follows. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/Lot-11/20220926_AE_SPK_1127_Change of Scope – Submission of Cost Estimate with latest SOR and MORTH..pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode — Change of Scope — Submission of Cost Estimate with latest SOR and MORTH-Reg. | Dear Sir,\n\nWith respect to the above subject and letter as stated in Ref No:(3) regarding submission of Cost Estimate for Change of Scope with latest SOR and MORTH, the same has been verified indetail\n\nby AE and observations are as stated below:\n\n1) Service Roads: In detailed measurements, embankment qty has been considered in the current submission where as in “In principle approval of COS “excavation qty has been considered, please clarify the same with supporting documents.\n\n2) Drain Excavation: Excavation qty considered without supporting documents, submit the same with supporting calculations.\n\n3) Steel Qty for structures: Qty of steel is calculated on the assumptions, update the same as per approved Bar Bending Schedule.\n\n4) Steel Qty for Drains: Qty of steel is calculated on the assumptions, update the same as per approved Bar Bending Schedule.\n\n5) Material leads: Lead calculation is not as per site.\n\n6) Usage Rates of Plant & Machinery: The Usage rates given in Standard Data book analysis - 2019 are delivered based on the fuel & labour rate of Delhi Region and as mentioned in Standard Data book analysis — 2019, Concerned States/UT’s should update the same while\n\npreparing the SOR. oh.\n\nPage 1 of 2\n\nwww.sainfra.com.\n7) Further to this an e-mail has been received from the Authority on dated 14.09. 2022 in which\n\nit is requested to furnish the supporting documents for the Issues referred to CCIE. Hence,\n\nthe same has been has been forwarded by AE on dated 15.09.2022 and instructed to submit\n\nthe same at the earliest.\n\nIn view of the above of all observations, the Cost Estimate for change of scope submitted by EPC\n\nContractor has been rejected and requested to submit the same by incorporating above observations.\n\nThis is for your information and necessary actions.\n\nWith Regards,\n\nYours faithfully,\n\nch,\n\nCH Balakrishna\n\nS.A. Infrastructure Cons\n\nKar-Wal, Six Lanning Project, Package-ll,\n\nKancheepuram\n\nCopy to:\n\n1. The Project Director, NHAI, PIU — Kancheepuram.\n\n2. H.O.S.A. Infrastructure Consultants Pvt. Ltd.\n\nPage 2 of 2 | FALSE | real_data
Change of scope proposals clarifications | Payments; Dispute Resolution; Change of Scope; EoT | Standard Schedule of Rates (For Basic Items only) Basic Rates (Excluding GST and Other Taxes) 2021-22 [with effect from 13.09.2021]. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-6/20210924_SPK_CGM_061_Change of Scope – Clarification sought on the Cost Estimate prepared for in Principal Approval of COS - reg.pdf | Change of Scope Proposal - Change of Scope - Clarification sought on the Cost Estimate prepared for in Principal Approval of COS - reg | Reference to our letter cited at (4) the EPC contractor had requested the Competent Authority for revisiting the approval of COS works without taking into account the deduction towards discount of 9.66% and issue a revised COS order, which is awaited. Further the EPC Contractor would like to represent the following: - 1. COS Cost Estimates as per latest SOR 2021-22: Tamil Nadu Govt has circulated the latest Government of Tamil Nadu: Public Works Department: Standard Schedule of Rates [For Basic Items Only] Basic Rates (Excluding GST & Other Taxes) 2021-2022 [With Effect from 13.09.2021]- The Cost Estimates were prepared and submitted using the SOR 2020-21 The COS order has been issued in the FY 2021 — 2022 and it is hereby requested that the EPC Contractor shall be permitted to submit revised Cost Estimate based on the SOR 2021 — 2022. Refer Clause 13.2.3 of the Contract Agreement which states “The Contractor’s quotation of costs for the Change of Scope shall be determined on the following principles: (a) For works where Schedule of Rates (SOR) of concerned circle of States Public Works Department are available shall be applicable for determination of costs. In case of non-availability of current SOR, the available Schedule of Rates shall be applied by updating the same based on WPI. 2. COS - Cost Estimates as per latest MoRTH Rates MORTH has released the “MORTH Standard Data Book for Analysis of Rates 2019 in 2 Vols- Plain Rolling Terrain (Vol-1) (Second Revision 2019)”. The Cost Estimates were prepared and submitted using the old MoRTH DATA book 2003. It is hereby requested that the EPC Contractor shall be permitted to derive the rates based on the latest data book. 3. Negative COS - Cost Estimates prepared as per 2020-21 The EPC Contractor had quoted the rates utilizing the SOR 2017-18 at the time of bidding; and instead of adopting those rates for deduction of Negative COS the EPC Contractor was instructed to utilize the SOR 2020-21 and due to these the amount for Negative Scope has increased. The detailed calculation will be submitted shortly. 4. Retaining wall justification wrt non availability of ROW. The COS proposal submitted by the EPC Contractor a length of 480m was proposed for construction of Retaining wall to avoid the overflow during rains or during opening of gate valves in the PWD canal adjacent to the existing/proposed six laning work on the LHS Service road of the Project Highway. Clause 6.27 of the Contract Agreement states that Provide RT/RE walls in approaches or at any locations as per site conditions to contain the Six laning within the available ROW as per Cross Sections provisions mentioned in Schedule-B confirming to IRC SP 87 2013 & Schedule D. But a per site conditions the available ROW is only 26m from the PCL (Project Centre line) of the alignment. The above mentioned width is sufficient for constructing six lane carriageway with SR on LHS. But the Construction of Retaining Wall is mandatory | FALSE | real_data
Change of scope proposals clarifications | Payments; Dispute Resolution; Change of Scope; EoT | Cost Estimates were prepared and submitted using the old MORTH DATA book | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-6/20210924_SPK_CGM_061_Change of Scope – Clarification sought on the Cost Estimate prepared for in Principal Approval of COS - reg.pdf | Change of Scope Proposal - Change of Scope - Clarification sought on the Cost Estimate prepared for in Principal Approval of COS - reg | Reference to our letter cited at (4) the EPC contractor had requested the Competent Authority for revisiting the approval of COS works without taking into account the deduction towards discount of 9.66% and issue a revised COS order, which is awaited. Further the EPC Contractor would like to represent the following: - 1. COS Cost Estimates as per latest SOR 2021-22: Tamil Nadu Govt has circulated the latest Government of Tamil Nadu: Public Works Department: Standard Schedule of Rates [For Basic Items Only] Basic Rates (Excluding GST & Other Taxes) 2021-2022 [With Effect from 13.09.2021]- The Cost Estimates were prepared and submitted using the SOR 2020-21 The COS order has been issued in the FY 2021 — 2022 and it is hereby requested that the EPC Contractor shall be permitted to submit revised Cost Estimate based on the SOR 2021 — 2022. Refer Clause 13.2.3 of the Contract Agreement which states “The Contractor’s quotation of costs for the Change of Scope shall be determined on the following principles: (a) For works where Schedule of Rates (SOR) of concerned circle of States Public Works Department are available shall be applicable for determination of costs. In case of non-availability of current SOR, the available Schedule of Rates shall be applied by updating the same based on WPI. 2. COS - Cost Estimates as per latest MoRTH Rates MORTH has released the “MORTH Standard Data Book for Analysis of Rates 2019 in 2 Vols- Plain Rolling Terrain (Vol-1) (Second Revision 2019)”. The Cost Estimates were prepared and submitted using the old MoRTH DATA book 2003. It is hereby requested that the EPC Contractor shall be permitted to derive the rates based on the latest data book. 3. Negative COS - Cost Estimates prepared as per 2020-21 The EPC Contractor had quoted the rates utilizing the SOR 2017-18 at the time of bidding; and instead of adopting those rates for deduction of Negative COS the EPC Contractor was instructed to utilize the SOR 2020-21 and due to these the amount for Negative Scope has increased. The detailed calculation will be submitted shortly. 4. Retaining wall justification wrt non availability of ROW. The COS proposal submitted by the EPC Contractor a length of 480m was proposed for construction of Retaining wall to avoid the overflow during rains or during opening of gate valves in the PWD canal adjacent to the existing/proposed six laning work on the LHS Service road of the Project Highway. Clause 6.27 of the Contract Agreement states that Provide RT/RE walls in approaches or at any locations as per site conditions to contain the Six laning within the available ROW as per Cross Sections provisions mentioned in Schedule-B confirming to IRC SP 87 2013 & Schedule D. But a per site conditions the available ROW is only 26m from the PCL (Project Centre line) of the alignment. The above mentioned width is sufficient for constructing six lane carriageway with SR on LHS. But the Construction of Retaining Wall is mandatory | FALSE | real_data
Change of scope proposals clarifications | Payments; Dispute Resolution; Change of Scope; EoT | the same has been reviewed and our observations are as given below for compliance. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/Lot-12/20200723_AE_SPK_368_Observations made on Change of Scope proposal submitted as per Article No. 13 of Contract Agreement.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode — Observations made on Change of Scope proposal submitted as per Article No. 13 of Contract Agreement - Reg. | With respect to above said references regarding submission of Change of Scope proposals, the same has been reviewed and our observations are as given below for compliance. 1. Individual Drawings to be submitted for LVUP’s @ chainage 80+060, 84+060, 89+130, 94+090 and 102+130 to verify the quantities. However proper justification for providing these underpasses to be attached. 2. Individual Drawings to be submitted for all Pipe/Box culverts to assess the actual quantities. 3. i. The Retaining wall proposed in Dhamal village Ch. From 83+800 to 85+000 (BHS). OGL’s and FRL’s to be submitted for finalizes the length of Retaining wall and at the same location drain also proposed. We observe that if retaining wall constructed above said location necessity of Drain to be substantiated. ii. Same as above at Vanichatram (Pond) i.e. from Ch. Km. from 102+740 to 102+810. 4. As per Schedule ‘B’ the MNB proposed in MCW @ Ch. 92+195 (LHS) shall be Reconstructed and Retaining and Widening in (RHS), so no COS involves in MCW. For continuous of Service Roads, the COS is applicable in-Service Roads only, so kindly resubmit the Drawings accordingly. 5. Quantities are submitted based on Typical Drawings, but it is asked to prepare individual Drawings and submit the quantities accordingly. 6. The quantum of earth work and road crust materials is to be assessed for the actual quantity. We observe that there is no proper back up calculations and the way the earthwork calculated is also not as per the actual proposed executions. 7. Separate SOR rate can’t be considered for COS works, should be as applicable. 8. It is found that rates for the Other materials were taken and escalated from 2018-2019 year but supporting documents for the same like Quotation, copy of SOR, TN GO’s were not provided and enclosed 9. The rates for few materials were taken directly without reference you are requested to provide the Quotation, Copy of SOR for supporting. 10. It is observed that rates for Plant and Machinery have been adopted from Proc. No. 4693/Con/NH/2018 dated 30.08.2018 circular with an increase of 5% per year. You are requested to produce the G.O stating Escalation of 5.00% per year can be allowed. Hence you are hereby asked to resubmit the COS proposal as per above observations for review and forwarding the same to the Authority. This is for your information and necessary action. | FALSE | real_data
Change of scope proposals clarifications | Payments; Dispute Resolution; Change of Scope; EoT | This has reference to the Contractor letter No.178 (28th cited) regarding submission of Cost Estimate for user Fee Plaza with 16 lanes and Ref No.9 Cited above the following are observations/Recommendations by the Authority Engineer. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/Lot-12/20230120_AE_SPK_1244_Change of Scope No.2 Proposal – For the Proposed Toll Plaza at Ch. Km.104+981 – Submission of Cost Estimate for User Fee Plaza with 16 Lanes.pdf | Change of Scope No.2 Proposal — For the Proposed Toll Plaza at Ch. Km.104+981 — Submission of Cost Estimate for User Fee Plaza with 16 Lanes- Reg. | Dear Sir, This has reference to the Contractor letter No. 178 (28 cited) regarding submission of Cost Estimate for User Fee Plaza with 16 Lanes and Ref No.9 Cited above the following are observations/recommendations by the Authority Engineer. IE observations/recommendations 1. Toll Lane Drawing e Details observation given below (1% Toll Lane Drawing) FOB drawing Admin Building (Toll Building e Details observation given below 1-Toll Lane Drawing- 1. Taper (1:10 in standard drawing) are not shown in drawing: 2. Traffic island dimension not shown in drawing. These islands shall be minimum 35 m length (22.5 m on approach side with middle of booth) and other is 12.5 M. Please enclose the Key plan for toll lanes showing the Lane Dividers/traffic Islands. 1. Scarder angle not shown in drawing. Scarder angle manage in such manner visibility of lane and board shown proper. 2. Median length increased from 600 mm to 800 mm 3. Contractor has Shown Two/Three-Wheeler Lane for exempted vehicles. IE found that width of this lane is less than required width for Three-Wheeler, which does not fulfill required objective. Further, sufficient land is available at both extreme ends. Hence, the Concessionaire is directed as to construct Two/Three-Wheeler Lane for the exempted vehicles 4. As per IRC: SP: 87:2013, not less than 2 middle toll lanes shall be capable of being used as reversible lanes to meet the demand of traffic flow, whereas it is observed that two middle reversible lanes are not being constructed by the Contractor. Hence, the Contractor is directed to construct two reversible as per the requirement 5. AE suggests that Static weigh Bridge being constructed by EPC Contractor be at sufficient distance from Extra wide lane approx. 100 M with proper approach road required for the movement of the heavy loaded long vehicles on Static weigh Bridge at LHS & RHS which is not provided. Hence, the AE suggests to shift the Bridge at required distance from the last extra wide lane to do not disturb the 2/3 Wheelers traffic, which requires for safety of 2/3 Wheelers. | FALSE | real_data
Change of scope proposals clarifications | Payments; Dispute Resolution; Change of Scope; EoT | The following observations are communicated vide letter No.909 dated 01.03.2022. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/Lot-12/20231214_AE_SPK_1587 - Requisition for De-Scoping of Hume Pipe Culverts2 +1 Total.pdf | Requisition for De-scoping of Hume Pipe Culverts 2 +1 Total (3Nos) as per Schedule - B which is not existing on ground at project site - Reg. | Dear Sir, With respect to the above said Ref. No.7 the following observations were communicated for necessary actions from your end. 1. Missing culverts: Relating to the missing culverts at Ch. Km. 84+099 & 84+115 our stand was already communicated vide letter No. 909 dated 01.03.2022. Further the necessity of the culverts at Ch. Km. 84+032 was also mentioned for which your response is awaited. 2. Culvert at Ch. Km. 103+450(103+461): At this location, it is observed the Service Road was completed. The photographs presented are also clearing the current situation. As communicated earlier also in case of culverts at Km 84.099 & 84.115, the contractor had not brought up this issue (non-availability culvert at this location) during the initial stage of road works which is not a prudent act by the Contractor. If the Scope is covered with some structure and if it is not available at site, the contractor should have notified to the Authority/Authority’s Engineer as and when it gets noticed. Hence, the Contractor is at this location. It cannot be assessed with the photos which are presenting the current situation. You are therefore, requested to re-visit the complete scope of works and intimate us to number of culverts which are not available at site, locations where culverts are required as per site condition and submit a negative COS also for our review and further appraisal to the Authority. This is for your information and for progressing of the works accordingly. | FALSE | real_data
Contractor's delay in submission of COS Proposals | Change of Scope; Contractor's Obligations; Dispute Resolution | the Project Completion Date is fast approaching and submissions related to COS are getting delayed from your end which is alarming. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/Lot-11/20201017_AE_SPK_445-Observations made on Change of Scope proposal submitted as per Article No. 13 of Contract Agreement and Compliance.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode — Observations made on Change of Scope proposal submitted as per Article No. 13 of Contract Agreement and Compliance - Reg. | Dear Sir, It is very unfortunate to note that despite of asking several times to comply the observations made on your submittal for the COS proposals vide above said Ref. No’s 7 & 8 till date there is no response from your end. You are aware that the Project completion date is fast approaching and the submissions relating to COS are getting delayed from your end which is alarming. Hence it has been advised to submit the same for proper verification and for obtaining the necessary approvals from Competent Authority well in advance. This is for your information and necessary action. € ultants Pvt. Ltd., Kar-Wal, Six Lanning Project, Package-ll, Kancheepuram Copy to: 1. The Project Director, NHAI, PIU —- Kancheepuram. 2. H.O.S.A. Infrastructure Consultants Pvt. Ltd. ot No. 7A/1, Sector 142, Noida 201301, +91-120-6148090 www.sainfra.com | FALSE | real_data
Contractor's delay in submission of COS Proposals | Change of Scope; Contractor's Obligations; Dispute Resolution | It is requested to submit the detailed estimate with reference Designs & Drawings and levels etc. for initiating the proposal for issuance of the final approvals. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/Lot-11/20220203_AE_SPK_857-Change of Scope proposal.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode — Change of Scope proposal - Reg. | Dear Sir, With respect to the above referred subject and letters, it is requested to submit the Detailed Estimate with reference Designs & Drawings and Levels etc., for initiating the proposal for issuance of the final approvals. This is for your kind information and necessary action. With Regards, Yours Faithfully CH Balahiishna Team Leader cum Senior Highway Engineer, S.A. Infrastructure Consultants Pvt. Ltd., Kar-Wal, Six Lanning Project, Package-ll, Kancheepuram Copy to: 1. The Project Director, NHAI, PIU — Kancheepuram. 2. H.O.S.A. Infrastructure Consultants Pvt. Ltd. | FALSE | real_data
Contractor's delay in submission of COS Proposals | Change of Scope; Contractor's Obligations; Dispute Resolution | even after lapse of one month from the date of discussion, the Contractor is yet to submit the revised COS proposal along with the COS proposal along with the cost with the Cost Implications as per CA immediately for taking further necessary action. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/Lot-12/20221125_PD_SPK_3670_Non submission of COS proposal.pdf | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet section of NH-4 from Km 71/015 to Km 107/091 in the State of Tamilnadu — Non-submission of COS Proposal - Reg. | This has reference to the Change of Scope Proposal No.02 submitted towards for Construction of User Fee Plaza at Km 104+956. In this regard, during the discussion held at the Regional Office, NHAI, Chennai on 29.10.2022, it was discussed and instructed to explore the possibility of 8+8 lanes within the available ROW as per the Policy Circular dated 24.05.2021. Further, it was requested to re-submit the proposal for further consideration along with the cost implication by 02.11.2022 itself. However, the same was not submitted. In this context, the Regional Officer, NHAI, Chennai along with PD, PIU-Kancheepuram visited the site on 09.11.2022 and inspected the line marking made towards proposing 8+8 lanes within the available ROW. Further, the Regional Officer, Chennai directed the Contractor to submit the revised COS proposal and to commence the works immediately. However, even after a lapse of one month from the date of discussion, the Contractor is yet to submit the revised COS proposal along with the Cost Estimate. Hence, it is requested to submit the revised COS proposal along with the Cost Implications as per CA immediately for taking further necessary action. Further, it may be intimated that any delay in account of this will not be considered. | FALSE | real_data
Contractor's delay in submission of COS Proposals | Change of Scope; Contractor's Obligations; Dispute Resolution | As mentioned by the EPC Contractor, instructions were given by the Authority for modification of the toll plaza on 29.10.22 and had submitted the drawings on 23.12.2022 i.e. late by 2 months. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/Lot-12/20230127_AE-SPK_1248_Delay in Toll Plaza Cost Estimate review and recommendation-Request for early COS Approval of Proposed Toll Plaza with 16 lanes at Km 104+981-Reg (1).pdf | Delay in Toll Plaza Cost Estimate review and recommendation-Request for early COS Approval of Proposed Toll Plaza with 16 lanes at Km 104+981-Reg | Dear Sir, Having gone through your above said Ref> No.10 communication regarding construction of Toll Plaza we want bring the following points to your kind information. As mentioned by the EPC Contractor, instructions were given by the Authority for. modification of the toll plaza on 29.10.22 and had submitted the drawings on 23.12.2022 i.e., late by 2 months. However, drawings were reviewed and comments were communicated on 20.01.2023 which is in a reasonable time. Anyway, the toll plaza is to be executed in COS. So, for construction, the drawings are important and not the estimate. Implication will be ascertained duly taking various points, which can be calculated at any time and value will not be changed if the derived realistically. Hence, the Contractor may be advised to submit the revised drawings (Cl 10.2) and estimate as per the consented drawings (Article 13) so as to commence the works physically at the earliest. This is for your information and necessary actions. | FALSE | real_data
change of scope due to local demand for additional structures, service road, utility ducts | Change of Scope; EoT; Dispute Resolution; Payments | Submission of additional cost estimates for additional pipe culverts and utility ducts under change of scope. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-3/17. Submission of cost estimates for additional pipe culverts & utility ducts under COS 23.05.2018.pdf | Submission of cost estimates for Additional Pipe Culverts and Utility ducts under Change of Scope — Reg. | Respected Sir, With reference to above subject, we are herewith submitting the cost estimates for additional pipe culverts (varying with schedule - B) and Utility ducts for crossing of water mains and electrical line under change of scope. | FALSE | real_data
change of scope due to local demand for additional structures, service road, utility ducts | Change of Scope; EoT; Dispute Resolution; Payments | the Authority Engineer has gone through the request for Construction of vehicular Underpass by the local villagers of village Thenkadapanthangal, Pulithangal and Musri of Walajahpet. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/Lot-12/20230608_AE_PD_21399_Submission of Revised Cost Estimate for Proposed Toll PlazaUser Fee plaza - Request for early COS Approval of Proposed Toll User Fee Plaza with 16 lanes at Km.104+981.pdf | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajapet from km 71.015 tol107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode —Submission of Revised Cost Estimate for Proposed Toll Plaza/User Fee plaza - Request for early COS Approval of Proposed Toll / User Fee Plaza with 16 lanes at Km.104+981- Reg. | This has reference to 20" cited letter, the Contractor had submitted the cost implication of Rs. Rs/- 3,81,82,081 towards COS due to modification of Toll Plaza and additional Service Roads at Toll Plaza. The AE reviewed the Contractor submission and following is being submitted for ready reference and further needful, please ; I. Toll Plaza : As per the Contract Agreement, the EPC Contractor is required to construct a 12+12 Lane Toll Plaza at Chennasamudram village, at designated Km. 104+917 with 11 No’s Manual operated and one Automatically operated toll lane on each side. However, NHAI had issued a Policy Circular No. 17.5.82 Dated 24" May 2021 wherein certain modifications were suggested to “provisions of Toll Plaza” which were not yet started by that time. As the construction of toll plaza was not commenced in this project, suggested modifications are to be implemented as per the said Circular. As such, Change of Scope is necessitated due to modifications of CA provisions. It was observed that 7+7 Lanes system considering the FASTAG is sufficient and accordingly necessary implications due to changes has been forwarded to your good office vide letter No. 19060 dated 31.08.2022. The same was discussed at RO Chennai office on 29.10.2022 and it is directed to explore the possibilities of making 8+8 lanes instead of 7+7 considering the availability existing land particulars. A re-survey on the feasibility of 8+8 lanes was conducted and found that it is possible to (Either side one No. Manual + 7 No’s Automatic) at Ch. Km. with a minor change in the location as compared to the Contract Agreement. Accordingly, the Contractor had submitted the drawings. These was verified and accepted for Good for Construction after incorporating the necessary corrections. Further, the EPC Contractor had submitted his cost proposals vide Ref No. 20 letter No. 268 dated 29.05.2023 for an 8+8 Toll Lane system with a POSITIVE CHANGE OF SCOPE -2 amounting to Rs/- 3,81,82,081. The Contractor's proposed for the Negative Change of Scope-2 towards the reduction of works in Toll Plaza. The same was reviewed by Authority's Engineer and following is being submitted herewith; - As per Clause 2.1 of Schedule C of Contract Agreement, 24 lanes Toll Plaza with fencing on all four side is provisioned. However, due to land issue and to follow the NHAI Policy Circular no. 15.5.82 dated 24 May 2021, 14 lanes Toll Plaza is proposed by the contractor. As per the traffic projection, 16 lane (8+8) Toll Plaza suffice the traffic requirement and as per the policy guidelines. - It is to submit that that a 10 lane Toll Plaza is in existence with flexible pavement, at this location. However, Contractor considers rehabilitation/strengthening of existing bituminous surface and proposed PQC/DLC in widening portion. However, as per Clause 2.1, schedule C of Contract Agreement, existing Toll Plaza shall be modified/widened to 24 lanes and also as per clause 6.9, Schedule B, Rigid pavement at Toll Plaza is provisioned from Km 104+230 to km 105+630, that is for 1400m length. Accordingly, widening of GSB and Subgrade and full width DLC and PQC is being considered in this COS. | FALSE | real_data
change of scope due to local demand for additional structures, service road, utility ducts | Change of Scope; EoT; Dispute Resolution; Payments | we request you to issue Change of Scope notice based on CE's instructions and as per clause 13.2.1 of contract agreement, since the work has to be executed at many locations. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/3. Request for COS notice-Delay in achieving MS-II & MS-III 26.10.2018.pdf | Request for Change of Scope notice for additional Utility ducts of 600 mm diameter RC pipe crossings for water mains and Electrical lines - Delay in achieving MS-II and MS-III | Respected Sir, We wish to bring to your kind attention regarding the unauthorised water pipelines across the project alignment. As you are aware, the stretch from Chainage 0+000 to 9+500 is infested with water pipes across the highway, laid by the local farmers in unauthorised manner. The Authority and AE have been repeatedly insisting us to take up execution in this stretch. We had completed Clearing & Grubbing, but could not proceed further due to these encumbrances. The local farmers requested the Chief Engineer (CE) during his visit on 022018 for provision of pipe crossings, as agriculture is their livelihood. The CE has resolved this issue by suggesting the provision of 600 mm diameter reinforced concrete pipes at approximately 500m c/c. The CE has also agreed to make financial sanction for the additional utility ducts as per the farmers’ requirement, and to consider this under Change of Scope (COS). Subsequently, we have taken up CD works and earthworks wherever possible, having already suffered huge delay due to this issue, which has a direct effect on achieving MS-II and MS-III. The locations of utility ducts were also finalized and approved by the Authority’s Engineer vide letter no. 01041028/02/020, dated 13% July 2018. However, no COS notice has so far been issued regarding this item. In this regard, we also invite your kind attention to the discussion in the meeting chaired by the OSD at Mumbai on 042018. Now, we request you to issue Change of Scope notice based on CE’s instructions and as per Clause 13.2.1 of contract agreement, since the work has to be executed at many locations. | FALSE | real_data
change of scope due to local demand for additional structures, service road, utility ducts | Change of Scope; EoT; Dispute Resolution; Payments | This refers to all the letters referred above instructing us to execute certain additional works, under change of scope. We have been instructed additional Minor Bridges, Box Culverts and Pipe culverts under Article — 13 & 13.1.1 whereas clause 13.2 "Procedure for change of scope" instructs for a notice from Authority Engineer io be issued to the contractor (please refer clause 13.2.1 & 13.2.2 in this regard | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/4. COS notice under 13.2.1 by AE 27.10.2018.pdf | Change of Scope notice under 13.2.1 by Authority Engineer | Respected Sir, This refers to all the letters referred above instructing us to execute certain additional works, under change of scope. We have been instructed additional Minor Bridges, Box Culverts and Pipe culverts under Article — 13 & 13.1.1 whereas clause 13.2 “Procedure for change of scope” instructs for a notice from Authority Engineer to be issued to the contractor (please refer clause 13.2.1 & 13.2.2 in this regard) As intimated in our letter 3 referred above, we are proceeding with submission of design / drawings / tentative cost impact, in anticipation of the aforesaid notice. However, we request you to direct the Authority Engineer, to issue us the Change of Scope notice, for the sake of good order and procedure for Change of Scope. Meanwhile, by way of submitting a copy of this letter to Authority Engineer/Team Leader, we are requesting him for necessary action for issuing the notice and simultaneously approving the designs & drawings. | FALSE | real_data
change of scope due to local demand for additional structures, service road, utility ducts | Change of Scope; EoT; Dispute Resolution; Payments | Ch.Km.76/850, Additional proposals like construction of retaining wall etc. are to be checked | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/119_01102019_Minutes of Monthly Progress review meeting Mom -3.pdf | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to 107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Minutes of Monthly Progress review meeting Mom -3 -Reg. | With respect to the above said reference please find enclosed herewith the minutes of meeting MoM -3 held on 25.09.2019. The venue and date for the next meeting will be intimated in due course of time. This is for your information and record. Assuring our best services at all times. | FALSE | real_data
change of scope due to local demand for additional structures, service road, utility ducts | Change of Scope; EoT; Dispute Resolution; Payments | Additional Underpasses, | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/162_11112019_Minutes of meeting_MOM 4.pdf | Consultancy services for Authority's Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Minutes of Monthly Progress review meeting Mom-4 -Reg. | With respect to the above said reference please find enclosed herewith the Minutes of Meeting Numbered as MoM-4 held on 30.10.2019. The venue and date for the next meeting are scheduled on 27.11.2019 at Consultants office around 11.00 A.M in Kancheepuram. All the concerned are requested to attend with necessary documents. This is for your information and record. Assuring our best services at all times. | FALSE | real_data
change of scope due to local demand for additional structures, service road, utility ducts | Change of Scope; EoT; Dispute Resolution; Payments | Ch.Km.76/850, Additional proposals like construction of retaining wall etc. are to be checked | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/162_11112019_Minutes of meeting_MOM 4.pdf | Consultancy services for Authority's Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Minutes of Monthly Progress review meeting Mom-4 -Reg. | With respect to the above said reference please find enclosed herewith the Minutes of Meeting Numbered as MoM-4 held on 30.10.2019. The venue and date for the next meeting are scheduled on 27.11.2019 at Consultants office around 11.00 A.M in Kancheepuram. All the concerned are requested to attend with necessary documents. This is for your information and record. Assuring our best services at all times. | FALSE | real_data
change of scope due to local demand for additional structures, service road, utility ducts | Change of Scope; EoT; Dispute Resolution; Payments | Additional Underpasses, | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/20191205_AE_NHAI_188_Minutes of Monthly Progress review meeting Mom-5.pdf | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to 107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Minutes of Monthly Progress review meeting Mom-5 -Reg. | With respect to the above said reference please find enclosed herewith the Minutes of Meeting Numbered as MoM-S held on 29.11.2019. The next meeting will be likely on 27.12.2019 at the Consultants office around 11.00 A.M in Kancheepuram. All the concerned are requested to attend with necessary documents. This is for your information and record. Assuring our best services at all times. | FALSE | real_data
change of scope due to local demand for additional structures, service road, utility ducts | Change of Scope; EoT; Dispute Resolution; Payments | The Project Director stated that additional proposals like construction of retaining wall etc. are to be checked | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/20191205_AE_NHAI_188_Minutes of Monthly Progress review meeting Mom-5.pdf | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to 107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Minutes of Monthly Progress review meeting Mom-5 -Reg. | With respect to the above said reference please find enclosed herewith the Minutes of Meeting Numbered as MoM-S held on 29.11.2019. The next meeting will be likely on 27.12.2019 at the Consultants office around 11.00 A.M in Kancheepuram. All the concerned are requested to attend with necessary documents. This is for your information and record. Assuring our best services at all times. | FALSE | real_data
change of scope proposal | Change of Scope; EoT; Dispute Resolution; Payments | it is hereby submitted that the tentative cost for making the provision will be around Rs.8.2 Cr. The proposal has been forwarded for attaining in principle approvals from Competent Authority as soon as possible. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/Lot-11/20210225_564–Request for Vehicular Underpass at Tenkadapathangal & Musiri Villages Ch. Km. 106+000.pdf | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajapet from km 71.015 to107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode — Request for Vehicular Underpass at Tenkadapathangal & Musiri Villages Ch. Km. 106+000 - Reg. | Sir, in continuation to the above said Ref. No.3 relating to the proposed subway at Musiri/Tenkadapathangal villages it is hereby submitted that the tentative cost for making the provision will be around Rs. 8.2 Cr. (Eight crore twenty lakhs rupees only). The said amount has been arrived based on the following arrangements. 1. Size of underpass/subway will be 1 X 7.0 X 3.0 2. The Main Carriageway has to be raised by 1.50mtrs and similarly the service roads have to be lowered by similar depth to get the 3.0mtr clearance. 3. RCC retaining wall has proposed on approaches of underpass. 4. The Musiri branch road has to be regraded in such a way to suit the service road/underpass sill level & Junction developments to be made. Hence based on the above the proposal has been forwarded for attaining the in principle approvals from Competent Authority as soon as possible. Assuring our best services at all times. Thanking You. | FALSE | real_data
change of scope proposal | Change of Scope; EoT; Dispute Resolution; Payments | In view of the above, the Authority Engineer hereby recommends the Change of Scope (No.2) Proposal due to additional Service Road Provision, one no. of CUP at Km.84+032, one No.Underpass @ 80+060, Foot Over Bridge at Dhamal Colony i.e.@ Km 81+600 instead of at 84+032, two Foot Over Bridges at 89+120 & 94+040 and subway at ch. Km.106+010 as mentioned above amounting to Rs.44,65,72,437/- | /Users/hareeshkb/GenAIWork/krishna/NewCategories/Lot-11/20210710_AE_PD_14586 - Resubmission of Change of Scope Proposal-2637616919918269630 10072021 AE with Estimates.pdf | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode—Resubmission of Change of Scope Proposal-2 -Reg. | In reference to the above-referred chronology of correspondence and based on the recent site visits on 3 & 17 of June, 2021, Contractor had submitted the revised Change of Scope -2 proposals vide letter No. 084 stated as Ref. No.1. to an amount of Rs/- 56,71,88,373. The submitted proposal reviewed by AE as per provision of the Contract Agreement and following is being submitted for ready reference and further needful, please; There are some additional works require based on the request received from Hon’ble Member of Parliament, Hon’ble Member of Legislative Assembly, Local District Level Authorities and as well as from the Local Residents. The same is being examined and considered for the COS-2. The details and the expenditure on each proposal is being worked out and submitted for the Approval of Competent Authority. Additional Service Roads in Kancheepuram & Ranipet District jurisdictions: It may be noted that the Project stretch, which is having a length of 36.076 Kms from Karaipettai to Walajhpet i.e. between Chainages 71+015 to 107+091 is in the territory of two districts namely Kancheepuram & Ranipet. The project length of 14.859 kms is under Kancheepuram District i.e. between 71+015 to 85+874. In Kancheepuram District, there is a shortage of service road provision. Hence the District Admission made a representation to the Authority (endorsed vide Ref. No.23) to have a continuous service road provision which will avoid merging & demerging of service road traffic with MCW. In view of this a survey was conducted and found that the service road provision has to be made between 75+580 to 76+240 & 77+400 to 78+800 which come to a length of 660+700 = 1360 Rmts. The same is being considered in this COS-2. Similarly, for the Ranipet district out of 21.145 kms length i.e between Ch. Km. 85+874 to 107+019 there is a shortage of service road provision. Hence as the similar representation was received from the District Safety Council of Ranipet District (Which was endorsed to this office vide ref. No.24) a survey was conducted and proposed to have the service road provision between Chainages 88+160 to 88+560 & 94+640 to 94+860 i.e. 220+400 = 620 Rimts lengths. Hence total length of additional service road proposed is 1360+620 = 1980 Rmts. Thiruppukuzhi Junction. (BLACK SPOT No. TN-02 /146) Ch. Km. 80+060. There is a cross road junction called Thiruppukuzhi at Ch. Km.80+060. On either side of the Project Highway there are temples, Primary school, Banks and it is one of the junction connecting the Baluchetty residents to other side of Carriageway. Nearer to this junction there is another junction called Musrivakkam at Ch. Km. 79+860. In similar fashion to the other junction, residents of Baluchetty village are crossing the Highway for their daily needs. | FALSE | real_data
change of scope proposal | Change of Scope; EoT; Dispute Resolution; Payments | In view of the above, considering the safety of the Villagers, Road Users and to avoid any road mishap, it is recommended to provide additional service roads, LVUP, Cattle/Pedestrian Underpass, Foot over Bridges and Subway/pedestrian Underpasses on the above said locations and approval is solicited for an amount of Rs.44,65,72,437/- | /Users/hareeshkb/GenAIWork/krishna/NewCategories/Lot-11/20210724_PD_RO_2021_COS Recommendation July 2021.pdf | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet Section of NH-4 from Km 71/015 to Km 107/091 in the State of Tamilnadu under residual NHDP (Phase — V) under Bharathmala Pariyojana on EPC Mode — Change of Scope Proposal 02 - Reg | I submit that, vide reference 18t cited above, the Authority Engineer — M/s. SA Infrastructure Consultants Pvt Ltd recommended the Comprehensive Change of Scope Proposal to obtain approval from the Competent Authority of NHAI for Rs. 44,65,72,437/- including GST for various representations received such as from Shri. G. Selvam, Hon’ble Member of Parliament, The District Collector, Ranipet District and Local Public vide 12t» to 224 reference cited above for Construction of Additional Service roads in Kancheepuram District, Additional Underpass (LVUP), Cattle Underpass and Pedestrian Underpass respectively. 2. Based on the above representations/requests received along the subject Project Stretch, the Authority Engineer vide letter 10" cited above recommended the Change of Scope Proposal submitted by the Contractor amounting for Rs. 93,85,74,885/- including GST. 3. After the scrutiny of the proposal, this office vide letter cited 9th above, recommended the Change of Scope proposal and approval of the competent authority was solicited for an amount of Rs. 102.06 Cr including GST towards providing Additional Service Roads in Kancheepuram & Ranipet District, Additional Underpass (LVUP) at Thiruppukuzhi Junction Km 80/060, Cattle/Pedestrian Underpass at Dhamal Lake Junction Km 84+032, Underpasses in Avalur Village at Km 89+124, in Srikarumbur Village at 94+090, in Bagaveli Village at 102+134 and Vehicular Underpass at Tenkadapathangal & Musuri Village at 106+000 respectively. | FALSE | real_data
change of scope proposal | Change of Scope; EoT; Dispute Resolution; Payments | In view of the above, the COS amounting to Rs.41,58,14,372/- (Rupees Forty One Crore Fifty Eight Lakhs Fourteen Thousand Three Hundred and Seventy Two only) including GST, is recommended for approval of Competent Authority. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/Lot-11/20210731_RO_CGM_2200_Recommendation of COS.pdf | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet Section of NH-4 from Km 71/015 to Km 107/091 in the State of Tamilnadu under residual NHDP (Phase - V) under Bharathmala Pariyojana on EPC Mode - Change of Scope Proposal - Approval of Competent Authority requested - Reg | This has reference to the Change of Scope (CoS) proposal in respect of the subject project, submitted by PD, PIU, Kancheepuram vide letter dated 24.07.2021 for Rs 44.65 Cr. 2. The CoS proposal was submitted by the contractor vide letter dated 23.06.2021 for Rs.48.71 Cr. This has been examined by the AE and they have forwarded the COS proposal amounting to Rs.44.65 Cr. vide letter dated 10.07.2021 to PD PIU Kancheepuram. PD has examined the proposal and submitted the same for Rs.44.65 Cr. to RO Chennai vide letter dated 24.07.2021. 3 The Project stretch from Karaipettai to Walajahpet Section of NH-4 from Km 71/015 to Km 107/091 is taken up for 6-lning from the existing 4-lane on EPC mode. The followings are the Project details: Length : 36.076 Km Contract Cost : Rs.533.36 Crore Contractor : M/s SPK & Co. Agreement date : 15.10.2018 Date of commencement : 11.02.2019 Construction period : 24 months Scheduled Date of completion — : 10.02.2021 Physical progress : 35.10% as on 31.07.2021 Financial Progress : 30.95% as on 31.07.2021 Expected date of completion: 20.12.2022 PAWAN brawn | FALSE | real_data
change of scope proposal | EoT | In view of the above, considering the safety of the Villagers, Road Users and to avoid any road mishap, it is recommended to provide additional service roads, LVUP, Cattle/Pedestrian Underpass, Foot over Bridges and Subway/pedestrian Underpasses on the above said locations and approval is solicited for an amount of Rs.44,65,72,437/- | synthetic_template_20250913 | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet Section of NH-4 from Km 71/015 to Km 107/091 in the State of Tamilnadu under residual NHDP (Phase — V) under Bharathmala Pariyojana on EPC Mode — Change of Scope Proposal 02 - Reg | I submit that, vide reference 18t cited above, the Authority Engineer — M/s. SA Infrastructure Consultants Pvt Ltd recommended the Comprehensive Change of Scope Proposal to obtain approval from the Competent Authority of NHAI for Rs. 44,65,72,437/- including GST for various representations received such as from Shri. G. Selvam, Hon’ble Member of Parliament, The District Collector, Ranipet District and Local Public vide 12t» to 224 reference cited above for Construction of Additional Service roads in Kancheepuram District, Additional Underpass (LVUP), Cattle Underpass and Pedestrian Underpass respectively. 2. Based on the above representations/requests received along the subject Project Stretch, the Authority Engineer vide letter 10" cited above recommended the Change of Scope Proposal submitted by the Contractor amounting for Rs. 93,85,74,885/- including GST. 3. After the scrutiny of the proposal, this office vide letter cited 9th above, recommended the Change of Scope proposal and approval of the competent authority was solicited for an amount of Rs. 102.06 Cr including GST towards providing Additional Service Roads in Kancheepuram & Ranipet District, Additional Underpass (LVUP) at Thiruppukuzhi Junction Km 80/060, Cattle/Pedestrian Underpass at Dhamal Lake Junction Km 84+032, Underpasses in Avalur Village at Km 89+124, in Srikarumbur Village at 94+090, in Bagaveli Village at 102+134 and Vehicular Underpass at Tenkadapathangal & Musuri Village at 106+000 respectively. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
change of scope proposal | EoT | In view of the above, the COS amounting to Rs.41,58,14,372/- (Rupees Forty One Crore Fifty Eight Lakhs Fourteen Thousand Three Hundred and Seventy Two only) including GST, is recommended for approval of Competent Authority. | synthetic_template_20250913 | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet Section of NH-4 from Km 71/015 to Km 107/091 in the State of Tamilnadu under residual NHDP (Phase - V) under Bharathmala Pariyojana on EPC Mode - Change of Scope Proposal - Approval of Competent Authority requested - Reg | This has reference to the Change of Scope (CoS) proposal in respect of the subject project, submitted by PD, PIU, Kancheepuram vide letter dated 24.07.2021 for Rs 44.65 Cr. 2. The CoS proposal was submitted by the contractor vide letter dated 23.06.2021 for Rs.48.71 Cr. This has been examined by the AE and they have forwarded the COS proposal amounting to Rs.44.65 Cr. vide letter dated 10.07.2021 to PD PIU Kancheepuram. PD has examined the proposal and submitted the same for Rs.44.65 Cr. to RO Chennai vide letter dated 24.07.2021. 3 The Project stretch from Karaipettai to Walajahpet Section of NH-4 from Km 71/015 to Km 107/091 is taken up for 6-lning from the existing 4-lane on EPC mode. The followings are the Project details: Length : 36.076 Km Contract Cost : Rs.533.36 Crore Contractor : M/s SPK & Co. Agreement date : 15.10.2018 Date of commencement : 11.02.2019 Construction period : 24 months Scheduled Date of completion — : 10.02.2021 Physical progress : 35.10% as on 31.07.2021 Financial Progress : 30.95% as on 31.07.2021 Expected date of completion: 20.12.2022 PAWAN brawn | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
change of scope proposal | Change of Scope | In view of the above, the Authority Engineer hereby recommends the Change of Scope (No.2) Proposal due to additional Service Road Provision, one no. of CUP at Km.84+032, one No.Underpass @ 80+060, Foot Over Bridge at Dhamal Colony i.e.@ Km 81+600 instead of at 84+032, two Foot Over Bridges at 89+120 & 94+040 and subway at ch. Km.106+010 as mentioned above amounting to Rs.44,65,72,437/- | synthetic_template_20250913 | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode—Resubmission of Change of Scope Proposal-2 -Reg. | In reference to the above-referred chronology of correspondence and based on the recent site visits on 3 & 17 of June, 2021, Contractor had submitted the revised Change of Scope -2 proposals vide letter No. 084 stated as Ref. No.1. to an amount of Rs/- 56,71,88,373. The submitted proposal reviewed by AE as per provision of the Contract Agreement and following is being submitted for ready reference and further needful, please; There are some additional works require based on the request received from Hon’ble Member of Parliament, Hon’ble Member of Legislative Assembly, Local District Level Authorities and as well as from the Local Residents. The same is being examined and considered for the COS-2. The details and the expenditure on each proposal is being worked out and submitted for the Approval of Competent Authority. Additional Service Roads in Kancheepuram & Ranipet District jurisdictions: It may be noted that the Project stretch, which is having a length of 36.076 Kms from Karaipettai to Walajhpet i.e. between Chainages 71+015 to 107+091 is in the territory of two districts namely Kancheepuram & Ranipet. The project length of 14.859 kms is under Kancheepuram District i.e. between 71+015 to 85+874. In Kancheepuram District, there is a shortage of service road provision. Hence the District Admission made a representation to the Authority (endorsed vide Ref. No.23) to have a continuous service road provision which will avoid merging & demerging of service road traffic with MCW. In view of this a survey was conducted and found that the service road provision has to be made between 75+580 to 76+240 & 77+400 to 78+800 which come to a length of 660+700 = 1360 Rmts. The same is being considered in this COS-2. Similarly, for the Ranipet district out of 21.145 kms length i.e between Ch. Km. 85+874 to 107+019 there is a shortage of service road provision. Hence as the similar representation was received from the District Safety Council of Ranipet District (Which was endorsed to this office vide ref. No.24) a survey was conducted and proposed to have the service road provision between Chainages 88+160 to 88+560 & 94+640 to 94+860 i.e. 220+400 = 620 Rimts lengths. Hence total length of additional service road proposed is 1360+620 = 1980 Rmts. Thiruppukuzhi Junction. (BLACK SPOT No. TN-02 /146) Ch. Km. 80+060. There is a cross road junction called Thiruppukuzhi at Ch. Km.80+060. On either side of the Project Highway there are temples, Primary school, Banks and it is one of the junction connecting the Baluchetty residents to other side of Carriageway. Nearer to this junction there is another junction called Musrivakkam at Ch. Km. 79+860. In similar fashion to the other junction, residents of Baluchetty village are crossing the Highway for their daily needs. Please confirm receipt of this correspondence. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
change of scope proposal | Change of Scope | In view of the above, the Authority Engineer hereby recommends the Change of Scope (No.2) Proposal due to additional Service Road Provision, one no. of CUP at Km.84+032, one No.Underpass @ 80+060, Foot Over Bridge at Dhamal Colony i.e.@ Km 81+600 instead of at 84+032, two Foot Over Bridges at 89+120 & 94+040 and subway at ch. Km.106+010 as mentioned above amounting to Rs.44,65,72,437/- | synthetic_template_20250913 | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode—Resubmission of Change of Scope Proposal-2 -Reg. | Kindly be informed that In reference to the above-referred chronology of correspondence and based on the recent site visits on 3 & 17 of June, 2021, Contractor had submitted the revised Change of Scope -2 proposals vide letter No. 084 stated as Ref. No.1. to an amount of Rs/- 56,71,88,373. The submitted proposal reviewed by AE as per provision of the Contract Agreement and following is being submitted for ready reference and further needful, please; There are some additional works require based on the request received from Hon’ble Member of Parliament, Hon’ble Member of Legislative Assembly, Local District Level Authorities and as well as from the Local Residents. The same is being examined and considered for the COS-2. The details and the expenditure on each proposal is being worked out and submitted for the Approval of Competent Authority. Additional Service Roads in Kancheepuram & Ranipet District jurisdictions: It may be noted that the Project stretch, which is having a length of 36.076 Kms from Karaipettai to Walajhpet i.e. between Chainages 71+015 to 107+091 is in the territory of two districts namely Kancheepuram & Ranipet. The project length of 14.859 kms is under Kancheepuram District i.e. between 71+015 to 85+874. In Kancheepuram District, there is a shortage of service road provision. Hence the District Admission made a representation to the Authority (endorsed vide Ref. No.23) to have a continuous service road provision which will avoid merging & demerging of service road traffic with MCW. In view of this a survey was conducted and found that the service road provision has to be made between 75+580 to 76+240 & 77+400 to 78+800 which come to a length of 660+700 = 1360 Rmts. The same is being considered in this COS-2. Similarly, for the Ranipet district out of 21.145 kms length i.e between Ch. Km. 85+874 to 107+019 there is a shortage of service road provision. Hence as the similar representation was received from the District Safety Council of Ranipet District (Which was endorsed to this office vide ref. No.24) a survey was conducted and proposed to have the service road provision between Chainages 88+160 to 88+560 & 94+640 to 94+860 i.e. 220+400 = 620 Rimts lengths. Hence total length of additional service road proposed is 1360+620 = 1980 Rmts. Thiruppukuzhi Junction. (BLACK SPOT No. TN-02 /146) Ch. Km. 80+060. There is a cross road junction called Thiruppukuzhi at Ch. Km.80+060. On either side of the Project Highway there are temples, Primary school, Banks and it is one of the junction connecting the Baluchetty residents to other side of Carriageway. Nearer to this junction there is another junction called Musrivakkam at Ch. Km. 79+860. In similar fashion to the other junction, residents of Baluchetty village are crossing the Highway for their daily needs. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
change of scope proposal | Payments | it is hereby submitted that the tentative cost for making the provision will be around Rs.8.2 Cr. The proposal has been forwarded for attaining in principle approvals from Competent Authority as soon as possible. | synthetic_template_20250913 | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajapet from km 71.015 to107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode — Request for Vehicular Underpass at Tenkadapathangal & Musiri Villages Ch. Km. 106+000 - Reg. | Sir, in continuation to the above said Ref. No.3 relating to the proposed subway at Musiri/Tenkadapathangal villages it is hereby submitted that the tentative cost for making the provision will be around Rs. 8.2 Cr. (Eight crore twenty lakhs rupees only). The said amount has been arrived based on the following arrangements. 1. Size of underpass/subway will be 1 X 7.0 X 3.0 2. The Main Carriageway has to be raised by 1.50mtrs and similarly the service roads have to be lowered by similar depth to get the 3.0mtr clearance. 3. RCC retaining wall has proposed on approaches of underpass. 4. The Musiri branch road has to be regraded in such a way to suit the service road/underpass sill level & Junction developments to be made. Hence based on the above the proposal has been forwarded for attaining the in principle approvals from Competent Authority as soon as possible. Assuring our best services at all times. Thanking You. We look forward to your response. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
change of scope proposal | Dispute Resolution | In view of the above, the Authority Engineer hereby recommends the Change of Scope (No.2) Proposal due to additional Service Road Provision, one no. of CUP at Km.84+032, one No.Underpass @ 80+060, Foot Over Bridge at Dhamal Colony i.e.@ Km 81+600 instead of at 84+032, two Foot Over Bridges at 89+120 & 94+040 and subway at ch. Km.106+010 as mentioned above amounting to Rs.44,65,72,437/- | synthetic_template_20250913 | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode—Resubmission of Change of Scope Proposal-2 -Reg. | We hereby confirm that In reference to the above-referred chronology of correspondence and based on the recent site visits on 3 & 17 of June, 2021, Contractor had submitted the revised Change of Scope -2 proposals vide letter No. 084 stated as Ref. No.1. to an amount of Rs/- 56,71,88,373. The submitted proposal reviewed by AE as per provision of the Contract Agreement and following is being submitted for ready reference and further needful, please; There are some additional works require based on the request received from Hon’ble Member of Parliament, Hon’ble Member of Legislative Assembly, Local District Level Authorities and as well as from the Local Residents. The same is being examined and considered for the COS-2. The details and the expenditure on each proposal is being worked out and submitted for the Approval of Competent Authority. Additional Service Roads in Kancheepuram & Ranipet District jurisdictions: It may be noted that the Project stretch, which is having a length of 36.076 Kms from Karaipettai to Walajhpet i.e. between Chainages 71+015 to 107+091 is in the territory of two districts namely Kancheepuram & Ranipet. The project length of 14.859 kms is under Kancheepuram District i.e. between 71+015 to 85+874. In Kancheepuram District, there is a shortage of service road provision. Hence the District Admission made a representation to the Authority (endorsed vide Ref. No.23) to have a continuous service road provision which will avoid merging & demerging of service road traffic with MCW. In view of this a survey was conducted and found that the service road provision has to be made between 75+580 to 76+240 & 77+400 to 78+800 which come to a length of 660+700 = 1360 Rmts. The same is being considered in this COS-2. Similarly, for the Ranipet district out of 21.145 kms length i.e between Ch. Km. 85+874 to 107+019 there is a shortage of service road provision. Hence as the similar representation was received from the District Safety Council of Ranipet District (Which was endorsed to this office vide ref. No.24) a survey was conducted and proposed to have the service road provision between Chainages 88+160 to 88+560 & 94+640 to 94+860 i.e. 220+400 = 620 Rimts lengths. Hence total length of additional service road proposed is 1360+620 = 1980 Rmts. Thiruppukuzhi Junction. (BLACK SPOT No. TN-02 /146) Ch. Km. 80+060. There is a cross road junction called Thiruppukuzhi at Ch. Km.80+060. On either side of the Project Highway there are temples, Primary school, Banks and it is one of the junction connecting the Baluchetty residents to other side of Carriageway. Nearer to this junction there is another junction called Musrivakkam at Ch. Km. 79+860. In similar fashion to the other junction, residents of Baluchetty village are crossing the Highway for their daily needs. We appreciate your cooperation in this regard. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Contractor's delay in commencing the COS works | Change of Scope | It is to note that despite Competent Authority's intimation vide above said reference No.1 relating to in-principle approvals to the additional works, efforts to commence these works are yet to be seen at site. Hence, it has been advised to commence the approved CoS works on priority. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode — Progress of Works intimated under Change of Scope proposals. | Dear Sir, It is to note that despite of Competent Authority's intimation vide above said reference No.1 relating to the in-principle approvals to the additional Works, efforts to commence these works are yet to be seen at site. You are aware that while according approvals to the EoT proposals it is informed that “The Contractor shall strictly adhere to the construction program submitted by him and complete the balance works including CoS works during this extended period by augmenting resources” Hence it has been advised to commence the approved CoS works on priority. This is for your information and necessary actions. With Regards, CH Balakri a a Team Leader cum‘ Senior Highway Engineer, S.A. Infrastructure Consultants Pvt. Ltd., Kar-Wal, Six Lanning Project, Package-ll, Kancheepuram Copy to: 1. The Project Director, NHAI, PIU — Kancheepuram. 2. H.O. S.A. Infrastructure Consultants Pvt. Ltd. EAE «1 1101A, 11th Floor, Tower A-ll, Corporate Park, Uttar Pradesh. INDIA. Tel. :+91-120-6148000 ¦ | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Contractor's delay in commencing the COS works | Change of Scope | It is to note that despite Competent Authority's intimation vide above said reference No.1 relating to in-principle approvals to the additional works, efforts to commence these works are yet to be seen at site. Hence, it has been advised to commence the approved CoS works on priority. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode — Progress of Works intimated under Change of Scope proposals. | Dear Sir, It is to note that despite of Competent Authority's intimation vide above said reference No.1 relating to the in-principle approvals to the additional Works, efforts to commence these works are yet to be seen at site. You are aware that while according approvals to the EoT proposals it is informed that “The Contractor shall strictly adhere to the construction program submitted by him and complete the balance works including CoS works during this extended period by augmenting resources” Hence it has been advised to commence the approved CoS works on priority. This is for your information and necessary actions. With Regards, CH Balakri a a Team Leader cum‘ Senior Highway Engineer, S.A. Infrastructure Consultants Pvt. Ltd., Kar-Wal, Six Lanning Project, Package-ll, Kancheepuram Copy to: 1. The Project Director, NHAI, PIU — Kancheepuram. 2. H.O. S.A. Infrastructure Consultants Pvt. Ltd. EAE «1 1101A, 11th Floor, Tower A-ll, Corporate Park, Uttar Pradesh. INDIA. Tel. :+91-120-6148000 ¦ Thank you for your attention to this matter. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Contractor's delay in commencing the COS works | Dispute Resolution | It is to note that despite Competent Authority's intimation vide above said reference No.1 relating to in-principle approvals to the additional works, efforts to commence these works are yet to be seen at site. Hence, it has been advised to commence the approved CoS works on priority. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode — Progress of Works intimated under Change of Scope proposals. | Dear Sir, It is to note that despite of Competent Authority's intimation vide above said reference No.1 relating to the in-principle approvals to the additional Works, efforts to commence these works are yet to be seen at site. You are aware that while according approvals to the EoT proposals it is informed that “The Contractor shall strictly adhere to the construction program submitted by him and complete the balance works including CoS works during this extended period by augmenting resources” Hence it has been advised to commence the approved CoS works on priority. This is for your information and necessary actions. With Regards, CH Balakri a a Team Leader cum‘ Senior Highway Engineer, S.A. Infrastructure Consultants Pvt. Ltd., Kar-Wal, Six Lanning Project, Package-ll, Kancheepuram Copy to: 1. The Project Director, NHAI, PIU — Kancheepuram. 2. H.O. S.A. Infrastructure Consultants Pvt. Ltd. EAE «1 1101A, 11th Floor, Tower A-ll, Corporate Park, Uttar Pradesh. INDIA. Tel. :+91-120-6148000 ¦ We await your further instructions. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Contractor's delay in commencing the COS works | Dispute Resolution | It is to note that despite Competent Authority's intimation vide above said reference No.1 relating to in-principle approvals to the additional works, efforts to commence these works are yet to be seen at site. Hence, it has been advised to commence the approved CoS works on priority. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode — Progress of Works intimated under Change of Scope proposals. | Dear Sir, It is to note that despite of Competent Authority's intimation vide above said reference No.1 relating to the in-principle approvals to the additional Works, efforts to commence these works are yet to be seen at site. You are aware that while according approvals to the EoT proposals it is informed that “The Contractor shall strictly adhere to the construction program submitted by him and complete the balance works including CoS works during this extended period by augmenting resources” Hence it has been advised to commence the approved CoS works on priority. This is for your information and necessary actions. With Regards, CH Balakri a a Team Leader cum‘ Senior Highway Engineer, S.A. Infrastructure Consultants Pvt. Ltd., Kar-Wal, Six Lanning Project, Package-ll, Kancheepuram Copy to: 1. The Project Director, NHAI, PIU — Kancheepuram. 2. H.O. S.A. Infrastructure Consultants Pvt. Ltd. EAE «1 1101A, 11th Floor, Tower A-ll, Corporate Park, Uttar Pradesh. INDIA. Tel. :+91-120-6148000 ¦ | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Contractor's delay in commencing the COS works | Contractor's Obligations | It is to note that despite Competent Authority's intimation vide above said reference No.1 relating to in-principle approvals to the additional works, efforts to commence these works are yet to be seen at site. Hence, it has been advised to commence the approved CoS works on priority. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode — Progress of Works intimated under Change of Scope proposals. | Dear Sir, It is to note that despite of Competent Authority's intimation vide above said reference No.1 relating to the in-principle approvals to the additional Works, efforts to commence these works are yet to be seen at site. You are aware that while according approvals to the EoT proposals it is informed that “The Contractor shall strictly adhere to the construction program submitted by him and complete the balance works including CoS works during this extended period by augmenting resources” Hence it has been advised to commence the approved CoS works on priority. This is for your information and necessary actions. With Regards, CH Balakri a a Team Leader cum‘ Senior Highway Engineer, S.A. Infrastructure Consultants Pvt. Ltd., Kar-Wal, Six Lanning Project, Package-ll, Kancheepuram Copy to: 1. The Project Director, NHAI, PIU — Kancheepuram. 2. H.O. S.A. Infrastructure Consultants Pvt. Ltd. EAE «1 1101A, 11th Floor, Tower A-ll, Corporate Park, Uttar Pradesh. INDIA. Tel. :+91-120-6148000 ¦ | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Contractor's delay in commencing the COS works | Contractor's Obligations | It is to note that despite Competent Authority's intimation vide above said reference No.1 relating to in-principle approvals to the additional works, efforts to commence these works are yet to be seen at site. Hence, it has been advised to commence the approved CoS works on priority. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode — Progress of Works intimated under Change of Scope proposals. | Dear Sir, It is to note that despite of Competent Authority's intimation vide above said reference No.1 relating to the in-principle approvals to the additional Works, efforts to commence these works are yet to be seen at site. You are aware that while according approvals to the EoT proposals it is informed that “The Contractor shall strictly adhere to the construction program submitted by him and complete the balance works including CoS works during this extended period by augmenting resources” Hence it has been advised to commence the approved CoS works on priority. This is for your information and necessary actions. With Regards, CH Balakri a a Team Leader cum‘ Senior Highway Engineer, S.A. Infrastructure Consultants Pvt. Ltd., Kar-Wal, Six Lanning Project, Package-ll, Kancheepuram Copy to: 1. The Project Director, NHAI, PIU — Kancheepuram. 2. H.O. S.A. Infrastructure Consultants Pvt. Ltd. EAE «1 1101A, 11th Floor, Tower A-ll, Corporate Park, Uttar Pradesh. INDIA. Tel. :+91-120-6148000 ¦ | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Rejection of COS request by Authority Engineer/Authority | Change of Scope; Payments; Dispute Resolution; EoT | In the view of the Contract Provision and IRC Specification, the Authority Engineer opines that Contractor request for COS does not attract the any variation from the scope of work. Thus request for consider COS is being rejected herewith. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/Lot-11/20220609_AE_SPK_1017-Change of Scope Proposal- Clarification on Proposal for Increasing the Height of the Existing RCC barrier for (i) ROB at Km 72+200.pdf | Six lanning of Karaipettai to Walajahpet Section of NH-4 (New NH-48) from Km 71+015 (Existing Km 71+000) to Km 107+091 (Existing Km 107+068) on EPC mode in the State of Tamil Nadu under NHDP Phase-V) - Change of Scope Proposal- Clarification on Proposal for Increasing the Height of the Existing RCC barrier for (i) ROB at Km 72+200 (ii) Flyover at Km 106+687 (RHS) as per Contract Agreement Provisions- Reg. | Dear Sir, With respect to the above subject and letter stated in ref No: (5), the Contractor has submitted the clarification regarding proposal for increasing the RCC barrier height @ ROB at Km 72+200 & Flyover at Km 106+687 (RHS) for which our comments are as follows: 1) The Contractor submitted the drawings vide letter stated as Ref No (3) and requested for positive COS & Extra time for the work of Existing RCC barrier (i) ROB at Km 72+200 (ii) Flyover at km 106+687(RHS), the same has been replied vide AE letter as stated in above Ref No (4). 2) Further to AE letter, Contractor once again submitted clarifications & requested for COS vide letter stated in above Ref No (5), the same has been reviewed and submit that as per Clause 6.16 of Schedule B of the Contract, ““*“RR — Repair & Rehabilitation” which clearly states that “The repairing and restoration work such as protection work, replacement of railing by crash barrier, Replacement of bearing and expansion joint, wearing coat, spalling & corroded reinforcement, RE wall panel, MBCB etc. of bridge is not limited and any other item as per site condition shall be carried out as per direction of Authority / Independent Engineer. Any Change in location of above structure or change in approaches length not consider under Change of Scope’. he Page 1 of 2 | FALSE | real_data
Rejection of COS request by Authority Engineer/Authority | Change of Scope; Payments; Dispute Resolution; EoT | the Contractor may go ahead with toll plaza works as provisioned in the Contract/Guidelines. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/Lot-12/20231201_AE_SPK_1573-Request to Descope Toll User fee Plaza to be Constructed as per Clause 2.1 Schedule – C and Schedule – H (Page 188).pdf | Request to Descope Toll / User fee Plaza to be Constructed as per Clause 2.1 Schedule — C and Schedule — H (Page 188) — Reg | In response to your letter No. 311 dated 24.11.2023 stated as Ref. No.4 relating to “Request to Descope Toll / User fee Plaza to be constructed as per Clause 2.1 Schedule — C and Schedule — H (Page 188). The Authority had invited the bids for this project, inclusive of toll plaza also. Based on which only, the Contractor had tendered for the project. The Construction of toll plaza is the requirement for the Authority provisioned in Schedule-C of the Contract. If the Authority wants to de-scope any works based on developments happening around the project, it might have advised the Contractor to propose the variation to that effect. However, the Authority had not communicated any variation | FALSE | real_data
Rejection of COS request by Authority Engineer/Authority | EoT | the Contractor may go ahead with toll plaza works as provisioned in the Contract/Guidelines. | synthetic_template_20250913 | Request to Descope Toll / User fee Plaza to be Constructed as per Clause 2.1 Schedule — C and Schedule — H (Page 188) — Reg | In response to your letter No. 311 dated 24.11.2023 stated as Ref. No.4 relating to “Request to Descope Toll / User fee Plaza to be constructed as per Clause 2.1 Schedule — C and Schedule — H (Page 188). The Authority had invited the bids for this project, inclusive of toll plaza also. Based on which only, the Contractor had tendered for the project. The Construction of toll plaza is the requirement for the Authority provisioned in Schedule-C of the Contract. If the Authority wants to de-scope any works based on developments happening around the project, it might have advised the Contractor to propose the variation to that effect. However, the Authority had not communicated any variation | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Rejection of COS request by Authority Engineer/Authority | EoT | In the view of the Contract Provision and IRC Specification, the Authority Engineer opines that Contractor request for COS does not attract the any variation from the scope of work. Thus request for consider COS is being rejected herewith. | synthetic_template_20250913 | Change of Scope Proposal as per Article -13 of Contract Agreement-Proposal of Increasing the Height of the Existing RCC barrier for (i) ROB at Km 72+200 (ii) Flyover at Km 106+687 (RHS) - Reg. | Dear Sir,\n\nIn reference to the subject matter and under letter ref (3), the Contractor has submitted the proposal for increasing the height of the existing RCC barrier for (i) ROB at Km 72+200 (ii) Flyover at Km 106+687(RHS) as COS proposal as per article-13 of Contract Agreement.\n\nIn this regards the Authority Engineer, issued the Monthly Progress review report vide letter no.785 dated 29.11.2021 and requested to the Contractor that “After laying of the DBM on the existing ROB at 72 km & at Fly over 106 km the height of the RCC Crash barrier has been reduced and further it will reduce after laying the BC. Hence it is advised to raise the height of the Crash barrier by\n\nproviding a Gl Pipe or any other suitable provision.”\n\nIt is submitted that, the existing height of the Crash barrier at ROB is averaging height 650 mm and similarly for flyover it is around 747mm. Thus, the EPC Contractor as requested to the Authority Engineer to increase the height of the Crash barrier as per IRC standard to 4.4m (1100mm).\n\nThe Contractor submitted the drawing with GI pipe over the top of Crash barrier to ensure requisite height as per IRC standards. And the length of railing provided for ROB and Flyover (RHS) are 881.259 and 685 m respectively. In this regard, the Contractor requested for positive COS & Extra time for the work of Existing RCC barrier (i) ROB at Km 72+200 (ii) Flyover at km 106+687(RHS). | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Rejection of COS request by Authority Engineer/Authority | Change of Scope | the Contractor may go ahead with toll plaza works as provisioned in the Contract/Guidelines. | synthetic_template_20250913 | Request to Descope Toll / User fee Plaza to be Constructed as per Clause 2.1 Schedule — C and Schedule — H (Page 188) — Reg | We would like to inform you that In response to your letter No. 311 dated 24.11.2023 stated as Ref. No.4 relating to “Request to Descope Toll / User fee Plaza to be constructed as per Clause 2.1 Schedule — C and Schedule — H (Page 188). The Authority had invited the bids for this project, inclusive of toll plaza also. Based on which only, the Contractor had tendered for the project. The Construction of toll plaza is the requirement for the Authority provisioned in Schedule-C of the Contract. If the Authority wants to de-scope any works based on developments happening around the project, it might have advised the Contractor to propose the variation to that effect. However, the Authority had not communicated any variation | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Rejection of COS request by Authority Engineer/Authority | Payments | In the view of the Contract Provision and IRC Specification, the Authority Engineer opines that Contractor request for COS does not attract the any variation from the scope of work. Thus request for consider COS is being rejected herewith. | synthetic_template_20250913 | Change of Scope Proposal as per Article -13 of Contract Agreement-Proposal of Increasing the Height of the Existing RCC barrier for (i) ROB at Km 72+200 (ii) Flyover at Km 106+687 (RHS) - Reg. | It is brought to your attention that Dear Sir,\n\nIn reference to the subject matter and under letter ref (3), the Contractor has submitted the proposal for increasing the height of the existing RCC barrier for (i) ROB at Km 72+200 (ii) Flyover at Km 106+687(RHS) as COS proposal as per article-13 of Contract Agreement.\n\nIn this regards the Authority Engineer, issued the Monthly Progress review report vide letter no.785 dated 29.11.2021 and requested to the Contractor that “After laying of the DBM on the existing ROB at 72 km & at Fly over 106 km the height of the RCC Crash barrier has been reduced and further it will reduce after laying the BC. Hence it is advised to raise the height of the Crash barrier by\n\nproviding a Gl Pipe or any other suitable provision.”\n\nIt is submitted that, the existing height of the Crash barrier at ROB is averaging height 650 mm and similarly for flyover it is around 747mm. Thus, the EPC Contractor as requested to the Authority Engineer to increase the height of the Crash barrier as per IRC standard to 4.4m (1100mm).\n\nThe Contractor submitted the drawing with GI pipe over the top of Crash barrier to ensure requisite height as per IRC standards. And the length of railing provided for ROB and Flyover (RHS) are 881.259 and 685 m respectively. In this regard, the Contractor requested for positive COS & Extra time for the work of Existing RCC barrier (i) ROB at Km 72+200 (ii) Flyover at km 106+687(RHS). | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Rejection of COS request by Authority Engineer/Authority | Payments | the Contractor may go ahead with toll plaza works as provisioned in the Contract/Guidelines. | synthetic_template_20250913 | Request to Descope Toll / User fee Plaza to be Constructed as per Clause 2.1 Schedule — C and Schedule — H (Page 188) — Reg | In response to your letter No. 311 dated 24.11.2023 stated as Ref. No.4 relating to “Request to Descope Toll / User fee Plaza to be constructed as per Clause 2.1 Schedule — C and Schedule — H (Page 188). The Authority had invited the bids for this project, inclusive of toll plaza also. Based on which only, the Contractor had tendered for the project. The Construction of toll plaza is the requirement for the Authority provisioned in Schedule-C of the Contract. If the Authority wants to de-scope any works based on developments happening around the project, it might have advised the Contractor to propose the variation to that effect. However, the Authority had not communicated any variation | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Rejection of COS request by Authority Engineer/Authority | Dispute Resolution | In the view of the Contract Provision and IRC Specification, the Authority Engineer opines that Contractor request for COS does not attract the any variation from the scope of work. Thus request for consider COS is being rejected herewith. | synthetic_template_20250913 | Change of Scope Proposal as per Article -13 of Contract Agreement-Proposal of Increasing the Height of the Existing RCC barrier for (i) ROB at Km 72+200 (ii) Flyover at Km 106+687 (RHS) - Reg. | Dear Sir,\n\nIn reference to the subject matter and under letter ref (3), the Contractor has submitted the proposal for increasing the height of the existing RCC barrier for (i) ROB at Km 72+200 (ii) Flyover at Km 106+687(RHS) as COS proposal as per article-13 of Contract Agreement.\n\nIn this regards the Authority Engineer, issued the Monthly Progress review report vide letter no.785 dated 29.11.2021 and requested to the Contractor that “After laying of the DBM on the existing ROB at 72 km & at Fly over 106 km the height of the RCC Crash barrier has been reduced and further it will reduce after laying the BC. Hence it is advised to raise the height of the Crash barrier by\n\nproviding a Gl Pipe or any other suitable provision.”\n\nIt is submitted that, the existing height of the Crash barrier at ROB is averaging height 650 mm and similarly for flyover it is around 747mm. Thus, the EPC Contractor as requested to the Authority Engineer to increase the height of the Crash barrier as per IRC standard to 4.4m (1100mm).\n\nThe Contractor submitted the drawing with GI pipe over the top of Crash barrier to ensure requisite height as per IRC standards. And the length of railing provided for ROB and Flyover (RHS) are 881.259 and 685 m respectively. In this regard, the Contractor requested for positive COS & Extra time for the work of Existing RCC barrier (i) ROB at Km 72+200 (ii) Flyover at km 106+687(RHS). We appreciate your cooperation in this regard. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Rejection of COS request by Authority Engineer/Authority | Dispute Resolution | the Contractor may go ahead with toll plaza works as provisioned in the Contract/Guidelines. | synthetic_template_20250913 | Request to Descope Toll / User fee Plaza to be Constructed as per Clause 2.1 Schedule — C and Schedule — H (Page 188) — Reg | In response to your letter No. 311 dated 24.11.2023 stated as Ref. No.4 relating to “Request to Descope Toll / User fee Plaza to be constructed as per Clause 2.1 Schedule — C and Schedule — H (Page 188). The Authority had invited the bids for this project, inclusive of toll plaza also. Based on which only, the Contractor had tendered for the project. The Construction of toll plaza is the requirement for the Authority provisioned in Schedule-C of the Contract. If the Authority wants to de-scope any works based on developments happening around the project, it might have advised the Contractor to propose the variation to that effect. However, the Authority had not communicated any variation | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Design & Drawings for COS works | EoT; Payments; Dispute Resolution; Change of Scope; Others | Based on the above it is requested to recalculate the drain invert levels and to be resubmitted. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/Lot-11/20220131_AE_SPK_847_Change of Scope - Submission of Drain Invert Level Profile for Service Road (COS) Locations.pdf | Change of Scope - Submission of Drain Invert Level Profile for Service Road (COS) Locations - Reg. | With respect to the above said reference regarding Submission of Drain Invert Levels following observations are communicated: a) At the following locations Drain and Road uniform offset of 225mm is not achieved. (i) 75+560 to 76+200 BHS (ii) 77+500 to 78+100 BHS (iii) 88+130 to 88+560 BHS Kindly correct the drain top levels accordingly to maintain the 225mm level difference. b) At the following locations Drain is shown on inner side (i.e., in between Service Road & Main Carriage Way), whereas it has to be in extreme outer side of Service Road as per present site condition. (i) 75+480 to 75+550 BHS (ii) 76+200 to 76+340 BHS (iii) 77+300 to 77+500 LHS 77+370 to 77+530 RHS (iv) 88+060 to 88+130 BHS (v) 94+860 to 94+960 BHS Hence based on the above it is requested to recalculate the Drain Invert levels and to be resubmitted. The Contractor is further requested to resubmit the revised drawing along with modifications marked in RED in the previous submission which is enclosed | FALSE | real_data
Design & Drawings for COS works | EoT; Payments; Dispute Resolution; Change of Scope; Others | We are hereby submitting the structure drawings for LVUP@ Km.79+860 | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-6/20230424_SPK_AE_243_Change of Scope - Submission of Structure Drawings for LVUP at Km.79+860 – Reg.pdf | Change of Scope - Submission of Structure Drawings for LVUP at Km.79+860 - Reg | With reference to above subject and letter cited at (2) above, we are hereby submitting the Structure Drawings for LVUP at Km.79+860 as below: S.No Description Drg No Sheets Rev NH48/STR/GAD/LVUP 1 GAD for COS LVUP at KM.79+860 /COS/1001 1 of 2 RO NH48/STR/GAD/LVUP 2 GAD for COS LVUP at KM.79+860 /COS/1001 2 of 2 RO 3 Detail of Reinforcement for LVUP NH48/STR/REN/LVUP/ 1x12.0x4.5 at KM.79+860 CH:79+860/2001 This is for your kind review and approval, please. | FALSE | real_data
Design & Drawings for COS works | EoT; Payments; Dispute Resolution; Change of Scope; Others | We are herewith re-submitting the drawings for Cattle Underpass (CUP) at Km.84.032 | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-6/20230719_SPK_AE_285_Change of Scope-Re-Submission of Drawings for CUP at Km.84+032 - Reg (1).pdf | Six laning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000) to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V- Change of Scope-Re-Submission of Drawings for CUP at Km.84+032 - Reg | Dear Sir, With reference to the above subject and the observations communicated vide your letter cited at ref (6) above has been incorporated as below: S1.No ¦ Observations ¦ Compliance 1. Structural design of Box Culvert proposed at 84+028 is in order. However, this culvert is abutting the proposed CUP @ 84+032 and hence drawing shown is not correct. Retaining walls to be shown as per actual requirement. The CUP location is shifted to chainage Km.84+034 to avoid abutting of structure with Box culvert at Km.84+028. Retaining wall length are incorporated in the CUP drawings. 2. However, it is asked to provide 12mm reinforcement instead of 10mm for the bar stated as W2 considering the requirements of requirement of IRC 112. As per IRC 112-2020, cl.16.3, “For walls subjected to predominantly out of plane bending, the rules of slab apply if they are more severe.” Box are predominantly out of plane bending hence rules of slab are applicable and provided bar is sufficient. 3. The junction improvement drawing showing the underpass and its approaches should be elaborated for better understanding of the functioning of the CUP. Noted. The junction improvement drawing is submitted for your reference. We are hereby re-submitting the drawings for Cattle Underpass (CUP) at Km.84+032 as below: S1.No Description Drg No Rev 1. Cattle Underpass (CUP) GAD for CUP at Km.84+032 Sheet 01 OF 02 NH-48/STR/GAD/CUP/CH:84+032/COS/1001 R2 2. GAD for CUP at Km 84+032 Sheet 02 OF 02 NH-48/STR/GAD/CUP/CH:84+032/COS/1001 R2 3. Details of Reinforcement for CUP at Km 84+032 Sheet 01 OF 01 NH-48/STR/REN/CUP/CH:84+032/COS/2001 R2 This is for your kind review and approval, please. | FALSE | real_data
Design & Drawings for COS works | EoT | Based on the above it is requested to recalculate the drain invert levels and to be resubmitted. | synthetic_template_20250913 | Change of Scope - Submission of Drain Invert Level Profile for Service Road (COS) Locations - Reg. | With respect to the above said reference regarding Submission of Drain Invert Levels following observations are communicated: a) At the following locations Drain and Road uniform offset of 225mm is not achieved. (i) 75+560 to 76+200 BHS (ii) 77+500 to 78+100 BHS (iii) 88+130 to 88+560 BHS Kindly correct the drain top levels accordingly to maintain the 225mm level difference. b) At the following locations Drain is shown on inner side (i.e., in between Service Road & Main Carriage Way), whereas it has to be in extreme outer side of Service Road as per present site condition. (i) 75+480 to 75+550 BHS (ii) 76+200 to 76+340 BHS (iii) 77+300 to 77+500 LHS 77+370 to 77+530 RHS (iv) 88+060 to 88+130 BHS (v) 94+860 to 94+960 BHS Hence based on the above it is requested to recalculate the Drain Invert levels and to be resubmitted. The Contractor is further requested to resubmit the revised drawing along with modifications marked in RED in the previous submission which is enclosed We look forward to your response. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Design & Drawings for COS works | EoT | We are herewith re-submitting the drawings for Cattle Underpass (CUP) at Km.84.032 | synthetic_template_20250913 | Six laning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000) to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V- Change of Scope-Re-Submission of Drawings for CUP at Km.84+032 - Reg | We hereby confirm that Dear Sir, With reference to the above subject and the observations communicated vide your letter cited at ref (6) above has been incorporated as below: S1.No ¦ Observations ¦ Compliance 1. Structural design of Box Culvert proposed at 84+028 is in order. However, this culvert is abutting the proposed CUP @ 84+032 and hence drawing shown is not correct. Retaining walls to be shown as per actual requirement. The CUP location is shifted to chainage Km.84+034 to avoid abutting of structure with Box culvert at Km.84+028. Retaining wall length are incorporated in the CUP drawings. 2. However, it is asked to provide 12mm reinforcement instead of 10mm for the bar stated as W2 considering the requirements of requirement of IRC 112. As per IRC 112-2020, cl.16.3, “For walls subjected to predominantly out of plane bending, the rules of slab apply if they are more severe.” Box are predominantly out of plane bending hence rules of slab are applicable and provided bar is sufficient. 3. The junction improvement drawing showing the underpass and its approaches should be elaborated for better understanding of the functioning of the CUP. Noted. The junction improvement drawing is submitted for your reference. We are hereby re-submitting the drawings for Cattle Underpass (CUP) at Km.84+032 as below: S1.No Description Drg No Rev 1. Cattle Underpass (CUP) GAD for CUP at Km.84+032 Sheet 01 OF 02 NH-48/STR/GAD/CUP/CH:84+032/COS/1001 R2 2. GAD for CUP at Km 84+032 Sheet 02 OF 02 NH-48/STR/GAD/CUP/CH:84+032/COS/1001 R2 3. Details of Reinforcement for CUP at Km 84+032 Sheet 01 OF 01 NH-48/STR/REN/CUP/CH:84+032/COS/2001 R2 This is for your kind review and approval, please. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Design & Drawings for COS works | Payments | Based on the above it is requested to recalculate the drain invert levels and to be resubmitted. | synthetic_template_20250913 | Change of Scope - Submission of Drain Invert Level Profile for Service Road (COS) Locations - Reg. | With respect to the above said reference regarding Submission of Drain Invert Levels following observations are communicated: a) At the following locations Drain and Road uniform offset of 225mm is not achieved. (i) 75+560 to 76+200 BHS (ii) 77+500 to 78+100 BHS (iii) 88+130 to 88+560 BHS Kindly correct the drain top levels accordingly to maintain the 225mm level difference. b) At the following locations Drain is shown on inner side (i.e., in between Service Road & Main Carriage Way), whereas it has to be in extreme outer side of Service Road as per present site condition. (i) 75+480 to 75+550 BHS (ii) 76+200 to 76+340 BHS (iii) 77+300 to 77+500 LHS 77+370 to 77+530 RHS (iv) 88+060 to 88+130 BHS (v) 94+860 to 94+960 BHS Hence based on the above it is requested to recalculate the Drain Invert levels and to be resubmitted. The Contractor is further requested to resubmit the revised drawing along with modifications marked in RED in the previous submission which is enclosed | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Design & Drawings for COS works | Payments | Based on the above it is requested to recalculate the drain invert levels and to be resubmitted. | synthetic_template_20250913 | Change of Scope - Submission of Drain Invert Level Profile for Service Road (COS) Locations - Reg. | Please note that With respect to the above said reference regarding Submission of Drain Invert Levels following observations are communicated: a) At the following locations Drain and Road uniform offset of 225mm is not achieved. (i) 75+560 to 76+200 BHS (ii) 77+500 to 78+100 BHS (iii) 88+130 to 88+560 BHS Kindly correct the drain top levels accordingly to maintain the 225mm level difference. b) At the following locations Drain is shown on inner side (i.e., in between Service Road & Main Carriage Way), whereas it has to be in extreme outer side of Service Road as per present site condition. (i) 75+480 to 75+550 BHS (ii) 76+200 to 76+340 BHS (iii) 77+300 to 77+500 LHS 77+370 to 77+530 RHS (iv) 88+060 to 88+130 BHS (v) 94+860 to 94+960 BHS Hence based on the above it is requested to recalculate the Drain Invert levels and to be resubmitted. The Contractor is further requested to resubmit the revised drawing along with modifications marked in RED in the previous submission which is enclosed | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Design & Drawings for COS works | Change of Scope | We are herewith re-submitting the drawings for Cattle Underpass (CUP) at Km.84.032 | synthetic_template_20250913 | Six laning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000) to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V- Change of Scope-Re-Submission of Drawings for CUP at Km.84+032 - Reg | Kindly be informed that Dear Sir, With reference to the above subject and the observations communicated vide your letter cited at ref (6) above has been incorporated as below: S1.No ¦ Observations ¦ Compliance 1. Structural design of Box Culvert proposed at 84+028 is in order. However, this culvert is abutting the proposed CUP @ 84+032 and hence drawing shown is not correct. Retaining walls to be shown as per actual requirement. The CUP location is shifted to chainage Km.84+034 to avoid abutting of structure with Box culvert at Km.84+028. Retaining wall length are incorporated in the CUP drawings. 2. However, it is asked to provide 12mm reinforcement instead of 10mm for the bar stated as W2 considering the requirements of requirement of IRC 112. As per IRC 112-2020, cl.16.3, “For walls subjected to predominantly out of plane bending, the rules of slab apply if they are more severe.” Box are predominantly out of plane bending hence rules of slab are applicable and provided bar is sufficient. 3. The junction improvement drawing showing the underpass and its approaches should be elaborated for better understanding of the functioning of the CUP. Noted. The junction improvement drawing is submitted for your reference. We are hereby re-submitting the drawings for Cattle Underpass (CUP) at Km.84+032 as below: S1.No Description Drg No Rev 1. Cattle Underpass (CUP) GAD for CUP at Km.84+032 Sheet 01 OF 02 NH-48/STR/GAD/CUP/CH:84+032/COS/1001 R2 2. GAD for CUP at Km 84+032 Sheet 02 OF 02 NH-48/STR/GAD/CUP/CH:84+032/COS/1001 R2 3. Details of Reinforcement for CUP at Km 84+032 Sheet 01 OF 01 NH-48/STR/REN/CUP/CH:84+032/COS/2001 R2 This is for your kind review and approval, please. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Design & Drawings for COS works | Change of Scope | We are hereby submitting the structure drawings for LVUP@ Km.79+860 | synthetic_template_20250913 | Change of Scope - Submission of Structure Drawings for LVUP at Km.79+860 - Reg | With reference to above subject and letter cited at (2) above, we are hereby submitting the Structure Drawings for LVUP at Km.79+860 as below: S.No Description Drg No Sheets Rev NH48/STR/GAD/LVUP 1 GAD for COS LVUP at KM.79+860 /COS/1001 1 of 2 RO NH48/STR/GAD/LVUP 2 GAD for COS LVUP at KM.79+860 /COS/1001 2 of 2 RO 3 Detail of Reinforcement for LVUP NH48/STR/REN/LVUP/ 1x12.0x4.5 at KM.79+860 CH:79+860/2001 This is for your kind review and approval, please. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Design & Drawings for COS works | Dispute Resolution | Based on the above it is requested to recalculate the drain invert levels and to be resubmitted. | synthetic_template_20250913 | Change of Scope - Submission of Drain Invert Level Profile for Service Road (COS) Locations - Reg. | This is to notify you that With respect to the above said reference regarding Submission of Drain Invert Levels following observations are communicated: a) At the following locations Drain and Road uniform offset of 225mm is not achieved. (i) 75+560 to 76+200 BHS (ii) 77+500 to 78+100 BHS (iii) 88+130 to 88+560 BHS Kindly correct the drain top levels accordingly to maintain the 225mm level difference. b) At the following locations Drain is shown on inner side (i.e., in between Service Road & Main Carriage Way), whereas it has to be in extreme outer side of Service Road as per present site condition. (i) 75+480 to 75+550 BHS (ii) 76+200 to 76+340 BHS (iii) 77+300 to 77+500 LHS 77+370 to 77+530 RHS (iv) 88+060 to 88+130 BHS (v) 94+860 to 94+960 BHS Hence based on the above it is requested to recalculate the Drain Invert levels and to be resubmitted. The Contractor is further requested to resubmit the revised drawing along with modifications marked in RED in the previous submission which is enclosed | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Design & Drawings for COS works | Others | We are hereby submitting the structure drawings for LVUP@ Km.79+860 | synthetic_template_20250913 | Change of Scope - Submission of Structure Drawings for LVUP at Km.79+860 - Reg | With reference to above subject and letter cited at (2) above, we are hereby submitting the Structure Drawings for LVUP at Km.79+860 as below: S.No Description Drg No Sheets Rev NH48/STR/GAD/LVUP 1 GAD for COS LVUP at KM.79+860 /COS/1001 1 of 2 RO NH48/STR/GAD/LVUP 2 GAD for COS LVUP at KM.79+860 /COS/1001 2 of 2 RO 3 Detail of Reinforcement for LVUP NH48/STR/REN/LVUP/ 1x12.0x4.5 at KM.79+860 CH:79+860/2001 This is for your kind review and approval, please. We look forward to your response. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Change of Scope Approval/order | EoT; Payments; Dispute Resolution; Change of Scope | This has reference to the Chief General Manager (T)-TN, NHAI HQs letter cited above, conveyed the approval of Competent Authority for revoking/cancelling the tender discount of 9.66% on the Change of Scope approved earlier towards taking up various items in the subject project | /Users/hareeshkb/GenAIWork/krishna/NewCategories/Lot-11/20220217_PD_SPK_705_Approval of COS without discounting of 9.66 %.pdf | NHAI, PIU, Kancheepuram — Six laning of Karaipettai to Walajahpet section of NH-4 from Km 71/015 to Km 107/091 in the State of Tamil Nadu — Clarification on Change of Scope Proposal —- Approval Communicated - Reg. | This has reference to the Chief General Manager (T)-TN, NHAI HQs letter cited above, conveyed the approval of Competent Authority for revoking / cancelling the tender discount of 9.66% on the Change of Scope approved earlier towards taking up various items in the subject project subject to recording the impact of Cos and EoT in Settlement Agreement to be signed before CCIE. Thus, the cost of Cos without tender discount is Rs.39.86 Crore as follows; Amount (Rs.) with Amount (Rs.) without Tender Description Tender Discount Discount of of 9.66% 9.66% (i) “Service Road 12,25,76,464 12,25,76,464 r LVUP at Thiruppukuzhi Jn at Km (ii) 20/060 12,03,66,631 12,03,66,631 (iii) CUP at Dhamal lake Jn at Km 84/032 1,03,36,041 1,03,36,041 Construction of 3 Nos Foot Over Bridge (iv) (KM 81/600, Km 89/120 & Km 4,32,24,249 4,32,24,249 94/090) ¦ _ ; ¦ (v) PUP at Musiri Village at Km 106/010 5,62,03,609 5,62,03,609 ¦ (vi) Total Civil Cost anaes 35,27,06,994 (vii) ae Cost after discount of 31,86,35,498 0 (viii) fast @ 12% on (vi) 3,82,36,260 4,23,24,839 (ix) Labour cess @ 1% of Civil Cost (vi) 31,86,;355 35,27,070 36,00,58,113 39,85,58,903 — weet raters : FA -5 va -6, Haet-10 ganar, as ect - 110075. GATT: 91-11-25074100 / 25074200. dame : http://www.nhai.gov.in Corporate Office : G-5 & 6, Sector-10, Dwarka, New Delhi-110075. Phone : 91 -11-25074100 / 25074200. Website : http://www.nhai.gov.in (x)_ ¦ Total Cost Contd.. National Highways Authority of India 2, The copy of the same is enclosed herewith for further necessary action. Encl: Copy of reference. Yours faithfully, \ ty \F#Joz/22— for Projet Be otor PIU- Kancheepuram | FALSE | real_data
Change of Scope Approval/order | Payments; Change of Scope; EoT; Dispute Resolution | We hereby request the Authority Engineer to confirm the change of location of LVUP from Km.80+060 to Km.79+860. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-6/20230309_SPK_AE_215_Construction of Light Vehicular Underpass at Musaravakkam instead of Thiruppukuzhi junction under positive Change of Scope - Approval of the revised location @ Km.79860 sought - Reg..pdf | Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km.71+015 to Km 107+091 on EPC Mode in the state of Tamil Nadu under NHDP Phase-V — Construction of Light Vehicular Underpass at Musaravakkam instead of Thiruppukuzhi junction under positive Change of Scope - Approval of the revised location @ Km.79/860 sought - Reg. | 1. As per the approval of COS communicated by the Authority, a LVUP at Thiruppukuzhi Junction @ Km.80/060 is required to be constructed. This location has been identified as Black spot and the black spot ID is TN-(02)-146 (2015 -18) by MoRT&H. But repeated representations are being received by the residents towards construction of Subway/LVUP at Musaravakkam & Baluchetty Chatiram junction @ Km.79/860. 2. The Hon’ble Member of Parliament for Kancheepuram is also requesting for construction of subway/LVUP at Musaravakkam & Baluchetty Chatiram Junction @ Km.79/860. Further several representations were received from Panchayat Presidents of Thirupukkuzhi, Musaravakkam & Melottivakkam Panchayat through CM cell petition towards construction of LYUP @ Musaravakkam. 3. This issue was discussed during the Road Safety meeting held with the Collector on 16.02.2023 and the District Collector also echoed the opinion of construction of LVUP @ Musaravakkam received through several petitions and representations. 4. Based on the instructions received from the Authority, the Authority Engineer examined the site condition, and it has been understood that the Authority Engineer has opined that it is feasible to construct a LVUP of size 1 x 12.0 x 4 at Musaravakkam village. 5. It may also be noted and as informed in the above paragraph the location has been identified as Black spot by MoRTH at Km 80/060, refer letters from PIU-Kanchipuram cited at (2) & (3) in this connection. 6. We hereby request the Authority Engineer to confirm the change of location of LVUP from Km.80/060 to Km.79/860, so that we shall communicate the same to our Design Consultant for further preparation of detailed design and drawings. | FALSE | real_data
Change of Scope Approval/order | Payments; Change of Scope; EoT; Dispute Resolution | Based on the above said chronology of correspondence, please find enclosed herewith Competent Authority's approvals for the Final COS proposals | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/Lot-12/20230707_IE_SPK_1418 - Final Change of Scope Order - Approval Communicated.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Final Change of Scope Order - Approval Communicated —- Reg. | Based on the above said chronology of correspondence, please find enclosed herewith the Competent Authority’s approvals for the Final COS proposals submitted by yourself vide Ref. No.4. Hence, as per the Contract Article No. 13.2.4 it is hereby asked to progress the Works accordingly. This is for your information and immediate actions. | FALSE | real_data
Change of Scope Approval/order | Payments; Change of Scope; EoT; Dispute Resolution | it is to inform that the Regional Officer, NHAI has accorded approval towards the estimate for the balance 9 locations for an amount of Rs.1,09,16,532/- (excluding GST) under Change of Scope (COS) | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/Lot-12/20200506_PD_AE_862-Blackspot Short term Measures.pdf | NHAI, PIU Kancheepuram - Six laning of Karaipettai to Walajahpet section of NH-4 (Km 71/015 to Km 107/8091) in the State of Tamil Nadu - Black Spots identified by Ministry during 2016, 2017 & 2018 — Recommendations of remedial measures — Estimate submitted for Short Term remedial measures for 09 Nos. of Black Spots locations — Approval Communicated - Reg. | With reference to the letter cited 1st above, requesting for the approval of Competent Authority of NHAI for the proposal of short term measures to mitigate the black spots in the Karaipettai to Walajahpet (Km 71/015 to Km 107/091) section of NH-4 for 10 locations and one cattle underpass for an amount of Rs. 2,42,17,503/- (including GST) under Change of Scope (COS) to the existing EPC Contractor. On scrutiny of the above proposals vide reference 2nd cited it has been communicated that as per the Ministry list 05.12.2019 Damal East Bypass junction is not in Ministry list of identified Black spots, and also the cattle under pass was provided without estimate. Hence, these two proposals were not considered by Competent Authority. In this regard, it is to inform that the Regional Officer, NHAI has accorded approval towards the estimate for the balance 9 locations for an amount of Rs. 1,09,16,532/- (excluding GST) under Change of Scope (COS) as detailed below: LS No. Junction 1 White Gate Jn. Km 71/000 to Km 71/500 22,52,588 2 Ariyaperumbakkam Jn Km 75/010 4,86,751 3 Kizambi Jn Km 76/846 4,37,538 4 Baluchettychathiram (East) Jn. Km 79/300 9,39,359 Total 18,93,853 19,68,926 3,94,448 4,03,188 20,20,046 Junction Thiruppukuzhi Jn. Km 80/060 Damal Lake Jn. Km 84/048 Perumbulipakkam Jn. Km 87/550 Ocheri Jn. Km 93/070 Kadaperi Jn. Km 100/080 (A) 1,03,96,697 Transportation @ 5% of (A) 5,19,835 Total 1,09,16,532 In view of urgency in rectifying Black spots, the EPC Contractor may be requested to take up and complete the short term measures within a month time and report it accordingly. Further it is also requested to submit the detailed estimate for Cattle Under Pass at the earliest for getting the approval of the Competent Authority. Further, for the 8 nos of High Mast Lights included in the estimate. | FALSE | real_data
QAP, EMP, EHS and Construction Programme | Contractor's Obligations | we are submitting the base line "Programme" pursuant to Clause 10.1 (iii) of the EPC Contract Agreement. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-1/2. Submission of base line programme.pdf | Submission of Base Line Programme - Reg. | With reference to the subject matter, we wish to inform you that we are submitting the base line “Programme” pursuant to Clause 10.1 (iii) of the EPC Contract Agreement for your kind perusal and record please. Please note that the programme is based on the assumption that the land is made available as per schedule —A, Annexure II of the CA. | FALSE | real_data
QAP, EMP, EHS and Construction Programme | Contractor's Obligations | As per the work program, Contractor planned an expenditure of Rs/- 88.085 Cr which is 16.52 % of the Contract Amount. However, the so far achieved financial progress is 35.10 % and the physical progress is 40.80%. Hence the cumulative physical progress will be 57.32% by the end of March 2022. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LOT-10/20211111_AE_PD_766_Submission of work program up to March 2022.pdf | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajapet from km 71.015 to107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Submission of work program up to March 2022-Reg. | Sir, Based on the review meeting held under the Chairmanship of Member Projects Tamil Nadu on dated 01.11.2021 and as a compliance to the above cited Ref. No. 1, the submitted work program up to March 2022 by the Contractor has been verified and forwarded to your good office with the following observations. As per the work program, Contractor planned an expenditure of Rs/- 88.085 Cr which is 16.52 % of the Contract Amount. However, the so far achieved financial progress is 35.10 % and the physical progress is 40.80%. Hence the cumulative physical progress will be 57.32% by the end of March 2022. From the above it is clear that as per the revised Completion Date i.e.,19" Dec 2022, the Contractor has to achieve the balance 42.68% in a span of 9 months. Hence the Contractor has been advised to take necessary steps in achieving the required progress This is for your kind information please. Thanking You. Kar-Wal, Six Lanning Project, Package-ll, Kancheepuram Encl : Work Program Copy to: 1.M/s S.P.K. & Co. 2.H.O. S.A. Infrastructure Consultants Pvt. Ltd Project Office : s+ Dr A £ ra nue, www.sainfra.com | FALSE | real_data
QAP, EMP, EHS and Construction Programme | Contractor's Obligations | Contractor has submitted the program for the works as per Clause 10.3 of agreement and Plan & Profile drawings and requesting for approval | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LOT-10/Lr.No.694_24042019 To SA_Mobilization of Site_Review of Programme.pdf | NHALI PIU - Krishnagiri - Consultancy services for Authority Engineer for supervision of Six laning of Karaipettai to Walajahpet section of NH-48 (old NH-4) from km.71+015 to km.107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase V- Mobilization at Site ~ Reg. | As you know that your firm has been appointed as Authority Engineer for the ee work and the contract agreement for civil work is signed on 15.10.2018 and appointed date is: declared as 11.2.2019 and the contractor has started the work and is in progress. 2.AS a part of contract agreement the contractor has submitted programme for the works as per clause 10.1.3 of agreement and Plan & Profile drawings and requesting for approvals. 3.As per para- 4 ,Annex-I ,Schedule-N of agreement ,the Authority Engineer shall review the programme for the works submitted by the contractor as per cl 10.1.3 of agreement and shall convey its comments to the contractor within a stipulated period of time. 4. As no communication is received on mobilisation of the Authority Engineer till date, it is requested to mobilise the staff at site under intimation to this office immediately for performing the duties of Authority Engineer. | FALSE | real_data
QAP, EMP, EHS and Construction Programme | Contractor's Obligations | This has reference to the captioned subject and as per clause 10.1.3 of Concession agreement, we are hereby submitting "Programme" for the works of the Project Highway as follows | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LOT-10/13A_13022019_Submission of programme as per Clause 10.1.3 of CA.pdf | SIX LANING OF KARAIPETTAI TO WALAJAPET SECTION OF NH - 4 (vn i +5) FROM KML 71+015 TO KM. 107+09) ON EPC MODE IN THE TAMIL NADU UNDER NHDP PHASE-V — Submission of Programme as per the Ganse 10.1.3 of Contract Agreement — Reg. | This has reference to the Captioned subject and as per clause 10.1.3 of Concession Agreement we are hereby submitting “Programme” for the works of the Project Highway as Revision ¦ No. of Copies Scanned by CamScanner | FALSE | real_data
QAP, EMP, EHS and Construction Programme | Contractor's Obligations | In response to your letter under reference (3) cited above, we are herewith submitting the Construction Baseline programme incorporating the comments suggested by you which also complies with the Clause 10.1.3 of EPC Agreement. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LOT-10/38_06082019_ Regarding submission of programme.pdf | Submission of Construction Baseline programme - reg | Dear Sir, In response to your letter under reference (3) cited above, we are herewith submitting the Construction Baseline programme incorporating the comments suggested by you which also complies with the Clause 10.1.3 of EPC Agreement. Further, we wish to inform you that through a separate letter, we are also submitting an application for Extension of time based on the impacted program considering the events which affected the progress. This is for your information and further necessary action. Thanking you and assuring our best of services at all times. Thanking you Yours faithfully, For SPK And Co., a. e. Encl: Baseline constructi amme CC: 1. Project Director — PIU, Kanchipuram. 2. H.O. S.A Infrastructure Consultants Pvt. Ltd. | FALSE | real_data
QAP, EMP, EHS and Construction Programme | Contractor's Obligations | Hence, you are requested to incorporate the above observations and resubmit the Construction Programme along with Physical progress, Financial progress, Cash Flow statement and resources. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LOT-10/078-20082019_Submission of Construction Baseline programme.pdf | Submission of Construction Baseline Programme -Reg | Dear Sir, This is with reference to the captained subject and vide reference letter cited (1), we have reviewed your submitted Construction Baseline Programme and our observations are as follows. Establishment of base camp shall be included in Pre-construction activities. 2. Site clearance activity should include Clearing & Grubbing and Dismantling of structures, etc.., 3. For the Stretch between Ch.Km.71+015 to Ch.Km.80+000 the commencement of DBM is falling 7 days period from WMM start date. Hence the duration of start date of DBM shall be corrected accordingly. Re-alignment section shall be shown separately. 5. Project facilities such as Land Scaping, Tree Plantation, Highway patrol units, etc., is not mentioned. The same shall be included. 6. The Critical Path is not mentioned. The same has to be furnished. | FALSE | real_data
QAP, EMP, EHS and Construction Programme | Contractor's Obligations | This has reference to your letter (1) & (2) cited above under subjected matter, we hereby submitting the revised Quality Assurance Plan (QAP) and Methodology after incorporating of your comments. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LOT-10/109_31102019_Submission of QAP & Methodology.pdf | Submission of Quality Assurance Plan (QAP) & Construction Methodology - Reg. | Dear Sir, This has reference to your letter (1) & (2) cited above under subjected matter, we hereby submitting the revised Quality Assurance Plan (QAP) and Methodology after incorporating of your comments. Revision No. of Copies Remarks R-1 1 Set R-1 1 Set This is for your kind review and approval, please. Thanking you and assuripg-efeur commitment and co-operation at all time. Yours faithfully, For SPK AND CO Managing Partner CK CC: The Project Director, NHAI, PIU - Kanchipuram. | FALSE | real_data
QAP, EMP, EHS and Construction Programme | Contractor's Obligations | This has reference to your letter (1) & (2) cited above under subjected matter, we hereby submitting the revised Quality Assurance Plan (QAP) and Methodology after incorporating of your comments. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LOT-10/069_14092019_Submission of QAP & Methodology.pdf | Submission of Quality Assurance Plan(QAP) & Construction Methodology - Reg. | Dear Sir, This has reference to your letter (1) & (2) cited above under subjected matter, we hereby submitting the revised Quality Assurance Plan (QAP) and Methodology after incorporating of your comments. Description Revision No. of Copies ¦ Remarks Quality Assurance Plan R-1 1 Set ¦ Construction Methodology R-1 1 Set ¦ ° This is for your kind review and approval, please. Thanking you and assuring of our commitment and co-operation at all time. Yours faithfully, For SPK AND CO / 5 (¦ Managing Partner > CC: The Project Director, NHAI, PIU - Kanchipuram. | FALSE | real_data
QAP, EMP, EHS and Construction Programme | Contractor's Obligations | Further to the Discussion & Meeting held at NHAI Regional Office, Chennai on 03rd April 2024, we are herewith submitting the Revised Construction Program for Balance Works as per Original Scope of Works - including the COS-OI & COS-02 (Toll Plaza) works. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LOT-10/20240408_SPK_AE_373_Submission of Revised Construction Program for Balance Works as per Original Scope of Works Including the COS-01 & COS-02 (Toll Plaza) –Reg.pdf | Submission of Revised Construction Program for Balance Works as per Original Scope of Works Including the COS-01 & COS-02 (Toll Plaza) - Reg | 1. Further to the Discussion & Meeting held at NHAI Regional Office, Chennai on 03"4 April 2024, we are herewith submitting the Revised Construction Program for Balance Works as per Original Scope of Works - including the COS-01 & COS-02 (Toll Plaza) works. 2. Due to our persistent efforts, borrow earth filling in the approaches of VUP at Km.76/846 and LVUP at Km.102/970 have been completed and traffic will be diverted shortly. Further the Flyover at Km 106+677 traffic will be diverted in the coming month. 3. The VUP at Km 87/544, LVUP at Km.90/080, VUP at Km.93/515 works are in progress and in the remaining approaches also all the efforts to divert traffic as per the program submitted will be adhered. 4. We have obtained permission for extraction of borrow earth from Vadangampattu and Kalathur borrow area in Tiruvannamalai and Ranipet district respectively, Extraction of borrow earth is in progress, but we are facing hurdles from Govt. Official due to the Parliament Elections and Model Code of Conduct. Further, we have applied for Borrow earth permissions for the following (1) Chithathur Borrow area from Ranipet District (2) Palaiyanthangal Borrow area from Kancheepuram District & (3) Mangalam Borrow area from Tiruvanamalai District and permission is expected after Model Code of Conduct ends for upcoming Parliament election. 2. lrulappasamy Thunai S.P.K. AND Co.., | FALSE | real_data
QAP, EMP, EHS and Construction Programme | Contractor's Obligations | RFI's for field works and filed/laboratory tests. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-3/8. Request for Inspection (RFI) 08.08.2017.pdf | Rehabilitation and Up-gradation of Paithan (Pategaon) — Mungi - Hadgaon — Bodhegaon- Ladjalgaon - Ghogaspargaon — Phulsangvi — Ukhandachakla — Dahiwandi — Shirur to 2-Lane with paved shoulder (Project Length 55.937 Km) on EPC basis in the state of Maharashtra (Package I — 56 KM) — Request For Inspection(RFi) - Reg. | Respected Sir, This refers to our letter no. RCM PVR JV/MH PWD/2017-18/42 dated 13th Jun 2017 and further discussions we had on 13th July 2017 with Sub Divisional Engineer. We thank you for deputing Mr. K.A. More, Assistant Engineer, Grade-II for inspection of works, receiving Request For Inspection and attending field & Laboratory tests. We will be raising RFI’s for field work and field / Laboratory tests, for the following items: Clearing & Grubbing, Dismantling of Flexible pavement & Drain and scarifying of existing BT surface, Sub grade construction, Shoulder, Morrum layer, Granular sub-base, Wet Mix Macadam, Dry Lean Concrete, Pavement Quality Concrete, PCC M15 grade (Leveling Course), Quadrant Filling, Filter Media behind walls, Curtain Wall/toe walls M-15, PCC M20 grade (Fdn & Substructure), Providing and Laying spun pipes Dia 1200 mm (Internal), Dry boulder Apron Pitching, Culvert numbering and painting, RCC M20 grade (Foundation), RCC M25 grade (Fdn & Substructure), RCC M35 grade (Fdn & Substructure, Super structure), PSC M45 grade (Superstructure), HYSD for substructure & Super structure, HI Strands for prestressing, Asphalt wearing course 65mm thick on top deck slab, RCC for Approach Slab with reinforcement, Drainage spouts, Elastomeric Bearing, Strip seal expansion joint, PCC for Approach Slab, Filter Media below slopes, Stone pitching on slopes, Weep Holes, PCC M15 grade for protection. | FALSE | real_data
QAP, EMP, EHS and Construction Programme | Contractor's Obligations | The Project Director asked the Consultant and the Contractor about revised works programme. The Consultant replied that the revised work programme is under review. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/162_11112019_Minutes of meeting_MOM 4.pdf | Consultancy services for Authority's Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Minutes of Monthly Progress review meeting Mom-4 -Reg. | With respect to the above said reference please find enclosed herewith the Minutes of Meeting Numbered as MoM-4 held on 30.10.2019. The venue and date for the next meeting are scheduled on 27.11.2019 at Consultants office around 11.00 A.M in Kancheepuram. All the concerned are requested to attend with necessary documents. This is for your information and record. Assuring our best services at all times. | FALSE | real_data
QAP, EMP, EHS and Construction Programme | Contractor's Obligations | Relating to the base line programme the Consultant replied that the revised programme will be approved within a week | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/20191205_AE_NHAI_188_Minutes of Monthly Progress review meeting Mom-5.pdf | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to 107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Minutes of Monthly Progress review meeting Mom-5 -Reg. | With respect to the above said reference please find enclosed herewith the Minutes of Meeting Numbered as MoM-S held on 29.11.2019. The next meeting will be likely on 27.12.2019 at the Consultants office around 11.00 A.M in Kancheepuram. All the concerned are requested to attend with necessary documents. This is for your information and record. Assuring our best services at all times. | FALSE | real_data
Change in location of structures as per site requirement | Payments; Others | Few culverts have been shifted to the appropriate locations | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-1/11. Change in loc of culverts.pdf | Change of location of culverts - Reg. | With reference to the above subject, we would like to inform your good self that during joint site inspection with the representatives of AE and Authority, few culverts have been shifted to the appropriate locations as mentioned in the enclosed statement. The reasons for change in location is due to- . 1) Un-matching of CA location with the existing culvert location and existing stream/ water way locations. 2) Culverts which are not possible to construct due to built-up section as the buildings exist on both sides of proposed location and there is no water way/ stream noticed. This is for your information and record please. | FALSE | real_data
Change in location of structures as per site requirement | Payments | Few culverts have been shifted to the appropriate locations | synthetic_template_20250913 | Change of location of culverts - Reg. | We would like to inform you that With reference to the above subject, we would like to inform your good self that during joint site inspection with the representatives of AE and Authority, few culverts have been shifted to the appropriate locations as mentioned in the enclosed statement. The reasons for change in location is due to- . 1) Un-matching of CA location with the existing culvert location and existing stream/ water way locations. 2) Culverts which are not possible to construct due to built-up section as the buildings exist on both sides of proposed location and there is no water way/ stream noticed. This is for your information and record please. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Change in location of structures as per site requirement | Payments | Few culverts have been shifted to the appropriate locations | synthetic_template_20250913 | Change of location of culverts - Reg. | With reference to the above subject, we would like to inform your good self that during joint site inspection with the representatives of AE and Authority, few culverts have been shifted to the appropriate locations as mentioned in the enclosed statement. The reasons for change in location is due to- . 1) Un-matching of CA location with the existing culvert location and existing stream/ water way locations. 2) Culverts which are not possible to construct due to built-up section as the buildings exist on both sides of proposed location and there is no water way/ stream noticed. This is for your information and record please. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Change in location of structures as per site requirement | Others | Few culverts have been shifted to the appropriate locations | synthetic_template_20250913 | Change of location of culverts - Reg. | With reference to the above subject, we would like to inform your good self that during joint site inspection with the representatives of AE and Authority, few culverts have been shifted to the appropriate locations as mentioned in the enclosed statement. The reasons for change in location is due to- . 1) Un-matching of CA location with the existing culvert location and existing stream/ water way locations. 2) Culverts which are not possible to construct due to built-up section as the buildings exist on both sides of proposed location and there is no water way/ stream noticed. This is for your information and record please. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Change in location of structures as per site requirement | Others | Few culverts have been shifted to the appropriate locations | synthetic_template_20250913 | Change of location of culverts - Reg. | Kindly be informed that With reference to the above subject, we would like to inform your good self that during joint site inspection with the representatives of AE and Authority, few culverts have been shifted to the appropriate locations as mentioned in the enclosed statement. The reasons for change in location is due to- . 1) Un-matching of CA location with the existing culvert location and existing stream/ water way locations. 2) Culverts which are not possible to construct due to built-up section as the buildings exist on both sides of proposed location and there is no water way/ stream noticed. This is for your information and record please. Thank you for your attention to this matter. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Requirement of Additional land | Authority's Obligations | The available ROW of 45m is not adequate to accommodate the carriageways, slip roads, drain along with utility corridors on both sides. | synthetic_template_20250913 | Additional Land required at 20+100 VOP - Reg. | With reference to the subject matter, we wish to bring to your kind notice that as per Schedule-B of the Contract Agreement (CA), an Overpass (VOP) should be constructed at Km 20+100 along the N.A.M expressway, as a Grade separated structure. As per the typical cross section (TCS-6), there is no provision for utility corridor at the edge of the slip roads. The available ROW of 45m is not adequate to accommodate the carriageways, slip roads, drain along with utility corridors on both sides. However, there are existing utilities within the proposed Right of Way which need to be relocated. In view of the above we request you to take-up the issue with the concerned Authorities and take necessary action for acquiring the necessary land and resolve the issue so that the work progress will not be affected. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Requirement of Additional land | Authority's Obligations | The available ROW of 45m is not adequate to accommodate the carriageways, slip roads, drain along with utility corridors on both sides. | synthetic_template_20250913 | Additional Land required at 20+100 VOP - Reg. | It is brought to your attention that With reference to the subject matter, we wish to bring to your kind notice that as per Schedule-B of the Contract Agreement (CA), an Overpass (VOP) should be constructed at Km 20+100 along the N.A.M expressway, as a Grade separated structure. As per the typical cross section (TCS-6), there is no provision for utility corridor at the edge of the slip roads. The available ROW of 45m is not adequate to accommodate the carriageways, slip roads, drain along with utility corridors on both sides. However, there are existing utilities within the proposed Right of Way which need to be relocated. In view of the above we request you to take-up the issue with the concerned Authorities and take necessary action for acquiring the necessary land and resolve the issue so that the work progress will not be affected. We look forward to your response. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Requirement of Additional land | Authority's Obligations | The available ROW of 45m is not adequate to accommodate the carriageways, slip roads, drain along with utility corridors on both sides. | synthetic_template_20250913 | Additional Land required at 20+100 VOP - Reg. | With reference to the subject matter, we wish to bring to your kind notice that as per Schedule-B of the Contract Agreement (CA), an Overpass (VOP) should be constructed at Km 20+100 along the N.A.M expressway, as a Grade separated structure. As per the typical cross section (TCS-6), there is no provision for utility corridor at the edge of the slip roads. The available ROW of 45m is not adequate to accommodate the carriageways, slip roads, drain along with utility corridors on both sides. However, there are existing utilities within the proposed Right of Way which need to be relocated. In view of the above we request you to take-up the issue with the concerned Authorities and take necessary action for acquiring the necessary land and resolve the issue so that the work progress will not be affected. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Requirement of Additional land | Authority's Obligations | The available ROW of 45m is not adequate to accommodate the carriageways, slip roads, drain along with utility corridors on both sides. | synthetic_template_20250913 | Additional Land required at 20+100 VOP - Reg. | We hereby confirm that With reference to the subject matter, we wish to bring to your kind notice that as per Schedule-B of the Contract Agreement (CA), an Overpass (VOP) should be constructed at Km 20+100 along the N.A.M expressway, as a Grade separated structure. As per the typical cross section (TCS-6), there is no provision for utility corridor at the edge of the slip roads. The available ROW of 45m is not adequate to accommodate the carriageways, slip roads, drain along with utility corridors on both sides. However, there are existing utilities within the proposed Right of Way which need to be relocated. In view of the above we request you to take-up the issue with the concerned Authorities and take necessary action for acquiring the necessary land and resolve the issue so that the work progress will not be affected. Please confirm receipt of this correspondence. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Requirement of Additional land | Authority's Obligations | The available ROW of 45m is not adequate to accommodate the carriageways, slip roads, drain along with utility corridors on both sides. | synthetic_template_20250913 | Additional Land required at 20+100 VOP - Reg. | With reference to the subject matter, we wish to bring to your kind notice that as per Schedule-B of the Contract Agreement (CA), an Overpass (VOP) should be constructed at Km 20+100 along the N.A.M expressway, as a Grade separated structure. As per the typical cross section (TCS-6), there is no provision for utility corridor at the edge of the slip roads. The available ROW of 45m is not adequate to accommodate the carriageways, slip roads, drain along with utility corridors on both sides. However, there are existing utilities within the proposed Right of Way which need to be relocated. In view of the above we request you to take-up the issue with the concerned Authorities and take necessary action for acquiring the necessary land and resolve the issue so that the work progress will not be affected. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Change of scope request for additional works or works not in the scope | Payments; Dispute Resolution; Change of Scope; EoT | Mandatory Monthly drone recording communicated from your end vide ref(4) above is additional works and services which are not included in the Sope of the project as contemplated by this Agreement (" the Change of Scope"). | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-6/20210924_SPK_AE_133_Mandatory Monthly Drone Video Recording of Project Highway during the Development, Construction and O&M Period – Request to initiate COS -Reg..pdf | Mandatory Monthly Drone Video Recording of Project Highway during the Development, Construction and O&M Period - Request to initiate COS -Reg. | The Mandatory Monthly Drone recording of Project Highway during Development, Construction and O&M period as per the NHAI/Policy Guidelines ref (2) cited is being taken up by the EPC Contractor and submitted the Drone Based Video Recording for the last 3 months — however the EPC Contractor would like to represent the following: 1. The requirement of Mandatory Monthly Drone recording communicated from your end vide ref (4) above is additional works and services which are not included in the Scope of the Project as contemplated by this Agreement (“the Change of Scope’). 2. Pursuant to Clause 13.1.1 of the Contract Agreement,” Any such Change of Scope shall be made and valued in accordance with the provisions of this Article 13”. Drone Based Video Surveying of the Project Highways as per the Policy circular issued by NHAI HQ is being carried out with the NHAI empanelled agency M/s. Marvel Geospatial Solutions Pvt. Ltd and the Rates per kilometer for the Drone Based Video Surveying are as per NHAI guidelines excluding the overhead and other charges. We hereby request to issue “Change of Scope” notice as per Clause 13.2.1 of the Contract Agreement for mandatory monthly drone recording of Project Highway. The Drone Survey will be conducted in presence of Authority’s Representatives hereby ensuring that no inconvenience caused to the road users or any public. Since the Employer has requested to carry out this additional work of Drone Based Video Recording for uploading in NHAI datalake, the EPC Contractor, though not in his scope, had carried out the Drone Based Survey for the past three months covering the proposed ROW, showing chainages, Median Centreline etc. which will be uploaded in the NHAI datalake shortly, anticipating that the same shall be considered under positive COS by the Authority. We kindly request the Authority Engineer to forward this COS notice request and recommend for getting the approval by the Authority at the earliest in order to facilitate the Contractor in submitting the requisite data. | FALSE | real_data
Change of scope request for additional works or works not in the scope | Payments; Dispute Resolution; Change of Scope; EoT | Hence, it is suggested/requested that an additional layer of 40mm thick DBM layer on par with MCW DBM thickness of 105mm under positive change of scope as per Article-13 of Contract Agreement | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-6/20211206_SPK_PD_MCW traffic plying over Slip road over a long period of time resulting in severe deterioration -Approval sought under (COS) as per Article -13 of the Contract Agreement for providing.pdf | Six laning of Karaipettai to Walajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V —MCW traffic plying over Slip road over a long period of time resulting in severe deterioration -Approval sought under Positive change of scope (COS) as per Article -13 of the Contract Agreement for providing Additional DBM layer over Slip road - reg | 1.The Contract Agreement of the subject project was executed on 15.10.2018 and the Appointed Date declared as 11.02.2019. The Contractor has achieved Project Milestone I and II and the physical progress achieved as on 30.11.2021 is 40.80 %. Extension of time for a period of 678 days was approved by the Competent Authority by revising SPCD as 19.12.2022. 2. The Total No. of VUPs and LVUPs as per Clause 6.11 & 6.12 of Schedule B of the Contract Agreement is 8 and 7 respectively. The total scope of Service Road as per Clause 6.6 of Schedule-B of the Contract Agreement is 23.010 (11.505+11.505) Kms. The total scope of Slip Road provided at Flyovers / VUPs / LVUPs as per Clause 6.7 of Schedule-B of the Contract Agreement is 36.562 (18.281 + 18.281) Kms. 3. Pursuant to Clause 6.9 of Schedule-B of the Contract Agreement, the minimum design for Pavement of Main carriageway shall be 65 MSA and SR shall be designed for minimum 20 MSA. However, the EPC Contractor finalised the Pavement Design for MCW with 80 MSA and the same is being adopted. . Slip roads are constructed initially and the entire main carriageway traffic is to be diverted on slip roads to facilitate construction of structures (VUP/PUP/Flyover) and its approaches. Majority of the structure works are also completed. . The details of slip road completed as on date is around 11km on LHS and 8.89Km on RHS. The details/stretches along with Date of Diversion of MCW traffic on to the SLIP Road are shown in the enclosed ANNEXURE - I. . Presently the MCW traffic is diverted on to the slip road, but the RE wall works on approaches to the structures are badly affected due to constraints / difficulties faced by the Contractor in procurement of borrow earth since inception of the project. . It is worth mentioning that this perennial problem prevailing in the state of Tamilnadu was also acknowledged by MoRT&H. A meeting was held at the residence of Hon’ble Union Minister of Road Transport & Highways with Contractor on 08 Sept 2021 at New Delhi with all the Contractors / Concessionaire of Tamil Nadu State executing projects under NHAI and Ministry to resolve this impasse. All the PDs were requested to support the Contractors / Concessionaires in getting approval of borrow earth from District Administration. . Further a meeting under the Chairmanship of Hon’ble Minister PWD, Tamilnadu was held on 12% September 2021 for review of various issues affecting the progress of the NHAI projects viz Borrow Earth Issues, LA issues etc. The Regional Officer NHAI, Chennai, PD-PIU, Kanchipuram and representatives of the Contractors were also present during the meeting. In continuation of this, another meeting, chaired by TN PWD Minister also took place on 20 September 2021 at Highways Research Station, Highways Department, Guindy, CHENNAI with the EPC Contractors of Tamilnadu & officials to discuss about various issues plaguing the progress of the works in Tamilnadu in view of getting approval of borrow earth from District Administration. .To put on record following are the various correspondences exchanged with District Administration / Authority for procurement of borrow earth since the inception of the project: | FALSE | real_data
Change of scope request for additional works or works not in the scope | Payments; Dispute Resolution; Change of Scope; EoT | However, as per the instructions of the Authority & Authority's Engineer, we are constructing the Project Highway beyond the mentioned under the 'Proposed ROW' in Annex-I of Schedule-A — comprising extra width of the road and additional width of the culverts. This is required to be treated under Change of Scope. Details of the extra work being carried out by us will be submitted shortly for your perusal. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/18. Additional work beyond the proposed ROW mentioned under sch A fro COS notice under clause 13.1.2(c) 23.05.2019.pdf | Rehabilitation and Up-gradation of Paithan (Pategaon) — Mungi - Hadgaon - Bodhegaon- Ladjalgaon — Ghogaspargaon — Phulsangvi — Ukhandachakla — Dahiwandi - Shirur to 2-Lane with paved shoulder (Project Length 55.937 Km) on EPC basis in the state of Maharashtra (Package ¦ - 56 KM) — Additional work beyond the proposed ROW mentioned under Schedule-A — Request for Change of Scope Notice under Clause 13.1.2 (c) | We request your kind attention to the following points with reference to the EPC Agreement: 1. Article 2 of the EPC Agreement states that: Under this Agreement, the scope of the Project (the "Scope of the Project") shall mean and include: 2. (a) construction of the Project Highway on the site set forth in Schedule-A and as specified in Schedule-B together with provision of Project Facilities as specified in Schedule-C, and in conformity with the Specifications and Standards set forth in Schedule-D; 3. Page no. 142-146 i.e. Annex-l of Schedule-A wherein the Site of the Project (Of Highway along with the “Existing” and “Proposed” ROW are tabulated: sample as given below: Existing Chainage Design ¦ Existing ¦ Proposed ¦ (m.) ¦ Chainage (m.) ¦ ROW ROW S.No. ¦ From To From To Length ¦ (m.) (m.) 0 200 0 200 ¦“ 200 ¦ 27 27 2 200 400 200 400 200 27 27 3 400 600 400. ¦ 600 200 ¦ 26 26 4 600 850 600 850 250 ¦ 24 oa 24 5 ¦ 850 1100 850 W0G_¦ 250 21 ¦ 6 ] 100 1350 _¦ 1100 ¦ 1350 250 ¦ 20 ¦ ¦ 7 1350 ¦ 1600 ¦ 1350 ¦ 1600 ¦ 250 ¦__20 8 1900 ¦ 1600 1900 ¦ 300 18 ¦ 9 2100 1900 2100 200 18 ) 2350 250 iz 20 ¦ 4. Page no. 178-179, wherein Typical cross-sections (TCS) of the Project Highway are shown. It can be seen from the TCS Schedule given in page 179, that TCS type 1A (approx. 43.882 km) and 1C (approx. 10.595 km) together represent about 94.477 km which is 97.4% of the total project length. The total width of the land required as per the TCS 1A is (top width of 14m + slope of embankment) about 18m + working strip of 3m on either side, it is about 24m. And for TCS IC, it is about 15.5m (12m + 3.5m) and including the working strips, it is 21.5m. 5. It is given to understand in the bidding document that the original scope of the Project is to construct the Project Highway on the Site set forth in Schedule-A and the provisions mentioned in Schedules B, C & Dare to be accommodated to the extent of available width of the Site as per point no. 2 above. 6. However, as per the instructions of the Authority & Authority’s Engineer, we are constructing the Project Highway beyond the Site mentioned under the ‘Proposed ROW' in Annex-l of Schedule-A — comprising extra width of the road and additional width of the culverts. This is required to be treated under Change of Scope. Details of the extra work being carried out by us will be submitted shortly for your perusal. We invite your attention to EE's letters 2017 & 2019 dated 06th July 2018 to the District Collectors of Beed and Ahmednagar, emphasising the essentiality of the additional width of ROW. In our letter ref (1) above, in the last page, we have expressed our satisfaction that the process of Land Acquisition is in Progress as it is required in the entire 55.937 Km, based on the essentiality of ROW shown in the Plan & Profile drawings, approved as per Schedule-D. In view of the above, we request you to kindly review and instruct the AE for notifying the additional work beyond the PROW under Change of Scope pursuant to Articles 13.1.2(c) & 13.2.1 of the EPC Agreement. | FALSE | real_data
Change of scope request for additional works or works not in the scope | Payments; Dispute Resolution; Change of Scope; EoT | In view of the above, we request you to kindly review and instruct the AE for notifying the additional work beyond the PROW under Change of Scope pursuant to Articles 13. I .2(c) & 13.2. I of the EPC Agreement | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/18. Additional work beyond the proposed ROW mentioned under sch A fro COS notice under clause 13.1.2(c) 23.05.2019.pdf | Rehabilitation and Up-gradation of Paithan (Pategaon) — Mungi - Hadgaon - Bodhegaon- Ladjalgaon — Ghogaspargaon — Phulsangvi — Ukhandachakla — Dahiwandi - Shirur to 2-Lane with paved shoulder (Project Length 55.937 Km) on EPC basis in the state of Maharashtra (Package ¦ - 56 KM) — Additional work beyond the proposed ROW mentioned under Schedule-A — Request for Change of Scope Notice under Clause 13.1.2 (c) | We request your kind attention to the following points with reference to the EPC Agreement: 1. Article 2 of the EPC Agreement states that: Under this Agreement, the scope of the Project (the "Scope of the Project") shall mean and include: 2. (a) construction of the Project Highway on the site set forth in Schedule-A and as specified in Schedule-B together with provision of Project Facilities as specified in Schedule-C, and in conformity with the Specifications and Standards set forth in Schedule-D; 3. Page no. 142-146 i.e. Annex-l of Schedule-A wherein the Site of the Project (Of Highway along with the “Existing” and “Proposed” ROW are tabulated: sample as given below: Existing Chainage Design ¦ Existing ¦ Proposed ¦ (m.) ¦ Chainage (m.) ¦ ROW ROW S.No. ¦ From To From To Length ¦ (m.) (m.) 0 200 0 200 ¦“ 200 ¦ 27 27 2 200 400 200 400 200 27 27 3 400 600 400. ¦ 600 200 ¦ 26 26 4 600 850 600 850 250 ¦ 24 oa 24 5 ¦ 850 1100 850 W0G_¦ 250 21 ¦ 6 ] 100 1350 _¦ 1100 ¦ 1350 250 ¦ 20 ¦ ¦ 7 1350 ¦ 1600 ¦ 1350 ¦ 1600 ¦ 250 ¦__20 8 1900 ¦ 1600 1900 ¦ 300 18 ¦ 9 2100 1900 2100 200 18 ) 2350 250 iz 20 ¦ 4. Page no. 178-179, wherein Typical cross-sections (TCS) of the Project Highway are shown. It can be seen from the TCS Schedule given in page 179, that TCS type 1A (approx. 43.882 km) and 1C (approx. 10.595 km) together represent about 94.477 km which is 97.4% of the total project length. The total width of the land required as per the TCS 1A is (top width of 14m + slope of embankment) about 18m + working strip of 3m on either side, it is about 24m. And for TCS IC, it is about 15.5m (12m + 3.5m) and including the working strips, it is 21.5m. 5. It is given to understand in the bidding document that the original scope of the Project is to construct the Project Highway on the Site set forth in Schedule-A and the provisions mentioned in Schedules B, C & Dare to be accommodated to the extent of available width of the Site as per point no. 2 above. 6. However, as per the instructions of the Authority & Authority’s Engineer, we are constructing the Project Highway beyond the Site mentioned under the ‘Proposed ROW' in Annex-l of Schedule-A — comprising extra width of the road and additional width of the culverts. This is required to be treated under Change of Scope. Details of the extra work being carried out by us will be submitted shortly for your perusal. We invite your attention to EE's letters 2017 & 2019 dated 06th July 2018 to the District Collectors of Beed and Ahmednagar, emphasising the essentiality of the additional width of ROW. In our letter ref (1) above, in the last page, we have expressed our satisfaction that the process of Land Acquisition is in Progress as it is required in the entire 55.937 Km, based on the essentiality of ROW shown in the Plan & Profile drawings, approved as per Schedule-D. In view of the above, we request you to kindly review and instruct the AE for notifying the additional work beyond the PROW under Change of Scope pursuant to Articles 13.1.2(c) & 13.2.1 of the EPC Agreement. | FALSE | real_data
Change of scope request for additional works or works not in the scope | Payments; Dispute Resolution | Realignment at Ch Km.102/500 to 102/800 | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/089_31082019_Minutes of Monthly Progress review meeting.pdf | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to 107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Minutes of Monthly Progress review meeting -Reg. | With respect to the above said reference please find enclosed herewith the minutes of meeting MoM -2 held on 27.08.2019. The venue and date for the next meeting will be intimated in due course of time. This is for your information and record. | FALSE | real_data
Change of scope request for additional works or works not in the scope | Payments; Dispute Resolution; Change of Scope; EoT | The existing culvert has to be removed/ dismantled to proceed with the construction activities as this was not in the scope of work. The farmers adjacent to the existing culvert on either side demanding for new CD work | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-2/4. 20240223_238_Cont_AE_Representation of GP to construct BC at Km 9+280.pdf | Representation from Gram Panchayat to construct CD work @ Ch: 9+280 - Reg. | With reference to the above subject, we would like to bring to your kind notice that we have received representation form Gram Panchayat (copy enclosed) addressed to the Executive Engineer to construct a culvert at Ch:9+280. An existing stone masonry culvert with 3 vents of 1m (photographs enclosed) was there at the said location and the same is mentioned in schedule — A of CA which is not covered in schedule — B. The existing culvert has to be removed/ dismantled to proceed with the construction activities as this was not in the scope of work. The farmers adjacent to the existing culvert on either side demanding for new CD work and they have stopped our construction activities. In this context, we request your good self to take up the matter with Authority and resolve the issue at the earliest. Thanking & assuring our best services always, Encl: As Mentioned Above. CC: 1. The Executive Engineer, (R&B), NH Division, Siddipet. | FALSE | real_data
Release of Performance security | Payments; Dispute Resolution | This is with reference to the Office Memorandum from Ministry of Finance, GOI dated 13-05-2020 (ref 1 above) on return of Performance Security in view of Force Majeure due to COVID-19 | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/20. Request for release of performance security due to covid-19 as per ministry office memorandum..pdf | Request for release of Performance Security due to COVID-19 as per Ministry office memorandum | This is with reference to the Office Memorandum from Ministry of Finance, GOI dated 132020 (ref 1 above) on return of Performance Security in view of Force Majeure due to COVID-19. As notified vide our above letters, the project progress has suffered badly in terms of time and cost due to land unavailability initially and due to occurrence of Force Majeure event (outbreak of Corona Virus) and subsequent lockdown in the recent past. Due to this there was huge idling of resources, disruption in payment schedule and cash flow issues which will affect future progress of the project. In order to mitigate the difficulties being faced by Contractors, the central government has issued the above stated Office Memorandum mentioning that “the contractor M/S RCM Infrastructure Ltd. — P V Ramanaiah & Co_JV (Government Department/Agency) may return the value of performance security to the contractor/supplier as is proportional to the supplies made/contract work completed to the total contract value”. Accordingly, we wish to avail the facility of revising the Bank guarantee (BG) for reduced amounts of Performance security, in place of original submitted BGs, for the amount equal to the latest stage payment (IPC-15), as mentioned below which will ease our credit facilities with the banks for better cash flow & in turn improve the progress of works. Original & Proposed Bank Guarantee details: Contract Price as per price schedule p.no.366 of CA 242,82,45,567 Value of Work Done till IPC-15 121,46,94,488 Balance Value of Work as per Contract Price = (A-B) 121,35,51,079 Performance security (PBG) submitted as per Cl.7.1.1 of the Contract = (5% of A) 12,14,00,000 Revised PBG value proposed as per the Office Memorandum under ref (1) above = (5% of C) 6,07,28,582 In view of the above, we request you to write to the bank to reduce the BG to the above effect which enables us to submit the revised BG at the earliest. | FALSE | real_data
Release of Performance security | Dispute Resolution | This is with reference to the Office Memorandum from Ministry of Finance, GOI dated 13-05-2020 (ref 1 above) on return of Performance Security in view of Force Majeure due to COVID-19 | synthetic_template_20250913 | Request for release of Performance Security due to COVID-19 as per Ministry office memorandum | This is with reference to the Office Memorandum from Ministry of Finance, GOI dated 132020 (ref 1 above) on return of Performance Security in view of Force Majeure due to COVID-19. As notified vide our above letters, the project progress has suffered badly in terms of time and cost due to land unavailability initially and due to occurrence of Force Majeure event (outbreak of Corona Virus) and subsequent lockdown in the recent past. Due to this there was huge idling of resources, disruption in payment schedule and cash flow issues which will affect future progress of the project. In order to mitigate the difficulties being faced by Contractors, the central government has issued the above stated Office Memorandum mentioning that “the contractor M/S RCM Infrastructure Ltd. — P V Ramanaiah & Co_JV (Government Department/Agency) may return the value of performance security to the contractor/supplier as is proportional to the supplies made/contract work completed to the total contract value”. Accordingly, we wish to avail the facility of revising the Bank guarantee (BG) for reduced amounts of Performance security, in place of original submitted BGs, for the amount equal to the latest stage payment (IPC-15), as mentioned below which will ease our credit facilities with the banks for better cash flow & in turn improve the progress of works. Original & Proposed Bank Guarantee details: Contract Price as per price schedule p.no.366 of CA 242,82,45,567 Value of Work Done till IPC-15 121,46,94,488 Balance Value of Work as per Contract Price = (A-B) 121,35,51,079 Performance security (PBG) submitted as per Cl.7.1.1 of the Contract = (5% of A) 12,14,00,000 Revised PBG value proposed as per the Office Memorandum under ref (1) above = (5% of C) 6,07,28,582 In view of the above, we request you to write to the bank to reduce the BG to the above effect which enables us to submit the revised BG at the earliest. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Release of Performance security | Dispute Resolution | orders were issued for reduction of the performance security to 3% of the contract value. | synthetic_template_20250913 | Request for Implementation of COVID Relief Measures pursuant to Ministry Circular no. COVID-19/Road Map/JS(H)/2020 dated 04.01.2022 - Reg. | We refer to the above-mentioned correspondence regarding submission of Performance Security Bank Guarantees (BGs) for the above project. Through our letters ref (2) & (3) above, we had submitted the BGs for performance security as per the details below: \n\n1. 0873IGL0008321 ¦ UNION BANK OF INDIA ¦ 7,59,78,000 ¦ 06-Sep-28\n2. 0873IGL0008421 ¦ UNION BANK OF INDIA ¦ 5,06,51,000 ¦ 07-Jul-23\n3. 0873IGL0008521 ¦ UNION BANK OF INDIA ¦ 2,00,00,000 ¦ 07-Jul-23\n4. 0873IGL0008621 ¦ UNION BANK OF INDIA ¦ 2,00,00,000 ¦ 07-Jul-23\n5. 08731IGL0008721 ¦ UNION BANK OF INDIA ¦ 2,00,00,000 ¦ 07-Jul-23\n6. 0873IGL0008821 ¦ UNION BANK OF INDIA ¦ 2,00,00,000 ¦ 08-Jul-23\n7. 0873IGL0008921 ¦ UNION BANK OF INDIA ¦ 2,00,00,000 ¦ 08-Jul-23\n8. 0873IGL0009021 ¦ UNION BANK OF INDIA ¦ 2,00,00,000 ¦ 08-Jul-23\n9. 0873IGL0009121 ¦ UNION BANK OF INDIA ¦ 94,22,916 ¦ 08-Jul-23\n\nVide MORTH Circular ref (4) above, the Under Secretary, Ministry of Road Transport and Highways (Highways Division), Government of India, orders were issued for reduction of the performance security to 3% of the contract value as one of the relief measures in view of the COVID-19 pandemic. Further, as intimated in our letter ref (5) above, we have achieved the first Milestone comprising achievement of 20% financial progress ahead of schedule. However, to continue at this pace in achieving the next Milestones, we would require ease of cash flow by way of relaxation in the value of Bank Guarantees in accordance with the circular.\n\nHence, we request you to consider reduction of Performance security to 3% of the contract value i.e., Rs. 7,59,76,809/- and return our BGs to that extent accordingly. This will improve our cash flows and contribute to the progress of the project.\n\n We appreciate your cooperation in this regard. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Release of Performance security | Payments | This is with reference to the Office Memorandum from Ministry of Finance, GOI dated 13-05-2020 (ref 1 above) on return of Performance Security in view of Force Majeure due to COVID-19 | synthetic_template_20250913 | Request for release of Performance Security due to COVID-19 as per Ministry office memorandum | It is brought to your attention that This is with reference to the Office Memorandum from Ministry of Finance, GOI dated 132020 (ref 1 above) on return of Performance Security in view of Force Majeure due to COVID-19. As notified vide our above letters, the project progress has suffered badly in terms of time and cost due to land unavailability initially and due to occurrence of Force Majeure event (outbreak of Corona Virus) and subsequent lockdown in the recent past. Due to this there was huge idling of resources, disruption in payment schedule and cash flow issues which will affect future progress of the project. In order to mitigate the difficulties being faced by Contractors, the central government has issued the above stated Office Memorandum mentioning that “the contractor M/S RCM Infrastructure Ltd. — P V Ramanaiah & Co_JV (Government Department/Agency) may return the value of performance security to the contractor/supplier as is proportional to the supplies made/contract work completed to the total contract value”. Accordingly, we wish to avail the facility of revising the Bank guarantee (BG) for reduced amounts of Performance security, in place of original submitted BGs, for the amount equal to the latest stage payment (IPC-15), as mentioned below which will ease our credit facilities with the banks for better cash flow & in turn improve the progress of works. Original & Proposed Bank Guarantee details: Contract Price as per price schedule p.no.366 of CA 242,82,45,567 Value of Work Done till IPC-15 121,46,94,488 Balance Value of Work as per Contract Price = (A-B) 121,35,51,079 Performance security (PBG) submitted as per Cl.7.1.1 of the Contract = (5% of A) 12,14,00,000 Revised PBG value proposed as per the Office Memorandum under ref (1) above = (5% of C) 6,07,28,582 In view of the above, we request you to write to the bank to reduce the BG to the above effect which enables us to submit the revised BG at the earliest. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Release of Performance security | Payments | orders were issued for reduction of the performance security to 3% of the contract value. | synthetic_template_20250913 | Request for Implementation of COVID Relief Measures pursuant to Ministry Circular no. COVID-19/Road Map/JS(H)/2020 dated 04.01.2022 - Reg. | We refer to the above-mentioned correspondence regarding submission of Performance Security Bank Guarantees (BGs) for the above project. Through our letters ref (2) & (3) above, we had submitted the BGs for performance security as per the details below: \n\n1. 0873IGL0008321 ¦ UNION BANK OF INDIA ¦ 7,59,78,000 ¦ 06-Sep-28\n2. 0873IGL0008421 ¦ UNION BANK OF INDIA ¦ 5,06,51,000 ¦ 07-Jul-23\n3. 0873IGL0008521 ¦ UNION BANK OF INDIA ¦ 2,00,00,000 ¦ 07-Jul-23\n4. 0873IGL0008621 ¦ UNION BANK OF INDIA ¦ 2,00,00,000 ¦ 07-Jul-23\n5. 08731IGL0008721 ¦ UNION BANK OF INDIA ¦ 2,00,00,000 ¦ 07-Jul-23\n6. 0873IGL0008821 ¦ UNION BANK OF INDIA ¦ 2,00,00,000 ¦ 08-Jul-23\n7. 0873IGL0008921 ¦ UNION BANK OF INDIA ¦ 2,00,00,000 ¦ 08-Jul-23\n8. 0873IGL0009021 ¦ UNION BANK OF INDIA ¦ 2,00,00,000 ¦ 08-Jul-23\n9. 0873IGL0009121 ¦ UNION BANK OF INDIA ¦ 94,22,916 ¦ 08-Jul-23\n\nVide MORTH Circular ref (4) above, the Under Secretary, Ministry of Road Transport and Highways (Highways Division), Government of India, orders were issued for reduction of the performance security to 3% of the contract value as one of the relief measures in view of the COVID-19 pandemic. Further, as intimated in our letter ref (5) above, we have achieved the first Milestone comprising achievement of 20% financial progress ahead of schedule. However, to continue at this pace in achieving the next Milestones, we would require ease of cash flow by way of relaxation in the value of Bank Guarantees in accordance with the circular.\n\nHence, we request you to consider reduction of Performance security to 3% of the contract value i.e., Rs. 7,59,76,809/- and return our BGs to that extent accordingly. This will improve our cash flows and contribute to the progress of the project.\n\n | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Notices for Achievement/ Non Achievement of Milestones | Dispute Resolution | 1. We have achieved the first Milestone comprising achievement of 20% financial progress ahead of schedule. 2. To continue at this pace in achieving the next Milestones, we would require ease of cash flow by way of relaxation in the value of Bank Guarantees. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-1/6. Req for implementatn of Covid relief measures.pdf | Request for Implementation of COVID Relief Measures pursuant to Ministry Circular no. COVID-19/Road Map/JS(H)/2020 dated 04.01.2022 - Reg. | We refer to the above-mentioned correspondence regarding submission of Performance Security Bank Guarantees (BGs) for the above project. Through our letters ref (2) & (3) above, we had submitted the BGs for performance security as per the details below: \n\n1. 0873IGL0008321 ¦ UNION BANK OF INDIA ¦ 7,59,78,000 ¦ 06-Sep-28\n2. 0873IGL0008421 ¦ UNION BANK OF INDIA ¦ 5,06,51,000 ¦ 07-Jul-23\n3. 0873IGL0008521 ¦ UNION BANK OF INDIA ¦ 2,00,00,000 ¦ 07-Jul-23\n4. 0873IGL0008621 ¦ UNION BANK OF INDIA ¦ 2,00,00,000 ¦ 07-Jul-23\n5. 08731IGL0008721 ¦ UNION BANK OF INDIA ¦ 2,00,00,000 ¦ 07-Jul-23\n6. 0873IGL0008821 ¦ UNION BANK OF INDIA ¦ 2,00,00,000 ¦ 08-Jul-23\n7. 0873IGL0008921 ¦ UNION BANK OF INDIA ¦ 2,00,00,000 ¦ 08-Jul-23\n8. 0873IGL0009021 ¦ UNION BANK OF INDIA ¦ 2,00,00,000 ¦ 08-Jul-23\n9. 0873IGL0009121 ¦ UNION BANK OF INDIA ¦ 94,22,916 ¦ 08-Jul-23\n\nVide MORTH Circular ref (4) above, the Under Secretary, Ministry of Road Transport and Highways (Highways Division), Government of India, orders were issued for reduction of the performance security to 3% of the contract value as one of the relief measures in view of the COVID-19 pandemic. Further, as intimated in our letter ref (5) above, we have achieved the first Milestone comprising achievement of 20% financial progress ahead of schedule. However, to continue at this pace in achieving the next Milestones, we would require ease of cash flow by way of relaxation in the value of Bank Guarantees in accordance with the circular.\n\nHence, we request you to consider reduction of Performance security to 3% of the contract value i.e., Rs. 7,59,76,809/- and return our BGs to that extent accordingly. This will improve our cash flows and contribute to the progress of the project.\n\n | FALSE | real_data
Notices for Achievement/ Non Achievement of Milestones | Dispute Resolution | We made the request not as any allegation but humbly to express our inadvertently our inability in achieving Milestone -I, Milestone-II and Milestone-III also. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-3/20. Land acquisition-Impact on appointed date & milestones 12.07.2018.pdf | Land acquisition - impact on Appointed date & Milestones — Reg. | Respected Sir, This refers to your letter no. NHD/Abad/TS-2/1891 dated 27th June 2018 on our request for land acquisition (Ref. Letter no. RCM PVR JV/MH PWD/2018-19/271 dated 14th June 2018). Annexure-l We wish to add a few lines in response to your letter NHD/Abad/TS-2/1891 dated 27th June 2018. As you are aware, the EPC contractor agreed the Appointment Date, on good faith, based on the Authority's warranty (please refer clause 5.29 & 5.2h ) (please refer our letter no. RCM PVR JV/MH PWD/2017-18/71 dated 10th August 2017) Annexure-ll At the early stage of commencement itself, the fact that land is not in possession of PWD was highlighted by the contractor. Please refer your letter no. NHD/Abad/TS-2/1787, dated 06th September 2017 advising the contractor not to cause any resentment of villagers. This confirms the factuals and acceptance of Authority, regarding non-possession of any land. Annexure-lll Our programme submitted was open-ended and we were prepared to work on any land, made available. Please refer our letter no. RCM PVR JV/MH PWD/2017-18/70 dated 10 August 2017, the penultimate para, in this connection. Whenever the work was disrupted by villagers, we opted for adjacent stretches, where no obstructions were at that time. Also please refer our letter no. RCM PVR JV/MH PWD/2017-18/75, dated 23rd August 2017, regarding de-mobilizing & remobilizing resources to nearby stretches. Annexure-IV The main objective for our representation is that after Mr. Galande, the S.D.E, conducted many meetings in nearly 5 villages convincingly, we had the right atmosphere to interact with property owners. But by then we lost nearly four to five working months. When we could achieve up to sub grade level, due to the need for review of Plan & Profile drawings by M/S Roughton International Ltd., in Association with SATRA Infrastructure Management Services Pvt. Ltd, we were not permitted to proceed to high value items. Please refer our Letter no. RCM PVR JV/MH PWD/2018-19/165 dated 10th February 2018 (page 2 last para). Annexure-V A meeting was conducted by the Superintending Engineer on 11th January 2018 in Aurangabad specifically for approval of Plan & Profile drawings. You are aware that the last date of milestone-I with 30 days grace period also expired by then. Annexure-VI We made the request not as any allegation but humbly to express our inadvertently our inability in achieving Milestone I, Milestone-II and Milestone-III also. We are glad that the land acquisition action is now in progress and it is now required in all 55.937 km, due to Plan & Profile drawings, approved as per schedule D. We are enclosing a status report also, to emphasis our aforesaid matter. We regret if our representation is found baseless and we wish to submit that the said letter may be considered null & valid, in such case. | FALSE | real_data
Notices for Achievement/ Non Achievement of Milestones | Dispute Resolution | wherever possible, having already suffered huge delay due to this issue, which has a direct effect on achieving MS-Il and MS-Ill. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/3. Request for COS notice-Delay in achieving MS-II & MS-III 26.10.2018.pdf | Request for Change of Scope notice for additional Utility ducts of 600 mm diameter RC pipe crossings for water mains and Electrical lines - Delay in achieving MS-II and MS-III | Respected Sir, We wish to bring to your kind attention regarding the unauthorised water pipelines across the project alignment. As you are aware, the stretch from Chainage 0+000 to 9+500 is infested with water pipes across the highway, laid by the local farmers in unauthorised manner. The Authority and AE have been repeatedly insisting us to take up execution in this stretch. We had completed Clearing & Grubbing, but could not proceed further due to these encumbrances. The local farmers requested the Chief Engineer (CE) during his visit on 022018 for provision of pipe crossings, as agriculture is their livelihood. The CE has resolved this issue by suggesting the provision of 600 mm diameter reinforced concrete pipes at approximately 500m c/c. The CE has also agreed to make financial sanction for the additional utility ducts as per the farmers’ requirement, and to consider this under Change of Scope (COS). Subsequently, we have taken up CD works and earthworks wherever possible, having already suffered huge delay due to this issue, which has a direct effect on achieving MS-II and MS-III. The locations of utility ducts were also finalized and approved by the Authority’s Engineer vide letter no. 01041028/02/020, dated 13% July 2018. However, no COS notice has so far been issued regarding this item. In this regard, we also invite your kind attention to the discussion in the meeting chaired by the OSD at Mumbai on 042018. Now, we request you to issue Change of Scope notice based on CE’s instructions and as per Clause 13.2.1 of contract agreement, since the work has to be executed at many locations. | FALSE | real_data
Notices for Achievement/ Non Achievement of Milestones | Dispute Resolution | We would like to submit that there is no delay in achievement of Milestone I as necessary documents in the form of submission of Stage Payment Statement - 05 has been submitted by the Contractor and the same has also been scrutinized and recommended 100% to the Authority and the payment also made by the Authority for the same on 04.08.2020 | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20200804_SPK_AE_124_Delay in Achieveing Project Milestone - I & II_Reply Made.pdf | Delay in achieving of Project Milestone I and II - Reply made - reg | Dear Sir, In response to reference (9) cited above, we would like to submit the following: 1. The EPC Contractor’s disagreement with the EOT approval was communicated to the Authority Engineer, vide letter under ref (4) with a request to revisit the same based on the actual ground conditions and grant interim EOT for 324 days as requested and justified by the EPC Contractor. It was also pointed out that EOT was granted by rescheduling all the Project Milestones and not for a specific Project Date to Clause 6 of Schedule J of the Contract Agreement. 2. This was reiterated vide EPC’s Contractor’s letter under reference (5) and the extract of Contract Agreement Page 198 is appended below: Upon extension of any or all of the aforesaid Project Milestones or the Scheduled Completion Date, as the case may be, under and in accordance with the provisions of this Agreement, the Project Completion Schedule shall be deemed to have been amended accordingly. 3. As per Cl. 6 of Schedule-J, upon extension of any or all of the aforesaid Project Milestones, the remaining Milestones gets shifted automatically along with the Project Completion Schedule and the determination should be done within framework of the EPC Contract Agreement. 4. The Authority Engineer communicated EOT recommendation of 112 days vide ref (6) cited above based on the reply from the Regional Officer, NHAI Chennai vide Letter No NHAI/11019/17/2009/RO/Chennai/ 1461 dated 30.04.2020 forwarded by the Project Director, PIU Kanchipuram to the Authority Engineer at ref (2) copied to the EPC Contractor. As mentioned above, the EPC Contractor has already conveyed his disagreement with the EOT approval accorded by the Authority. Since Authority Engineer is aware of the actual ground conditions, it is hereby once again requested to appraise the same to the Authority for revisiting the EOT already approved and recommend for 324 days as sought by the Contractor with valid justifications. 5. EPC Contractor requested the Authority to revisit the EOT recommendation based on the actual ground conditions and grant interim EOT for 324 days and the same was communicated to the Authority vide letter under ref (5) cited above. Since there was no response from the Authority to our letter cited at (5) in this regard, the EPC Contractor vide letter under ref (8) cited above once again reminded the Authority, to revisit the EOT already approved. 6. It was highlighted that even as on date, i.e. 17 months after declaration of Appointed Date, 297 no of poles, 13 no of transformers and 3 HT towers were yet to be relocated. Moreover, it was also pointed out that as on date only 50% of length of Project Highway was available as work front, after taking into account the stretches, affected. | FALSE | real_data
Notices for Achievement/ Non Achievement of Milestones | Dispute Resolution | Therefore we do not agree that the Contractor is liable to pay damages due to delay in non-achievement of the said milestones. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20201119_SPK_AE_160_Contractor failure in achieving mile stone 1,2,&3.pdf | Six laning of Karaipcttai to Walajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - Contractor’s failure in achieving Project Mile Stone 1,2 & 3 applying of Damages vide Contract Article No. 10.3.2 & 10.3.3 - Reply made -Reg. | We are in receipt of your letter ref (26) cited above, our reply for the same is as follows: 1. The Contract Agreement for this Project was executed on 15.10.2018. The Appointed Date was fixed as 11.02.2019 and the same was communicated vide ref (2) cited above. 2. The Appointed date was declared as 11.02.2019 by the Authority taking into account the land handed over in terms of the available area without taking into consideration, the requirement of the Contract provision as per Clause 4.1.3 (a) of the EPC agreement which talks about the handing over of land only in terms of length of the Project Highway. The memorandum and appendix prepared in terms of area gave a deceptive / false picture about the availability of vacant access. Taking into consideration all the encumbrances, hindrances, utilities etc. the vacant access available on the appointed date declared was worked out and it was less than 90% and hence requested the Authority vide letter under ref (3) cited above for modification of the appointed date on which 90% of encumbrance free land would be made available to the Contractor. 3. The Authority in its response vide ref (4) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. 4. The EPC contractor vide ref (5) cited above in reply reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that the impacted length due to encroachments and encumbrances was 12.18 km which accounted to 33.77% of the project length. The workable length available to the contractor was only 66.23% of the project length. The EPC contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of encumbrance / encroachment / obstruction. | FALSE | real_data
Notices for Achievement/ Non Achievement of Milestones | Dispute Resolution | We request you to accelerate the works by improving the resources so as to achieve the scheduled milestones / completion of the project, as you are already behind the schedule about 10% at the end of April 22. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/2022066_AE_SPK_1012-Disruptions of Works due to Heavy rainfall before and after cyclone Asani.pdf | Disruptions of Works due to Heavy rainfall before and after cyclone Asani - Reg. | This is with reference to the captioned subject and letter stated as Ref No (2) where it is mentioned that works had been hampered because of heavy rainfall on 01.05.2022 and also due to effect of the cyclone Asani from 09 to 10 May 2022 in both Kancheepuram and Ranipet districts. Further, a prediction note of RMC Chennai was also attached as per which light to moderate rains were predicted due to the Cyclone Asani at one or two places over Kancheepuram, Chengalpattu, Tiruvallur, Villupuram, Tiruvannamalai. Furthermore, it is mentioned in the Para- NO.4 of page -1 that “The complete stretch of Project Highway received copious rains thereby causing flooding and serious disruption in normal and routine planned works. This sudden rainfall disrupted the construction work due to the moist condition of constructed layers which prevented us to carry out any further works”. In this regard, we would like to bring the following to your kind notice. 1. Prior to “Asani” cyclone, majority of widening to six lane was completed in almost all the places and approaches to grade separated structures were in progress. You have dumped the fill material in the RE approaches without further progress such as grading and compaction, at many places. Vide our letter 977 dated 30.04.2022 wherein, we have highlighted this issue and requested you to complete the balance works. However, you have not attended to the same. Now due to the current rainfall, these stretches become non-workable due to heavy moisture in the loose soil dumped which reflects the poor planning of works at your end. 2. From the S-Curve submitted, the planned Vs achieved progress is as follows. Planned (In Cr) ¦ Achieved (In Cr) T8688. 8.88 1) 2 ¦Feb-22 ¦ SS 16.59) ¦ 511 Lo 2 eS a a a eee From the above, it is cleared that you have not achieved what you have planned. In this regard, your attention is requested to the following works which can be taken up immediately to improve your cash flow. Several Culverts have been completed for service roads and MCW are yet to be taken up. (88+487, 89+371, 90+253 etc.) Drain works to a length of 19Kms. PUP at Km 106 where Plan & Profile and structural drawings approvals communicated Laying of BC in service roads & Main Carriageway for a considerable length. Hence, we request you to accelerate the works by improving the resources so as to achieve the scheduled milestones/completion of the project, as you are already behind the schedule about 10% at the end of April-22. This is for your information and necessary actions. | FALSE | real_data
Notices for Achievement/ Non Achievement of Milestones | Dispute Resolution | It is requested to clarify the delay and submit all necessary documents relating to the Milestone Achievement | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/20200716_AE_SPK_361_ Delay in Achieving of Project Mile Stones I and II.pdf | Delay in Achieving of Project Mile Stones I and II | In reference to the above cited subject, it is submitted that the Competent Authority has been approved the Extension of time in the Project Milestones vide letter referred at Sr. No. 1. Subsequent to this, the revised Milestone Dates are mentioned hereunder; Duration as per E.O.T Schedule-J Date: M.S.-1 180 Days 09.08.2019 29.11.2019, M.S.-2 365 Days 10.02.2020 10.02.2020. In reference to the above table, it is submitted that the milestone dates have been passed but Contractor did not submit any milestone achievement related documents, so far. The stipulated completion of works with the above Mile Stone Schedules are 10% & 30%. Whereas based on the last IPC which was measured on March 25 the progress of works is around 5% only. It is requested to please clarify the delay and submit all necessary documents relating to the Milestone Achievement. Further delay in the submission of requisite documents, this will lead to the imposition of Liquidated Damages as per the provisions of the Contract Agreement. This is for your information and necessary action from your end. | FALSE | real_data
Notices for Achievement/ Non Achievement of Milestones | Dispute Resolution | Owing to the above delays, we may not be able to achieve Milestone-Il which is due in April'24. It may please be noted that we may run out of work fronts and our resources may become idle as all the available work fronts are already being tackled | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-2/2. 20231215_165_Cont_AE_Accumulated delays till Nov-23.pdf | Notice under clause 10.5.(V)- Accumulated delays till 30" November 2023 - Reg. | We refer to the above letters, wherein we have intimated the Authority about the following issues/Bottlenecks prevailing in the project which are hampering the progress of the works: 1. Handing over of the Balance land. 2. Clearance from the Forest department. 3. GAD Approval from the Railway Authorities. However, the issues are yet to be cleared and hence the same continue to hamper the progress. In this regard, pursuant to clause 10.5.(V) of the EPC Contract agreement, we herewith submit the accumulated delays as on 30" November 2023. SLMI — DMCPL (JV) (A Joint Venture of M/s. SLMI Infra Projects Private Limited & M/s. Dwarakamai Constructions Pvt. Ltd.) H.No.1223, Street No.5, Tarnaka, Secunderabad — 500017. Accumulated delays Till 30-Nov-2023. Description of Delay Events From the above the total accumulated delay as on 30.11.2023 is 303 days. Handing over of ROW/Construction Zone on at least 90% of the total length of the Project Highway Still Continuing. Handing over of the balance Land (to be handed over in 150 days) Still Continuing. Clearance from Forest Department Still Continuing. GAD Approval from Railway Authorities ~ Owing to the above delays, we may not be able to achieve Milestone-II which is due in April’24. It may please be noted that we may run out of work fronts and our resources may become idle as all the available work fronts are already being tackled. In view of the above, we request your office to pursue with the Authority to clear the issues at the earliest and provide hindrance free work fronts over the entire length of the Project Highway. | FALSE | real_data
Releasing of BG submitted against mobilization advance | Authority's Obligations; Others | We request you to pass necessary orders for release of BGS towards Mobilization Advance amounting to Rs 8,00,00,000/- and return our BGs. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-1/7. Request for Release of BG_Mobilization advance.pdf | Request for release of Bank Guarantees (BGs) towards Mobilization Advance- Reg. | We refer ta the above-mentioned correspondence regarding submission of Bank Guarantees (BGs) towards mobilization Advance for the above project. Through our ietters ref (2) above, we had submitted the BGs for Mobilization Advance as per Issuing Bank ¦, Amountiine) ¦ Validity 21931IGL0000723 UNION BANK OF INDIA 4,00,00,000 08-Feb-25 2 21931IGL0000723 UNION BANK OF INDIA 4,00,00,000 08-Feb-25 We request you to pass necessary orders for release of BGS towards Mobilization Advance amounting to Rs. 8,00,00,000/- and return our BGs (SL No. 1& 2 in the table above) to that extent accordingly. This will improve our cash flows and contribute to the progress of the project. | FALSE | real_data
Releasing of BG submitted against mobilization advance | Authority's Obligations | We request you to pass necessary orders for release of BGS towards Mobilization Advance amounting to Rs 8,00,00,000/- and return our BGs. | synthetic_template_20250913 | Request for release of Bank Guarantees (BGs) towards Mobilization Advance- Reg. | We refer ta the above-mentioned correspondence regarding submission of Bank Guarantees (BGs) towards mobilization Advance for the above project. Through our ietters ref (2) above, we had submitted the BGs for Mobilization Advance as per Issuing Bank ¦, Amountiine) ¦ Validity 21931IGL0000723 UNION BANK OF INDIA 4,00,00,000 08-Feb-25 2 21931IGL0000723 UNION BANK OF INDIA 4,00,00,000 08-Feb-25 We request you to pass necessary orders for release of BGS towards Mobilization Advance amounting to Rs. 8,00,00,000/- and return our BGs (SL No. 1& 2 in the table above) to that extent accordingly. This will improve our cash flows and contribute to the progress of the project. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Releasing of BG submitted against mobilization advance | Others | We request you to pass necessary orders for release of BGS towards Mobilization Advance amounting to Rs 8,00,00,000/- and return our BGs. | synthetic_template_20250913 | Request for release of Bank Guarantees (BGs) towards Mobilization Advance- Reg. | We would like to inform you that We refer ta the above-mentioned correspondence regarding submission of Bank Guarantees (BGs) towards mobilization Advance for the above project. Through our ietters ref (2) above, we had submitted the BGs for Mobilization Advance as per Issuing Bank ¦, Amountiine) ¦ Validity 21931IGL0000723 UNION BANK OF INDIA 4,00,00,000 08-Feb-25 2 21931IGL0000723 UNION BANK OF INDIA 4,00,00,000 08-Feb-25 We request you to pass necessary orders for release of BGS towards Mobilization Advance amounting to Rs. 8,00,00,000/- and return our BGs (SL No. 1& 2 in the table above) to that extent accordingly. This will improve our cash flows and contribute to the progress of the project. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Releasing of BG submitted against mobilization advance | Others | We request you to pass necessary orders for release of BGS towards Mobilization Advance amounting to Rs 8,00,00,000/- and return our BGs. | synthetic_template_20250913 | Request for release of Bank Guarantees (BGs) towards Mobilization Advance- Reg. | We refer ta the above-mentioned correspondence regarding submission of Bank Guarantees (BGs) towards mobilization Advance for the above project. Through our ietters ref (2) above, we had submitted the BGs for Mobilization Advance as per Issuing Bank ¦, Amountiine) ¦ Validity 21931IGL0000723 UNION BANK OF INDIA 4,00,00,000 08-Feb-25 2 21931IGL0000723 UNION BANK OF INDIA 4,00,00,000 08-Feb-25 We request you to pass necessary orders for release of BGS towards Mobilization Advance amounting to Rs. 8,00,00,000/- and return our BGs (SL No. 1& 2 in the table above) to that extent accordingly. This will improve our cash flows and contribute to the progress of the project. We await your further instructions. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Extension of Time Proposals | EoT; Dispute Resolution | We take this opportunity to summarize the facts chronologically as below giving rise to the claim for an Extension of Time ("EOT") in accordance with the provisions of this Agreement on account of various delay events. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-1/8. Request to grant an Extension of Time under Clause 10.5 of the Contract Agreement..pdf | Request to grant an Extension of Time under Clause 10.5 of the Contract Agreement | 1. This is with reference to our various representations/submissions regarding various events on delay which has adversely affected the construction activities of Project and are still persisting at site resulting delay in completion of construction works as per scope envisaged under Contract Agreement. 2. We take this opportunity to summarize the facts chronologically as below giving rise to the claim for an Extension of Time (“EOT”) in accordance with the provisions of this Agreement on account of various delay events. Contract Particulars: Development Corporation Limited Authority Engineer Accepted Contract Price Construction Period Appointed Date 26.11.2021 Stipulated Completion Date ¦ 19.05.2023 Request for EOT by this 135 days Cl 01.10.2023 Revised Completion Date Background Facts: 3. The National Highway & Infrastructure Development Corporation Limited (“Authority”) had issued the LOA dated 02.09.2021 (Ref#01) in favor of B.R Goyal Infrastructure Limited (“Contractor"). The formal Contract Agreement was signed on 08.10.2021. In pursuant to the conditions of LOA, we had submitted the Performance Security and Additional Performance Security in the form of Bank Guarantees (PBG and APBG) vide our letters dated 28.09.2021 and 02.11.2021 (Ref #2 & 4 above). It is in place to mention that the Contractor have discharged its prime obligation i.e. submission of Performance Security and Additional Performance Security, well within time limit. To ensure the start of construction activities immediate after declaration of Appointed Date, Contractor has mobilized the adequate manpower & machinery resources at site after receiving of LOA. In pursuant to the provisions of the Contract Agreement, Authority’s primary obligation is to provide the 90% length of ROW within 30 days from the date of Agreement. However, after signing of CA, both the parties visited the site and it | FALSE | real_data
Extension of Time Proposals | EoT; Dispute Resolution | Further, we wish to inform you that through a separate letter, we are also submitting an application for Extension of time based on the impacted program considering the events which affected the progress. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LOT-10/38_06082019_ Regarding submission of programme.pdf | Submission of Construction Baseline programme - reg | Dear Sir, In response to your letter under reference (3) cited above, we are herewith submitting the Construction Baseline programme incorporating the comments suggested by you which also complies with the Clause 10.1.3 of EPC Agreement. Further, we wish to inform you that through a separate letter, we are also submitting an application for Extension of time based on the impacted program considering the events which affected the progress. This is for your information and further necessary action. Thanking you and assuring our best of services at all times. Thanking you Yours faithfully, For SPK And Co., a. e. Encl: Baseline constructi amme CC: 1. Project Director — PIU, Kanchipuram. 2. H.O. S.A Infrastructure Consultants Pvt. Ltd. | FALSE | real_data
Extension of Time Proposals | EoT; Dispute Resolution | 1. Application for extension of time/Revision of milestone dates. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-3/18. Application of EOT or revision of milestone dates 14.06.2018.pdf | Application for extension of time/Revision of Mile Stone dates - Reg. | As the construction of project highway/structures could not proceed, as scheduled in the construction programme, submitted vide our letter no RCM PVR JV/MH PWD/2017-18/40, dated 02nd Jun 2018, we requested for the following. Annexure- i. Amendment of Appointment date (Please refer our letter no. RCM PVR JV/MH PWD/2018-19/151, date 30 Jan 2018) Annexure-I ii. Modification of date of milestone(s) by 120 days (Please refer our Letter no. RCM PVR JV/MH PWD/2018-19/165, date 10th Feb 2018) Annexure-III In your reply to our letter dated 10th Feb 2018 stated above, reference has been made to article/clause 10.1.3 We submit that a) as per terms of contract conditions, we submitted the original construction programme vide letter no. RCM PVR JV/MH PWD/2017-18/40, Dated 02nd Jun 2018 and Annexure-I b) the revised programme, as per article 10.1.3, vide letter no. RCM PVR JV/MH PWD/2018-19/235, date 02nd May 2018 guner regarding Appointed Date, in sl no. 3, you have stated that as the Appointed Date is declared, no EOT can be determined. We had a detailed discussion with the Team Leader on 03rd May 2018 and clarified the following. Schedule-A states that the site comprises of PROW width, which is the same as existing ROW, which implies that the land for 50.587 Km is already in possession of Authority. Please refer clause 5.2 (g) Annexure-V On good faith, The Appointed Date was accepted and encumbrances and existing utilities were recorded in Memorandum by Us. The statement is yet to be countersigned by Authority/Authority Engineer (Please refer our letter no. RCM PVR JV/MH PWD/2017-18/71, dated 10th August 2018). On commencement of works, we were intimated by revenue department of Maharashtra state (Tahsildar) that even the land on which the existing road is running is also not registered/alienated as a property/possession of PWD. Kindly refer our letter no. RCM PVR JV/MH PWD/2018-19/151, date 10th Jan 2018(Annexure-II). The reason for acceptance of Appointed Date was only good faith and the ground reality, when enlightened to Authority, the Authority commenced action for acquisition of entire land width. Kindly refer clause 5.2(h) regarding the commitment of Authority which is a warranty given by Authority Annexure-VI(a,b) The scope of the project {21.a) states that construction, as specified in schedule B & C. will conform to schedule D the technical specification. In order to achieve 80 Kmph in plain terrain & 40 kmph in hilly terrain (reference schedule B of 2.2 page 174) all the kinks, sharp Curves require geometric improvements. Hence, when the horizontal alignment gets changed/improved. deviating from the existing center line, such shifting of center line, results in additional land width requirement. Annexure-VII The assumption and decision of Authority/DPR consultants to procure land for major realignment (only for 5.35 Km) is absurd due to the reasons explained above. You have rightly stated in sl. No 4 referring to article 10.5.2/10.5.1 regarding the entitlement of extension of time by the contractor which is applicable as the works were affected and the Mile Stone could not be achieved. The details of programme of work achieved quantities etc are regularly furnished in all MPR's. The deficit in financial progress is also reflected in the S-Curve forming part of MPR. We reproduce the summary here under: SI.No. Targeted - Achieved Up to Sep 4.37 - 4.35 Oct 8.98 - 8.295 Nov 16.44 - 11.491 Dec 25.9 - 14.691 Jan 33.65 - 21.002 Feb 44.29 - 24.322 March 54.45 - 34.270 Please refer page 15 of MPR wherein a tabulation showing the affected length stretches are given in detail (copy enclosed all MPR) enable a proper evaluation of the time lost. | FALSE | real_data
Extension of Time Proposals | EoT; Dispute Resolution | The same was also communicated in our Extension of Time (EOT) letters ref (8) & (13) above. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/2. Encroachements & Encumbrances in the ROW 11.10.2018.pdf | Encroachments & Encumbrances in the ROW -Reg. | With reference to above subject & letters, we would like to bring to your kind notice that the progress of work continues to suffer the ramifications of presence of Encroachments & Encumbrances in the ROW. Please refer to your letter ref (2) above wherein it was intimated that ROW to the tune of 90.44% was available for execution, enclosing Schedule-A of the Agreement. However, when we subsequently visited the Site we had encountered numerous encroachments & encumbrances and thus realized the fact that the available ROW was far less than 90.44%. Hence, we have submitted an Appendix containing the encroachments & encumbrances, vide letter ref (3) above for your joint verification and signing. The same was also communicated in our Extension of Time (EOT) letters ref (8) & (13) above. Further, through various letters referred above, we have intimated to the Authority & Authority Engineer as and when we had faced obstructions to the progress of work due to encroachments & encumbrances. We are once again enlisting below the locations which are not comprehensive, where we are unable to progress with the works even today along with the reasons. | FALSE | real_data
Extension of Time Proposals | EoT; Dispute Resolution | So far determination of EOT is awaited. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/5. Reply to request for expediting slow process of works 06.12.2018.pdf | Reply to request for expediting Slow Progress of works — Reg. | Respected Sir, This is with reference to the above subject and your above referred letter requesting to expedite the progress of works. We wish to draw your kind attention to our letters ref (2) and (3) above, through which we had submitted a detailed analysis of the delay events and their impact on progress. So far determination of EOT is awaited. We also request your kind attention to our letter to the EE, ref (4) above, requesting to issue COS notice for additional utility ducts. As you are aware, the pending land acquisition is the first of the major reasons for stoppage of work at various locations / various stages. Delay in approval of COS is the second major reason, apart from other delay events, for not being able to proceed with unobstructed work fronts. We request you to look into the above issues and resolve at an early date, which will enhance the progress at site. | FALSE | real_data
Extension of Time Proposals | EoT; Dispute Resolution | please refer to our letter ref (7) above requesting extension of time & revision of milestones. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/7. Status of Work Front Available 26.12.2018.pdf | Status of work front available — Reg. | Respected Sir, This is with reference to your letter #(1) above regarding the status of work front available, wherein it was mentioned that a length of 41.075 Km was available for work. In this regard, please refer to our letter ref (7) above requesting extension of time & revision of milestones. A total length of 34.35 Km was affected due to pending COS decisions/orders. Please refer to letters (2) to (6) & (8) above regarding structures identified under COS. A total of 269 structures are approved by the AE for Change of Scope. You will appreciate the fact that, despite our repeated requests, COS orders for these structures are still pending. Authority and Authority’s Engineer categorically specified not to take up any COS works until COS orders issued. In addition to this, we continue to get affected by the perennial land acquisition issues, as the property owners have obstructed execution of works. The details are explained in our letter ref (7) above. Apropos to the above, we wish to mention you that, after accounting for all the encroachments and encumbrances as on date, we are able to execute works at very few locations which covers a length of around 22.237 Kms. | FALSE | real_data
Extension of Time Proposals | EoT; Dispute Resolution | 1. We have applied for Extension of Time vide our letter ref (3) above along with SOP format for EOT vide ref (2) above, wherein the reasons for non-achievement of Milestones as defined in Schedule-J of the Agreement are elaborated. 2. The Authority/AE are yet to communicate their approval on the EOT, which is pending since long. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/13.Request for Releasee of Payment Withheld against Non Achived of Milestones 02.03.2019.pdf | Request for Release of Payment Withheld against Non-Achievement of Milestones | This is with reference to our payments to the tune of Rs.1,500,0000 that are withheld till our Stage Payment IPC-07 against non-achievement of Milestones. We wish to clarify the following in this regard: 1. We have applied for Extension of Time vide our letter ref (3) above along with SOP format for EOT vide ref (2) above, wherein the reasons for non-achievement of Milestones as defined in Schedule-J of the Agreement are elaborated. 2. The Authority/AE are yet to communicate their approval on the EOT, which is pending since long. 3. Pursuant to Clause 10.3.3 of the EPC Agreement, “The Authority shall notify the Contractor of its decisions to impose Damages in pursuance with the provisions of this Clause 10.3. Provided that no deductions on account of Damages shall be effected by the Authority without notifying the Contractor of its decision to impose the Damages, and taking into consideration the representation, if any, made by the Contractor within 20 (twenty) days of such notice....". There was no notification from the Authority in this regard. 4. We invite to your attention letter no. 01041028/02/0021, dated 26 July 2018, by the Team Leader, specifically stating that no damages are recommended by them on non achievement of milestone, even though Executive Engineer referred Clause 10.3.2 of the EPC Agreement. In view of the above, withholding payments for non-achievement of Milestones is against the provisions of the EPC Agreement. Also, our application for extension of time / revision of milestone dates are being considered benignly. Hence, we request you to recommend for release of the withheld amounts at the earliest. | FALSE | real_data
Extension of Time Proposals | EoT; Dispute Resolution | It is observed that, as per your analysis of the delay events, not attributable to the Contractor, we are rightfully entitled for EOT of 547 days i.e. up to 30.11.2020. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/15. Request for handling over of full ROW 09.04.2019.pdf | Request for Handing over of full ROW | We request your kind attention to your letter # (1) above, wherein you have recommended extension of Time (EOT) for a period of 180 days, pursuant to Clause 10.5 of the EPC Agreement. We thank you for recommending the EOT duly mentioning the reasons that are beyond our control. It is observed that, as per your analysis of the delay events, not attributable to the Contractor, we are rightfully entitled for EOT of 547 days i.e. up to 30.11.2020. However, we fail to understand the reason why the recommendation was limited to 30.11.2019 (which is less than the entitled EOT based on delay calculations). Please also note that we have been notifying the further delays accumulating on some of the issues which are yet to be resolved. Please refer our letters ref (2) and (3) above, inter alia in this regard. Further, it is mentioned in your letter ref (1) above, that the EOT duration determined was subject to the condition that the ROW for the affected reaches will be handed over to the Contractor by 31.03.2019 and all the hindrances/obstructions will also be removed by 31.03.2019. It is to inform that no further land was been handed over by the Authority and no hindrances/obstructions were removed till date. In view of the above, it is to mention that we are eligible for further delay until the handing over of full ROW, i.e. the entire length of the Project Highway, free of encroachments and encumbrances at the earliest. | FALSE | real_data
Extension of Time Proposals | EoT; Dispute Resolution | The required information as demanded by the Authority engineer vide letter under reference Sr. No. 5 is as follows. We once again request the Authority Engineer to determine and communicate the extension of time early. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/79_30092019_ Supporting Documents for EOT-I_R2.pdf | Six laning of Karaipettai to Walajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - Rescheduling of Project Milestones — Request for Extension of time - Supporting details - Reg. | The required information as demanded by the Authority Engineer vide letter under reference at Sr. No. 5 is as follows. 1) Rainfall Data You are aware that Tamilnadu gets majority of rain from North East monsoon which starts from October end and continues up to December. From South West monsoon also Tamilnadu gets some portion of rain. This year, area under which Project Highway falls got excess rainfall from South West monsoon. Hence, it has impacted the progress of the work. Rainfall Data from June 2019 to till October-2019 is enclosed as Annexure — 1. Photos showing some of the affected portions of the work due to South West monsoon rain are enclosed as Annexure-2. 2) Aadhi Athi Varadhar - Festival The Aadhi Athi Varadhar festival was conducted during the period between 01.07.2019 and 18.08.2019. Entire district administration of Kanchipuram was pre-occupied with the smooth functioning of Aadhi Athi Varadhar festival which happens once in 40 years. Hence, we had a lukewarm response relating to processing our application towards extraction of borrow earth. This severely hampered the contractors plan to commence earth work. Due to unprecedented number of pilgrims visiting Kancheepuram during this event, district administration and police did not allow the vehicles the Kanchipuram town and hence vehicles were parked on the prepared OGL bed. Due to this we couldn’t proceed with further construction works at those locations. Paper cuttings during the Festival period is attached as Annexure — 3. 3) Borrow Earth Permission The EPC Contractor has been making sincere efforts towards getting permission for extraction of borrow earth since February 2019. First Model code of conduct was in force on the eve of Parliament Elections from 10/03/2019 and the same was lifted only on 25/05/2019 and then for Vellore Lok sabha constituency from 10/03/2019 to 09/08/2019 as the polling for this constituency was postponed by the Election Commission. During this period, Revenue Authorities from both the districts of Kanchipuram and Vellore were reluctant to receive the application for procuring borrow earth as they were busy with the election work. This also hampered the commencement of earth work. Due to above mentioned reasons permission for borrow earth was getting delayed. However, in the best interest of early completion of the project we are now procuring the borrow earth from a third party from 16.09.2019 the date on which the third party got the permission for borrow earth. The approval letter for Borrow Earth permission for the Third Party is attached as Annexure - 4. You must be aware that the quantum of overburden earth available in private quarries are meager and adequate quantity of borrow earth can be procured only from lakes / ponds maintained by the Government. We are likely to get the permission for borrowed earth soon. We once again request the Authority Engineer to determine and communicate the Extension of Time early. This is for your information and further necessary action. | FALSE | real_data
Extension of Time Proposals | EoT; Dispute Resolution | We hereby request the Authority Engineer to revisit the EOT/Rescheduling of Milestones already recommended in light of the justifications cited above. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20200129_SPK_AE_001_Reply on Rescheduling of Project Milestone - Request for EoT.pdf | Reply on Rescheduling of Project Milestones — Request for Extension of Time - Reg. | The Authority Engineer vide ref (3) cited above communicated his recommendation on the above captioned subject. The EPC Contractor would like to submit his observations which are as follows: 1. The EPC Contractor vide his letter No. 49 / SPK / Kar - Wal / PD / NHAI dated 17.06.2019 requested the Authority to consider the ROW handed over in terms of length (as per Cl. 4.1.3 and not in terms of area and shift the Appointed Date based on the actual date of removal of encumbrance / encroachment / obstruction for which response is still awaited from the Authority. Further, it is worth mentioning that the AE also reiterated our stand wherein it was mentioned in Authority Engineer recommendation that “It is also worth mentioning that this memorandum was signed based on the % of area of the project ROW, in place of % of length, as mentioned in the Clause 4.1.3 (a).” 2. The assessment of hindrance length by the EPC contractor is correct as irrespective of hindrance available on one side, the same has to be considered for entire six laning width. In this regard it is hereby requested that the definition of ROW as per Article 28 shall be referred for further clarity. Further a working strip of at least 3 m wide shall be available parallel from the toe of the embankment pursuant to Clause 8.3.1 of the Contract Agreement. Authority Engineer has not based on this provision. 3. We totally deny with the observation of the Authority Engineer in not considering delay in handing over of land by the Authority pursuant to 4.1.3 (a) and 8.3.2 of the Contract Agreement. It is worth mentioning that even as on date 90% of encumbrance free land is yet to be handed over which is against the provisions of the Contract Agreement as 90% of land should have been handed over within 30 days of the execution of the agreement as per 4.1.3 (a) i.e on or before 15/11 / 2019. The joint inspection done on 24.10.2019 and on which the Authority Engineer’s representative signed would prove that only 62.51% of length was available on that day. Even today the Authority Engineer may carry out a joint inspection and will find that hardly 70% of the length is available for work front if imparted length is considered. 4. The EPC Contractor is obligated to comply only with the provisions of the Contract Agreement and not bound by any internal circular of the Authority as mentioned in AE recommendation. Hence, we disagree with the contention of the Authority Engineer that the EPC Contractor is not entitled for EOT in light of the circular issued by the Authority dated 16.08.2019. 5. It has been explicitly mentioned in Authority Engineer’s recommendation that shifting of utilities was being taken care by the Authority. Further the Contract Agreement between the Authority and Utility shifting agency was executed only on 19.07.2019. It is evident that shifting of utilities was not taken up till 19.07.2019, i.e 158 days from the declaration of Appointed Date by the Authority. Since the Authority is taking care of utility shifting and the agency appointed by the Authority commenced the works only after 180 days of the Appointed Date, period of 180 days mentioned in Clause 9.2is has no relevance. Hence, we deny with the contention of the Authority Engineer that the Contractor is entitled for time extension only beyond 180 days. The project duration is only 24 months and first 6 months are very crucial for the EPC contractor to progress the works based on his targeted programme. The Authority Engineer is also reiterating our concern wherein it has been mentioned that, ’The shifting of Utilities is important for this project, as the project is a Toll road and considering this, the Contractor submitted Construction Methodology, stating that first service road is to be constructed and after diverting the traffic over there, Main carriageway would be constructed ” . Utility shifting work is also not progressing as the encumbrances have not been removed and space is not made available for relocating the utility. 6. We would like to submit that as per Cl. 6 of Schedule-J , the Extension of Time recommendation is for Scheduled Project Completion Date and not confined to Milestone I. Based on the EOT recommended, all the milestones get automatically rescheduled accordingly. Hence, we do not agree with the contention of the Authority Engineer that the Extension of Time for Project. | FALSE | real_data
Extension of Time Proposals | EoT; Dispute Resolution | This is with respect to the extension of time (EOT) approved by the Authority for a period of 112 days for Project Milestone-I without affecting changes in Scheduled Project Completion Period vide ref (3) cited above. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20200713_SPK_RO_42_Reminder - Request for revisiting the EOT already recommended - Rev2.pdf | Extension of Time and Rescheduling of Project Milestones - EOT granted for 112 days not acceptable to the EPC contractor - Request for revisiting the EOT recommended - Reminder sent - Reg. | 1. This is with respect to the Extension of Time(EOT} approved by the Authority for. a period of 112 days for Project Milestone-I without effecting changes in Scheduled Project Completion Period vide ref (3) cited above.The EPC Contrator disagrees and does not accept the grant of EOT approval for 112 days, the reasons for disgreeement of this approval are elaborated in our submission to the Authority Engineer vide ref (4) cited above. 2. The EPC contractor requested the Authority/NHAI to revisit the EOT determined/approved and communicate 324 days as interim Extension of time vide ref (5) cited above but, we are yet to receive response in this regard. Copy of the same is herewith enclosed as Annexure 1. 3. The Authority is yet to fulfil the obligations relating to handing over of ROW as per Sub Clause 8.2 of the Contract Agreement. Copy of the newspaper publication regarding LA status / notification for acquiring land for the Project Highway (Kanchipuram District} is herewith enclosed as Annexure 2. By not fulfilling the obligations as per the provisions of the Contract Agreement, the Authority committed a material default pursuant to Sub clause 23.2.1 (a) of the Contract Agreement. 4. The electrical pole/Transformer shifting is yet to be completed by the Authority even as on date and following are the Chainages whether shifting is required to be carried out: No.of Transformers In addition to the above, following locations listed below where shifting of High Tension(HT) Towerlines are required to be carried out: No. of HT Towers Status All Material mobilized at site. Due to Lockdown Estimate Approved on 22.02.2020. Electrical Contractor engaged by EPC Contractor on 20.03.2020 for shifting works. Due to Lockdown work yet to be taken-up. Estimate yet to be approved. Estimate yet to be approved. | FALSE | real_data
Extension of Time Proposals | EoT; Dispute Resolution | It is pertinent to mention that the Authority Engineer also in principle agreed to our proposal for interim extension of 324 days and the same was also presented during VC meeting conducted by the Regional Officer, Chennai on 13.04.2020 attended by the Project Director, Mgr. Tech, Team leader of AE and the Managing Partner of EPC Contractor. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20200804_SPK_AE_124_Delay in Achieveing Project Milestone - I & II_Reply Made.pdf | Delay in achieving of Project Milestone I and II - Reply made - reg | Dear Sir, In response to reference (9) cited above, we would like to submit the following: 1. The EPC Contractor’s disagreement with the EOT approval was communicated to the Authority Engineer, vide letter under ref (4) with a request to revisit the same based on the actual ground conditions and grant interim EOT for 324 days as requested and justified by the EPC Contractor. It was also pointed out that EOT was granted by rescheduling all the Project Milestones and not for a specific Project Date to Clause 6 of Schedule J of the Contract Agreement. 2. This was reiterated vide EPC’s Contractor’s letter under reference (5) and the extract of Contract Agreement Page 198 is appended below: Upon extension of any or all of the aforesaid Project Milestones or the Scheduled Completion Date, as the case may be, under and in accordance with the provisions of this Agreement, the Project Completion Schedule shall be deemed to have been amended accordingly. 3. As per Cl. 6 of Schedule-J, upon extension of any or all of the aforesaid Project Milestones, the remaining Milestones gets shifted automatically along with the Project Completion Schedule and the determination should be done within framework of the EPC Contract Agreement. 4. The Authority Engineer communicated EOT recommendation of 112 days vide ref (6) cited above based on the reply from the Regional Officer, NHAI Chennai vide Letter No NHAI/11019/17/2009/RO/Chennai/ 1461 dated 30.04.2020 forwarded by the Project Director, PIU Kanchipuram to the Authority Engineer at ref (2) copied to the EPC Contractor. As mentioned above, the EPC Contractor has already conveyed his disagreement with the EOT approval accorded by the Authority. Since Authority Engineer is aware of the actual ground conditions, it is hereby once again requested to appraise the same to the Authority for revisiting the EOT already approved and recommend for 324 days as sought by the Contractor with valid justifications. 5. EPC Contractor requested the Authority to revisit the EOT recommendation based on the actual ground conditions and grant interim EOT for 324 days and the same was communicated to the Authority vide letter under ref (5) cited above. Since there was no response from the Authority to our letter cited at (5) in this regard, the EPC Contractor vide letter under ref (8) cited above once again reminded the Authority, to revisit the EOT already approved. 6. It was highlighted that even as on date, i.e. 17 months after declaration of Appointed Date, 297 no of poles, 13 no of transformers and 3 HT towers were yet to be relocated. Moreover, it was also pointed out that as on date only 50% of length of Project Highway was available as work front, after taking into account the stretches, affected. | FALSE | real_data
Extension of Time Proposals | EoT; Dispute Resolution | After understanding the ground reality, RO promised that EOT would be granted soon. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20201119_SPK_AE_160_Contractor failure in achieving mile stone 1,2,&3.pdf | Six laning of Karaipcttai to Walajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - Contractor’s failure in achieving Project Mile Stone 1,2 & 3 applying of Damages vide Contract Article No. 10.3.2 & 10.3.3 - Reply made -Reg. | We are in receipt of your letter ref (26) cited above, our reply for the same is as follows: 1. The Contract Agreement for this Project was executed on 15.10.2018. The Appointed Date was fixed as 11.02.2019 and the same was communicated vide ref (2) cited above. 2. The Appointed date was declared as 11.02.2019 by the Authority taking into account the land handed over in terms of the available area without taking into consideration, the requirement of the Contract provision as per Clause 4.1.3 (a) of the EPC agreement which talks about the handing over of land only in terms of length of the Project Highway. The memorandum and appendix prepared in terms of area gave a deceptive / false picture about the availability of vacant access. Taking into consideration all the encumbrances, hindrances, utilities etc. the vacant access available on the appointed date declared was worked out and it was less than 90% and hence requested the Authority vide letter under ref (3) cited above for modification of the appointed date on which 90% of encumbrance free land would be made available to the Contractor. 3. The Authority in its response vide ref (4) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. 4. The EPC contractor vide ref (5) cited above in reply reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that the impacted length due to encroachments and encumbrances was 12.18 km which accounted to 33.77% of the project length. The workable length available to the contractor was only 66.23% of the project length. The EPC contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of encumbrance / encroachment / obstruction. | FALSE | real_data
Extension of Time Proposals | EoT; Dispute Resolution | We therefore request your good self to consider the plight faced by the EPC Contractor and kindly scrutinize our application for extension of time for a period of 9 months owing to outbreak of Pandemic COVID-19 based on circular notified by MoRT&H under Atmanirbhar Bharat dated 06.10.2020 vide NHAI/Policy Guidelines/Atmanirbhar Bharat/2020 Policy No. 18.57/2020 dated 15th October 2020 and recommend for an interim extension of 270 days for all Milestones and the Scheduled Completion Date to the Authority at the earliest. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20210419_SPK _AE_069_EOT under Atmanirbhar Bharat Relief.pdf | Contractor’s Entitlement to Extension of Time (EOT) due to COVID Pandemic - Force Majeure Event-EOT application for interim extension of time of 270 days under Atmanirbhar Bharat Relief - reg | Your kind attention is invited to the references cited above which in brief are as below: 1. The EPC Contractor notified the outbreak of Pandemic Covid 19 as Force Majeure Event vide ref (3) above as per Article 21 of the Contract Agreement. 2. The restrictions imposed through various Orders / Circulars / Communications / Guidelines by various Government instrumentalities had severe impact on the scheduled progress. 3. We are enlisting below the major implications and direct effects due to outbreak of Pandemic COVID - 19 on the Project below for your ready reference: a. Scarcity of workers and labourers and persistent fear of contracting COVID — 19 is reducing their general productivity. b. Those working at Site are performing under restrictive conditions with additional protections and safety, which are affecting the productivity of our manpower. c. Exodus of skilled works and huge problem in getting the skilled and unskilled labour. d. Non-availability of technicians / Engineers required for undertaking periodic and time bound maintenance of various plant and machineries e. Maintaining social distancing and other norms ordered by the Governments have impacted the productivity of existing labour at site. f. Due to the closure of factories / manufacturing units on account of lock down and constraints in transportation, procurement of various of critical raw materials & supplies required for various critical construction activities etc.is seriously affected. g. Procurement of materials for shifting of utilities are also delayed as the manufactures are unable to supply ordered quantities. 4. Some of the examples of the execution of works that were delayed due to COVID-19 and nationwide lockdown/unlocking in phased manner are listed below: a. During the process of unlocking to boost up the economy. Government has awarded several projects simultaneously. Because of this, the demand for all major construction material has shot up and _ outpaced _ the production /manufacturing capacity. The primary manufactures of cement and steel are not able to meet the supply required for the Project. b. Due to continued restrictions on public transportation and fear of pandemic, labour scarcity persists. | FALSE | real_data
Extension of Time Proposals | EoT; Dispute Resolution | Considering general election and the festival, period from 10.03.2019 to 18.08.2019 may be considered for the EOT for the first milestone as unforeseen event under the Non political and Political events | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/189_Rescheduling of Project Milestones - EOT - 1.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under BharatmalaPariyojana on EPC mode — Rescheduling of Project Mile Stone- Request for Extension of Time -Reg. | Having gone through your documents related to Rescheduling of Project Milestone-Request for Extension of Time EoT-1 please find enclosed herewith the Authority Engineers recommendations on the same subject. This is for your information and necessary action. | FALSE | real_data
Extension of Time Proposals | EoT; Dispute Resolution | In view of Clause 8.3.2 of the Contract Agreement, the Contractor cited reason of land not handed over pursuant to Clause 4.1.3 (a) is not acceptable and cannot be considered for entitlement for EOT | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/264_18022020_Rescheduling of Project Milestones – Request for Extension of Time.pdf | Rescheduling of Project Milestones — Request for Extension of Time -Reg. | In reference to the above-mentioned subject and Contractor letter No. SPK/KW/SAIC/NH-48/2020/001 dated 29.01.2020 regarding the rescheduling of Project Milestone, in this regard, it is submitted that AE has computed the 176 days for extension of time in Milestones I and II. The same was recommended vide AE letter No. SAICPL/Kar-Wal/H.O./NH-48/TN/2019/10451 dated 30.11.2019 to the Authority for their acceptance and further needful. However, the Contractor submitted his reservations on the computation of the nos. of delay days and requested for rescheduling of Project Milestones for a period of 324 days instead of recommended 176 nos. of days. In this regard, AE is hereby submitted point wise reply of your raised observations for your ready reference and record, please; 4. Modification of Appointed date and Handing Over in % of area. The appointed date was communicated by the Authority letter No. NHAI/PIU.K.giri/NH-4/SPK/PS/2019/972 Dated 03.06.2019. it is also submitted that as per cl 8.2.2 the authority shall provide the Right of Way to the Contractor in respect of all land included in the Appendix by the date specified in Schedule-A for those parts of the site referred to therein, or no later than 90 days of the appointed date for those parts of the site which have not been specified in Schedule-A. It is well evident that the lands specified in Annexure-II, Schedule-A of agreement are available from the day one and as on appointed date, the existing and proposed ROW is same and no parts of the site is mentioned as not available in Schedule-A and joint memorandum signed on 11.01.2019 except for the lands for widening of plaza at Chennasamudram. Hence authority has fulfilled the obligation. This was informed vide Authority letter No. NHAI/PIU.K.giri/NH-4/SPK/PS/2019/972 Dated 03.06.2019. In view of above, the request of the Contractor to modify the appointed date is not eligible as per agreement due to the following reasons (i) As per cl 4.1.3, 8.2.1 & 8.2.2, 8.2.3 — The agreement is signed on 15.10.2018 and the Joint memorandum is signed by both the parties on 30.01.2019 and appointed date is declared for the project on 11.02.2019 to commence the work. (i) The Authority Engineer vide Letter No. SAICPL/Kar-Wal/H.O./NH-48/TN/2019/10451 Dated 30.11.2019. informed that the contractor consciously agreed and signed the Joint memorandum and aware that the unencumbered and the vacant land available after joint inspection is 93.65%. (iii) Further, it is submitted that the Joint memorandum was signed on 11.01.2019 & the appointment date is declared as 11.02.2019. The Contractor has requested the Authority for modifying the Appointment date based on the length of Project Highway handed over, vide letter No. 29/SPK/Kar-Wal/PD/NHAI/ Dated 13.05.2019. On this account and in view of clause 8.3.2 of the Contract Agreement, the Contractor cited reason of land not handed over pursuant to Clause 4.1.3 (a) is not acceptable and cannot be considered for Entitlement for EOT. 2. Assessment of Hindrance length. The assessment of hindrance length is already enumerated in Point No. 01 above. It is to remind the contractor that the Joint memorandum was signed by both the parties on 30.01.2019 as per the provisions of the Contract Agreement. The AE hereby like to reiterate the clause 8.2.1. “The Authority Representative and the Contractor shall, within 30 (thirty) days of the date of this Agreement, inspect the Site and prepare a memorandum containing an inventory of the Site including the vacant and unencumbered land, buildings, structures, road works, trees and any other immovable property on or attached to the Site. Subject to the provisions of Clause 8.2.3, such memorandum shall have appended thereto an appendix (the “Appendix”) specifying in reasonable detail those parts of the Site to which vacant access and Right of Way has not been given to the Contractor. Signing of the memorandum, in two counterparts (each of which shall constitute an original), by the authorized representatives of the Parties shall be deemed to constitute a valid evidence of giving the Right of Way to the Contractor for discharging its obligations under and in accordance with the provisions of this Agreement and for no other purpose whatsoever’. AE would like to further clarify that cl. 8.3.1 last para stating that “For the avoidance of doubt, the Parties expressly agree that the Damages specified hereunder and the Time Extension specified in Clause 10.5 shall be restricted only to failure of the Authority to provide the Right of Way for and in respect of the width of the roadway, its embankment and a parallel working strip at least 3 (three) meters wide”. The width of the roadway can be treated as one side of the road since it is neither mentioned “Total width nor Full width’. Hence the Authority Engineer has done the analysis of Hindrance free length is clear with the above illustrated iteration. | FALSE | real_data
Extension of Time Proposals | EoT; Dispute Resolution | The Competent Authority from NHAI examined the proposals and after considering reliable grounds an EOT to a period of 112 days for Milestone I has been sanctioned. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/334_10062020_Rescheduling of Project Mile Stone -1, Extension of Time Granted for 112 Days by the Competent Authority.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode — Rescheduling of Project Mile Stone -1, Extension of Time Granted for 112 Days by the Competent Authority - Reg. | W.r.t above said reference No.32 & 25 it is to clarify that based on submissions from the Authority Engineer vide said Ref. No. 24 the Competent Authority from NHAI examined the proposals and after considering reliable grounds an EOT to a period of 112 days for Mile Stone-1 has been sanctioned. Further the reasons for conclusion and the rectifications has also been suggested which will be taken care by yourself. Hence please accord priority in complying & achieving the required progress. | FALSE | real_data
Extension of Time Proposals | EoT; Dispute Resolution | In this regard, the Regional Officer, NHAI vide reference 2nd cited has approved rescheduling of Milestone I only by 112 days without any change scheduled project completion period stipulated in the Contract Agreement and a copy of the Regional Officer, NHAI, Chennai letter cited 2nd in the above reference is enclosed herewith. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/878_07052020_EOT recommendation for NH 48 project.pdf | NHAI, PIU Kancheepuram - Six laning of Karaipettai to Walajapet section of NH-4 (New NH-48) from Km 71/015 to Km 107/091 in the State of Tamil Nadu under NHDP Phase V under Bharatmala Pariyojana on EPC mode — Extension of Time & Rescheduling of Project Milestones — Reg. | Please refer to your letter cited 1st in the reference, recommending therewith a period of 177 days for the Extension of Time for Project Milestone I to the Contractor, M/s. S.P.K. & CO., for the above subject EPC Project. In this regard, the Regional Officer, NHAI vide reference 2nd cited has approved rescheduling of Milestone I only by 112 days without any change scheduled project completion period stipulated in the Contract Agreement and a copy of the Regional Officer, NHAI, Chennai letter cited 2nd in the above reference is enclosed herewith. In view of the above and as directed by the Regional Officer, NHAI, Chennai, the Contractor, M/s. S.P.K. & CO., may be requested to accelerate the progress of subject work and to achieve the prescribed milestones for completing the work in stipulated time period as per the Contract Agreement. | FALSE | real_data
Extension of Time Proposals | EoT; Dispute Resolution | Considering general election and the festival, period from 10.03.2019 to 18.08.2019 may be considered for the EOT for the first milestone as unforeseen event under the Non political and Political events | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/20191130_AE_PD_10451_Recommendation of EOT I for a period of 178 days.pdf | Application for EOT | This is with reference to the captioned subject and application for EOT received from the Contractor, in this regard, it is submitted that the Contract Agreement was signed between Contractor M/s SPK & Co. and the NHAI for Six Laning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km 71+015 to Km 107+091 in the State of Tamil Nadu under NHDP Phase - V. The following are the main contractual data ; Contract Seen Date : 15/10/2018 Length of the Project 36.076 Km Project Cost INR 533,36,67,000 Appointed Date : 11/02/2019 Construction Period : 730 days from Appointed Date Scheduled Completion Date: 09/02/2021 DLP Period : 4 years from the Provisional Certificate Project Milestone ~ Days from Project Milestone Appointed Date Milestone - -1 180 Days 09/08/2019 Not achieved 365 Days 10/02/2020 To be achieved 550 Days 13/08/2020 730 Days 09/02/2021 To be Achieved In view of the above, Authority's Engineer has scrutinized the EOT application and Authority's Engineer observations are being summarized hereunder in light of the Contract Agreement; Scheduled Date ¦ Status Procurement of the Site; As mentioned in the Clause 8.2.1 of the Contract Agreement, which reproduced herewith “the Authority Representative and the Contractor shall, within 30 days of the date of this Agreement, inspect the Site and prepare a memorandum containing an inventory of the site including the vacant and unencumbered land, buildings, structures, road works, trees and any other immovable property on or attached to the site. Subject to the provisions of Clause 8.2.3, such memorandum shall have appended thereto an appendix (the “Appendix”) specifying in reasonable detail those parts of the site to which vacant access and Right of Way has not been given to the Contractor. Signing of the memorandum, in two counterparts (each of which shall constitute an original), by the Authorized Representatives of the Parties shall be deemed to constitute a valid evidence of giving the Right of Way to the Contractor for discharging its obligations under and in accordance with the provisions of this Agreement and for no other purpose whatsoever.” | FALSE | real_data
Extension of Time Proposals | EoT; Dispute Resolution | As per policy guidelines issued by the Authority under Atmanirbhar Bharat, Contractor may claim suitable EOT due to pandemic COVID 19 situation. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/20200827_AE_SPK_394_Delay in achieving of Project Milestones I and II.pdf | Delay in achieving of Project Milestones I and II - Reg | Dear Sir, In reference to the above-mentioned subject and Contractor letter refereed at (12) cited above, we would like to submit the following para wise reply: 1. Having gone through your disagreement with the approved for 112 days vide above said reference was reviewed and our comments was communicated through Ref. No.6. However, your contention for 324 vide above said No.4 by mentioning the points such as 1. Delay in handing over of ROW, 2. Delay in shifting of utilities, 3. Delay in Appointment of Authority Engineer 4. Delay in appointment of Proof & Safety Consultant & 5. Delay in procurement of Borrow earth was already addressed in our EoT recommendations letter. Hence, we stand by our earlier observations and reiterating the same issue is unprofitable. Further your request for 324 days and justifying yourself based on the above same grounds can’t be accepted. More ever, it should be noted that reasons submitted by the Contractor for delay, are nowhere concern with the delay in the works, such appointment of AE and the procurement of borrow earth, is the prime responsibility of the Contactor. He has to apply for such permits before the Appointed Date, but unfortunately, these permits applied very late by the Contractor. 2. The Extension of Time justifying for Mile Stone -1 based on the above said/suitable grounds was recommended vide C.C. CL. No. 10.5.1. & 2. Hence any delay in the Works effected due to the above reasons is already compensated in the EOT. However, mixing the same with WHOLE WORKS according Schedule “J” Point 6 is not accepted. This should also be noted that the progress of works is not appreciable even as on date. So, Contractor requested to please expedite the work progress instead of finding the reasons of delay. 3. Same as Point No.2 4. We reiterate that the approval of EoT for 112 days from the Competent Authority based on our recommendations and their own assessment. However, your disagreement on the same issue with the Authority is noted. 5. Same as point No.4. 6. Your contention for availability of land is deviating from the Joint Memorandum signed by both the parties. This issue was already addressed in the Point No.1. However, considering the balance in shifting of electrical utilities the EoT was recommended. But your contention to delay in achieving the Mile Stone due to non-shifting total electrical utilities is not acceptable. The AE do not agree the affected length as mentioned by the Contractor, however in case Contractor feels that encumbrances are not allowing him to proceed with the works, then Contractor may discuss with the Authority for the length not handed over in the Memorandum signed between the parties in light of Article 8 Right of Way of the Contract Agreement. 7. At no point of time the Authority Engineer has agreed to your contention of 324 days EoT. The AE opinion has been submitted while processing the EOT request. Presenting your grievances will not be accepted as approval of your contention for 324 days. It is requested to such one side conclusions shall not be accepted and they are beyond the good industry practice. Noted, but as mentioned in our letter as referenced No.9 and as on date the Project Mile Stone -3 has also lapsed where in which your stage payment certification should be 60% against which you achieved only 14.38%. This clear cut indicates in lack of progress at with in the available land itself. The delay in progress with specific points has already intimated to you vide our letter No’s SAICPL/Kar-Wal/TL/NH-48/TN/02B//71/2020/361, 367 & 380 Dated 10th July 2020, 23 July and 07th August 2020 respectively. Hence once again it is asked to mobilize your resources to achieve the required progress as per the scheduled completion date. | FALSE | real_data
Extension of Time Proposals | EoT; Dispute Resolution | Rescheduling of milestone I only by 112 days without any change in Scheduled project completion period stipulated in the contract agreement is approved. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20200430_RO_PD_1461_Approval of 112 days for interim EOT I.pdf | NHAT, RO. Chennai ~ PIU, “Kancheepuram _ Six laning of Karaipettai to Walajapet section of NH4 (New NH-48) from km 71/015 to km 107/091 in the State of Tamil Nadu under N NHDP Phase V- rescheduling of Project Mile stone I | Please refer your letter cited at (1) on the above mentioned subject and esting for Extension of Time & Rescheduling of project Milestones. In this snection, in pursuance of the details and the report furnished in your letter dated 0 and the Authority Engineer(AE) letter at (2) under reference, the delay of 112 days mei ioned towards shifting of scattered electrical utility lines/poles in some ss retches of Project Highway appears to be delay on part of the Authority. Further, the j of 47 days delay due to excess rainfall from 15.10.2019 to 31.10.2019 : recom nended in your & AE’s letter is a overlap in the above mentioned period of 12 days. Accordingly, rescheduling of Milestone I only by 112 days without any change in the Scheduled Project Completion period stipulated in the Contract Agreement is approved. vee 2. As brought out in the AE’s letter cited under reference (2) the deployment of ma y ig not complete which indicates that the Contractor is not putting efforts to the pace, progress of the work and to complete the project. As such, for any ¦/ delay in achievement of progress beyond the rescheduled period of Mile Stone I and other Milestones the Contractor will be solely responsible for such delays. Hence, the Contractor shall be directed to make all out efforts to accelerate the progress, to achieve the prescribed milestones so that the work could be completed by the time . period stipulated in the Contract agree | FALSE | real_data
Extension of Time Proposals | EoT; Dispute Resolution | The availability of land at the time of Appointed Date is not matching with the joint memorandum signed by yourself and the Authority.Hence necessary proof if any form a valid source be submitted for verification and substantiation of your request. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210503_AE_SPK_614-EOT by the Authority for a period of 112 days not agreeable to the EPC Contractor-.pdf | Extension of Time recommendation by the Authority for a period of 112 days not agreeable to the EPC Contractor- Request for considering EoT as discussed during the Review Meetings — Reg. | Dear Sir, Having gone through the submission vide said Ref. No.46 regarding the disagreement with the Authority for a period of 112 days and asking the EOT for a period of 678 days based on the meetings and the site condition we hereby communicate the following for your further needful; 1. Your proposals basically depending on the availability of land as of now and on the Appointed Date. But the availability of land at the time of Appointed Date is not matching with the Joint Memorandum signed by yourself and the Authority. Hence, necessary proof if any form a valid source be submitted for verification and substantiation of your request. 2. The Memorandum signed by both the parties and accordingly Appointed Date declared. 3. We observe that there are many discrepancies in the calculations made relating to the available land itself. It is quoted that there is number of meetings and conclusions were made in favor of yourself. If so the case the necessary proof may be submitted for verification and to substantiate the recommendations from our end. | FALSE | real_data
Extension of Time Proposals | EoT; Dispute Resolution | The comprehensive extension of time proposal for 678 days from the scheduled completion date (i.e from 09.02.2021) with the revised date of completion of the project as 20.12.2022 is submitted herewith for approval of the competent authority | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210709_PD_RO_1893_Comprehensive EOT recommendation.pdf | NHAI, PIU, Kancheepuram - Six laning of Karaipettai to Walajahpet section of NH-4 (Km 71/015 to Km 107/091) in the State of Tamil Nadu — Comprehensive Proposal / Revised Extension of Time & Rescheduling of Project Milestones upto 20.12.2022 -— Proposal submitted for approval - Reg. | I submit that, the Authority Engineer vide letter 1* cited above, recommended the Comprehensive Extension of Time Proposal for the period of 398 days i.e upto 13.03.2022 towards completion of the subject project. 2. In this regard, it is submitted that, the Regional Officer, NHAI, Chennai vide letter cited 9'8 above, approved the EoT for a period of 112 days for Milestone-1 against the contractor’s claim of 324 days. However, the contractor vide letter cited 8" above, requested the Authority for considering the EoT for a period of 324 days. 3. In this context, the Contractor was requested to submit the Comprehensive Extension of Time proposal for completion of work and the Contractor vide reference letter cited 4" and 5t above, submitted the Comprehensive EoT Proposal for a period of 678 days i.e., upto 20.12.2022 citing the delays in execution of work due to various reasons such as Covid-19 pandemic, delay in handing over of ROW, delay in Shifting of Utilities / Electrical Towers, delay in Appointment of Authority Engineer, delay in appointment of Proof & Safety Consultant, delay in Procurement of Barrow earth due to Vellore Constituency re-election etc. 4. In this regard, the Authority Engineer vide letter 15' cited above, recommended the Comprehensive Extension of Time Proposal for the period of 398 days i.e upto 13.03.2022 towards completion of the subject project as follows a) Authority Engineer Recommendation: “The AE would like to submit that as provision of Article 10.5.1 stated that “Without prejudice to any other provision of this Agreement for and in respect of Extension of Time, the Contractor shall be entitled to extension of time in the Project Mile Stone is or will be delayed by any of the following, namely: • Delay in providing the Right of Way, Environmental Clearance or Approval of railway Authorities specified in Article 4.1.1. • Any other cause or delay which entitles the Contractor to Extension of Time in accordance with the provisions of this Agreement. In view of the above, pursuant mentioned Article 10.5.1, Article 4.1.6 (a) & (e) of the Contract Agreement, the Authority Engineer opinion are being submitted herewith for further needful; i. Delay due to Force Majeure: Pandemic Coronavirus (COVID-19) As the COVID -19 Pandemic was started and its effect was falling on the project, the Contractor noticed the Authority and the AE through references mentioned as 25, 26 & 27.: In this regard the Contractor claimed total 270 days vide letter No. SPK/ KW/SAIC/ NH-48/2021/069 Dated 19.04.2021 mentioned as ref. No. 46 & 48. However, as per the guidelines issued by the MoRT & H and the Govt. of India, Under Atmanirbhar Bharat Scheme, the Authority Engineer has recommended the EoT under Atmanirbhar Bharat Scheme for a period of 6 months vide letter No. SAICPL/ Kar-IL | FALSE | real_data
Extension of Time Proposals | EoT; Dispute Resolution | The delay on account of land and utilities (without quantification of delays due to earth) is quantified as 530 days, while the EOT required is 678 days.The difference may be considered as in-direct delay due to unavailability of earth and also some delays on part of Contractor.Nonetheless, the responsibility of earth lies with the Contractor.Therefore, the delay is on account of the Contractor as well as the Authority.In view of the above,it is recommended that extension of time for 678 days,i.e upto 19th Decemeber 2022 may be considered without any cost to NHAI or the Contractor. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210805_RO_CGM_ Recommendation for EOT to CGM for 678 days.pdf | NHAI, PIU, Kancheepuram - Six laning of Karaipettai to Walajahpet section of NH-4 (Km 71/015 to Km 107/091) in the State of Tamil Nadu - Comprehensive Proposal / Revised Extension of Time & Rescheduling of Project Milestones- Reg. | This has reference to the proposal of extension of time for the above project received from PD, PIU, Kancheepuram vide letter No.1893 dated 09.07.2021 cited at 34 The project of 6-laning of Karaipettai - Walajahpet of NH-4 (Km 71/015 to Km 107/091) on EPC mode basis has been awarded to M/s SPK & Co. and the Contract Agreement is signed on 15.10.2018 and Appointed Date for the project was declared on 11.02.2019. The following are the details of the project; Length : 36.08 Km Awarded Cost : 533.37 Crore Agreement Date : 15.10.2018 Appointed Date : 11.02.2019 Schedule completion date : 09.02.2021 Physical progress : 36% Financial progress : 31% The scheduled project mile stone as per Clause 10.3.2 of Schedule-J are as under; 1. Project Milestone I: 10% contract price, Schedule date as per Contract: 180th day from the Appointed Date, i.e.09.08.2019, Status of Achievement: Achieved on 27.07.2020 2. Project Milestone II: 30% contract price, Schedule date as per Contract: 365th day from the Appointed Date, i.e. 10.02.2020, Status of Achievement: Achieved on 15.06.2021 3. Project Milestone III: 60% contract price, Schedule date as per Contract: 550th day from the Appointed Date, i.e. 13.08.2020, Status of Achievement: Yet to be achieved 4. Project Milestone IV: 100% contract price, Schedule date as per Contract: 730th day from the Appointed Date, i.e.09.02.2021, Status of Achievement: Yet to be achieved Due to various reasons of delay, the Extension of Time (EOT) for Mile Stone 1 was approved for 112 days by the RO vide letter No. 1461 dated 30.04.2020 in accordance with NHAI Policy Circular No. 9.2.32.2020 dt.17.01.2020. The length of the project is 36.08 Km. As on the Appointed Date, 90% of the land was handed over as per the Joint Memorandum. However, there were several buildings, structures, utilities and the effective land was only 66.23%. The entire possession has been given on 21.06.2021 (except toll plaza location which is still pending). The Contractor, M/s SPK & Co. has requested for an EOT of 678 days vide their letter dated 16.04.2021 cited 2nd above, which was examined by Authority Engineer (AE) vide their letter dated 30.06.2021. The Authority Engineer recommended an EOT of 398 days and PD, Kancheepuram recommended EOT of 818 days as under; 1. Delay due to Force Majeure: EOT recommended by AE: 183 days, EOT recommended by PD: 183 days 2. Delay in Handing over of unencumbered Land and water pipelines: EOT recommended by AE: 180 days, EOT recommended by PD: 325 days 3. Shifting of Electrical towers: EOT recommended by AE: 25 days, EOT recommended by PD: 194 days 4. Shifting of Water Supply pipelines: EOT recommended by AE: 0 days, EOT recommended by PD: 116 days 5. Delay in appointment of AE: EOT recommended by AE: 0 days, EOT recommended by PD: 0 days 6. Delay in proof and safety consultant: EOT recommended by AE: 0 days, EOT recommended by PD: 0 days. | FALSE | real_data
Handing over of land /Possession of site. | Authority's Obligations | As intimated in our earlier letters, there are Land Acquisition issues in some of the sections of the project Highway. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-1/10. Notified achivement of MS-II artcl-10 Sch-J of EPC.pdf | Notification on achievement of Milestone-II pursuant to Article 10.3.2 and as per Clause 3.1 & 3.2 of Schedule J of the EPC Agreement - Reg. | We request your kind attention to Clause 3.1 & 3.2 of the Schedule-J of the EPC Agreement in accordance with which, prior to 365th day from the Appointed Date i.e., 23-Jul-2022, we are required to have submitted to the Authority duly and validly prepared Stage Payment Statements for an amount not less than 35% of the Contract Price. It is our pleasure to mention that in accordance with Clause 3.2 of the Schedule-J, we have completed works for a value of INR 107.04 Cr (42.27%) as certified under IPC-7 i.e., before end of March 2022 and achieved Project Milestone-II ahead of schedule (relevant page of IPC-7 attached for your ready reference). As intimated in our earlier letters, there are Land Acquisition issues in some of the sections of the Project Highway (first 19 Kms & at Major bridge @ 5+260). We request your office to kindly expedite clearances at these locations to help us progress at similar pace and in achieving our next milestones and maintaining a healthy cash flow. | FALSE | real_data
Handing over of land /Possession of site. | Authority's Obligations | Land held up due to LA. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-3/1. Status of work front available to RCM 28.06.2018.pdf | Consultancy Service for Authority’s Engineer for Supervision of Rehabilitation and Up-gradation to 2 Lane with Paved Shoulder / 4-Lane Standards of National Highway (i) Section 0+000 from design chainage Km to 55+937 Km of NH-752E from Paithan to Shirur (Project length 55.937) & (ii) Section from design chainage km 55+937 Km to 114+486 Km of NH-752E from Shirur to Kharda (Project length 58.549 Kms) on EPC Mode.- Status of Work front available to M/s. RCM | With reference to above, the status of work front available for various items such as Subgrade, GSB, DLC, PQC and pipe culverts are tabulated below. Work Total Length Completed Description of Item Till Date Available(Kms) (Km) as per Available(km) due to L.A. IPC Subgrade 41.075 32.075 GSB 41.075 10.03 DLC 41.075 9.23 PQC 41.075 1.32 Structure(Pipe Culverts) Nos. | FALSE | real_data
Handing over of land /Possession of site. | Authority's Obligations | we were intimated by revenue department of Maharashtra state (Tahsildar) that even the land on which the existing road is running is also not registered /alienated as a property / possession of PWD. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-3/18. Application of EOT or revision of milestone dates 14.06.2018.pdf | Application for extension of time/Revision of Mile Stone dates - Reg. | As the construction of project highway/structures could not proceed, as scheduled in the construction programme, submitted vide our letter no RCM PVR JV/MH PWD/2017-18/40, dated 02nd Jun 2018, we requested for the following. Annexure- i. Amendment of Appointment date (Please refer our letter no. RCM PVR JV/MH PWD/2018-19/151, date 30 Jan 2018) Annexure-I ii. Modification of date of milestone(s) by 120 days (Please refer our Letter no. RCM PVR JV/MH PWD/2018-19/165, date 10th Feb 2018) Annexure-III In your reply to our letter dated 10th Feb 2018 stated above, reference has been made to article/clause 10.1.3 We submit that a) as per terms of contract conditions, we submitted the original construction programme vide letter no. RCM PVR JV/MH PWD/2017-18/40, Dated 02nd Jun 2018 and Annexure-I b) the revised programme, as per article 10.1.3, vide letter no. RCM PVR JV/MH PWD/2018-19/235, date 02nd May 2018 guner regarding Appointed Date, in sl no. 3, you have stated that as the Appointed Date is declared, no EOT can be determined. We had a detailed discussion with the Team Leader on 03rd May 2018 and clarified the following. Schedule-A states that the site comprises of PROW width, which is the same as existing ROW, which implies that the land for 50.587 Km is already in possession of Authority. Please refer clause 5.2 (g) Annexure-V On good faith, The Appointed Date was accepted and encumbrances and existing utilities were recorded in Memorandum by Us. The statement is yet to be countersigned by Authority/Authority Engineer (Please refer our letter no. RCM PVR JV/MH PWD/2017-18/71, dated 10th August 2018). On commencement of works, we were intimated by revenue department of Maharashtra state (Tahsildar) that even the land on which the existing road is running is also not registered/alienated as a property/possession of PWD. Kindly refer our letter no. RCM PVR JV/MH PWD/2018-19/151, date 10th Jan 2018(Annexure-II). The reason for acceptance of Appointed Date was only good faith and the ground reality, when enlightened to Authority, the Authority commenced action for acquisition of entire land width. Kindly refer clause 5.2(h) regarding the commitment of Authority which is a warranty given by Authority Annexure-VI(a,b) The scope of the project {21.a) states that construction, as specified in schedule B & C. will conform to schedule D the technical specification. In order to achieve 80 Kmph in plain terrain & 40 kmph in hilly terrain (reference schedule B of 2.2 page 174) all the kinks, sharp Curves require geometric improvements. Hence, when the horizontal alignment gets changed/improved. deviating from the existing center line, such shifting of center line, results in additional land width requirement. Annexure-VII The assumption and decision of Authority/DPR consultants to procure land for major realignment (only for 5.35 Km) is absurd due to the reasons explained above. You have rightly stated in sl. No 4 referring to article 10.5.2/10.5.1 regarding the entitlement of extension of time by the contractor which is applicable as the works were affected and the Mile Stone could not be achieved. The details of programme of work achieved quantities etc are regularly furnished in all MPR's. The deficit in financial progress is also reflected in the S-Curve forming part of MPR. We reproduce the summary here under: SI.No. Targeted - Achieved Up to Sep 4.37 - 4.35 Oct 8.98 - 8.295 Nov 16.44 - 11.491 Dec 25.9 - 14.691 Jan 33.65 - 21.002 Feb 44.29 - 24.322 March 54.45 - 34.270 Please refer page 15 of MPR wherein a tabulation showing the affected length stretches are given in detail (copy enclosed all MPR) enable a proper evaluation of the time lost. | FALSE | real_data
Handing over of land /Possession of site. | Authority's Obligations | Kindly note that 02nd Jun 2017, being the Appointed Date, 365 days have already elapsed. We invite your attention to the foot note in the same page defining that "The date specified herein shall in no case be beyond 365 days | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-3/19. Handling over of land of project highway 365 days deadline 14.06.2018.pdf | Handing over of land of Project highway - 365 days dead line - Reg. | Respected Sir, The Authority, under clause 5.2 (h) of contract agreement, has given a warranty that the contractor can commence work in 90 % of total length of project highway. We have already reported that this warranty is baseless, untrue and has resulted in non availability of entire project highway, with consequential effect of prolongation of all the works programmed, causing additional cost/expenses, to the contractor. Without prejudice to what is reported above, regarding the balance 10 % of highway structure, we invite your attention to clause 8.2.3 and schedule -A specified therein, for dates of handing over. 6 JUN 201Beduie-a Annex Il “dates for providing Right of way” (page 167) may please the te referred, in this context. rete last date for handing over is specified as 365 days from the Appointed Date. 1 AG" ost-Kindly note that 02" Jun 2017, being the Appointed Date, 365 days have already elapsed. We invite your attention to the foot note in the same page defining that “The date specified herein shall in no case be beyond 365 days. Since the works are going on only in limited work-fronts, due to personal interaction of the Contractor with the property owners, we request you to take necessary action for acquisition of 100 % length of project highway. | FALSE | real_data
Handing over of land /Possession of site. | Authority's Obligations | At the early stage of commencement itself, the fact that land is not in possession of PWD was highlighted by the contractor. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-3/20. Land acquisition-Impact on appointed date & milestones 12.07.2018.pdf | Land acquisition - impact on Appointed date & Milestones — Reg. | Respected Sir, This refers to your letter no. NHD/Abad/TS-2/1891 dated 27th June 2018 on our request for land acquisition (Ref. Letter no. RCM PVR JV/MH PWD/2018-19/271 dated 14th June 2018). Annexure-l We wish to add a few lines in response to your letter NHD/Abad/TS-2/1891 dated 27th June 2018. As you are aware, the EPC contractor agreed the Appointment Date, on good faith, based on the Authority's warranty (please refer clause 5.29 & 5.2h ) (please refer our letter no. RCM PVR JV/MH PWD/2017-18/71 dated 10th August 2017) Annexure-ll At the early stage of commencement itself, the fact that land is not in possession of PWD was highlighted by the contractor. Please refer your letter no. NHD/Abad/TS-2/1787, dated 06th September 2017 advising the contractor not to cause any resentment of villagers. This confirms the factuals and acceptance of Authority, regarding non-possession of any land. Annexure-lll Our programme submitted was open-ended and we were prepared to work on any land, made available. Please refer our letter no. RCM PVR JV/MH PWD/2017-18/70 dated 10 August 2017, the penultimate para, in this connection. Whenever the work was disrupted by villagers, we opted for adjacent stretches, where no obstructions were at that time. Also please refer our letter no. RCM PVR JV/MH PWD/2017-18/75, dated 23rd August 2017, regarding de-mobilizing & remobilizing resources to nearby stretches. Annexure-IV The main objective for our representation is that after Mr. Galande, the S.D.E, conducted many meetings in nearly 5 villages convincingly, we had the right atmosphere to interact with property owners. But by then we lost nearly four to five working months. When we could achieve up to sub grade level, due to the need for review of Plan & Profile drawings by M/S Roughton International Ltd., in Association with SATRA Infrastructure Management Services Pvt. Ltd, we were not permitted to proceed to high value items. Please refer our Letter no. RCM PVR JV/MH PWD/2018-19/165 dated 10th February 2018 (page 2 last para). Annexure-V A meeting was conducted by the Superintending Engineer on 11th January 2018 in Aurangabad specifically for approval of Plan & Profile drawings. You are aware that the last date of milestone-I with 30 days grace period also expired by then. Annexure-VI We made the request not as any allegation but humbly to express our inadvertently our inability in achieving Milestone I, Milestone-II and Milestone-III also. We are glad that the land acquisition action is now in progress and it is now required in all 55.937 km, due to Plan & Profile drawings, approved as per schedule D. We are enclosing a status report also, to emphasis our aforesaid matter. We regret if our representation is found baseless and we wish to submit that the said letter may be considered null & valid, in such case. | FALSE | real_data
Handing over of land /Possession of site. | Authority's Obligations | As you are aware, the pending land acquisition is the first of the major reasons for stoppage of work at various locations / various stages | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/5. Reply to request for expediting slow process of works 06.12.2018.pdf | Reply to request for expediting Slow Progress of works — Reg. | Respected Sir, This is with reference to the above subject and your above referred letter requesting to expedite the progress of works. We wish to draw your kind attention to our letters ref (2) and (3) above, through which we had submitted a detailed analysis of the delay events and their impact on progress. So far determination of EOT is awaited. We also request your kind attention to our letter to the EE, ref (4) above, requesting to issue COS notice for additional utility ducts. As you are aware, the pending land acquisition is the first of the major reasons for stoppage of work at various locations / various stages. Delay in approval of COS is the second major reason, apart from other delay events, for not being able to proceed with unobstructed work fronts. We request you to look into the above issues and resolve at an early date, which will enhance the progress at site. | FALSE | real_data
Handing over of land /Possession of site. | Authority's Obligations | we continue to get affected by the perennial land acquisition issues. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/7. Status of Work Front Available 26.12.2018.pdf | Status of work front available — Reg. | Respected Sir, This is with reference to your letter #(1) above regarding the status of work front available, wherein it was mentioned that a length of 41.075 Km was available for work. In this regard, please refer to our letter ref (7) above requesting extension of time & revision of milestones. A total length of 34.35 Km was affected due to pending COS decisions/orders. Please refer to letters (2) to (6) & (8) above regarding structures identified under COS. A total of 269 structures are approved by the AE for Change of Scope. You will appreciate the fact that, despite our repeated requests, COS orders for these structures are still pending. Authority and Authority’s Engineer categorically specified not to take up any COS works until COS orders issued. In addition to this, we continue to get affected by the perennial land acquisition issues, as the property owners have obstructed execution of works. The details are explained in our letter ref (7) above. Apropos to the above, we wish to mention you that, after accounting for all the encroachments and encumbrances as on date, we are able to execute works at very few locations which covers a length of around 22.237 Kms. | FALSE | real_data
Handing over of land /Possession of site. | Authority's Obligations | From the above. if is clear that pending COS orders/decisions & LA problems are the reasons for the slow progress of work- Even our existing resources are being subjected to ungainful deployment, due to jack of work fronts, as already intimated in our letter ref (2} above. At this juncture. mobilising additional resources wi51 only add to the huge financial loss already incurred by us. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/10. Regarding slow progress of work 31.01.2019.pdf | Regarding Slow progress of Work | This is with reference to your letter ref (1) above, regarding slow progress of work, wherein you have instructed us to mobilise additional resources in order to complete the works within the stipulated time. We invite your kind attention to our letter ref (3) above; we have clearly mentioned that works in 34.35 Km of the project are held up due to pending COS orders/decisions. Further, we have also mentioned that works are also hampered due to Land Acquisition (LA) problems at various stretches. From the above, it is clear that pending COS orders/decisions & LA problems are the reasons for slow progress of works. Even our existing resources are being subjected to unfruitful deployment, due to lack of work fronts, as already intimated in our letter ref (2) above. At this juncture, mobilising additional resources will only add to the huge financial loss already incurred by us. In view of the above, we request you to pursue the Authority on issuing COS orders and handing over balance ROW, free of encroachments and encumbrances. | FALSE | real_data
Handing over of land /Possession of site. | Authority's Obligations | In view of the above, it is to mention that we are eligible for further delay until encroachment , and encumbrance free ROW for the entire length of the Project Highway is handed over. We request you to pursue the Authority for handing over of full ROW. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/15. Request for handling over of full ROW 09.04.2019.pdf | Request for Handing over of full ROW | We request your kind attention to your letter # (1) above, wherein you have recommended extension of Time (EOT) for a period of 180 days, pursuant to Clause 10.5 of the EPC Agreement. We thank you for recommending the EOT duly mentioning the reasons that are beyond our control. It is observed that, as per your analysis of the delay events, not attributable to the Contractor, we are rightfully entitled for EOT of 547 days i.e. up to 30.11.2020. However, we fail to understand the reason why the recommendation was limited to 30.11.2019 (which is less than the entitled EOT based on delay calculations). Please also note that we have been notifying the further delays accumulating on some of the issues which are yet to be resolved. Please refer our letters ref (2) and (3) above, inter alia in this regard. Further, it is mentioned in your letter ref (1) above, that the EOT duration determined was subject to the condition that the ROW for the affected reaches will be handed over to the Contractor by 31.03.2019 and all the hindrances/obstructions will also be removed by 31.03.2019. It is to inform that no further land was been handed over by the Authority and no hindrances/obstructions were removed till date. In view of the above, it is to mention that we are eligible for further delay until the handing over of full ROW, i.e. the entire length of the Project Highway, free of encroachments and encumbrances at the earliest. | FALSE | real_data
Handing over of land /Possession of site. | Authority's Obligations | Non handing over of encumbrance free & hindrance free land by the Authority is a matter of serious concern leading to huge losses to NHAI. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20200713_SPK_RO_42_Reminder - Request for revisiting the EOT already recommended - Rev2.pdf | Extension of Time and Rescheduling of Project Milestones - EOT granted for 112 days not acceptable to the EPC contractor - Request for revisiting the EOT recommended - Reminder sent - Reg. | 1. This is with respect to the Extension of Time(EOT} approved by the Authority for. a period of 112 days for Project Milestone-I without effecting changes in Scheduled Project Completion Period vide ref (3) cited above.The EPC Contrator disagrees and does not accept the grant of EOT approval for 112 days, the reasons for disgreeement of this approval are elaborated in our submission to the Authority Engineer vide ref (4) cited above. 2. The EPC contractor requested the Authority/NHAI to revisit the EOT determined/approved and communicate 324 days as interim Extension of time vide ref (5) cited above but, we are yet to receive response in this regard. Copy of the same is herewith enclosed as Annexure 1. 3. The Authority is yet to fulfil the obligations relating to handing over of ROW as per Sub Clause 8.2 of the Contract Agreement. Copy of the newspaper publication regarding LA status / notification for acquiring land for the Project Highway (Kanchipuram District} is herewith enclosed as Annexure 2. By not fulfilling the obligations as per the provisions of the Contract Agreement, the Authority committed a material default pursuant to Sub clause 23.2.1 (a) of the Contract Agreement. 4. The electrical pole/Transformer shifting is yet to be completed by the Authority even as on date and following are the Chainages whether shifting is required to be carried out: No.of Transformers In addition to the above, following locations listed below where shifting of High Tension(HT) Towerlines are required to be carried out: No. of HT Towers Status All Material mobilized at site. Due to Lockdown Estimate Approved on 22.02.2020. Electrical Contractor engaged by EPC Contractor on 20.03.2020 for shifting works. Due to Lockdown work yet to be taken-up. Estimate yet to be approved. Estimate yet to be approved. | FALSE | real_data
Handing over of land /Possession of site. | Authority's Obligations | The availability of land to commence the Chinnasamudram toll plaza works was discussed. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/089_31082019_Minutes of Monthly Progress review meeting.pdf | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to 107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Minutes of Monthly Progress review meeting -Reg. | With respect to the above said reference please find enclosed herewith the minutes of meeting MoM -2 held on 27.08.2019. The venue and date for the next meeting will be intimated in due course of time. This is for your information and record. | FALSE | real_data
Handing over of land /Possession of site. | Authority's Obligations | The availability of land to commence the Chinnasamudram toll plaza works was discussed, for which the Project Director stated that there is a dispute in the court relating to additional land requirement and asked to look in to the other alternatives like provision of staggered Toll Plaza so as to avoid additional land requirement, | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/119_01102019_Minutes of Monthly Progress review meeting Mom -3.pdf | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to 107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Minutes of Monthly Progress review meeting Mom -3 -Reg. | With respect to the above said reference please find enclosed herewith the minutes of meeting MoM -3 held on 25.09.2019. The venue and date for the next meeting will be intimated in due course of time. This is for your information and record. Assuring our best services at all times. | FALSE | real_data
Handing over of land /Possession of site. | Authority's Obligations | As the demarcation of land completed second time, the meeting between the owners and the Revenue official is pending to remove the encroachment obstacles. It was opined to expedite the same. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/119_01102019_Minutes of Monthly Progress review meeting Mom -3.pdf | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to 107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Minutes of Monthly Progress review meeting Mom -3 -Reg. | With respect to the above said reference please find enclosed herewith the minutes of meeting MoM -3 held on 25.09.2019. The venue and date for the next meeting will be intimated in due course of time. This is for your information and record. Assuring our best services at all times. | FALSE | real_data
Handing over of land /Possession of site. | Authority's Obligations | In addition to the above, the Contractor informed that the PWD/BDO tank bunds are existing in the alignment of the Project Highway. The same has been addressed to the Authority vide reference letter (5) and enter upon permission for the same is under progress with the concerned department. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/20191130_AE_PD_10451_Recommendation of EOT I for a period of 178 days.pdf | Application for EOT | This is with reference to the captioned subject and application for EOT received from the Contractor, in this regard, it is submitted that the Contract Agreement was signed between Contractor M/s SPK & Co. and the NHAI for Six Laning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km 71+015 to Km 107+091 in the State of Tamil Nadu under NHDP Phase - V. The following are the main contractual data ; Contract Seen Date : 15/10/2018 Length of the Project 36.076 Km Project Cost INR 533,36,67,000 Appointed Date : 11/02/2019 Construction Period : 730 days from Appointed Date Scheduled Completion Date: 09/02/2021 DLP Period : 4 years from the Provisional Certificate Project Milestone ~ Days from Project Milestone Appointed Date Milestone - -1 180 Days 09/08/2019 Not achieved 365 Days 10/02/2020 To be achieved 550 Days 13/08/2020 730 Days 09/02/2021 To be Achieved In view of the above, Authority's Engineer has scrutinized the EOT application and Authority's Engineer observations are being summarized hereunder in light of the Contract Agreement; Scheduled Date ¦ Status Procurement of the Site; As mentioned in the Clause 8.2.1 of the Contract Agreement, which reproduced herewith “the Authority Representative and the Contractor shall, within 30 days of the date of this Agreement, inspect the Site and prepare a memorandum containing an inventory of the site including the vacant and unencumbered land, buildings, structures, road works, trees and any other immovable property on or attached to the site. Subject to the provisions of Clause 8.2.3, such memorandum shall have appended thereto an appendix (the “Appendix”) specifying in reasonable detail those parts of the site to which vacant access and Right of Way has not been given to the Contractor. Signing of the memorandum, in two counterparts (each of which shall constitute an original), by the Authorized Representatives of the Parties shall be deemed to constitute a valid evidence of giving the Right of Way to the Contractor for discharging its obligations under and in accordance with the provisions of this Agreement and for no other purpose whatsoever.” | FALSE | real_data
Handing over of land /Possession of site. | Authority's Obligations | The Consultant informed that the Contractor's submission based on the available land a staggered toll plaza drawing was submitted by the Contractor and the same under review. The Contractor has submitted the hindrances, encumbrance and utilities details which was jointly done with Authority Engineer. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/20191205_AE_NHAI_188_Minutes of Monthly Progress review meeting Mom-5.pdf | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to 107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Minutes of Monthly Progress review meeting Mom-5 -Reg. | With respect to the above said reference please find enclosed herewith the Minutes of Meeting Numbered as MoM-S held on 29.11.2019. The next meeting will be likely on 27.12.2019 at the Consultants office around 11.00 A.M in Kancheepuram. All the concerned are requested to attend with necessary documents. This is for your information and record. Assuring our best services at all times. | FALSE | real_data
Handing over of land /Possession of site. | Authority's Obligations | Your contention for availability of land is deviating from the Joint Memorandum signed by both the parties. The issue was already addressed in the point no.1 | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/20200827_AE_SPK_394_Delay in achieving of Project Milestones I and II.pdf | Delay in achieving of Project Milestones I and II - Reg | Dear Sir, In reference to the above-mentioned subject and Contractor letter refereed at (12) cited above, we would like to submit the following para wise reply: 1. Having gone through your disagreement with the approved for 112 days vide above said reference was reviewed and our comments was communicated through Ref. No.6. However, your contention for 324 vide above said No.4 by mentioning the points such as 1. Delay in handing over of ROW, 2. Delay in shifting of utilities, 3. Delay in Appointment of Authority Engineer 4. Delay in appointment of Proof & Safety Consultant & 5. Delay in procurement of Borrow earth was already addressed in our EoT recommendations letter. Hence, we stand by our earlier observations and reiterating the same issue is unprofitable. Further your request for 324 days and justifying yourself based on the above same grounds can’t be accepted. More ever, it should be noted that reasons submitted by the Contractor for delay, are nowhere concern with the delay in the works, such appointment of AE and the procurement of borrow earth, is the prime responsibility of the Contactor. He has to apply for such permits before the Appointed Date, but unfortunately, these permits applied very late by the Contractor. 2. The Extension of Time justifying for Mile Stone -1 based on the above said/suitable grounds was recommended vide C.C. CL. No. 10.5.1. & 2. Hence any delay in the Works effected due to the above reasons is already compensated in the EOT. However, mixing the same with WHOLE WORKS according Schedule “J” Point 6 is not accepted. This should also be noted that the progress of works is not appreciable even as on date. So, Contractor requested to please expedite the work progress instead of finding the reasons of delay. 3. Same as Point No.2 4. We reiterate that the approval of EoT for 112 days from the Competent Authority based on our recommendations and their own assessment. However, your disagreement on the same issue with the Authority is noted. 5. Same as point No.4. 6. Your contention for availability of land is deviating from the Joint Memorandum signed by both the parties. This issue was already addressed in the Point No.1. However, considering the balance in shifting of electrical utilities the EoT was recommended. But your contention to delay in achieving the Mile Stone due to non-shifting total electrical utilities is not acceptable. The AE do not agree the affected length as mentioned by the Contractor, however in case Contractor feels that encumbrances are not allowing him to proceed with the works, then Contractor may discuss with the Authority for the length not handed over in the Memorandum signed between the parties in light of Article 8 Right of Way of the Contract Agreement. 7. At no point of time the Authority Engineer has agreed to your contention of 324 days EoT. The AE opinion has been submitted while processing the EOT request. Presenting your grievances will not be accepted as approval of your contention for 324 days. It is requested to such one side conclusions shall not be accepted and they are beyond the good industry practice. Noted, but as mentioned in our letter as referenced No.9 and as on date the Project Mile Stone -3 has also lapsed where in which your stage payment certification should be 60% against which you achieved only 14.38%. This clear cut indicates in lack of progress at with in the available land itself. The delay in progress with specific points has already intimated to you vide our letter No’s SAICPL/Kar-Wal/TL/NH-48/TN/02B//71/2020/361, 367 & 380 Dated 10th July 2020, 23 July and 07th August 2020 respectively. Hence once again it is asked to mobilize your resources to achieve the required progress as per the scheduled completion date. | FALSE | real_data
Handing over of land /Possession of site. | Authority's Obligations | Contractor informed that the Revenue staff are not able spare time after Deepawali festival | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20201123_AE_SPK_480_Minutes of Monthly Progress review meeting Mom – 08.pdf | Consultancy services for Authority's Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode - Minutes of Monthly Progress review meeting Mom — 08 — Reg. | With respect to the above said reference please find enclosed herewith the Minutes of Meeting Numbered as MoM - 08 held on 21.11.2020 The next meeting will be likely on 23.12.2020 at the Consultants office around 11.00 A.M in Kancheepuram. All the concerned are requested to attend with necessary documents. This is for your information and record. Assuring our best services at all times. | FALSE | real_data
Handing over of land /Possession of site. | Authority's Obligations | The consultant asked to commence the drain and underpass works in the available land after clearing of obstructions. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210302_AE_SPK_569-Minutes of Monthly Progress review meeting Mom – 09.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode. - Minutes of Monthly Progress review meeting Mom — 09 — Reg. | With respect to the above said reference please find enclosed herewith the Minutes of Meeting Numbered as MoM - 09 held on 26.02.2021 The next meeting will be likely on 19 March 2021 at Team Leader office around 11.00 A.M in Kancheepuram. All the concerned are requested to attend with necessary documents. This is for your information and record. Assuring our best services at all times. | FALSE | real_data
Handing over of land /Possession of site. | Authority's Obligations | The delay analysis is considered based on the delay in handing over of particular land in respect of the total project length that is weightage delay.Based on this total delay due to the hindrance / encumbrance is 180 delay days. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210630_AE_PD_14484_Comprehensive EOT proposal.pdf | Extension of Time Comprehensive proposal- Reg. | With reference to the captioned subject and from the above mentioned chronology of correspondences, it can be understood that despite of approving an EoT for a period of 112 days for Mile Stone-1, the Contractor is disagreeing with the approval of the Authority and again highlighted the impediments adversely effected the First Mile Stone as well as other Milestone including the Scheduled Completion Date. The Contractor submitted the comprehensive proposal and requested for an extension of time. | FALSE | real_data
Handing over of land /Possession of site. | Authority's Obligations | In view of the above, we once again request your office to arrange for handing over of the balance land & removal of encumbrances at the earliest. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-2/10. 20240109_191_Cont_AE_Request of handing of Balance land & Removal of Emcumbrances.pdf | Request for handing over of balance land & clearance of encumbrances & encroachments within the ROW- (Reminder-1)- Reg. | Please refer to our letter at #2 above, wherein we have requested for handing over of the balance hindrance-free Right of Way (ROW). As intimated in our letter, the land available with the Contractor for execution of the works as on that date was only 32.758 Kms out of 69.978 Kms which is 46.81% of the total length of the project. The details of the land available as on date is tabulated below & detailed chainages are shown in the strip map annexed herewith. Even after two months from our above referred letter, the land availability status remains same, as no further land is cleared / handed over by the Authority. We are progressing with the works at few of the locations where land acquisition is not yet complete, by convincing the land owners. However, there is a risk of the land owners stopping the work at any point in time. Though we have achieved the 1* Milestone much earlier than the scheduled date, we are running out of work fronts for achieving further progress, which will have a negative impact on the subsequent milestones. In view of the above, we once again request your office to arrange for handing over of the balance land & removal of encumbrances at the earliest. | FALSE | real_data
Outbreak of epidemic or pandemic | EoT | Further, the Ministry of Home Affairs vide its order under ref (18) cited above extended the lockdown for a further period till 31.05.2020. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/26_19052020_ Extension of lockdown till 31.05.2020.pdf | Six laning of Karaipettai to Walajahpet Section of NH-4 (New NH-48) - Force, Majeure Event due to outbreak of Covid 19 - Lockdown imposed by Government of India from 24.03.2020 to 03.05.2020 extended till 17.05.2020 - Further extension of lockdown till 31.05.2020 - Intimation of the same - Reg. | After obtaining necessary approval from the District Administration, the EPC Contractor in the interest of completion of the Project Highway took proactive measures to bring back the labourers / operators from different districts within the State by arranging transportation. Accordingly, activities with available local manpower have been commenced at site and works are progressing. As communicated in our earlier correspondences, the return of migrant labourers to the Project Highway is yet to happen and this would result in further delay of kick-starting the already stalled activities which were executed by the migrant labourers. It is pertinent to mention that the State Government is making all arrangements for movement of migrant labourers to their respective states and several special trains are also arranged for their movement. Further, the Ministry of Home Affairs vide its order under ref (18) cited above extended the lockdown for a further period till 31.05.2020. Our Project Highway traverses through Kancheepuram and Ranipet districts where prevalence of Covid 19 cases are on the rise and these are the two out of twelve districts where Tamil Nadu Government has not allowed any further relaxations during this Lockdown 4.0. We already notified the above event of outbreak of Covid 19 as Force Majeure Event vide ref (3) cited above. The impact of time and cost during the lockdown period and also the subsequent re mobilizing period etc till things get completely normal with no restrictions, would be assessed and submitted in due course of time. This is for your information and further necessary action. | FALSE | real_data
Outbreak of epidemic or pandemic | EoT | In continuation to this advisory, Govt. of India declared complete lockdown from 24th March 2020 and necessary orders under Disaster Management Act 2005 have been passed by Ministry of Home affairs. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20200402_SPK_AE_054_Works standstill due to of outbreak of Corona virus.pdf | Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km.71+015 (Existing Km 71/000) to Km 107+091 (Existing Km 107/068) on EPC Mode in the state of Tamil Nadu under NHDP Phase-V - Progress review by Member (Technical) on 04.03.2020 - Works standstill due to of outbreak of Corona virus — Reg. | Dear Sir, It has been directed by the Member (Technical) during project review meeting on 04.03.2020 to demonstrate substantial progress in the months of March and April. A target of 2.5% per month was fixed. The EPC Contractor worked on continuous basis in order to achieve the targets as directed by the Member (Technical) during the review meeting. Accordingly, SR works for commencement of structure at Km.85+874 completed and diversion of main carriage way traffic into the service road was also planned. But unfortunately due to outbreak of Corona Virus (COVID - 19), the entire construction activities were halted since 22.03.2020. The district administration with the aid of police personnel curbed the movements of our trucks and other construction equipments in order to prevent the spread of this novel virus. Further, on 17th March 2020, the Government of India issued an advisory urging to all residing in India to take social distancing, quarantine, etc., measures as a strategy for implementation till 31st Mar 2020. Due to this serious outbreak of the virus, the labour force and technical manpower deployed in our project site got panicked and many of them have left the project site to their native places fearing getting infected with the said virus. Also, several cases are reported across the country, where people who are suspected to have come in contact with the virus, escaped from the quarantines and hospitals and therefore under such situation, the labourers/construction machinery operators deployed at our project site are finding it difficult to move out of their base camp and report to the site for duty. In continuation to this advisory, Govt. of India declared complete lockdown from 24th March 2020 and necessary orders under Disaster Management Act 2005 have been passed by Ministry of Home Affairs. We also notified the above as Force Majeure event in accordance with the provision of Article 21.2(a), 21.5.2 of the EPC Agreement vide ref (4) cited above. Hence, we would like to submit that we shall not be in a position to achieve rate of progress as discussed during the meeting held on 04.03.2020 due to extraordinary kind of situation prevailing in the country as detailed above. We shall make all out efforts in enhancing the progress of works after reviewing the ground situation post lifting of lockdown on 15.04.2020. | FALSE | real_data
Outbreak of epidemic or pandemic | EoT | Since the COVID-19 cases are alarmingly increasing, the Tamil Nadu Government ordered to enforce complete lockdown under Disaster Management Act 2005, for 12 days from 19.06.2020 to 30.06.2020 in Greater Chennai Police Commissionerate areas in Thiruvallur, Chengalpet and kanchipuram Districts. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20200620_SPK_NHAI_85_Lockdown imposed from 19.06.2020 to 30.06.2020.pdf | Six laning of Karaipettai to Walajahpet Section of NH-4 (New NH-48) - Force Majeure Event due to outbreak of Covid 19 - Lockdown imposed by Government of India from 24.03.2020 to 03.05.2020 extended till 31.05.2020 - Lockdown announced by TN Government from 19.06.2020 to 30.06.2020 in Chennai, Chengalpattu, Kanchipuram and Thiruvallur districts due to alarming increase of COVID 19 cases - Intimation of the same - reg | Dear Sir, Since the COVID 19 cases are alarmingly increasing, the Tamil Nadu Government ordered to enforce complete lockdown under Disaster Management Act 2005, for 12 days from 19.06.2020 to 30.06.2020 in Greater Chennai Police Commissionarate areas in Thiruvallur, Chengalpet and Kanchipuram Districts. Copy of the above-mentioned order is herewith enclosed as Annexure 1. Our Project Highway traverses through Kancheepuram and Ranipet districts where prevalence of Covid 19 cases are on the rise due to which there are restrictions in the movement of our scarcely available work force and Machineries. It is pertinent to mention that the TN Police is restricting the traffic movements by placing barricades along the Project Highway at Ch.85+875 where PCC laid for construction of VUP - Ch.85+869. Further construction of VUP couldn’t be proceeded due to placing of barricades by the police as mentioned above. As communicated in our earlier correspondences, the return of migrant labourers to the Project Highway is yet to happen and this would result in further delay of kick-starting the already stalled activities which were executed by the migrant labourers. It is pertinent to mention that the State Government is making all arrangements for movement of migrant labourers to their respective states and several Shramik special trains are also arranged for their movement. We already notified the above event of outbreak of Covid 19 as Force Majeure Event vide ref (3) cited above. The impact of time and cost during the lockdown period and the subsequent re mobilizing period etc till things get completely normal with no restrictions, would be assessed and submitted in due course of time. This is for your information and further necessary action. | FALSE | real_data
Outbreak of epidemic or pandemic | EoT | The progress was badly hampered due to outbreak of Pandemic COVID-19 and the Contractor notified the same as Force Majeure event in accordance with the provision of Article 21 of the Contract Agreement vide letter under ref (12) cited above. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20201119_SPK_AE_160_Contractor failure in achieving mile stone 1,2,&3.pdf | Six laning of Karaipcttai to Walajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - Contractor’s failure in achieving Project Mile Stone 1,2 & 3 applying of Damages vide Contract Article No. 10.3.2 & 10.3.3 - Reply made -Reg. | We are in receipt of your letter ref (26) cited above, our reply for the same is as follows: 1. The Contract Agreement for this Project was executed on 15.10.2018. The Appointed Date was fixed as 11.02.2019 and the same was communicated vide ref (2) cited above. 2. The Appointed date was declared as 11.02.2019 by the Authority taking into account the land handed over in terms of the available area without taking into consideration, the requirement of the Contract provision as per Clause 4.1.3 (a) of the EPC agreement which talks about the handing over of land only in terms of length of the Project Highway. The memorandum and appendix prepared in terms of area gave a deceptive / false picture about the availability of vacant access. Taking into consideration all the encumbrances, hindrances, utilities etc. the vacant access available on the appointed date declared was worked out and it was less than 90% and hence requested the Authority vide letter under ref (3) cited above for modification of the appointed date on which 90% of encumbrance free land would be made available to the Contractor. 3. The Authority in its response vide ref (4) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. 4. The EPC contractor vide ref (5) cited above in reply reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that the impacted length due to encroachments and encumbrances was 12.18 km which accounted to 33.77% of the project length. The workable length available to the contractor was only 66.23% of the project length. The EPC contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of encumbrance / encroachment / obstruction. | FALSE | real_data
Outbreak of epidemic or pandemic | EoT | Owing to increase in no of cases due to 2nd wave of COVID-19, the Tamil Nadu Government under Disaster Management Act 2005 extended the lock down till 30/04/2021 with existing guidelines and further restrictions. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20210415_SPK_PD_029_Regarding Spread of second wave of covid 19.pdf | Six laning of Karaipettai to Walajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V — Regarding spread of Second wave of “Covid 19”- Government restrictions and its effect on the Project — Notification of Force Majeure as per Article-21 of the Contract Agreement - Reg. | 1. With reference to the above subject, it is to inform that there is an outbreak of second wave of COVID-19 in India which has made the situation worst again. In this regard, looking to the severity of impact in various states, the Government of India and State Government have again taken some necessary steps of imposing restrictions like partial lockdown, night curfew, following social distancing, producing negative COVID-19 test report, etc. varying from state to state to contain spread of Pandemic and to combat the effects among the people. 2. The measures taken by different states to contain spread of pandemic have resulted in partial disruption of supply chain and elopement of Skilled and Unskilled labour in the fear of possibility of complete lockdown. The repatriation of labours due to fear and scare for the present situation are affecting the progress of work. Consequently, there is shortage of skilled labour resulting in slow pace of the project progress. Further, the guidelines to follow social distancing continues to remain in effect due to which the Contractor is compelled to work with minimum staff and labour so as to adhere to the same. 3. Hence it is pertinent to mention that there are guidelines issued by State Governments to present negative COVID-19 test report while crossing state borders due to which supply chain management has severely disrupted for major materials like Cement, Steel, Bitumen, etc. This has slowed down the production, procurement, and transportation of major materials at site which has badly affected desired pace of work progress. | FALSE | real_data
Outbreak of epidemic or pandemic | EoT | We are enlisting below the major implications and direct effects due to outbreak of Pandemic COVID-19 on the project below for your ready reference. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20210419_SPK _AE_069_EOT under Atmanirbhar Bharat Relief.pdf | Contractor’s Entitlement to Extension of Time (EOT) due to COVID Pandemic - Force Majeure Event-EOT application for interim extension of time of 270 days under Atmanirbhar Bharat Relief - reg | Your kind attention is invited to the references cited above which in brief are as below: 1. The EPC Contractor notified the outbreak of Pandemic Covid 19 as Force Majeure Event vide ref (3) above as per Article 21 of the Contract Agreement. 2. The restrictions imposed through various Orders / Circulars / Communications / Guidelines by various Government instrumentalities had severe impact on the scheduled progress. 3. We are enlisting below the major implications and direct effects due to outbreak of Pandemic COVID - 19 on the Project below for your ready reference: a. Scarcity of workers and labourers and persistent fear of contracting COVID — 19 is reducing their general productivity. b. Those working at Site are performing under restrictive conditions with additional protections and safety, which are affecting the productivity of our manpower. c. Exodus of skilled works and huge problem in getting the skilled and unskilled labour. d. Non-availability of technicians / Engineers required for undertaking periodic and time bound maintenance of various plant and machineries e. Maintaining social distancing and other norms ordered by the Governments have impacted the productivity of existing labour at site. f. Due to the closure of factories / manufacturing units on account of lock down and constraints in transportation, procurement of various of critical raw materials & supplies required for various critical construction activities etc.is seriously affected. g. Procurement of materials for shifting of utilities are also delayed as the manufactures are unable to supply ordered quantities. 4. Some of the examples of the execution of works that were delayed due to COVID-19 and nationwide lockdown/unlocking in phased manner are listed below: a. During the process of unlocking to boost up the economy. Government has awarded several projects simultaneously. Because of this, the demand for all major construction material has shot up and _ outpaced _ the production /manufacturing capacity. The primary manufactures of cement and steel are not able to meet the supply required for the Project. b. Due to continued restrictions on public transportation and fear of pandemic, labour scarcity persists. | FALSE | real_data
Outbreak of epidemic or pandemic | EoT | Lockdown has been extended till 14.06.2021 with relaxations and copy of the press release by TN Government along with news article is herewith enclosed as Annexure 1. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20210607_SPK_PD_48_Update on FM event as on 06062021.pdf | Six laning of Karaipettai to Walajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V” — Regarding spread of Second wave of “Covid 19”- Government restrictions and its effect on the Project -Update on Force Majeure Event - Lockdown extended till 14/06/2021 with relaxations —Reg. | Vide ref (22) above the EPC Contractor notified the outbreak of Second wave of COVID 19 as Force Majeure Event pursuant to Article 21 of the Contract Agreement. | FALSE | real_data
Outbreak of epidemic or pandemic | EoT | lockdown which was extended till 05.07.2021 has been further extended till 12.07.2021 with some more relaxations. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20210706_SPK_NHAI_ 046_Update on Force Majeure Event.pdf | Six laning of Karaipettai to Walajahpet Section of NH-4 (New NH-48) - Regarding spread of Second wave of “Covid 19”- Government restrictions and its effect on the Project -Update on Force Majeure Event - Lockdown extended till 12/07/2021 with further relaxations - Reg. | Vide ref (22) above the EPC Contractor notified the outbreak of Second wave of COVID-19 as Force Majeure Event pursuant to Article-21 of the Contract Agreement. The second wave of COVID-19 Pandemic in the country is more severe than the first wave of the Pandemic. The total active cases in the country as on 05/07/2021 is 4,82,071 and in last 24 hours fresh cases reported are 39,796. The second wave of the COVID-19 Pandemic is very severe which once again compelled the Government instrumentalities to impose strict restrictions to contain the spread of the second wave. | FALSE | real_data
Outbreak of epidemic or pandemic | EoT | lockdown which was extended till 12.07.2021 has been further extended till 19.07.2021 with some more relaxations. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20210712_SPK_PD_050_Update on Force Majeure Event as on 11.07.2021.pdf | Six laning of Karaipettai to Walajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V” — Regarding spread of Second wave of “Covid 19”- Government restrictions and its effect on the Project -Update on Force Majeure Event - Lockdown extended till 19/07/2021 with further relaxations — Reg. | Vide ref (22) above the EPC Contractor notified the outbreak of Second wave of COVID-19 as Force Majeure Event pursuant to Article-21 of the Contract Agreement. The second wave of COVID-19 Pandemic in the country is more severe than the first wave of the Pandemic. The total active cases in the country as on 12/07/2021 is 4,50,899 and in last 24 hours fresh cases reported are 37,154. The second wave of the COVID-19 Pandemic is very severe which once again compelled the Government instrumentalities to impose strict restrictions to contain the spread of the second wave. Restrictions like partial lockdown, full lockdown in the weekends, micro containment, night curfew, COVID-19 appropriate behaviour, social distancing, mandatory RT-PCR test report, Sec 11 under Cr.PC are already in force depending upon the severity in different parts of the Country. | FALSE | real_data
Outbreak of epidemic or pandemic | EoT | It is to inform that one time labour travel to worksite is allowed as per COVID 19 guidelines | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/849_04052020_Request for permission for labour movement.pdf | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet Section of NH-4 (Chennai - Bangalore National Highway) from Km 71+017 to Km 107+091 - Work halted due to COVID-19 - Recommencement of Six Laning Work by the EPC Contractor M/s. SPK & Co., — Urgent need for Labourers - Permission for the Construction Labours to come from various districts to The Base Camp at Kilambi Village in Kanchipuram Taluk & District - Reg. | I wish to inform that NHAI has taken up the work of Six laning of Karaipettai to Walajahpet section of NH-4 and the work has been awarded to M/s. SPK and Co., The work has been halted due to COVID-19 containment measures. In this regard, it is to state that all construction activities in rural areas are permitted as per Para 7.ii.c of the guidelines issued by the Ministry of Home Affairs, Government of India dated 01.05.2020 cited 2nd in the above reference. Further, Construction of Road works has been permitted as per the Tamil Nadu Government Order cited 3rd in the reference. Since the above subject project work is one of the crucial works for the road infrastructure development works in Tamil Nadu, construction laborers are needed urgently for the above six laning work. The work has to be done in the rural area and the working of labour in rural area is permitted in the construction activities. It is to inform that one time labour travel to worksite is allowed as per COVID-19 guidelines. It is therefore requested to allow the Vehicles and Labourers as per the list enclosed in the Annexure to this letter to come from Tirunelveli, Thoothukudi, Virudhunagar, Madurai, Trichy, Thiruvarur, Thanjavur, Ariyalur, Perambalur, Villupuram, Chengalpet, Thiruvallur and Kanchipuram Districts to the Base Camp at Kilambi Village, Kanchipuram Taluk & District for the Six Laning work of Karaipettai to Walajahpet Section of NH-4 (Chennai - Bangalore National Highway). It is once again informed that one time labour travel to worksite is allowed as per the COVID-19 guidelines. | FALSE | real_data
Outbreak of epidemic or pandemic | EoT | It is hereby concluded that the resultant EOT based on the above two circulars is 180 days only and the same is being informed to the Authority for according the necessary approvals. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210504_AE_SPK-616_Contractor’s Entitlement to Extension of Time (EOT) due to COVID Pandemic.pdf | Contractor’s Entitlement to Extension of Time (EOT) due to COVID Pandemic — Force Majeure Event -EOT application for interim extension of time of 270 days under Atmanirbhar Bharat Relief — Reg. | It is in response to the above said ref. No.23 the Contractor where in which it is requested to recommend to the Authority for an Extension of Time to a total period of 270 based on the MoRT & H Circulars dated 03.06.2020 and 06 October 2020 which states 6 and 3 months separately. However, after studying carefully we observe that based on the earlier circular dated 03 June 2020 an extension time for a period of six months is allowable based on the site condition. Hence it has been asked to substantiate your claim for an Extension of Time to six months with necessary documentary proof for verification. Further even-though the Atmanirbhar Policy extended to a period of another 3 months based on the 06 October 2020 circular but relating to the EoT it is clearly mentioned that “Extension of Time to Contractor/Concessionaire and consultants are to be read in Agreement with the O.M. No. 18/04/2020-PPD dated 13.05.2020 of Depot. Of Expenditure regarding Force Majeure Clause (FMC) and Depot. Of Expenditure O.M. No. 18/04/2020 — PPD dated 13.05.2020 according to which 3 months EoT can’t be recommended. Hence it is hereby concluded that the resultant EOT based on the above two circulars is 180 days only: and the same is being informed to the Authority for according the necessary approvals. This is for your information and compliance if any. | FALSE | real_data
Outbreak of epidemic or pandemic | EoT | We observe that there is no effect on the progress of construction activities and supply of materials to the project.However as explained above still if any difficulty faced, the Contractor is hereby asked to submit the proof of record for verification and the SOP based on the recent guidelines. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210506_AE_PD_619 – Notification of force Majeure submitted by the Contractor; Comments.pdf | Six laning of Karaipettai to Walajahpet section of NH-4 (New NH - 48) from Ch. Km. 71+015 to 107+091 (36.076 Km) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode — Notification of force Majeure submitted by the Contractor; Comments — Reg. | In response to the above said Ref. No. 23 regarding the notification of “Force Majeure” submitted by the Contractor through Ref. No. 22, our para wise comments are as under for your reference and necessary action. Para-1. “With reference to the above subject, it is to inform that there is an outbreak of second wave of COVID-19 in India which has made the situation worst again. In this regard, looking to the severity of impact in various states, the Government of India and State Government have again taken some necessary steps of imposing restrictions like partial lockdown, night curfew, following social distancing, producing negative COVID-19 test report, etc. varying from state to state to contain spread of Pandemic and to combat the effects among the people”. The impact of the recent Govt. steps such as Partial lockdown, Night Curfew, Following of Social Distancing relating to the said construction work has to be explained. However, till date we observe that there is neither stoppage of any night work nor any effects on the ongoing woks based on the new Rules & Regulations. Para-2. “The measures taken by different states to contain spread of pandemic have resulted in partial disruption of supply chain and elopement of Skilled and Unskilled labour in the fear of possibility of complete lockdown. The repatriation of labours due to fear and scare for the present situation are affecting the progress of work. Consequently, there is shortage of skilled labour resulting in slow pace of the project progress. Further, the guidelines to follow social distancing continues to remain in effect due to which the Contractor is compelled to work with minimum staff and labour so as to adhere to the same’. As explained above and to substantiate the difficulty/claim Contractor has been asked to submit the labor records and any other relevant data as a proof, so that same can be reviewed on the facts basis. Para-3. “Hence, it is pertinent to mention that there are guidelines issued by State Governments to present negative COVID-19 test report while crossing state borders due to which supply chain management has severely disrupted for major materials like Cement, Steel, Bitumen, etc. This has slowed down the production, procurement, and transportation of major materials at site which has badly affected desired pace of work progress”. For the basic materials like cement, steel & Bitumen etc. approvals have been obtained to the parties who are within the state also. Hence we observe that there is no effect on supply of materials as the latest curbs are limited to state to state transport system only. | FALSE | real_data
Outbreak of epidemic or pandemic | EoT | In view of the above,it is requested to issue suitable instructions to the concerned officials to cooperate to carry out the above work and necessary permission may be accorded for the movement of materials,machineries,personnel etc. to the work site. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210508_PD_DC_1448_Permission for working during lockdown.pdf | NHAI-PIU Kancheepuram - Six laning of Karaipettai to Walajahpet section of NH-4 (Km 71/015 to Km 107/091) in the State of Tamil Nadu — Carrying out the Construction Work - Regarding. | I wish to inform that the Honorable Chief Minister of Tamil Nadu vide press release cited above, announced complete lock down from 10.05.2021 (04:00 am) to 24.05.2021 (04:00am) in order to control the spread of the 2nd wave of Covid. However, exemption has been given to carry out the ongoing works. In this regard, it is informed that the work of Six laning of Karaipettai to Walajahpet section of NH-4 (Km 71/015 to Km 107/091) is being carried out by the Contractor- M/s. S.P.K & Co, Kanchipuram. This Project is being implemented for the Public Purpose and has to be completed at the earliest. So, the work has to be carried out continuously to complete the work. The work is being supervised by the Consultant M/s. SA Infrastructure Pvt Ltd. In view of the above, it is requested to issue suitable instructions to the concerned officials to cooperate to carry out the above work and necessary permission may be accorded for the movement of materials, machineries, personnel etc., to the work site. Further permission has to be accorded to the Engineers, Staffs of the Contractor and the Consultant to work site along with the vehicles. Further it is assured that the instructions issued by the Government on COVID will be followed without any deviation. | FALSE | real_data
Outbreak of epidemic or pandemic | EoT | In view of above facts,considering the COVID-19 pandemic effect, the Authority Engineer hereby recommends Extension of Time for 6 months in totla as per the NHAI/Policy Guidelines/Atmanirbhar Bharat Policy No.18.46/2020 dated 22/06/2020 for the Project Milestones and Scheduled Completion Date as mentioned above without imposition of any cost or penalty to either party, due to prevailing situation of Covid-19. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210616_AE_PD_14354_Extension on account of COVID 19 for a period of 6 months.pdf | Extension of time on account of COVID-19 Pandemic-Reg. | In regard to the above mentioned letters and subject, it is submitted that Contractor vide letter no.006 dated 25.03.2020 had intimated regarding the Covid-19 as a Force Majeure Event and requested the extension of time for 270 days due to Covid-19 vide letter No 073 dated 07.05.2020. The Contractor vide letter No. 073 dated 07.05.2020 submitted that; a) The progress of the work was badly hampered due to the outbreak of Covid-19 pandemic and same has been considered as Force Majeure Event as per Article 21 of the Contract Agreement. b) Disruption in supply chain management, which affected the availability of spare parts of the production units like plants and construction machinery which hampered the production of material and construction of work at site due to restriction imposed on movement coupled with deficient inventory levels with manufacturer's warehouses. c) The contractor was adhered to various restrictions imposed by the Statutory Authorities. d) Due to the lockdown and pandemic effect, the Project was reeling under severe shortage of workforce. All the trains and other transportation mode were suspended too. e) Absence of most of the Contractor's staff, workers, subcontractors and labourers due to uncertainty of COVID-19 situation. Assembling of people was not permitted as per the Government notification. f) For transiting between the districts, e-passes were issued by the Govt of Tamil Nadu but these e-passes were only attributed for attending death ceremony, marriage ceremony and health issues. g) Reduced output levels owing to observing stringent safety norms and need to practice social distancing on the construction site as the disease is very fatal and spreading at a higher rate. The above submitted proposal was reviewed by the Authority Engineer for 270 days Extension of Time for Project Milestones & Schedule Completion Date on the ground of COVID-19 pandemic in light of various policy guidelines issued under the Atmanirbhar Bharat Policy and the following is being submitted for ready reference and further needful, please; The Authority Engineer would like to bring kind attention on the project specific dates; The Contract Signing Date ; 15/10/2018 Length of the Project : 36.076 Km Project Cost : INR 533,36,67,000 Appointed Date : 11/02/2019 Construction Period : 730 days from Appointed Date EOT given in MS -I : 112 days for Milestone Stone - I Further to the above, AE would like to submit the provision of Contract Agreement and Atmnirbhar Bharat Policy Guidelines for ready reference, please. 1. Relevant Provisions of CA on Force Majeure: a. Classification of Force Majeure: As per clause 21.1, “As used in this Agreement, the expression “Force Majeure” or “Force Majeure Event” shall, mean occurrence in India of any or all of Non-Political Event, Indirect Political Event and Political Event, as defined in Clauses 21.2, 21.3 and 21.4 respectively, if it affects the performance by the Party claiming the benefit of Force Majeure (the “Affected Party”) of its obligations under this Agreement and which act or event (a) is beyond the reasonable control of the Affected Party, and (b) the Affected Party could not have prevented or overcome by exercise of due diligence and following Good Industry Practice, and (c) has Material Adverse Effect on the Affected Party.” | FALSE | real_data
Outbreak of epidemic or pandemic | EoT | Authoirty Engineer has recommended the EOT under Atmanirbhar bharat scheme for a period of 6 months. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210630_AE_PD_14484_Comprehensive EOT proposal.pdf | Extension of Time Comprehensive proposal- Reg. | With reference to the captioned subject and from the above mentioned chronology of correspondences, it can be understood that despite of approving an EoT for a period of 112 days for Mile Stone-1, the Contractor is disagreeing with the approval of the Authority and again highlighted the impediments adversely effected the First Mile Stone as well as other Milestone including the Scheduled Completion Date. The Contractor submitted the comprehensive proposal and requested for an extension of time. | FALSE | real_data
Outbreak of epidemic or pandemic | EoT | The extension for a period of 183 days which was recommended by the Authority Engineer is recommended by this office. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210709_PD_RO_1893_Comprehensive EOT recommendation.pdf | NHAI, PIU, Kancheepuram - Six laning of Karaipettai to Walajahpet section of NH-4 (Km 71/015 to Km 107/091) in the State of Tamil Nadu — Comprehensive Proposal / Revised Extension of Time & Rescheduling of Project Milestones upto 20.12.2022 -— Proposal submitted for approval - Reg. | I submit that, the Authority Engineer vide letter 1* cited above, recommended the Comprehensive Extension of Time Proposal for the period of 398 days i.e upto 13.03.2022 towards completion of the subject project. 2. In this regard, it is submitted that, the Regional Officer, NHAI, Chennai vide letter cited 9'8 above, approved the EoT for a period of 112 days for Milestone-1 against the contractor’s claim of 324 days. However, the contractor vide letter cited 8" above, requested the Authority for considering the EoT for a period of 324 days. 3. In this context, the Contractor was requested to submit the Comprehensive Extension of Time proposal for completion of work and the Contractor vide reference letter cited 4" and 5t above, submitted the Comprehensive EoT Proposal for a period of 678 days i.e., upto 20.12.2022 citing the delays in execution of work due to various reasons such as Covid-19 pandemic, delay in handing over of ROW, delay in Shifting of Utilities / Electrical Towers, delay in Appointment of Authority Engineer, delay in appointment of Proof & Safety Consultant, delay in Procurement of Barrow earth due to Vellore Constituency re-election etc. 4. In this regard, the Authority Engineer vide letter 15' cited above, recommended the Comprehensive Extension of Time Proposal for the period of 398 days i.e upto 13.03.2022 towards completion of the subject project as follows a) Authority Engineer Recommendation: “The AE would like to submit that as provision of Article 10.5.1 stated that “Without prejudice to any other provision of this Agreement for and in respect of Extension of Time, the Contractor shall be entitled to extension of time in the Project Mile Stone is or will be delayed by any of the following, namely: • Delay in providing the Right of Way, Environmental Clearance or Approval of railway Authorities specified in Article 4.1.1. • Any other cause or delay which entitles the Contractor to Extension of Time in accordance with the provisions of this Agreement. In view of the above, pursuant mentioned Article 10.5.1, Article 4.1.6 (a) & (e) of the Contract Agreement, the Authority Engineer opinion are being submitted herewith for further needful; i. Delay due to Force Majeure: Pandemic Coronavirus (COVID-19) As the COVID -19 Pandemic was started and its effect was falling on the project, the Contractor noticed the Authority and the AE through references mentioned as 25, 26 & 27.: In this regard the Contractor claimed total 270 days vide letter No. SPK/ KW/SAIC/ NH-48/2021/069 Dated 19.04.2021 mentioned as ref. No. 46 & 48. However, as per the guidelines issued by the MoRT & H and the Govt. of India, Under Atmanirbhar Bharat Scheme, the Authority Engineer has recommended the EoT under Atmanirbhar Bharat Scheme for a period of 6 months vide letter No. SAICPL/ Kar-IL | FALSE | real_data
Outbreak of epidemic or pandemic | EoT | Hence based on the above "It is communicated as stated in the Ref.No.38 vide Para.No.5 the impact on the project willl be ascertained as per the provision given in the Contract Agreement.As,it is submitted that as on date there is no guidelines issued by the NHAI/MoRT&H regarding any relaxation due to second wave of Covid 19 pandemic.If any, guidelines to be issued by the Authority in this regard,then the case be reviewed accordingly.Otherwise same to be dealt as per the contract provisions. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210716_AE_PD_654_Update on FM Event – Lock down Extended till 19072021.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode — Regarding Spread of Second Wave of COVID-19 Government restrictions and its effect on the Project — Update on Force Majeure Event — Lock down Extended till 49/07/2021 with further relaxations - Reply - Reg. | This is in reference to the telephonic discussions had with yourself & the Contractor's latest communication No. SPK/NHAI/PD/NH-48/2021/050 dated 12.07.2021 stated as Ref.37. relating to the spread of Second Wave of “COVID-19” —Government restriction and its effect on the Project- update on Force Majeure event, Lock Down extended till 19/7/2021 with further relaxations; for which our comments are as under: The above mentioned list of references from 1 to 20 are related to the First Wave of COVID-19. The losses/damages occurred to the Contractor due to the first wave were already compensated in our recommendations vide letter No. SAICPL/Kar-Wal/TL/NH-48/TN/2A/71/2021/14484 Dated 30.06.2021 stated as Ref. No.39. The remaining list of references i.e from 21 to 37, 40 & 41 are related to the Second Wave of COVID-19. For the reference letter No. SPK/NHAI/PD/NH-48/2021/029 dated 15.04.2021, as sought by yourself vide letter No. NHAI/11036/4/2019/PIU.Kanchee/1335 dated 05.05.2021 our comments were communicated through letter No. SAICPL/Kar-Wal/TL/NH-48/TN/02A/7H/2021/619 dated 06.05.2021 asking the Contractor to submit the proof of record for verification and the SOP based on the Second Wave Guide Lines. However, the Contractor continued to communicate to the Authority based on the weekly wise SOP’s issued from the Government, mentioned as references from 22 to 37. | FALSE | real_data
Mix Designs for Pavement Layers & Structural Concrete | Contractor's Obligations | We are here with submitting the Concrete Mix designs for PQC (M40 Grade) along with test reports | synthetic_template_20250913 | Submission of PQC (M40 Grade) Mix Design for approval- Reg. | With reference to above subject, we are here with submitting the Concrete Mix designs for PQC (M40 Grade) along with Test reports for your kind perusal and approval. The following Sources of the Materials have been used in the mix design. 1. Aggregate (SLMI Crusher, 32+400, RHS, 2.0Km lead, Cherla Gauraram Village) 2. Water (SLMI Crusher camp) 3. Cement (Orient - OPC 53 grade) 4. Admixture (Asian Paints SC Maximoplast PC 200) | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Mix Designs for Pavement Layers & Structural Concrete | Contractor's Obligations | We are here with submitting the Concrete Mix designs for PQC (M40 Grade) along with test reports | synthetic_template_20250913 | Submission of PQC (M40 Grade) Mix Design for approval- Reg. | This is to notify you that With reference to above subject, we are here with submitting the Concrete Mix designs for PQC (M40 Grade) along with Test reports for your kind perusal and approval. The following Sources of the Materials have been used in the mix design. 1. Aggregate (SLMI Crusher, 32+400, RHS, 2.0Km lead, Cherla Gauraram Village) 2. Water (SLMI Crusher camp) 3. Cement (Orient - OPC 53 grade) 4. Admixture (Asian Paints SC Maximoplast PC 200) | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Mix Designs for Pavement Layers & Structural Concrete | Contractor's Obligations | We are here with submitting the Concrete Mix designs for PQC (M40 Grade) along with test reports | synthetic_template_20250913 | Submission of PQC (M40 Grade) Mix Design for approval- Reg. | With reference to above subject, we are here with submitting the Concrete Mix designs for PQC (M40 Grade) along with Test reports for your kind perusal and approval. The following Sources of the Materials have been used in the mix design. 1. Aggregate (SLMI Crusher, 32+400, RHS, 2.0Km lead, Cherla Gauraram Village) 2. Water (SLMI Crusher camp) 3. Cement (Orient - OPC 53 grade) 4. Admixture (Asian Paints SC Maximoplast PC 200) | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Mix Designs for Pavement Layers & Structural Concrete | Contractor's Obligations | We are here with submitting the Concrete Mix designs for PQC (M40 Grade) along with test reports | synthetic_template_20250913 | Submission of PQC (M40 Grade) Mix Design for approval- Reg. | With reference to above subject, we are here with submitting the Concrete Mix designs for PQC (M40 Grade) along with Test reports for your kind perusal and approval. The following Sources of the Materials have been used in the mix design. 1. Aggregate (SLMI Crusher, 32+400, RHS, 2.0Km lead, Cherla Gauraram Village) 2. Water (SLMI Crusher camp) 3. Cement (Orient - OPC 53 grade) 4. Admixture (Asian Paints SC Maximoplast PC 200) | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Mix Designs for Pavement Layers & Structural Concrete | Contractor's Obligations | We are here with submitting the Concrete Mix designs for PQC (M40 Grade) along with test reports | synthetic_template_20250913 | Submission of PQC (M40 Grade) Mix Design for approval- Reg. | With reference to above subject, we are here with submitting the Concrete Mix designs for PQC (M40 Grade) along with Test reports for your kind perusal and approval. The following Sources of the Materials have been used in the mix design. 1. Aggregate (SLMI Crusher, 32+400, RHS, 2.0Km lead, Cherla Gauraram Village) 2. Water (SLMI Crusher camp) 3. Cement (Orient - OPC 53 grade) 4. Admixture (Asian Paints SC Maximoplast PC 200) | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Delay in construction activities | EoT; Dispute Resolution | Further delay in the approval of the GAD may disturb the planned schedule, and may lead to idling of our resources and delay in the completion of the project. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-1/13. Request for GAD of RUB at Km.16+676.pdf | Request for General Arrangement Drawing Approval (GAD) of RUB at Km.16+676 - Reg. | This is with reference to the construction of Road under Bridge (RUB) at km 16+676 as per Clause 7.4.3 of the Schedule-B of the EPC Contract Agreement (CA). As per Clause 3.1 (iii) of the CA, “The Authority shall, upon submission of the Performance Security as per the RFP by the Contractor, shall provide to the Contractor: (a) No less than 90% (ninety per cent) of the required Right of Way of the Construction Zone of total length of the Project Highway within a period of 30 (thirty) days from the date of this Agreement, which shall be in contiguous stretches of length not less than 5 (five) kilometer. (b) approval of the general arrangement drawings (the "GAD") from railway authorities to enable the Contractor to construct road over- bridges/ under- bridges at level crossings on the Project Highway in accordance with the Specifications and Standards, and subject to the terms and conditions specified in such approval, within a period of 60 (sixty) days from the Appointed Date, and reimbursement of all the costs and expenses paid by the Contractor to the railway authorities for and in respect of the road over-bridges/ under bridges; and (c) all environmental clearances as he 4.3.” As per Clause 3.1 (ili) (6) mentioned above, the Authority was supposed to provide GAD approval from the Railway Authorities within 60 days from the Appointed Date (i.e., 1-Apr-23 which is within 60 days from 31.01.2023). However, even as on date, the GAD is yet to be provided by the Authority. Thus, there is a delay of around 213 days up to 31-Oct-2023, in providing the GAD. As you are aware, even JEWS approval of the GAD, the construction of Se has to be done delay in the approval of the GAD may disturb the planned schedule, and may lead to ding of our resources and delay in the completion of the Project. In view of the above, we request the Authority to provide the GAD approval from the Railway Authorities at the earliest. | FALSE | real_data
Delay in construction activities | EoT; Dispute Resolution | As communicated in our earlier correspondences, the return of migrant laborers to the Project Highway is yet to happen and this would result in further delay of kick-starting the already stalled activities which were executed by the migrant laborers. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/26_19052020_ Extension of lockdown till 31.05.2020.pdf | Six laning of Karaipettai to Walajahpet Section of NH-4 (New NH-48) - Force, Majeure Event due to outbreak of Covid 19 - Lockdown imposed by Government of India from 24.03.2020 to 03.05.2020 extended till 17.05.2020 - Further extension of lockdown till 31.05.2020 - Intimation of the same - Reg. | After obtaining necessary approval from the District Administration, the EPC Contractor in the interest of completion of the Project Highway took proactive measures to bring back the labourers / operators from different districts within the State by arranging transportation. Accordingly, activities with available local manpower have been commenced at site and works are progressing. As communicated in our earlier correspondences, the return of migrant labourers to the Project Highway is yet to happen and this would result in further delay of kick-starting the already stalled activities which were executed by the migrant labourers. It is pertinent to mention that the State Government is making all arrangements for movement of migrant labourers to their respective states and several special trains are also arranged for their movement. Further, the Ministry of Home Affairs vide its order under ref (18) cited above extended the lockdown for a further period till 31.05.2020. Our Project Highway traverses through Kancheepuram and Ranipet districts where prevalence of Covid 19 cases are on the rise and these are the two out of twelve districts where Tamil Nadu Government has not allowed any further relaxations during this Lockdown 4.0. We already notified the above event of outbreak of Covid 19 as Force Majeure Event vide ref (3) cited above. The impact of time and cost during the lockdown period and also the subsequent re mobilizing period etc till things get completely normal with no restrictions, would be assessed and submitted in due course of time. This is for your information and further necessary action. | FALSE | real_data
Delay in construction activities | EoT; Dispute Resolution | But unfortunately due to outbreak of Corona virus (COVID-19), the entire construction activities were halted since 22.03.2020. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20200402_SPK_AE_054_Works standstill due to of outbreak of Corona virus.pdf | Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km.71+015 (Existing Km 71/000) to Km 107+091 (Existing Km 107/068) on EPC Mode in the state of Tamil Nadu under NHDP Phase-V - Progress review by Member (Technical) on 04.03.2020 - Works standstill due to of outbreak of Corona virus — Reg. | Dear Sir, It has been directed by the Member (Technical) during project review meeting on 04.03.2020 to demonstrate substantial progress in the months of March and April. A target of 2.5% per month was fixed. The EPC Contractor worked on continuous basis in order to achieve the targets as directed by the Member (Technical) during the review meeting. Accordingly, SR works for commencement of structure at Km.85+874 completed and diversion of main carriage way traffic into the service road was also planned. But unfortunately due to outbreak of Corona Virus (COVID - 19), the entire construction activities were halted since 22.03.2020. The district administration with the aid of police personnel curbed the movements of our trucks and other construction equipments in order to prevent the spread of this novel virus. Further, on 17th March 2020, the Government of India issued an advisory urging to all residing in India to take social distancing, quarantine, etc., measures as a strategy for implementation till 31st Mar 2020. Due to this serious outbreak of the virus, the labour force and technical manpower deployed in our project site got panicked and many of them have left the project site to their native places fearing getting infected with the said virus. Also, several cases are reported across the country, where people who are suspected to have come in contact with the virus, escaped from the quarantines and hospitals and therefore under such situation, the labourers/construction machinery operators deployed at our project site are finding it difficult to move out of their base camp and report to the site for duty. In continuation to this advisory, Govt. of India declared complete lockdown from 24th March 2020 and necessary orders under Disaster Management Act 2005 have been passed by Ministry of Home Affairs. We also notified the above as Force Majeure event in accordance with the provision of Article 21.2(a), 21.5.2 of the EPC Agreement vide ref (4) cited above. Hence, we would like to submit that we shall not be in a position to achieve rate of progress as discussed during the meeting held on 04.03.2020 due to extraordinary kind of situation prevailing in the country as detailed above. We shall make all out efforts in enhancing the progress of works after reviewing the ground situation post lifting of lockdown on 15.04.2020. | FALSE | real_data
Delay in construction activities | EoT; Dispute Resolution | As communicated in our earlier correspondences, the return of migrant laborers to the Project Highway is yet to happen and this would result in further delay of kick-starting the already stalled activities which were executed by the migrant laborers. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20200620_SPK_NHAI_85_Lockdown imposed from 19.06.2020 to 30.06.2020.pdf | Six laning of Karaipettai to Walajahpet Section of NH-4 (New NH-48) - Force Majeure Event due to outbreak of Covid 19 - Lockdown imposed by Government of India from 24.03.2020 to 03.05.2020 extended till 31.05.2020 - Lockdown announced by TN Government from 19.06.2020 to 30.06.2020 in Chennai, Chengalpattu, Kanchipuram and Thiruvallur districts due to alarming increase of COVID 19 cases - Intimation of the same - reg | Dear Sir, Since the COVID 19 cases are alarmingly increasing, the Tamil Nadu Government ordered to enforce complete lockdown under Disaster Management Act 2005, for 12 days from 19.06.2020 to 30.06.2020 in Greater Chennai Police Commissionarate areas in Thiruvallur, Chengalpet and Kanchipuram Districts. Copy of the above-mentioned order is herewith enclosed as Annexure 1. Our Project Highway traverses through Kancheepuram and Ranipet districts where prevalence of Covid 19 cases are on the rise due to which there are restrictions in the movement of our scarcely available work force and Machineries. It is pertinent to mention that the TN Police is restricting the traffic movements by placing barricades along the Project Highway at Ch.85+875 where PCC laid for construction of VUP - Ch.85+869. Further construction of VUP couldn’t be proceeded due to placing of barricades by the police as mentioned above. As communicated in our earlier correspondences, the return of migrant labourers to the Project Highway is yet to happen and this would result in further delay of kick-starting the already stalled activities which were executed by the migrant labourers. It is pertinent to mention that the State Government is making all arrangements for movement of migrant labourers to their respective states and several Shramik special trains are also arranged for their movement. We already notified the above event of outbreak of Covid 19 as Force Majeure Event vide ref (3) cited above. The impact of time and cost during the lockdown period and the subsequent re mobilizing period etc till things get completely normal with no restrictions, would be assessed and submitted in due course of time. This is for your information and further necessary action. | FALSE | real_data
Delay in construction activities | EoT; Dispute Resolution | Due to this unexpected heavy downpour, the entire works of the project highway have come to standstill owing to following reasons. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20200713_SPK_AE_99_Intimation on Work affected due to Unexpected Rainfall.pdf | Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km.71+015 to Km 107+091 on EPC Mode in the state of Tamil Nadu under NHDP Phase-V - Work affected due to Unexpected Rainfall - Reg. | This is with reference to the subject matter; we wish to intimate that usually Tamilnadu gets majority of rain from North East monsoon which starts from October end and continues up to December. From South West monsoon also Tamilnadu gets some portion of rain. This year, area under which Project Highway is located got excess rainfall from South West monsoon. Hence, it has impacted the progress of the work. Cumulative Rainfall recorded in the recent days is as follows: Cumulative Rainfall Period of Rainfall " (mm) 01.06.2020 - 30.06.2020 447.40 01.07.2020 - 10.07.2020 300.40 ' Due to this unexpected heavy downpour, the entire works of the Project Highway have come to standstill owing to following reasons: 1. The Aggregates viz Coarse, Fine and Crusher dust are in moist condition due to which we are unable to commence operations of Hot Mix Plant and Batching Plant. 2. No further highway works could be carried out due to waterlogging and extremely moist conditions at borrow earth locations. Also, weather Report for June & July month is enclosed as Annexure - I. Photos showing work affected stretches due to rainfall is enclosed as Annexure - II. This is for your kind information & record, please. ~ | FALSE | real_data
Delay in construction activities | EoT; Dispute Resolution | The entire works of the Project Highway have come to standstill owing to non-operation of borrow area due to unexpected heavy downpour. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20201205_SPK_PD_074_Intimation of water stagnation in Idntified Borrow Area.pdf | Intimation of Stagnation of Water in Identified Borrow Areas — Reg. | With reference to the above subject; we wish to bring your notice that, due to occurrence of “NIVAR & BUREVI Cyclone” there has been a heavy/continuous rain in Kanchipuram & Ranipet Districts. The entire works of the Project Highway have come to standstill owing to non-operation of Borrow area due to unexpected heavy downpour. Since, there has been a complete waterlogging in all the identified Borrow areas of Kanchipuram & Ranipet District, it is not possible to operate the Borrow Areas for a minimum period of 3 months. RE wall back filling for approaches of 3.Nos. of LVUP’s are hampered due to ponding of borrow areas. RE Panels are even stacked at site for commencement of back filling works. Photos showing the stagnation of water in the identified borrow areas of Kanchipuram & Ranipet Districts is enclosed as Annexure - I. This is for your kind information & record, please. | FALSE | real_data
Delay in construction activities | EoT; Dispute Resolution | It is clear indication of Contractor's failure ,even, if we consider proportionate physical progress as per claimed 66.23% of land by the Contractor,which is not line of the actual working land available at site and the memorandum signed between the parties | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20201228_AE_SPK_506_Contractor’s failure in achieving Project Mile Stone 1, 2 & 3 applying of Damages vide Contract Article No. 10.3.2 & 10.3.3.pdf | Contractor’s failure in achieving Project Mile Stone 1, 2 & 3 applying of Damages vide Contract Article No. 10.3.2 & 10.3.3 - Reg. | In response to the reference letter no. 27, our replies are as follows, As per the Contractor's view point of 66.23% of available workable length, the Financial Progress of 6.62% on prorate basis is supposed to be achieved by the Contractor on the revised date of MS-¦ on 29.11.2019 including EOT of 112 days as approved by the Authority vide letter No NHAI/11019/17/2009/RO Chennai/1461 & NHAI/11036/4/2019/PIU. Kanchee/878 respectively dated 30.04.2020 & 07.05.2020. However, Contractor achieved a Financial Progress of 0.713% as on due date. Even, as on March 2020, the Financial Progress is about 5%. Hence it is clear indication of Contractor's failure, even if, we consider proportionate physical progress as per claimed 66.23% of land as by the Contractor, which is not line of the actual working land available at site and the memorandum signed between the parties. Further, it may be noted that the Estimates for various Pipelines were approved 02.07.2020 to 07.07.2020. But after a lapse of 5 months i.e. on 02.12.2020 the Contractor has commenced the excavation works for shifting of the Pipe lines. Hence, such land cannot be considered under hindrances/encumbrances, as shifting of water pipe lines are the responsibility of the Contractor, as per the Contract Article 9.2 of the Contract. In response to the Pt. No. 30, the Contractor is requested to produce a valid Document based on the discussions held in RO Meeting stating that the EOT is in consideration with RO, as any such information is not communicated to the Authority Engineer, hence cannot be cognizant. This is for your information and for necessary compliance. | FALSE | real_data
Safety measures during construction. | Contractor's Obligations | This is with reference to the subject matter; the Compliance Report is attached as Annexure -I. This is for information that most of the recommendations of the Safety Expert have been complied as per requirement at site. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LOT-10/20210831_SPK_AE_119_Submission of Compliance Report – Site Safety report for the month of July 2021 by Road Safety Expert.pdf | Submission of Compliance Report — Site Safety report for the month of July 2021 by Road Safety Expert —Reg. | Dear Sir, This is with reference to the subject matter; the Compliance Report is attached as Annexure -I. This is for information that most of the recommendations of the Safety Expert have been complied as per requirement at site. This is for your information and record. Thanking you and assuring our best of services always. Yours faithfully, For SPK AND Co., Managing ner Encl - As Above Ce - The Project Director, NHAI, PIU - Kancheepuram, kancheepurampiu@gmail.com 1¦Page Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km.71+015 (Existing Km 71/000) to Km 107+091 (Existing Km 107/068) on EPC Mode in the state of Tamil Nadu under NHDP Phase-V Annexure-I | FALSE | real_data
Safety measures during construction. | Contractor's Obligations | We hereby request you to provide disposal points in between Km 29+000 to 55+937, for disposing the unsuitable and dismantled materials. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-3/9. Disposal point between 29+000 to 55+937 08.08.2017.pdf | Rehabilitation and Up-gradation of Paithan (Pategaon) — Mungi - Hadgaon - Bodhegaon- Ladjalgaon — Ghogaspargaon — Phulsangvi — Ukhandachakla — Dahiwandi — Shirur to 2-Lane with paved shoulder” (Project Length 55.937 Km) on EPC basis in the state of Maharashtra (Package I — 56 KM) — Disposal point between 29+000 to 55+937 - Reg. | With reference to above subject, we would like to bring your kind notice that we have started the Clearing & Grubbing, Earth work excavation, Embankment & Sub grade filling in the stretch, from Chainage 36+950 to 42+000. As you are aware we get unsuitable material in road way excavation and dismantled materials from structure dismantling at various locations. We hereby request you to provide disposal points in-between Km 29+000 to 55+937, for disposing the unsuitable and dismantled materials. | FALSE | real_data
Safety measures during construction. | Contractor's Obligations | It is strongly recommended to have a sufficient truck lay bye provision at least at a 25 to 30 Km interval along the National Highways | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/097_03092019_Directions of Supreme Court committee on Road Safety.pdf | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 tol07.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Directions of Supreme Court committee on Road Safety Reg. | Our response to your letter bearing No. NHAI/11012/6/2019/PIU. Kanchee/1961 dated 23 August 2019 relating to the directions of Supreme Court Committee on Road Safety is as follows: Rear End Collusions: The Supreme Court Committee on Road Safety is mainly pointing towards the REAR END collusion of vehicles and accidents causing due to TREES and other FIXED OBJECTS. In this regard it is to say that REAR END collusions are occurring because vehicles especially loaded trucks are parking on the Highway to have basic requirements of the truck drivers like Food, Water and sleep. Similarly, to have the minimum maintenance like checking of Tyre’s Air content, Making ready of the punctured tires etc. In this regard it is strongly recommended to have a sufficient Truck Lay Bye provisions at least at a 25 to 30 Kms interval all along the National Highways with all the above said facilities. This may prevent the unauthorized parking of vehicles on the Highway which in turn will avoid rear end collusion of vehicles. Patrolling Vehicles: Utilization of Patrolling vehicles to prevent stoppage of trucks or any other vehicle on the Highway is somewhat help full but not at the full extent. The Patrolling vehicle may be given a ranze of 30 to 40 Kms. For roaming the total stretch for one trip it may take 1.5 to 2.0 hrs to the Patrolling vehicle. Hence it can’t be useful all the time because everywhere the Patrolling vehicle can’t be present and dictate to stop parking of vehicles on the Highway. Hence it is totally depending on the drivers Safety Alertness in parking the vehicle on the Highway. In this regard it is suggested to have a Satellite surveillance on all the NH road network. This will not only help in tracking the unauthorized parking but also helps in getting necessary data relating to accidents and any other unwanted incident happening on the Highway. Hence your good self is requested to look in to the above observations for a favorable solution. | FALSE | real_data
Safety measures during construction. | Contractor's Obligations | The Project Director informed to have joint inspection with police department officials and District Administration for the improvement of black spot locations for the Vellore jurisdiction and instructed to study the feasibility of their representation / proposals. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/162_11112019_Minutes of meeting_MOM 4.pdf | Consultancy services for Authority's Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Minutes of Monthly Progress review meeting Mom-4 -Reg. | With respect to the above said reference please find enclosed herewith the Minutes of Meeting Numbered as MoM-4 held on 30.10.2019. The venue and date for the next meeting are scheduled on 27.11.2019 at Consultants office around 11.00 A.M in Kancheepuram. All the concerned are requested to attend with necessary documents. This is for your information and record. Assuring our best services at all times. | FALSE | real_data
Safety measures during construction. | Contractor's Obligations | 1. Safety Precautions 2. we have engaged a Safety Manager, along with dedicated safety staff and labour force, to ensure comprehensive safety measures are implemented and maintained across the entire section. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-2/12. 20240728_564_Cont_AE_Progress of works.pdf | Rehabilitation and Upgradation of Satana to Mangrul (Chandwad) Section of NH 752 G Design Ch. KM 64+000 to KM 1014140 Two Lane with Paved Shoulder / Four Lane Configuration in the state of Maharashtra on EPC Mode. Reg. Progress of works. | We refer to your letter at ref. 2, wherein you have conveyed your observations on the progress of works in the above-mentioned project stretch. In this regard, please find our para-wise reply below: 1. Slow Progress of works It is mentioned in your letter that the work front of 11.4 Km from Km.64+000 to 75+400 is available to us. This is contrary to the actual site condition, the land available for works as on date is only 8.52 Km. The details of unavailable stretches are as follows: a) Km 65+000 to 66+490 (1.490 km) - Satana Market: Full width of the Right of Way (ROW) is not available as the encroachments have not been removed. Despite several meetings held with the Satana Tehsildar, Local MLA and the public, in the presence of the Authority and Authority’s Engineer (AE), the issue remains unresolved even as on date. b) Km 66+520 to 66+600 (LHS), 67+560 to 67+650 (LHS), 71+930 to 72+000 (LHS): Land Acquisition at the above locations is not yet completed by the Authority even as on date. c) Km 68+780 to 68+830 (LHS): Encroachments have not been removed, specifically a temple, which has not been removed by the Authority. d) Km 74+100 to 74+700 & 74+900 to 75+400 - Thengode-Lohner Market: Full width of the ROW is not available at these locations as the encroachments have not been removed even as on date. The status of completed works in the available stretch of 8.52 km is as below: ° PQC (Pavement Quality Concrete): 2.3 km (LHS) ° DLC (Dry Lean Concrete): 3.70 km (LHS) ° GSB (Granular Sub-base): 4.1 km (LHS) ° Subgrade: 4.6 km (LHS) ° Subgrade widening on RHS: km 69+000 to 74+600, i.e., 5.6 km. The works of minor bridges at Km. 67+710 and 68+800 could not be started due to the pending land acquisition issues which are yet to be cleared. Though the construction of Minor Bridge at km 71+910 was commenced in the last month, the same got halted due to heavy rains. To avoid idling, the manpower was shifted to other works and was again remobilized to the structure on 27.07.2024 and the work was resumed. The work on the slab drains at km 70+050 and km 70+100 is in progress and will be completed within a month. We assure you that all pipe culvert works from km 64+000 to 75+000 will be completed within a month. For the four-lane portion from km 64+000 to km 64+800, the scope of new Jersey-type divider is only of 590 meters, for which the PCC work is completed, balance work is in progress and will be completed at the earliest. The terminal slab work on one half of km 94+420 (RHS) is pending and will be completed after diversion of traffic movement onto LHS. 2. Shifting of Utilities Regarding shifting of Electrical Utilities, we wish to submit that the estimate approvals for shifting the utilities were accorded by the Competent Authority for Chandwad section in the month of May’24 and for Deola and Satana sections in the Month of June’24. Despite the delayed approvals from the authorities, we have completed the works for Chandwad section, and the works of Deola and Satana sections were started as soon as we have received the approvals, and the works are in progress. | FALSE | real_data
Safety measures during construction. | Contractor's Obligations | you are hereby notified to undertake the short term road safety measures at identified Black spots. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-2/16. 20240625_240_AE_Cont_Road Safety Interventions at Identified Blackspots on ORR to Medak section.pdf | Rehabilitation and Upgradation of Hyderabad Outer Ring Road to Medak section of NH-765D from existing Km 15.970 (Design Km 0.00) to existing Km 78.700 (Design Km 62.92) to Two Lane with paved shoulders / Four Lane in the State of Telangana on EPC Mode. | With reference to 4" cited (copy enclosed) you are hereby notified to undertake the short term road safety measures at identified Black spots on ORR Hyderabad to Medak Road Section of NH-765D from km 0/000 to Km 62/920 in the State of Telangana and submit the compliance report immediately. | FALSE | real_data
Completion certificate | Authority's Obligations | Completion Certificate in the form set forth in Schedule - L is herewith attached. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-2/17. 20240711_3270_AE_Cont_Issuance of Completion Certificate for the Project.pdf | Issuance of Completion Certificate pursuant to Article 12.4 of the EPC Agreement - Regarding. | In pursuant to approval for issuance of Completion Certificate as per Article - 12 of EPC Agreement, conveyed by Superintending Engineer (R&B) National Highway Circle, Hyderabad vide letter 3"4 cited, the Completion Certificate in the form set forth in Schedule - L (the “Completion Certificate”) is herewith attached. | FALSE | real_data
Completion certificate | Authority's Obligations | 1. Reference is invited towards the Review Meeting chaired by the Director (T), HQ, NHIDCL on 15 Jul 2024, wherein it was informed by the chair that the balance works within the hindered stretches can be delinked and Completion Certificate can be issued. It was also informed that the delinked stretches can be taken up for execution, as and when the land is made available by the Authority. 2. We hereby request that the hindered stretch of 5.410 Km be delinked from the original scope of work and Completion Certificate be issued to us as per the Article 12 of the EPC Contract. | synthetic_template_20250913 | Upgradation to 2-lane with Paved Shoulders of Khawkawn-Ngopa section of NH-102B of Aizawl-Imphal Economic Corridor from existing chainage Km 0.000 to Km 32.976 (Design chainage Km 0.000 to Km 31.280(Package-I) in the State of Mizoram under Bharatmala Pariyojna on EPC mode: (Delinking of hindered stretches and issuance of Completion Certificate — Reg) | Reference is invited towards the Review Meeting chaired by the Director (T), HQ, NHIDCL on 15 Jul 2024, wherein it was informed by the chair that the balance works within the hindered stretches can be delinked and Completion Certificate can be issued. It was also informed that the delinked stretches can be taken up for execution, as and when the land is made available by the Authority. In this regard, the following facts, as already communicated to your good office, are reproduced as under: - a) A stretch of 5.410 Km out of the total stretch of 31.280 Km is impeded till dated due to non-availability of work front within the Forest Land (5.15 Km) and non-acquisition of land at proposed re-alignment (0.260 Km). b) The works in the available stretch of 25.870 Km has been completed in all respects as on 31 May 2024 and intimated to your good office vide our letter mentioned at sl (iii). c) The Physical & Financial Progress of the project as on date is as under- Physical Progress: - 84.68% (achieved on 31 May 2024) Financial Progress: - 83.23% d) Our manpower & machineries are idle on the project site awaiting handing over of the balance work-front by the Authority. In light of the above, we hereby request that the hindered stretch of 5.410 Km be delinked from the original scope of work and Completion Certificate be issued to us as per the Article 12 of the EPC Contract. The delinked stretch shall be constructed during the Defects Liability Period, as and when made available by the Authority. We look forward to your response. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Completion certificate | Authority's Obligations | 1. Reference is invited towards the Review Meeting chaired by the Director (T), HQ, NHIDCL on 15 Jul 2024, wherein it was informed by the chair that the balance works within the hindered stretches can be delinked and Completion Certificate can be issued. It was also informed that the delinked stretches can be taken up for execution, as and when the land is made available by the Authority. 2. We hereby request that the hindered stretch of 5.410 Km be delinked from the original scope of work and Completion Certificate be issued to us as per the Article 12 of the EPC Contract. | synthetic_template_20250913 | Upgradation to 2-lane with Paved Shoulders of Khawkawn-Ngopa section of NH-102B of Aizawl-Imphal Economic Corridor from existing chainage Km 0.000 to Km 32.976 (Design chainage Km 0.000 to Km 31.280(Package-I) in the State of Mizoram under Bharatmala Pariyojna on EPC mode: (Delinking of hindered stretches and issuance of Completion Certificate — Reg) | Reference is invited towards the Review Meeting chaired by the Director (T), HQ, NHIDCL on 15 Jul 2024, wherein it was informed by the chair that the balance works within the hindered stretches can be delinked and Completion Certificate can be issued. It was also informed that the delinked stretches can be taken up for execution, as and when the land is made available by the Authority. In this regard, the following facts, as already communicated to your good office, are reproduced as under: - a) A stretch of 5.410 Km out of the total stretch of 31.280 Km is impeded till dated due to non-availability of work front within the Forest Land (5.15 Km) and non-acquisition of land at proposed re-alignment (0.260 Km). b) The works in the available stretch of 25.870 Km has been completed in all respects as on 31 May 2024 and intimated to your good office vide our letter mentioned at sl (iii). c) The Physical & Financial Progress of the project as on date is as under- Physical Progress: - 84.68% (achieved on 31 May 2024) Financial Progress: - 83.23% d) Our manpower & machineries are idle on the project site awaiting handing over of the balance work-front by the Authority. In light of the above, we hereby request that the hindered stretch of 5.410 Km be delinked from the original scope of work and Completion Certificate be issued to us as per the Article 12 of the EPC Contract. The delinked stretch shall be constructed during the Defects Liability Period, as and when made available by the Authority. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Completion certificate | Authority's Obligations | 1. Reference is invited towards the Review Meeting chaired by the Director (T), HQ, NHIDCL on 15 Jul 2024, wherein it was informed by the chair that the balance works within the hindered stretches can be delinked and Completion Certificate can be issued. It was also informed that the delinked stretches can be taken up for execution, as and when the land is made available by the Authority. 2. We hereby request that the hindered stretch of 5.410 Km be delinked from the original scope of work and Completion Certificate be issued to us as per the Article 12 of the EPC Contract. | synthetic_template_20250913 | Upgradation to 2-lane with Paved Shoulders of Khawkawn-Ngopa section of NH-102B of Aizawl-Imphal Economic Corridor from existing chainage Km 0.000 to Km 32.976 (Design chainage Km 0.000 to Km 31.280(Package-I) in the State of Mizoram under Bharatmala Pariyojna on EPC mode: (Delinking of hindered stretches and issuance of Completion Certificate — Reg) | Reference is invited towards the Review Meeting chaired by the Director (T), HQ, NHIDCL on 15 Jul 2024, wherein it was informed by the chair that the balance works within the hindered stretches can be delinked and Completion Certificate can be issued. It was also informed that the delinked stretches can be taken up for execution, as and when the land is made available by the Authority. In this regard, the following facts, as already communicated to your good office, are reproduced as under: - a) A stretch of 5.410 Km out of the total stretch of 31.280 Km is impeded till dated due to non-availability of work front within the Forest Land (5.15 Km) and non-acquisition of land at proposed re-alignment (0.260 Km). b) The works in the available stretch of 25.870 Km has been completed in all respects as on 31 May 2024 and intimated to your good office vide our letter mentioned at sl (iii). c) The Physical & Financial Progress of the project as on date is as under- Physical Progress: - 84.68% (achieved on 31 May 2024) Financial Progress: - 83.23% d) Our manpower & machineries are idle on the project site awaiting handing over of the balance work-front by the Authority. In light of the above, we hereby request that the hindered stretch of 5.410 Km be delinked from the original scope of work and Completion Certificate be issued to us as per the Article 12 of the EPC Contract. The delinked stretch shall be constructed during the Defects Liability Period, as and when made available by the Authority. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Completion certificate | Authority's Obligations | Completion Certificate in the form set forth in Schedule - L is herewith attached. | synthetic_template_20250913 | Issuance of Completion Certificate pursuant to Article 12.4 of the EPC Agreement - Regarding. | In pursuant to approval for issuance of Completion Certificate as per Article - 12 of EPC Agreement, conveyed by Superintending Engineer (R&B) National Highway Circle, Hyderabad vide letter 3"4 cited, the Completion Certificate in the form set forth in Schedule - L (the “Completion Certificate”) is herewith attached. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Completion certificate | Authority's Obligations | Completion Certificate in the form set forth in Schedule - L is herewith attached. | synthetic_template_20250913 | Issuance of Completion Certificate pursuant to Article 12.4 of the EPC Agreement - Regarding. | In pursuant to approval for issuance of Completion Certificate as per Article - 12 of EPC Agreement, conveyed by Superintending Engineer (R&B) National Highway Circle, Hyderabad vide letter 3"4 cited, the Completion Certificate in the form set forth in Schedule - L (the “Completion Certificate”) is herewith attached. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Delinking impacted length | Dispute Resolution | We hereby request that the hindered stretch of 5.410 Km be delinked from the original scope of work and Completion Certificate be issued to us as per the Article 12 of the EPC Contract. | synthetic_template_20250913 | Upgradation to 2-lane with Paved Shoulders of Khawkawn-Ngopa section of NH-102B of Aizawl-Imphal Economic Corridor from existing chainage Km 0.000 to Km 32.976 (Design chainage Km 0.000 to Km 31.280(Package-I) in the State of Mizoram under Bharatmala Pariyojna on EPC mode: (Delinking of hindered stretches and issuance of Completion Certificate — Reg) | Reference is invited towards the Review Meeting chaired by the Director (T), HQ, NHIDCL on 15 Jul 2024, wherein it was informed by the chair that the balance works within the hindered stretches can be delinked and Completion Certificate can be issued. It was also informed that the delinked stretches can be taken up for execution, as and when the land is made available by the Authority. In this regard, the following facts, as already communicated to your good office, are reproduced as under: - a) A stretch of 5.410 Km out of the total stretch of 31.280 Km is impeded till dated due to non-availability of work front within the Forest Land (5.15 Km) and non-acquisition of land at proposed re-alignment (0.260 Km). b) The works in the available stretch of 25.870 Km has been completed in all respects as on 31 May 2024 and intimated to your good office vide our letter mentioned at sl (iii). c) The Physical & Financial Progress of the project as on date is as under- Physical Progress: - 84.68% (achieved on 31 May 2024) Financial Progress: - 83.23% d) Our manpower & machineries are idle on the project site awaiting handing over of the balance work-front by the Authority. In light of the above, we hereby request that the hindered stretch of 5.410 Km be delinked from the original scope of work and Completion Certificate be issued to us as per the Article 12 of the EPC Contract. The delinked stretch shall be constructed during the Defects Liability Period, as and when made available by the Authority. We await your further instructions. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Delinking impacted length | Dispute Resolution | We hereby request that the hindered stretch of 5.410 Km be delinked from the original scope of work and Completion Certificate be issued to us as per the Article 12 of the EPC Contract. | synthetic_template_20250913 | Upgradation to 2-lane with Paved Shoulders of Khawkawn-Ngopa section of NH-102B of Aizawl-Imphal Economic Corridor from existing chainage Km 0.000 to Km 32.976 (Design chainage Km 0.000 to Km 31.280(Package-I) in the State of Mizoram under Bharatmala Pariyojna on EPC mode: (Delinking of hindered stretches and issuance of Completion Certificate — Reg) | Reference is invited towards the Review Meeting chaired by the Director (T), HQ, NHIDCL on 15 Jul 2024, wherein it was informed by the chair that the balance works within the hindered stretches can be delinked and Completion Certificate can be issued. It was also informed that the delinked stretches can be taken up for execution, as and when the land is made available by the Authority. In this regard, the following facts, as already communicated to your good office, are reproduced as under: - a) A stretch of 5.410 Km out of the total stretch of 31.280 Km is impeded till dated due to non-availability of work front within the Forest Land (5.15 Km) and non-acquisition of land at proposed re-alignment (0.260 Km). b) The works in the available stretch of 25.870 Km has been completed in all respects as on 31 May 2024 and intimated to your good office vide our letter mentioned at sl (iii). c) The Physical & Financial Progress of the project as on date is as under- Physical Progress: - 84.68% (achieved on 31 May 2024) Financial Progress: - 83.23% d) Our manpower & machineries are idle on the project site awaiting handing over of the balance work-front by the Authority. In light of the above, we hereby request that the hindered stretch of 5.410 Km be delinked from the original scope of work and Completion Certificate be issued to us as per the Article 12 of the EPC Contract. The delinked stretch shall be constructed during the Defects Liability Period, as and when made available by the Authority. We await your further instructions. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Delinking impacted length | Authority's Obligations | We hereby request that the hindered stretch of 5.410 Km be delinked from the original scope of work and Completion Certificate be issued to us as per the Article 12 of the EPC Contract. | synthetic_template_20250913 | Upgradation to 2-lane with Paved Shoulders of Khawkawn-Ngopa section of NH-102B of Aizawl-Imphal Economic Corridor from existing chainage Km 0.000 to Km 32.976 (Design chainage Km 0.000 to Km 31.280(Package-I) in the State of Mizoram under Bharatmala Pariyojna on EPC mode: (Delinking of hindered stretches and issuance of Completion Certificate — Reg) | Reference is invited towards the Review Meeting chaired by the Director (T), HQ, NHIDCL on 15 Jul 2024, wherein it was informed by the chair that the balance works within the hindered stretches can be delinked and Completion Certificate can be issued. It was also informed that the delinked stretches can be taken up for execution, as and when the land is made available by the Authority. In this regard, the following facts, as already communicated to your good office, are reproduced as under: - a) A stretch of 5.410 Km out of the total stretch of 31.280 Km is impeded till dated due to non-availability of work front within the Forest Land (5.15 Km) and non-acquisition of land at proposed re-alignment (0.260 Km). b) The works in the available stretch of 25.870 Km has been completed in all respects as on 31 May 2024 and intimated to your good office vide our letter mentioned at sl (iii). c) The Physical & Financial Progress of the project as on date is as under- Physical Progress: - 84.68% (achieved on 31 May 2024) Financial Progress: - 83.23% d) Our manpower & machineries are idle on the project site awaiting handing over of the balance work-front by the Authority. In light of the above, we hereby request that the hindered stretch of 5.410 Km be delinked from the original scope of work and Completion Certificate be issued to us as per the Article 12 of the EPC Contract. The delinked stretch shall be constructed during the Defects Liability Period, as and when made available by the Authority. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Delinking impacted length | Authority's Obligations | We hereby request that the hindered stretch of 5.410 Km be delinked from the original scope of work and Completion Certificate be issued to us as per the Article 12 of the EPC Contract. | synthetic_template_20250913 | Upgradation to 2-lane with Paved Shoulders of Khawkawn-Ngopa section of NH-102B of Aizawl-Imphal Economic Corridor from existing chainage Km 0.000 to Km 32.976 (Design chainage Km 0.000 to Km 31.280(Package-I) in the State of Mizoram under Bharatmala Pariyojna on EPC mode: (Delinking of hindered stretches and issuance of Completion Certificate — Reg) | Reference is invited towards the Review Meeting chaired by the Director (T), HQ, NHIDCL on 15 Jul 2024, wherein it was informed by the chair that the balance works within the hindered stretches can be delinked and Completion Certificate can be issued. It was also informed that the delinked stretches can be taken up for execution, as and when the land is made available by the Authority. In this regard, the following facts, as already communicated to your good office, are reproduced as under: - a) A stretch of 5.410 Km out of the total stretch of 31.280 Km is impeded till dated due to non-availability of work front within the Forest Land (5.15 Km) and non-acquisition of land at proposed re-alignment (0.260 Km). b) The works in the available stretch of 25.870 Km has been completed in all respects as on 31 May 2024 and intimated to your good office vide our letter mentioned at sl (iii). c) The Physical & Financial Progress of the project as on date is as under- Physical Progress: - 84.68% (achieved on 31 May 2024) Financial Progress: - 83.23% d) Our manpower & machineries are idle on the project site awaiting handing over of the balance work-front by the Authority. In light of the above, we hereby request that the hindered stretch of 5.410 Km be delinked from the original scope of work and Completion Certificate be issued to us as per the Article 12 of the EPC Contract. The delinked stretch shall be constructed during the Defects Liability Period, as and when made available by the Authority. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Delinking impacted length | Payments | We hereby request that the hindered stretch of 5.410 Km be delinked from the original scope of work and Completion Certificate be issued to us as per the Article 12 of the EPC Contract. | synthetic_template_20250913 | Upgradation to 2-lane with Paved Shoulders of Khawkawn-Ngopa section of NH-102B of Aizawl-Imphal Economic Corridor from existing chainage Km 0.000 to Km 32.976 (Design chainage Km 0.000 to Km 31.280(Package-I) in the State of Mizoram under Bharatmala Pariyojna on EPC mode: (Delinking of hindered stretches and issuance of Completion Certificate — Reg) | We hereby confirm that Reference is invited towards the Review Meeting chaired by the Director (T), HQ, NHIDCL on 15 Jul 2024, wherein it was informed by the chair that the balance works within the hindered stretches can be delinked and Completion Certificate can be issued. It was also informed that the delinked stretches can be taken up for execution, as and when the land is made available by the Authority. In this regard, the following facts, as already communicated to your good office, are reproduced as under: - a) A stretch of 5.410 Km out of the total stretch of 31.280 Km is impeded till dated due to non-availability of work front within the Forest Land (5.15 Km) and non-acquisition of land at proposed re-alignment (0.260 Km). b) The works in the available stretch of 25.870 Km has been completed in all respects as on 31 May 2024 and intimated to your good office vide our letter mentioned at sl (iii). c) The Physical & Financial Progress of the project as on date is as under- Physical Progress: - 84.68% (achieved on 31 May 2024) Financial Progress: - 83.23% d) Our manpower & machineries are idle on the project site awaiting handing over of the balance work-front by the Authority. In light of the above, we hereby request that the hindered stretch of 5.410 Km be delinked from the original scope of work and Completion Certificate be issued to us as per the Article 12 of the EPC Contract. The delinked stretch shall be constructed during the Defects Liability Period, as and when made available by the Authority. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Delinking impacted length | Payments | We hereby request that the hindered stretch of 5.410 Km be delinked from the original scope of work and Completion Certificate be issued to us as per the Article 12 of the EPC Contract. | synthetic_template_20250913 | Upgradation to 2-lane with Paved Shoulders of Khawkawn-Ngopa section of NH-102B of Aizawl-Imphal Economic Corridor from existing chainage Km 0.000 to Km 32.976 (Design chainage Km 0.000 to Km 31.280(Package-I) in the State of Mizoram under Bharatmala Pariyojna on EPC mode: (Delinking of hindered stretches and issuance of Completion Certificate — Reg) | This is to notify you that Reference is invited towards the Review Meeting chaired by the Director (T), HQ, NHIDCL on 15 Jul 2024, wherein it was informed by the chair that the balance works within the hindered stretches can be delinked and Completion Certificate can be issued. It was also informed that the delinked stretches can be taken up for execution, as and when the land is made available by the Authority. In this regard, the following facts, as already communicated to your good office, are reproduced as under: - a) A stretch of 5.410 Km out of the total stretch of 31.280 Km is impeded till dated due to non-availability of work front within the Forest Land (5.15 Km) and non-acquisition of land at proposed re-alignment (0.260 Km). b) The works in the available stretch of 25.870 Km has been completed in all respects as on 31 May 2024 and intimated to your good office vide our letter mentioned at sl (iii). c) The Physical & Financial Progress of the project as on date is as under- Physical Progress: - 84.68% (achieved on 31 May 2024) Financial Progress: - 83.23% d) Our manpower & machineries are idle on the project site awaiting handing over of the balance work-front by the Authority. In light of the above, we hereby request that the hindered stretch of 5.410 Km be delinked from the original scope of work and Completion Certificate be issued to us as per the Article 12 of the EPC Contract. The delinked stretch shall be constructed during the Defects Liability Period, as and when made available by the Authority. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Submission of Design and Drawings | Contractor's Obligations | As intimated in our letter 3 referred above, we are proceeding with submission of design / drawings / tentative cost impact, in anticipation of the aforesaid notice. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/4. COS notice under 13.2.1 by AE 27.10.2018.pdf | Change of Scope notice under 13.2.1 by Authority Engineer | Respected Sir, This refers to all the letters referred above instructing us to execute certain additional works, under change of scope. We have been instructed additional Minor Bridges, Box Culverts and Pipe culverts under Article — 13 & 13.1.1 whereas clause 13.2 “Procedure for change of scope” instructs for a notice from Authority Engineer to be issued to the contractor (please refer clause 13.2.1 & 13.2.2 in this regard) As intimated in our letter 3 referred above, we are proceeding with submission of design / drawings / tentative cost impact, in anticipation of the aforesaid notice. However, we request you to direct the Authority Engineer, to issue us the Change of Scope notice, for the sake of good order and procedure for Change of Scope. Meanwhile, by way of submitting a copy of this letter to Authority Engineer/Team Leader, we are requesting him for necessary action for issuing the notice and simultaneously approving the designs & drawings. | FALSE | real_data
Submission of Design and Drawings | Contractor's Obligations | 1. We are herewith submitting one soft copy & three hard copies of Plan & Profile of the project highway from Ch: 1+000 to Ch 15+300. | synthetic_template_20250913 | Submission of Plan & Profile - Reg. | With reference to the above subject, pursuant to the Article 10 clause 10.2.iv of the contract Agreement, we are herewith submitting one soft copy & three hard copies of Plan & Profile of the project highway from Ch: 1+000 to Ch 15+300. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Submission of Design and Drawings | Contractor's Obligations | As intimated in our letter 3 referred above, we are proceeding with submission of design / drawings / tentative cost impact, in anticipation of the aforesaid notice. | synthetic_template_20250913 | Change of Scope notice under 13.2.1 by Authority Engineer | This is to notify you that Respected Sir, This refers to all the letters referred above instructing us to execute certain additional works, under change of scope. We have been instructed additional Minor Bridges, Box Culverts and Pipe culverts under Article — 13 & 13.1.1 whereas clause 13.2 “Procedure for change of scope” instructs for a notice from Authority Engineer to be issued to the contractor (please refer clause 13.2.1 & 13.2.2 in this regard) As intimated in our letter 3 referred above, we are proceeding with submission of design / drawings / tentative cost impact, in anticipation of the aforesaid notice. However, we request you to direct the Authority Engineer, to issue us the Change of Scope notice, for the sake of good order and procedure for Change of Scope. Meanwhile, by way of submitting a copy of this letter to Authority Engineer/Team Leader, we are requesting him for necessary action for issuing the notice and simultaneously approving the designs & drawings. Please confirm receipt of this correspondence. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Submission of Design and Drawings | Contractor's Obligations | As intimated in our letter 3 referred above, we are proceeding with submission of design / drawings / tentative cost impact, in anticipation of the aforesaid notice. | synthetic_template_20250913 | Change of Scope notice under 13.2.1 by Authority Engineer | It is brought to your attention that Respected Sir, This refers to all the letters referred above instructing us to execute certain additional works, under change of scope. We have been instructed additional Minor Bridges, Box Culverts and Pipe culverts under Article — 13 & 13.1.1 whereas clause 13.2 “Procedure for change of scope” instructs for a notice from Authority Engineer to be issued to the contractor (please refer clause 13.2.1 & 13.2.2 in this regard) As intimated in our letter 3 referred above, we are proceeding with submission of design / drawings / tentative cost impact, in anticipation of the aforesaid notice. However, we request you to direct the Authority Engineer, to issue us the Change of Scope notice, for the sake of good order and procedure for Change of Scope. Meanwhile, by way of submitting a copy of this letter to Authority Engineer/Team Leader, we are requesting him for necessary action for issuing the notice and simultaneously approving the designs & drawings. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Submission of Design and Drawings | Contractor's Obligations | As intimated in our letter 3 referred above, we are proceeding with submission of design / drawings / tentative cost impact, in anticipation of the aforesaid notice. | synthetic_template_20250913 | Change of Scope notice under 13.2.1 by Authority Engineer | Respected Sir, This refers to all the letters referred above instructing us to execute certain additional works, under change of scope. We have been instructed additional Minor Bridges, Box Culverts and Pipe culverts under Article — 13 & 13.1.1 whereas clause 13.2 “Procedure for change of scope” instructs for a notice from Authority Engineer to be issued to the contractor (please refer clause 13.2.1 & 13.2.2 in this regard) As intimated in our letter 3 referred above, we are proceeding with submission of design / drawings / tentative cost impact, in anticipation of the aforesaid notice. However, we request you to direct the Authority Engineer, to issue us the Change of Scope notice, for the sake of good order and procedure for Change of Scope. Meanwhile, by way of submitting a copy of this letter to Authority Engineer/Team Leader, we are requesting him for necessary action for issuing the notice and simultaneously approving the designs & drawings. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Submission of Design and Drawings | Contractor's Obligations | As intimated in our letter 3 referred above, we are proceeding with submission of design / drawings / tentative cost impact, in anticipation of the aforesaid notice. | synthetic_template_20250913 | Change of Scope notice under 13.2.1 by Authority Engineer | Respected Sir, This refers to all the letters referred above instructing us to execute certain additional works, under change of scope. We have been instructed additional Minor Bridges, Box Culverts and Pipe culverts under Article — 13 & 13.1.1 whereas clause 13.2 “Procedure for change of scope” instructs for a notice from Authority Engineer to be issued to the contractor (please refer clause 13.2.1 & 13.2.2 in this regard) As intimated in our letter 3 referred above, we are proceeding with submission of design / drawings / tentative cost impact, in anticipation of the aforesaid notice. However, we request you to direct the Authority Engineer, to issue us the Change of Scope notice, for the sake of good order and procedure for Change of Scope. Meanwhile, by way of submitting a copy of this letter to Authority Engineer/Team Leader, we are requesting him for necessary action for issuing the notice and simultaneously approving the designs & drawings. We await your further instructions. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Slow Progress of Works | EoT; Payments | From the above it is clear that as per the revised Completion Date i.e., 19th Dec 2022, the Contractor has to achieve the balance 42.68% in a span of 9 months. Hence the Contractor has been advised to take necessary steps in achieving the required progress | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LOT-10/20211111_AE_PD_766_Submission of work program up to March 2022.pdf | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajapet from km 71.015 to107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Submission of work program up to March 2022-Reg. | Sir, Based on the review meeting held under the Chairmanship of Member Projects Tamil Nadu on dated 01.11.2021 and as a compliance to the above cited Ref. No. 1, the submitted work program up to March 2022 by the Contractor has been verified and forwarded to your good office with the following observations. As per the work program, Contractor planned an expenditure of Rs/- 88.085 Cr which is 16.52 % of the Contract Amount. However, the so far achieved financial progress is 35.10 % and the physical progress is 40.80%. Hence the cumulative physical progress will be 57.32% by the end of March 2022. From the above it is clear that as per the revised Completion Date i.e.,19" Dec 2022, the Contractor has to achieve the balance 42.68% in a span of 9 months. Hence the Contractor has been advised to take necessary steps in achieving the required progress This is for your kind information please. Thanking You. Kar-Wal, Six Lanning Project, Package-ll, Kancheepuram Encl : Work Program Copy to: 1.M/s S.P.K. & Co. 2.H.O. S.A. Infrastructure Consultants Pvt. Ltd Project Office : s+ Dr A £ ra nue, www.sainfra.com | FALSE | real_data
Slow Progress of Works | EoT | As we are aware, the Project Highway has been experiencing unseasonal rainfalls during the past two months. This is having an impact on our scheduled progress of work. This unseasonal rainfall particularly in the evening hours, the program for the night soil shifting works gets badly affected. This is affecting the filling works on structure approaches on round the clock basis. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LOT-10/20240823_SPK_PD_100_Slow progress – Reply made.pdf | Six laning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km. 71+015 (Existing km 71+000) to Km 107+091 (Existing km 107+068) on EPC mode in the State of Tamil Nadu under NHDP Phase-V” — Slow progress — Reply made - Reg. | This is w.r.t your letter under ref (3) relating to slow progress of works and our pointwise response is as follows: Point a: The Contractor has achieved work output of Rs.32.46Cr from 01.05.2024 to 21.08.2024 and likely to achieve Rs.75 crores before 31.10.2024. Point b: Out of 4 structures, traffic has been diverted over the Flyover @ Km.106/677.Work have been completed up to GSB top level in all the remaining three structures viz. LVUP @ Km.90/075, VUP @ Km.87/540 and PUP @ Km.106/010. We had scheduled to divert traffic over all the above mentioned three structures by end of this month but due to heavy unseasonal rains during the 1st two weeks of this month, our schedule got affected. Please refer our letter No 414 dated 16.08.2024 in this regard. We are making all efforts to divert traffic over the above mentioned three structures latest by 1st week of September 2024. Point c: RE wall works up to Service Road level have been completed @ Km.93/115(A2) and the remaining RE wall works up to Service Road level at Km 75/045(A1), Km 79/302(A2), Km 79/860, Km.80/800, Km 98/414 and Km 99/465 are in progress and we are scheduling to complete filling works up to Service Road level before 31.10.2024. | FALSE | real_data
Slow Progress of Works | EoT | We request you to look into the above issues and resolve at an early date, which will enhance the progress at site. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/5. Reply to request for expediting slow process of works 06.12.2018.pdf | Reply to request for expediting Slow Progress of works — Reg. | Respected Sir, This is with reference to the above subject and your above referred letter requesting to expedite the progress of works. We wish to draw your kind attention to our letters ref (2) and (3) above, through which we had submitted a detailed analysis of the delay events and their impact on progress. So far determination of EOT is awaited. We also request your kind attention to our letter to the EE, ref (4) above, requesting to issue COS notice for additional utility ducts. As you are aware, the pending land acquisition is the first of the major reasons for stoppage of work at various locations / various stages. Delay in approval of COS is the second major reason, apart from other delay events, for not being able to proceed with unobstructed work fronts. We request you to look into the above issues and resolve at an early date, which will enhance the progress at site. | FALSE | real_data
Slow Progress of Works | EoT | Apropos to the above, we wish to mention you that, after accounting for all the encroachments and encumbrances as on date, we are able to execute works at very few locations which covers a length of around 22.237 Kms. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/7. Status of Work Front Available 26.12.2018.pdf | Status of work front available — Reg. | Respected Sir, This is with reference to your letter #(1) above regarding the status of work front available, wherein it was mentioned that a length of 41.075 Km was available for work. In this regard, please refer to our letter ref (7) above requesting extension of time & revision of milestones. A total length of 34.35 Km was affected due to pending COS decisions/orders. Please refer to letters (2) to (6) & (8) above regarding structures identified under COS. A total of 269 structures are approved by the AE for Change of Scope. You will appreciate the fact that, despite our repeated requests, COS orders for these structures are still pending. Authority and Authority’s Engineer categorically specified not to take up any COS works until COS orders issued. In addition to this, we continue to get affected by the perennial land acquisition issues, as the property owners have obstructed execution of works. The details are explained in our letter ref (7) above. Apropos to the above, we wish to mention you that, after accounting for all the encroachments and encumbrances as on date, we are able to execute works at very few locations which covers a length of around 22.237 Kms. | FALSE | real_data
Slow Progress of Works | EoT | Consequently, there is shortage of skilled labor resulting in slow pace of the project progress. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20210415_SPK_PD_029_Regarding Spread of second wave of covid 19.pdf | Six laning of Karaipettai to Walajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V — Regarding spread of Second wave of “Covid 19”- Government restrictions and its effect on the Project — Notification of Force Majeure as per Article-21 of the Contract Agreement - Reg. | 1. With reference to the above subject, it is to inform that there is an outbreak of second wave of COVID-19 in India which has made the situation worst again. In this regard, looking to the severity of impact in various states, the Government of India and State Government have again taken some necessary steps of imposing restrictions like partial lockdown, night curfew, following social distancing, producing negative COVID-19 test report, etc. varying from state to state to contain spread of Pandemic and to combat the effects among the people. 2. The measures taken by different states to contain spread of pandemic have resulted in partial disruption of supply chain and elopement of Skilled and Unskilled labour in the fear of possibility of complete lockdown. The repatriation of labours due to fear and scare for the present situation are affecting the progress of work. Consequently, there is shortage of skilled labour resulting in slow pace of the project progress. Further, the guidelines to follow social distancing continues to remain in effect due to which the Contractor is compelled to work with minimum staff and labour so as to adhere to the same. 3. Hence it is pertinent to mention that there are guidelines issued by State Governments to present negative COVID-19 test report while crossing state borders due to which supply chain management has severely disrupted for major materials like Cement, Steel, Bitumen, etc. This has slowed down the production, procurement, and transportation of major materials at site which has badly affected desired pace of work progress. | FALSE | real_data
Slow Progress of Works | EoT | The consultant expressed their concern over the slow progress of RE wall works | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20201123_AE_SPK_480_Minutes of Monthly Progress review meeting Mom – 08.pdf | Consultancy services for Authority's Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode - Minutes of Monthly Progress review meeting Mom — 08 — Reg. | With respect to the above said reference please find enclosed herewith the Minutes of Meeting Numbered as MoM - 08 held on 21.11.2020 The next meeting will be likely on 23.12.2020 at the Consultants office around 11.00 A.M in Kancheepuram. All the concerned are requested to attend with necessary documents. This is for your information and record. Assuring our best services at all times. | FALSE | real_data
Slow Progress of Works | EoT | It is requested to please review the possibilities of the opening of work front,by making small efforts. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210217_AE_SPK_559-Slow Progress of Underpasses works.pdf | Slow Progress of Underpasses works - Reg. | It's time and again brought to your kind notice that the Works of the Underpasses, its approach ramp activities & Fly over at Ch. Km. 106+687 are not progressing according to completion targets. There is a considerable delay in all activities as illustrated below: Ch. Km. 76+846: Size: 1 X 30.0 X 5.5 kilambi junction: There is a delay in construction of slip/diversion road works at this junction. The culverts wing wall/ return wall activities had prolonged for a longer time. These reasons delayed the diversion of traffic and as well as construction of underpass at this location. Ch. Km. 79+302: Size: 1 X 20.0 X 5.5 Baluchetty East: The bitumen works for the left service road were completed on 22.05.2020. It took much time to divert the traffic on Left Service road so as to commence the Left Carriageway Works of underpass. However, PCC was laid for the Left carriageway structure on 09.10.2020. Similarly, for the Right Carriageway DBM has completed on 24.05.2020. Diversion of traffic got delayed and completed the PCC for right Carriageway structure on 27.12.2020. But, unfortunately, till date no approach ramp/ RE wall works commenced at both the side, reasons best known to the Contractor. Ch. Km. 80+805: Size: 1 X 20.0 X 5.5 Baluchetty West. Right side service road DBM works are completed on 27.11.2020. Hence traffic can be diverted for Right Carriageway. But till date no action taken by the Contractor, which getting delayed the work progress at this location also. Ch. Km. 82+566: Size: 1 X 20.0 X 5.5 Damal East: Right side service road DBM was completed on 16.09.2020, but till date no activity for diverting the traffic and commencement of underpass works taken by the Contractor. Similarly, for Left Carriageway also, works are almost completed except a small stretch, which may not affect the works of diversion. Ch. Km. 85+874: Size: 1 X 12.0 X 4.0 Ponniammanpattarai. Despite of diverting the traffic for underpass works well before 06.02.2020 laying of PCC for RE wall works ranged from 02.08.2020 to 25.01.2021. but, RE wall works progress is very slow, which may be seen at site. Ch. Km. 87+540: Size: 1 X 15.0 X 5.5 Perumbulipakkam. Despite of completing the service roads on either side of the underpass on 26.05.2020, but, as on date, diversion of traffic has not been taken up. Hence, underpass construction works are yet to start, as without diverting the traffic that cannot be taken up. Ch. Km. 90+092: Size: 1 X 12.0 X 4.0 Kalathur Village. Commencing of Service road works are getting delayed. Ch. Km. 93+115: Size: 1 X 20.0 X 5.5 Ocheri. Dismantling of structures has been completed. But to remove the debris and commencement of service road works are getting delayed due to unknown reasons as there is no hinderances. Ch. Km. 95+412: Size: 1 X 12.0 X 4.0 Perikarumbur. PCC for the shell has completed on 49.08.2020 which indicates that RE Wall works can start simultaneously. But till date approaches are yet to start. Ch. Km. 96+477: Size: 1 X 12.0 X 4.0 Periya Gramam village. PCC for the shell has been laid on 11.08.2020, but work progress at approaches are very slow. Ch. Km. 98+423: Size: 1 X 20.0 X 5.5 Kaveripakkam Jn. Dismantling of structures was completed. Removal of debris and commencement of service road activities are yet to be attended. Ch. Km. 99+175: Size: 1 X 12.0 X 4.0 Bajana kovil village (RHS) and Anna Street (LHS) dismantling of structures had been completed. But Service road works are getting delayed. Ch. Km. 100+603: Size: 1 X 12.0 X 4.0 Sumaithangi Jn. Drain works are in progress Service road activities are to be commenced. Ch. Km. 102+980: Size: 1 X 12.0 X 4.0 Vanichatram : Service road works are now in progress. Ch. Km. 106+687: Size: 3 X 25.0 X 5.5 Fly over at Walajahpet junction. — Despite of approving the drawings for the flyover on 11.09.2020 till date no activity has commenced. From the above it is clear that despite having sufficient work front to commence the RE wall works, but no serious efforts are being made by the Contractor. There is a clear chance of commencement of earth work at 80+805, 85+874, 95+412 & 96+477 but the works are getting delayed due to the reasons best known to you. Hence it is a clear evident that wherever and whenever earth is available efforts to extract the same and commence the works, but same is being delayed at your end. As per the provision of the Contract Agreement, Contractor has to arrange all applicable permits for extracting the earth from the borrow area, but despite making serious efforts, stating that non availability of earth through your communication number SPK/KW/SAIC/NH-48/2021/009 dated 08.01.2021, is just eyewash. There is penalty of work fronts available, as listed above, if Contractor diverted the traffic, he may commenced the works. But no serious efforts are being made by the Contractor. | FALSE | real_data
Slow Progress of Works | EoT | Slow Progress of works | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-2/12. 20240728_564_Cont_AE_Progress of works.pdf | Rehabilitation and Upgradation of Satana to Mangrul (Chandwad) Section of NH 752 G Design Ch. KM 64+000 to KM 1014140 Two Lane with Paved Shoulder / Four Lane Configuration in the state of Maharashtra on EPC Mode. Reg. Progress of works. | We refer to your letter at ref. 2, wherein you have conveyed your observations on the progress of works in the above-mentioned project stretch. In this regard, please find our para-wise reply below: 1. Slow Progress of works It is mentioned in your letter that the work front of 11.4 Km from Km.64+000 to 75+400 is available to us. This is contrary to the actual site condition, the land available for works as on date is only 8.52 Km. The details of unavailable stretches are as follows: a) Km 65+000 to 66+490 (1.490 km) - Satana Market: Full width of the Right of Way (ROW) is not available as the encroachments have not been removed. Despite several meetings held with the Satana Tehsildar, Local MLA and the public, in the presence of the Authority and Authority’s Engineer (AE), the issue remains unresolved even as on date. b) Km 66+520 to 66+600 (LHS), 67+560 to 67+650 (LHS), 71+930 to 72+000 (LHS): Land Acquisition at the above locations is not yet completed by the Authority even as on date. c) Km 68+780 to 68+830 (LHS): Encroachments have not been removed, specifically a temple, which has not been removed by the Authority. d) Km 74+100 to 74+700 & 74+900 to 75+400 - Thengode-Lohner Market: Full width of the ROW is not available at these locations as the encroachments have not been removed even as on date. The status of completed works in the available stretch of 8.52 km is as below: ° PQC (Pavement Quality Concrete): 2.3 km (LHS) ° DLC (Dry Lean Concrete): 3.70 km (LHS) ° GSB (Granular Sub-base): 4.1 km (LHS) ° Subgrade: 4.6 km (LHS) ° Subgrade widening on RHS: km 69+000 to 74+600, i.e., 5.6 km. The works of minor bridges at Km. 67+710 and 68+800 could not be started due to the pending land acquisition issues which are yet to be cleared. Though the construction of Minor Bridge at km 71+910 was commenced in the last month, the same got halted due to heavy rains. To avoid idling, the manpower was shifted to other works and was again remobilized to the structure on 27.07.2024 and the work was resumed. The work on the slab drains at km 70+050 and km 70+100 is in progress and will be completed within a month. We assure you that all pipe culvert works from km 64+000 to 75+000 will be completed within a month. For the four-lane portion from km 64+000 to km 64+800, the scope of new Jersey-type divider is only of 590 meters, for which the PCC work is completed, balance work is in progress and will be completed at the earliest. The terminal slab work on one half of km 94+420 (RHS) is pending and will be completed after diversion of traffic movement onto LHS. 2. Shifting of Utilities Regarding shifting of Electrical Utilities, we wish to submit that the estimate approvals for shifting the utilities were accorded by the Competent Authority for Chandwad section in the month of May’24 and for Deola and Satana sections in the Month of June’24. Despite the delayed approvals from the authorities, we have completed the works for Chandwad section, and the works of Deola and Satana sections were started as soon as we have received the approvals, and the works are in progress. | FALSE | real_data
Authority Engineer | Authority's Obligations | 3.As per para- 4 ,Annex-I ,Schedule-N of agreement ,the Authority' Engineer shall review the programme for the works submitted by the contractor as per cl 10.1.3 of agreement and shall convey its comments to the contractor within a stipulated period of time. | synthetic_template_20250913 | NHALI PIU - Krishnagiri - Consultancy services for Authority Engineer for supervision of Six laning of Karaipettai to Walajahpet section of NH-48 (old NH-4) from km.71+015 to km.107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase V- Mobilization at Site ~ Reg. | We would like to inform you that As you know that your firm has been appointed as Authority Engineer for the ee work and the contract agreement for civil work is signed on 15.10.2018 and appointed date is: declared as 11.2.2019 and the contractor has started the work and is in progress. 2.AS a part of contract agreement the contractor has submitted programme for the works as per clause 10.1.3 of agreement and Plan & Profile drawings and requesting for approvals. 3.As per para- 4 ,Annex-I ,Schedule-N of agreement ,the Authority Engineer shall review the programme for the works submitted by the contractor as per cl 10.1.3 of agreement and shall convey its comments to the contractor within a stipulated period of time. 4. As no communication is received on mobilisation of the Authority Engineer till date, it is requested to mobilise the staff at site under intimation to this office immediately for performing the duties of Authority Engineer. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Authority Engineer | Authority's Obligations | 3.As per para- 4 ,Annex-I ,Schedule-N of agreement ,the Authority' Engineer shall review the programme for the works submitted by the contractor as per cl 10.1.3 of agreement and shall convey its comments to the contractor within a stipulated period of time. | synthetic_template_20250913 | NHALI PIU - Krishnagiri - Consultancy services for Authority Engineer for supervision of Six laning of Karaipettai to Walajahpet section of NH-48 (old NH-4) from km.71+015 to km.107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase V- Mobilization at Site ~ Reg. | As you know that your firm has been appointed as Authority Engineer for the ee work and the contract agreement for civil work is signed on 15.10.2018 and appointed date is: declared as 11.2.2019 and the contractor has started the work and is in progress. 2.AS a part of contract agreement the contractor has submitted programme for the works as per clause 10.1.3 of agreement and Plan & Profile drawings and requesting for approvals. 3.As per para- 4 ,Annex-I ,Schedule-N of agreement ,the Authority Engineer shall review the programme for the works submitted by the contractor as per cl 10.1.3 of agreement and shall convey its comments to the contractor within a stipulated period of time. 4. As no communication is received on mobilisation of the Authority Engineer till date, it is requested to mobilise the staff at site under intimation to this office immediately for performing the duties of Authority Engineer. Please confirm receipt of this correspondence. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Authority Engineer | Authority's Obligations | 3.As per para- 4 ,Annex-I ,Schedule-N of agreement ,the Authority' Engineer shall review the programme for the works submitted by the contractor as per cl 10.1.3 of agreement and shall convey its comments to the contractor within a stipulated period of time. | synthetic_template_20250913 | NHALI PIU - Krishnagiri - Consultancy services for Authority Engineer for supervision of Six laning of Karaipettai to Walajahpet section of NH-48 (old NH-4) from km.71+015 to km.107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase V- Mobilization at Site ~ Reg. | As you know that your firm has been appointed as Authority Engineer for the ee work and the contract agreement for civil work is signed on 15.10.2018 and appointed date is: declared as 11.2.2019 and the contractor has started the work and is in progress. 2.AS a part of contract agreement the contractor has submitted programme for the works as per clause 10.1.3 of agreement and Plan & Profile drawings and requesting for approvals. 3.As per para- 4 ,Annex-I ,Schedule-N of agreement ,the Authority Engineer shall review the programme for the works submitted by the contractor as per cl 10.1.3 of agreement and shall convey its comments to the contractor within a stipulated period of time. 4. As no communication is received on mobilisation of the Authority Engineer till date, it is requested to mobilise the staff at site under intimation to this office immediately for performing the duties of Authority Engineer. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Authority Engineer | Authority's Obligations | 3.As per para- 4 ,Annex-I ,Schedule-N of agreement ,the Authority' Engineer shall review the programme for the works submitted by the contractor as per cl 10.1.3 of agreement and shall convey its comments to the contractor within a stipulated period of time. | synthetic_template_20250913 | NHALI PIU - Krishnagiri - Consultancy services for Authority Engineer for supervision of Six laning of Karaipettai to Walajahpet section of NH-48 (old NH-4) from km.71+015 to km.107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase V- Mobilization at Site ~ Reg. | As you know that your firm has been appointed as Authority Engineer for the ee work and the contract agreement for civil work is signed on 15.10.2018 and appointed date is: declared as 11.2.2019 and the contractor has started the work and is in progress. 2.AS a part of contract agreement the contractor has submitted programme for the works as per clause 10.1.3 of agreement and Plan & Profile drawings and requesting for approvals. 3.As per para- 4 ,Annex-I ,Schedule-N of agreement ,the Authority Engineer shall review the programme for the works submitted by the contractor as per cl 10.1.3 of agreement and shall convey its comments to the contractor within a stipulated period of time. 4. As no communication is received on mobilisation of the Authority Engineer till date, it is requested to mobilise the staff at site under intimation to this office immediately for performing the duties of Authority Engineer. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Authority Engineer | Authority's Obligations | 3.As per para- 4 ,Annex-I ,Schedule-N of agreement ,the Authority' Engineer shall review the programme for the works submitted by the contractor as per cl 10.1.3 of agreement and shall convey its comments to the contractor within a stipulated period of time. | synthetic_template_20250913 | NHALI PIU - Krishnagiri - Consultancy services for Authority Engineer for supervision of Six laning of Karaipettai to Walajahpet section of NH-48 (old NH-4) from km.71+015 to km.107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase V- Mobilization at Site ~ Reg. | We would like to inform you that As you know that your firm has been appointed as Authority Engineer for the ee work and the contract agreement for civil work is signed on 15.10.2018 and appointed date is: declared as 11.2.2019 and the contractor has started the work and is in progress. 2.AS a part of contract agreement the contractor has submitted programme for the works as per clause 10.1.3 of agreement and Plan & Profile drawings and requesting for approvals. 3.As per para- 4 ,Annex-I ,Schedule-N of agreement ,the Authority Engineer shall review the programme for the works submitted by the contractor as per cl 10.1.3 of agreement and shall convey its comments to the contractor within a stipulated period of time. 4. As no communication is received on mobilisation of the Authority Engineer till date, it is requested to mobilise the staff at site under intimation to this office immediately for performing the duties of Authority Engineer. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Video recording of the Project Highway (before inception & during construction) | Contractor's Obligations | We acknowledge receipt of your letter NHAI/PIU-K'giri/NH4/SPK/PS/2019/233 dated 11.02.2019 S.No.2 cited above, please find enclosed herewith a copy of site videography conducted in the month December from 12.12.2018 to 13.12.2018 to ascertain the existing condition of the road and other pictures as required by you. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LOT-10/15_21032019_Video recording.pdf | Site Videography conducted in December | Dear Sir, We acknowledge receipt of your letter NHAI/PIU-K'gini/NH4/SPK/PS/2019/233 dated 11.02.2019 SLNo.2 cited above, please find enclosed herewith a Copy of site videography conducted in the month of December from 12.12.2018 to 13.12.2018 to ascertain the existing condition of the road and other pictures as required by you. This is submitted for your information and necessary record please. Thanking you, Yours faithfully, For SPK And Co., Encl: As Above Scanned by CamScanner | FALSE | real_data
Video recording of the Project Highway (before inception & during construction) | Contractor's Obligations | It is mandatory to submit the drone based video recording of the project highway during the construction period covering the entire ROW showing the chainages,proposed ROW,Median centreline etc. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210617_AE_SPK_633_Mandatory monthly Drone Video Recording of Project Highway.pdf | Six Lanning of Karaipettai to Walajapet from km 71 015 to 107.091 of NH-4 (New NH-48) in the State of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojna on EPC mode — Mandatory monthly Drone Video Recording of Project Highway during the development, Construction and O & M period — Reg. | Please find enclosed herewith a communication bearing No. NHAI/11036/4/2019/PIU.Kanchee/1607 dated 15 June 2021 from the Project Director PIU NHAI Kancheepuram which is a self-explanatory about the Contract Article No. 11.16; according to which it is mandatory to submit the Drone-based Video Recording” of the Project Highway during the construction period covering the entire ROW showing the Chainages, proposed ROW, median centreline, etc. Hence it has been asked to make necessary arrangements to comply the NAHI Circular stated as Ref. No. 2 and to upload the same in the Data Lake. This is for your information and immediate necessary actions. | FALSE | real_data
Video recording of the Project Highway (before inception & during construction) | Contractor's Obligations | With reference to above cited subject Competent Authority has issued policy circular as referenced above regarding mandatory monthly drone video recording of Project Highway during the development,construction and O&M period. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210625_AE_SPK_639-Mandatory monthly Drone Video Recording of Project Highway.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode — Mandatory monthly Drone Video Recording of Project Highway during the development Construction and O & M Period - Reg. | With reference to above cited subject Competent Authority has issued Policy Circular as referenced above regarding Mandatory Monthly Drone Video recording of Project Highway during the Development, Construction and O & M period. In view of the above you are requested to ensure compliance as per the NHAI policy guide lines circular dated 10.06.2021. This is for your information and immediate necessary action. | FALSE | real_data
Video recording of the Project Highway (before inception & during construction) | Contractor's Obligations | we are herewith submitting the video recording for the 4th quarter of the project | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-2/6. 20240321_256_Cont_AE_Submission of Video Recording 4th quarter of the project.pdf | Submission of Video Recording of the project - Reg. | With reference to the above subject, we are herewith submitting the video recording for the 4" quarter of the project for your kind information and record please. | FALSE | real_data
Video recording of the Project Highway (before inception & during construction) | Contractor's Obligations | It is mandatory to submit the drone based video recording of the project highway during the construction period covering the entire ROW showing the chainages,proposed ROW,Median centreline etc. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71 015 to 107.091 of NH-4 (New NH-48) in the State of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojna on EPC mode — Mandatory monthly Drone Video Recording of Project Highway during the development, Construction and O & M period — Reg. | Please find enclosed herewith a communication bearing No. NHAI/11036/4/2019/PIU.Kanchee/1607 dated 15 June 2021 from the Project Director PIU NHAI Kancheepuram which is a self-explanatory about the Contract Article No. 11.16; according to which it is mandatory to submit the Drone-based Video Recording” of the Project Highway during the construction period covering the entire ROW showing the Chainages, proposed ROW, median centreline, etc. Hence it has been asked to make necessary arrangements to comply the NAHI Circular stated as Ref. No. 2 and to upload the same in the Data Lake. This is for your information and immediate necessary actions. Thank you for your attention to this matter. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Video recording of the Project Highway (before inception & during construction) | Contractor's Obligations | We acknowledge receipt of your letter NHAI/PIU-K'giri/NH4/SPK/PS/2019/233 dated 11.02.2019 S.No.2 cited above, please find enclosed herewith a copy of site videography conducted in the month December from 12.12.2018 to 13.12.2018 to ascertain the existing condition of the road and other pictures as required by you. | synthetic_template_20250913 | Site Videography conducted in December | This is to notify you that Dear Sir, We acknowledge receipt of your letter NHAI/PIU-K'gini/NH4/SPK/PS/2019/233 dated 11.02.2019 SLNo.2 cited above, please find enclosed herewith a Copy of site videography conducted in the month of December from 12.12.2018 to 13.12.2018 to ascertain the existing condition of the road and other pictures as required by you. This is submitted for your information and necessary record please. Thanking you, Yours faithfully, For SPK And Co., Encl: As Above Scanned by CamScanner | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Video recording of the Project Highway (before inception & during construction) | Contractor's Obligations | It is mandatory to submit the drone based video recording of the project highway during the construction period covering the entire ROW showing the chainages,proposed ROW,Median centreline etc. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71 015 to 107.091 of NH-4 (New NH-48) in the State of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojna on EPC mode — Mandatory monthly Drone Video Recording of Project Highway during the development, Construction and O & M period — Reg. | Please find enclosed herewith a communication bearing No. NHAI/11036/4/2019/PIU.Kanchee/1607 dated 15 June 2021 from the Project Director PIU NHAI Kancheepuram which is a self-explanatory about the Contract Article No. 11.16; according to which it is mandatory to submit the Drone-based Video Recording” of the Project Highway during the construction period covering the entire ROW showing the Chainages, proposed ROW, median centreline, etc. Hence it has been asked to make necessary arrangements to comply the NAHI Circular stated as Ref. No. 2 and to upload the same in the Data Lake. This is for your information and immediate necessary actions. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Video recording of the Project Highway (before inception & during construction) | Contractor's Obligations | It is mandatory to submit the drone based video recording of the project highway during the construction period covering the entire ROW showing the chainages,proposed ROW,Median centreline etc. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71 015 to 107.091 of NH-4 (New NH-48) in the State of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojna on EPC mode — Mandatory monthly Drone Video Recording of Project Highway during the development, Construction and O & M period — Reg. | Please find enclosed herewith a communication bearing No. NHAI/11036/4/2019/PIU.Kanchee/1607 dated 15 June 2021 from the Project Director PIU NHAI Kancheepuram which is a self-explanatory about the Contract Article No. 11.16; according to which it is mandatory to submit the Drone-based Video Recording” of the Project Highway during the construction period covering the entire ROW showing the Chainages, proposed ROW, median centreline, etc. Hence it has been asked to make necessary arrangements to comply the NAHI Circular stated as Ref. No. 2 and to upload the same in the Data Lake. This is for your information and immediate necessary actions. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Elections in the state | EoT | We have obtained permission for extraction of borrow earth from Vadangampattu and Kalathur borrow area in Tiruvannamalai and Ranipet district respectively, Extraction of borrow earth is in progress, but we are facing hurdles from Govt. Official due to the Parliament Elections and Model Code of Conduct. Further, we have applied for Borrow earth permissions for the following (1) Chithathur Borrow area from Ranipet District (2) Palaiyanthangal Borrow area from Kancheepuram District & (3) Mangalam Borrow area from Tiruvanamalai District and permission is expected after Model Code of Conduct ends for upcoming Parliament election. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LOT-10/20240408_SPK_AE_373_Submission of Revised Construction Program for Balance Works as per Original Scope of Works Including the COS-01 & COS-02 (Toll Plaza) –Reg.pdf | Submission of Revised Construction Program for Balance Works as per Original Scope of Works Including the COS-01 & COS-02 (Toll Plaza) - Reg | 1. Further to the Discussion & Meeting held at NHAI Regional Office, Chennai on 03"4 April 2024, we are herewith submitting the Revised Construction Program for Balance Works as per Original Scope of Works - including the COS-01 & COS-02 (Toll Plaza) works. 2. Due to our persistent efforts, borrow earth filling in the approaches of VUP at Km.76/846 and LVUP at Km.102/970 have been completed and traffic will be diverted shortly. Further the Flyover at Km 106+677 traffic will be diverted in the coming month. 3. The VUP at Km 87/544, LVUP at Km.90/080, VUP at Km.93/515 works are in progress and in the remaining approaches also all the efforts to divert traffic as per the program submitted will be adhered. 4. We have obtained permission for extraction of borrow earth from Vadangampattu and Kalathur borrow area in Tiruvannamalai and Ranipet district respectively, Extraction of borrow earth is in progress, but we are facing hurdles from Govt. Official due to the Parliament Elections and Model Code of Conduct. Further, we have applied for Borrow earth permissions for the following (1) Chithathur Borrow area from Ranipet District (2) Palaiyanthangal Borrow area from Kancheepuram District & (3) Mangalam Borrow area from Tiruvanamalai District and permission is expected after Model Code of Conduct ends for upcoming Parliament election. 2. lrulappasamy Thunai S.P.K. AND Co.., | FALSE | real_data
Elections in the state | EoT | Though during the meeting held on 22.10.2020 it was decided to grant EOT for 210 days purely based on (i) account of election as well as the issue of (ii) non-availability of earth only but was not communicated in time/till date, we request the Authority Engineer to review the details submitted from our end and recommend Extension of time for a period of 678 days to the Authority pursuant to Clause 10.5.1 of the Contract Agreement. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20210416_SPK_AE_067_EOT request with Delay analysis.pdf | Six laning of Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V -EOT recommendation by the Authority for a period of 112 days not agreeable to the EPC Contractor — Request for considering EOT as discussed during the Review Meetings- reg | We are writing to express our concerns regarding the EOT recommendation by the Authority for a period of 112 days, which is not agreeable to the EPC Contractor. We request that the EOT be considered as discussed during the Review Meetings. The project involves six laning of the Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km 71+015 to km 107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase-V. We have referenced several documents and meetings in support of our request, and we hope for a favorable consideration. | FALSE | real_data
Elections in the state | EoT | Considering general election and the festival, period from 10.03.2019 to 18.08.2019 may be considered for the EOT for the first milestone as unforeseen event under the Non political and Political events | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/189_Rescheduling of Project Milestones - EOT - 1.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under BharatmalaPariyojana on EPC mode — Rescheduling of Project Mile Stone- Request for Extension of Time -Reg. | Having gone through your documents related to Rescheduling of Project Milestone-Request for Extension of Time EoT-1 please find enclosed herewith the Authority Engineers recommendations on the same subject. This is for your information and necessary action. | FALSE | real_data
Elections in the state | EoT | The not-achievement of the Project Milestone-I has already been recommended for EOT, based on the actual facts. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/264_18022020_Rescheduling of Project Milestones – Request for Extension of Time.pdf | Rescheduling of Project Milestones — Request for Extension of Time -Reg. | In reference to the above-mentioned subject and Contractor letter No. SPK/KW/SAIC/NH-48/2020/001 dated 29.01.2020 regarding the rescheduling of Project Milestone, in this regard, it is submitted that AE has computed the 176 days for extension of time in Milestones I and II. The same was recommended vide AE letter No. SAICPL/Kar-Wal/H.O./NH-48/TN/2019/10451 dated 30.11.2019 to the Authority for their acceptance and further needful. However, the Contractor submitted his reservations on the computation of the nos. of delay days and requested for rescheduling of Project Milestones for a period of 324 days instead of recommended 176 nos. of days. In this regard, AE is hereby submitted point wise reply of your raised observations for your ready reference and record, please; 4. Modification of Appointed date and Handing Over in % of area. The appointed date was communicated by the Authority letter No. NHAI/PIU.K.giri/NH-4/SPK/PS/2019/972 Dated 03.06.2019. it is also submitted that as per cl 8.2.2 the authority shall provide the Right of Way to the Contractor in respect of all land included in the Appendix by the date specified in Schedule-A for those parts of the site referred to therein, or no later than 90 days of the appointed date for those parts of the site which have not been specified in Schedule-A. It is well evident that the lands specified in Annexure-II, Schedule-A of agreement are available from the day one and as on appointed date, the existing and proposed ROW is same and no parts of the site is mentioned as not available in Schedule-A and joint memorandum signed on 11.01.2019 except for the lands for widening of plaza at Chennasamudram. Hence authority has fulfilled the obligation. This was informed vide Authority letter No. NHAI/PIU.K.giri/NH-4/SPK/PS/2019/972 Dated 03.06.2019. In view of above, the request of the Contractor to modify the appointed date is not eligible as per agreement due to the following reasons (i) As per cl 4.1.3, 8.2.1 & 8.2.2, 8.2.3 — The agreement is signed on 15.10.2018 and the Joint memorandum is signed by both the parties on 30.01.2019 and appointed date is declared for the project on 11.02.2019 to commence the work. (i) The Authority Engineer vide Letter No. SAICPL/Kar-Wal/H.O./NH-48/TN/2019/10451 Dated 30.11.2019. informed that the contractor consciously agreed and signed the Joint memorandum and aware that the unencumbered and the vacant land available after joint inspection is 93.65%. (iii) Further, it is submitted that the Joint memorandum was signed on 11.01.2019 & the appointment date is declared as 11.02.2019. The Contractor has requested the Authority for modifying the Appointment date based on the length of Project Highway handed over, vide letter No. 29/SPK/Kar-Wal/PD/NHAI/ Dated 13.05.2019. On this account and in view of clause 8.3.2 of the Contract Agreement, the Contractor cited reason of land not handed over pursuant to Clause 4.1.3 (a) is not acceptable and cannot be considered for Entitlement for EOT. 2. Assessment of Hindrance length. The assessment of hindrance length is already enumerated in Point No. 01 above. It is to remind the contractor that the Joint memorandum was signed by both the parties on 30.01.2019 as per the provisions of the Contract Agreement. The AE hereby like to reiterate the clause 8.2.1. “The Authority Representative and the Contractor shall, within 30 (thirty) days of the date of this Agreement, inspect the Site and prepare a memorandum containing an inventory of the Site including the vacant and unencumbered land, buildings, structures, road works, trees and any other immovable property on or attached to the Site. Subject to the provisions of Clause 8.2.3, such memorandum shall have appended thereto an appendix (the “Appendix”) specifying in reasonable detail those parts of the Site to which vacant access and Right of Way has not been given to the Contractor. Signing of the memorandum, in two counterparts (each of which shall constitute an original), by the authorized representatives of the Parties shall be deemed to constitute a valid evidence of giving the Right of Way to the Contractor for discharging its obligations under and in accordance with the provisions of this Agreement and for no other purpose whatsoever’. AE would like to further clarify that cl. 8.3.1 last para stating that “For the avoidance of doubt, the Parties expressly agree that the Damages specified hereunder and the Time Extension specified in Clause 10.5 shall be restricted only to failure of the Authority to provide the Right of Way for and in respect of the width of the roadway, its embankment and a parallel working strip at least 3 (three) meters wide”. The width of the roadway can be treated as one side of the road since it is neither mentioned “Total width nor Full width’. Hence the Authority Engineer has done the analysis of Hindrance free length is clear with the above illustrated iteration. | FALSE | real_data
Elections in the state | EoT | Though during the meeting held on 22.10.2020 it was decided to grant EOT for 210 days purely based on (i) account of election as well as the issue of (ii) non-availability of earth only but was not communicated in time/till date, we request the Authority Engineer to review the details submitted from our end and recommend Extension of time for a period of 678 days to the Authority pursuant to Clause 10.5.1 of the Contract Agreement. | synthetic_template_20250913 | Six laning of Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V -EOT recommendation by the Authority for a period of 112 days not agreeable to the EPC Contractor — Request for considering EOT as discussed during the Review Meetings- reg | We are writing to express our concerns regarding the EOT recommendation by the Authority for a period of 112 days, which is not agreeable to the EPC Contractor. We request that the EOT be considered as discussed during the Review Meetings. The project involves six laning of the Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km 71+015 to km 107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase-V. We have referenced several documents and meetings in support of our request, and we hope for a favorable consideration. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Elections in the state | EoT | Though during the meeting held on 22.10.2020 it was decided to grant EOT for 210 days purely based on (i) account of election as well as the issue of (ii) non-availability of earth only but was not communicated in time/till date, we request the Authority Engineer to review the details submitted from our end and recommend Extension of time for a period of 678 days to the Authority pursuant to Clause 10.5.1 of the Contract Agreement. | synthetic_template_20250913 | Six laning of Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V -EOT recommendation by the Authority for a period of 112 days not agreeable to the EPC Contractor — Request for considering EOT as discussed during the Review Meetings- reg | We are writing to express our concerns regarding the EOT recommendation by the Authority for a period of 112 days, which is not agreeable to the EPC Contractor. We request that the EOT be considered as discussed during the Review Meetings. The project involves six laning of the Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km 71+015 to km 107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase-V. We have referenced several documents and meetings in support of our request, and we hope for a favorable consideration. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Elections in the state | EoT | We have obtained permission for extraction of borrow earth from Vadangampattu and Kalathur borrow area in Tiruvannamalai and Ranipet district respectively, Extraction of borrow earth is in progress, but we are facing hurdles from Govt. Official due to the Parliament Elections and Model Code of Conduct. Further, we have applied for Borrow earth permissions for the following (1) Chithathur Borrow area from Ranipet District (2) Palaiyanthangal Borrow area from Kancheepuram District & (3) Mangalam Borrow area from Tiruvanamalai District and permission is expected after Model Code of Conduct ends for upcoming Parliament election. | synthetic_template_20250913 | Submission of Revised Construction Program for Balance Works as per Original Scope of Works Including the COS-01 & COS-02 (Toll Plaza) - Reg | 1. Further to the Discussion & Meeting held at NHAI Regional Office, Chennai on 03"4 April 2024, we are herewith submitting the Revised Construction Program for Balance Works as per Original Scope of Works - including the COS-01 & COS-02 (Toll Plaza) works. 2. Due to our persistent efforts, borrow earth filling in the approaches of VUP at Km.76/846 and LVUP at Km.102/970 have been completed and traffic will be diverted shortly. Further the Flyover at Km 106+677 traffic will be diverted in the coming month. 3. The VUP at Km 87/544, LVUP at Km.90/080, VUP at Km.93/515 works are in progress and in the remaining approaches also all the efforts to divert traffic as per the program submitted will be adhered. 4. We have obtained permission for extraction of borrow earth from Vadangampattu and Kalathur borrow area in Tiruvannamalai and Ranipet district respectively, Extraction of borrow earth is in progress, but we are facing hurdles from Govt. Official due to the Parliament Elections and Model Code of Conduct. Further, we have applied for Borrow earth permissions for the following (1) Chithathur Borrow area from Ranipet District (2) Palaiyanthangal Borrow area from Kancheepuram District & (3) Mangalam Borrow area from Tiruvanamalai District and permission is expected after Model Code of Conduct ends for upcoming Parliament election. 2. lrulappasamy Thunai S.P.K. AND Co.., | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Elections in the state | EoT | Considering general election and the festival, period from 10.03.2019 to 18.08.2019 may be considered for the EOT for the first milestone as unforeseen event under the Non political and Political events | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under BharatmalaPariyojana on EPC mode — Rescheduling of Project Mile Stone- Request for Extension of Time -Reg. | Having gone through your documents related to Rescheduling of Project Milestone-Request for Extension of Time EoT-1 please find enclosed herewith the Authority Engineers recommendations on the same subject. This is for your information and necessary action. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Damages | Payments; Dispute Resolution | Considering the sincere efforts taken from our end for completing the Project Highway it is requested not to levy damages as we will put all efforts in timely completion of the Project Highway. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LOT-10/20240408_SPK_AE_373_Submission of Revised Construction Program for Balance Works as per Original Scope of Works Including the COS-01 & COS-02 (Toll Plaza) –Reg.pdf | Submission of Revised Construction Program for Balance Works as per Original Scope of Works Including the COS-01 & COS-02 (Toll Plaza) - Reg | 1. Further to the Discussion & Meeting held at NHAI Regional Office, Chennai on 03"4 April 2024, we are herewith submitting the Revised Construction Program for Balance Works as per Original Scope of Works - including the COS-01 & COS-02 (Toll Plaza) works. 2. Due to our persistent efforts, borrow earth filling in the approaches of VUP at Km.76/846 and LVUP at Km.102/970 have been completed and traffic will be diverted shortly. Further the Flyover at Km 106+677 traffic will be diverted in the coming month. 3. The VUP at Km 87/544, LVUP at Km.90/080, VUP at Km.93/515 works are in progress and in the remaining approaches also all the efforts to divert traffic as per the program submitted will be adhered. 4. We have obtained permission for extraction of borrow earth from Vadangampattu and Kalathur borrow area in Tiruvannamalai and Ranipet district respectively, Extraction of borrow earth is in progress, but we are facing hurdles from Govt. Official due to the Parliament Elections and Model Code of Conduct. Further, we have applied for Borrow earth permissions for the following (1) Chithathur Borrow area from Ranipet District (2) Palaiyanthangal Borrow area from Kancheepuram District & (3) Mangalam Borrow area from Tiruvanamalai District and permission is expected after Model Code of Conduct ends for upcoming Parliament election. 2. lrulappasamy Thunai S.P.K. AND Co.., | FALSE | real_data
Damages | Payments; Dispute Resolution | Therefore we do not agree that the Contractor is liable to pay damages due to delay in non-achievement of the said milestones. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20201119_SPK_AE_160_Contractor failure in achieving mile stone 1,2,&3.pdf | Six laning of Karaipcttai to Walajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - Contractor’s failure in achieving Project Mile Stone 1,2 & 3 applying of Damages vide Contract Article No. 10.3.2 & 10.3.3 - Reply made -Reg. | We are in receipt of your letter ref (26) cited above, our reply for the same is as follows: 1. The Contract Agreement for this Project was executed on 15.10.2018. The Appointed Date was fixed as 11.02.2019 and the same was communicated vide ref (2) cited above. 2. The Appointed date was declared as 11.02.2019 by the Authority taking into account the land handed over in terms of the available area without taking into consideration, the requirement of the Contract provision as per Clause 4.1.3 (a) of the EPC agreement which talks about the handing over of land only in terms of length of the Project Highway. The memorandum and appendix prepared in terms of area gave a deceptive / false picture about the availability of vacant access. Taking into consideration all the encumbrances, hindrances, utilities etc. the vacant access available on the appointed date declared was worked out and it was less than 90% and hence requested the Authority vide letter under ref (3) cited above for modification of the appointed date on which 90% of encumbrance free land would be made available to the Contractor. 3. The Authority in its response vide ref (4) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. 4. The EPC contractor vide ref (5) cited above in reply reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that the impacted length due to encroachments and encumbrances was 12.18 km which accounted to 33.77% of the project length. The workable length available to the contractor was only 66.23% of the project length. The EPC contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of encumbrance / encroachment / obstruction. | FALSE | real_data
Damages | Payments; Dispute Resolution | Imposition of liquidated damages as per the provisions of the Contract Agreement | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/20200716_AE_SPK_361_ Delay in Achieving of Project Mile Stones I and II.pdf | Delay in Achieving of Project Mile Stones I and II | In reference to the above cited subject, it is submitted that the Competent Authority has been approved the Extension of time in the Project Milestones vide letter referred at Sr. No. 1. Subsequent to this, the revised Milestone Dates are mentioned hereunder; Duration as per E.O.T Schedule-J Date: M.S.-1 180 Days 09.08.2019 29.11.2019, M.S.-2 365 Days 10.02.2020 10.02.2020. In reference to the above table, it is submitted that the milestone dates have been passed but Contractor did not submit any milestone achievement related documents, so far. The stipulated completion of works with the above Mile Stone Schedules are 10% & 30%. Whereas based on the last IPC which was measured on March 25 the progress of works is around 5% only. It is requested to please clarify the delay and submit all necessary documents relating to the Milestone Achievement. Further delay in the submission of requisite documents, this will lead to the imposition of Liquidated Damages as per the provisions of the Contract Agreement. This is for your information and necessary action from your end. | FALSE | real_data
Damages | Payments; Dispute Resolution | The damages amount to be payable is 0.05% of each delays days in non achievement of the said milestones | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20201106_AE_SPK_463_Contractor’s failure in achieving the Project Mile Stone 1, 2 & 3.pdf | Contractor’s failure in achieving the Project Mile Stone 1, 2 & 3. Applying of Damages Vide Contract Article No. 10.3.2. & 10.3.3. - Reg. | This is with reference to the captioned subject and non-achievement of Project Mile Stones by the Contractor. In this regard it is submitted that the Contract Agreement was signed between EPC Contractor M/s S.P.K. & Co and the NHAI for Six laning of Karaipettai to Walajahpet Section of NH-4 ( New NH-48) i.e. from Ch. Km. 71+ 015 to 107+091 in the state of Tamil Nadu under NHDP Phase -V. The following are the main Contractual data. The Contract Signing date : 15/10/2018 Length of the Project : 36.076 Km Project Cost : INR 533,36,67,000 Appointed Date > 11/02/2019 Construction Period : 730 days from the Appointed date. Schedule Completion date: 09/02/2021 DLP Period : 4 Years from the Provisional certificate. Mile Stones : Detailed Below. In this regard, it is submitted that provisions of the Contract Agreement, Article. No. 10.3.2, which stated that, “The Contractor shall construct the Project highway in accordance with the Project completion Schedule set forth in Annexure -1 Schedule “J” Further to the above, as per the Project Milestones dates given in the Schedule “J” the Project Milestones are as follows; Description Original/revised P Milestone Date MS-1 Achievement of 10% of the Contract Price. Achieved. MS-2 Achievement of 30 % of the Contract Price. Achieved 20.03% of contract Price on 18.09.2020 MS-3 Achievement of 60 % of the Contract Price. 10.02.2020 13.07.2020 To be achieved 09.02.2021 To be achieved In view of the above, it is submitted that as on date, no data provided by the Contractor for achievement of the Milestones. Hence it can be treated as that MS — ¦, Il and Ill have been not achieved by the Contractor on scheduled dates. Therefore, as per provisions of the Contract Agreement Article 10.3.2, Contractor is liable to pay damages to the Authority. The damages amount to be payable is 0.05% of each delay days in non-achievement of the said Milestones. In this regard, it is being requested to please clarify the situation and submit reasons why not damages/ penalty be imposed as per the provisions of Contract Agreement. | FALSE | real_data
Occurrence of unseasonal rainfall | EoT | This is in reference to the above referred communications bearing No's 384 & 394 dated 25.05.204 & 24.06.2024 respectively regarding rain fall during the months of May & June of 2024 for which after verification of the same, our observations are as stated below: | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LOT-10/20240704_SPK_AE_1786 Unseasonal rainfall during the month of May 2024 and in JUNE month 1 to 22.06.2024 Reporting of same-reg..pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode: Unseasonal rainfall during the month of May 2024 and in June month 1* to 22.06.2024 — Reporting of the same-Reg. | Dear Sir, This is in reference to the above referred communications bearing No’s 384 & 394 dated 25.05.204 & 24.06.2024 respectively regarding rain fall during the months of May & June of 2024 for which after verification of the same, our observations are as stated below: The data and the dates mentioned in both the communications are not matching for one page to the other page. Further it is to be noted that till date we did not receive any hard copy of the letter No. 394 dated 24.06.2024 and the supporting documents/Annexures as well. Considering the above you are hereby asked to re-submit these communications properly with relevant data for evaluation/verifications. This is for your information and necessary immediate actions. | FALSE | real_data
Occurrence of unseasonal rainfall | EoT | We once again request the Authority Engineer to consider the works hampered due to unseasonal rainfall based on the facts presented from our end. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LOT-10/20240729_SPK_AE_405_Intimation of unseasonal rainfall during the period from 01.07.2024 to 15.07.2024 – Reply made.pdf | Intimation of unseasonal rainfall during the period from 01.07.2024 to 15.07.2024 — Reply made - Reg. | Dear Sir, This is w.r.t your letter under ref (2) above regarding your views on unseasonal rainfall and our response is as follows: 1. We have been facing several constraints in procurement of borrow earth since inception of the Project Highway. This fact has also been acknowledged by the MoRT&H and it is pertinent to mention that NHAI foreclosed 4 major highway projects in Tamil Nadu as the Contractors couldn’t procure soil for earthwork and had to wait for months together to get statutory clearances. 2. NHAI projects awarded to Contractors from 2018 to 2022 costing approximately 17000 crores in TN and were originally scheduled to be completed within a year to 30 months are running behind the schedule. NHAI officials said that the delay of the project was due to various reasons including land acquisition issues, forest department clearances and non-availability of borrow earth permission as the water bodies were brimming due to heavy rainfall in recent months. News article of DT Next dated 25t» December 2023 is herewith enclosed as Annexure 1 for your kind reference.( 32 NHAI's projects costing Rs 17,000 crore delayed in TN (dtnext.in)) 3. It is pertinent to mention that our adjacent package of Six laning of Sriperumbudur to Kanchipuram has come to stand still as the Contractor could not source borrow earth and not a single structure approach has been completed as on date. This reiterates the fact that there is extreme difficulty in procuring the borrow earth along our Project Highway. . We have been updating regularly AE about the status of procurement of borrow earth and the AE is also very much aware of the difficulties faced from our end in | FALSE | real_data
Occurrence of unseasonal rainfall | EoT | This is with reference to the subject matter, we wish to intimate that usually Tamil Nadu gets majority of rain from North East monsoon which starts from October end and continues up to December. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20200713_SPK_AE_99_Intimation on Work affected due to Unexpected Rainfall.pdf | Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km.71+015 to Km 107+091 on EPC Mode in the state of Tamil Nadu under NHDP Phase-V - Work affected due to Unexpected Rainfall - Reg. | This is with reference to the subject matter; we wish to intimate that usually Tamilnadu gets majority of rain from North East monsoon which starts from October end and continues up to December. From South West monsoon also Tamilnadu gets some portion of rain. This year, area under which Project Highway is located got excess rainfall from South West monsoon. Hence, it has impacted the progress of the work. Cumulative Rainfall recorded in the recent days is as follows: Cumulative Rainfall Period of Rainfall " (mm) 01.06.2020 - 30.06.2020 447.40 01.07.2020 - 10.07.2020 300.40 ' Due to this unexpected heavy downpour, the entire works of the Project Highway have come to standstill owing to following reasons: 1. The Aggregates viz Coarse, Fine and Crusher dust are in moist condition due to which we are unable to commence operations of Hot Mix Plant and Batching Plant. 2. No further highway works could be carried out due to waterlogging and extremely moist conditions at borrow earth locations. Also, weather Report for June & July month is enclosed as Annexure - I. Photos showing work affected stretches due to rainfall is enclosed as Annexure - II. This is for your kind information & record, please. ~ | FALSE | real_data
Occurrence of unseasonal rainfall | EoT | Further the impact due to cyclonic storms Nivar and Burevi were severe as unprecedented rainfall took place for almost a fortnight period since 23/11/2020 till 10/12/2020. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20210108_SPK_AE_009_Earthwork activites Hampered.pdf | Earthwork activities totally hampered due to flooding of Borrow Areas- Reg. | 1. The EPC Contractor vide above mentioned references intimated the Authority Engineer relating to adverse impact on the progress of works due to rainfall. 2. Further the impact due to cyclonic storms Nivar and Burevi were severe as unprecedented rainfall took place for almost a fortnight period since 23/11/2020 till 10/12/2020. The same has also been intimated by the EPC Contractor vide letter under ref (3). 3. The EPC Contractor is finding it extremely difficult to proceed with Earthworks since June 2020 as majority of the borrow areas identified are flooded. Necessary photographs are herewith enclosed as Annexure 1. 4. The EPC Contractor has already completed majority of the earthworks in at grade section and works are in progress at elevated sections. You are also aware that the EPC contractor has completed 86,140 Sqm of RE panel casting which is approximately 70% of the total requirement. 5. RES wall filling in the approaches of the structures are badly hampered due to non-accessibility of borrow earth since all the Borrow areas are flooded. This is for your information and record. | FALSE | real_data
Occurrence of unseasonal rainfall | EoT | Now due to the recent cyclones such as NIVAR & BUREVI, the district had experienced heavy and copious rains and all the above identified borrow locations have been completely filled up with the water. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20210120_005_SPK_RO_Delay in obtaining permission for Borrow area.pdf | Delay in Obtaining Permission of Borrow Earth - Ranipet District - Reg. | Dear Sir, This is with reference to the above said references (2) to (7); we wish to submit that, since from the Appointed Date we have been approaching the Ranipet District administration for obtaining necessary permission for extracting Borrow earth. Correspondences for the same is enclosed as ready reference. Application for extracting borrow earth from the identified Borrow area which were submitted to the district administration are as follows: S.No ¦ Chainage ¦ 1 ¦ 101+310 2 ¦ 101+310 Name of the tank Marutheri Lake Bagaveli Lake Sumaithangi Lake Kaveripakkam Lake However, we wish to inform that. we are awaiting for the necessary permission from the District Collector to date. Now due to the recent cyclones such as NIVAR & BUREVI, the district had experienced heavy and copious rains and all the above identified borrow locations have been completely filled up with water. In this connection, we wish to mention that; widening sections of project road (i.e, 20.77Km.) is in the verge of completion and only balance scope for earthwork is required for approaches of the elevated sections. Due to non-availability of Borrow earth, all Elevated sections (i.e, totalling 13.90Km.) of RE Wall/RE Fill works has come to standstill despite more than 70% of completion of casting of RE panel. Further, delay. in extraction of Borrow earth will lead to delay in achieving the target. In this regard, we kindly request your good-self to intervene and forward our difficulties in obtaining permission of Borrow Earth to the Chief Secretary -— Government of Tamil nadu to issue suitable instructions to the concerned officials to accord permission to extract earth in order to facilitate the EPC Contractor in early completion of Project. This is for your immediate 8& necessary action, please. | FALSE | real_data
Borrow area | Contractor's Obligations | The project has a requirement of approximately 12,20,000 cum of embankment and subgrade filling. In this regard the EPC Contractor has identified the following tank locations for extracting borrow earth. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/005_Encl.pdf | Request for approval of extraction of Borrow earth | We, M/s. SPK and Co,. had bagged the above mentioned project work through competitive bidding to be executed on EPC (Engineering Procurement Contract) mode and accordingly contract agreement executed with the employer M/s. National Highways Authority of India on 15.10.2018. The project comprises of construction of various Structures along with its approaches Viz, VUP, LVUP, Minor Bridges & Flyover. The project has to be completed on time bound basis and the targets are very stiff for completion. The project has a requirement of approximately 12,20,000 cum of embankment and subgrade filling. In order to complete the project on time bound manner, the contractor has to get approval of the competent authority to extract the required filling/Borrow area materials. In this regard the EPC contractor has identified the following tank locations for extracting borrow earth. baa Va aoraio ¦ Ras 102+700 LHS Name of the village Sumaithangi, Vellore Sumaithangi, Vellore We hereby request your good self to review the application submitted and the permission may please be granted for extracting the earth from the above mentioned borrow area locations at the earliest in order to facilitate the EPC contractor in early completion of the project. Name of the tank Sumaithangi Lake Poondi lake We shall be remitting the necessary royalty payment as per the statutory requirements. | FALSE | real_data
Borrow area | Contractor's Obligations | Hence, we are getting only lukewarm response relating to processing our application towards extraction of borrow earth. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/40_07082019_Rescheduling of Project Milestones – Request for Extension of time.pdf | Rescheduling of Project Milestones - Request for Extension of time - Reg. | The Contract agreement for the above mentioned project was executed on 15.10.2018. The appointed date was fixed as 11.02.2019 and the same was communicated vide ref (3) cited above. The Copy of the same is herewith enclosed as Annexure 1. The Authority in its response vide ref (5) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. The copy of the same is enclosed as Annexure 3. The EPC contractor vide ref (6) cited above reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that still the condition remained the same and dismantling/ removal of structures fouling was not started and shifting of Electric pole and power line also not started. The impacted length due to encroachments and encumbrances was 12.18 Km which accounted to 33.77% of the project highway. The workable length available to the Contractor based on the impacted length was 66.23% of the Project Highway length. The EPC Contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of removal of encumbrance / encroachment / obstruction. The copy of ref (7) is herewith enclosed as Annexure 4. It is almost six months since the declaration of appointed date, removal/ dismantling of structures/encroachments have not been started. Also, the work of shifting of power line and electric pole of LT line and HT lines crossings have not been started yet. The following are some of the key contractual dates and events since the inception of the project to till date: 1. Total length of the project highway: 36.076 Km 2. Date of Signing of agreement: 152018 3. Submission of Performance BG as per Clause 7.1.1 of the Contract Agreement: 262018 4. Target date for preparation of Memorandum as per Clause 8.2.1 of the Contract Agreement: 142018 5. Actual date of signing of Memorandum of land handing over: 112019 6. Declaration of appointed date by the Authority: 112019 7. ROW to be handed over as on appointed date as per Clause 8.2.2 & Annexure II: 35.468 Km | FALSE | real_data
Borrow area | Contractor's Obligations | Permission for the extraction of earth in Kancheepuram and Ranipet District is yet to be provided by the District Administration. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20201119_SPK_AE_160_Contractor failure in achieving mile stone 1,2,&3.pdf | Six laning of Karaipcttai to Walajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - Contractor’s failure in achieving Project Mile Stone 1,2 & 3 applying of Damages vide Contract Article No. 10.3.2 & 10.3.3 - Reply made -Reg. | We are in receipt of your letter ref (26) cited above, our reply for the same is as follows: 1. The Contract Agreement for this Project was executed on 15.10.2018. The Appointed Date was fixed as 11.02.2019 and the same was communicated vide ref (2) cited above. 2. The Appointed date was declared as 11.02.2019 by the Authority taking into account the land handed over in terms of the available area without taking into consideration, the requirement of the Contract provision as per Clause 4.1.3 (a) of the EPC agreement which talks about the handing over of land only in terms of length of the Project Highway. The memorandum and appendix prepared in terms of area gave a deceptive / false picture about the availability of vacant access. Taking into consideration all the encumbrances, hindrances, utilities etc. the vacant access available on the appointed date declared was worked out and it was less than 90% and hence requested the Authority vide letter under ref (3) cited above for modification of the appointed date on which 90% of encumbrance free land would be made available to the Contractor. 3. The Authority in its response vide ref (4) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. 4. The EPC contractor vide ref (5) cited above in reply reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that the impacted length due to encroachments and encumbrances was 12.18 km which accounted to 33.77% of the project length. The workable length available to the contractor was only 66.23% of the project length. The EPC contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of encumbrance / encroachment / obstruction. | FALSE | real_data
Borrow area | Contractor's Obligations | Since, there has been a complete waterlogging in all the identified Borrow areas of Kanchipuram & Ranipet district, it is not possible to operate the Borrow areas for a minimum of 3 months. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20201205_SPK_PD_074_Intimation of water stagnation in Idntified Borrow Area.pdf | Intimation of Stagnation of Water in Identified Borrow Areas — Reg. | With reference to the above subject; we wish to bring your notice that, due to occurrence of “NIVAR & BUREVI Cyclone” there has been a heavy/continuous rain in Kanchipuram & Ranipet Districts. The entire works of the Project Highway have come to standstill owing to non-operation of Borrow area due to unexpected heavy downpour. Since, there has been a complete waterlogging in all the identified Borrow areas of Kanchipuram & Ranipet District, it is not possible to operate the Borrow Areas for a minimum period of 3 months. RE wall back filling for approaches of 3.Nos. of LVUP’s are hampered due to ponding of borrow areas. RE Panels are even stacked at site for commencement of back filling works. Photos showing the stagnation of water in the identified borrow areas of Kanchipuram & Ranipet Districts is enclosed as Annexure - I. This is for your kind information & record, please. | FALSE | real_data
Borrow area | Contractor's Obligations | The EPC Contractor is finding it extremely difficult to proceed with earthworks since June 2020 as majority of the borrow areas identified are flooded. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20210108_SPK_AE_009_Earthwork activites Hampered.pdf | Earthwork activities totally hampered due to flooding of Borrow Areas- Reg. | 1. The EPC Contractor vide above mentioned references intimated the Authority Engineer relating to adverse impact on the progress of works due to rainfall. 2. Further the impact due to cyclonic storms Nivar and Burevi were severe as unprecedented rainfall took place for almost a fortnight period since 23/11/2020 till 10/12/2020. The same has also been intimated by the EPC Contractor vide letter under ref (3). 3. The EPC Contractor is finding it extremely difficult to proceed with Earthworks since June 2020 as majority of the borrow areas identified are flooded. Necessary photographs are herewith enclosed as Annexure 1. 4. The EPC Contractor has already completed majority of the earthworks in at grade section and works are in progress at elevated sections. You are also aware that the EPC contractor has completed 86,140 Sqm of RE panel casting which is approximately 70% of the total requirement. 5. RES wall filling in the approaches of the structures are badly hampered due to non-accessibility of borrow earth since all the Borrow areas are flooded. This is for your information and record. | FALSE | real_data
Borrow area | Contractor's Obligations | In this regard, we kindly request your good-self to intervene and forward our difficulties in obtaining permission of borrow earth to the Chief Secretary - Government of Tamil Nadu to issue suitable instructions to the concerned officials to accord permission to extract earth in order to facilitate the EPC Contractor in early completion of Project. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20210120_005_SPK_RO_Delay in obtaining permission for Borrow area.pdf | Delay in Obtaining Permission of Borrow Earth - Ranipet District - Reg. | Dear Sir, This is with reference to the above said references (2) to (7); we wish to submit that, since from the Appointed Date we have been approaching the Ranipet District administration for obtaining necessary permission for extracting Borrow earth. Correspondences for the same is enclosed as ready reference. Application for extracting borrow earth from the identified Borrow area which were submitted to the district administration are as follows: S.No ¦ Chainage ¦ 1 ¦ 101+310 2 ¦ 101+310 Name of the tank Marutheri Lake Bagaveli Lake Sumaithangi Lake Kaveripakkam Lake However, we wish to inform that. we are awaiting for the necessary permission from the District Collector to date. Now due to the recent cyclones such as NIVAR & BUREVI, the district had experienced heavy and copious rains and all the above identified borrow locations have been completely filled up with water. In this connection, we wish to mention that; widening sections of project road (i.e, 20.77Km.) is in the verge of completion and only balance scope for earthwork is required for approaches of the elevated sections. Due to non-availability of Borrow earth, all Elevated sections (i.e, totalling 13.90Km.) of RE Wall/RE Fill works has come to standstill despite more than 70% of completion of casting of RE panel. Further, delay. in extraction of Borrow earth will lead to delay in achieving the target. In this regard, we kindly request your good-self to intervene and forward our difficulties in obtaining permission of Borrow Earth to the Chief Secretary -— Government of Tamil nadu to issue suitable instructions to the concerned officials to accord permission to extract earth in order to facilitate the EPC Contractor in early completion of Project. This is for your immediate 8& necessary action, please. | FALSE | real_data
Borrow area | Contractor's Obligations | In this regard, we hereby request your good self to forward our application to the District Collector - Ranipet. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20210127_SPK_PD_006_Request for obtaining permission of borrow earth.pdf | Request for Obtaining Permission of Borrow Earth - Reg. | Dear Sir, This has reference to the subject matter; vide reference (7), the EPC Contractor has requested the District Collector - Ranipet for approval of extraction of Earth from the identified Borrow area. In this regard, we hereby request your goodself to forward our application to the District collector-Ranipet. Application for extracting borrow earth from the identified Borrow area which were submitted to the district administration are as follows: Remarks S.No ¦ Chainage¦ Side Name of the tank R.S No. 98+420 RHS Ponnapanthangal Eri Kalpanapattu 8+ seHOG, Beal Aalanthangal Eri This is for your immediate & necessary action, please. | FALSE | real_data
Borrow area | Contractor's Obligations | The EPC Contractor vide letter (13) cited above, applied for Extension of time (EOT) for a period of 324 days considering delay in providing vacant access for 90% and 100% length of the Project Highway as per Contract provisions, delay in shifting of utilities, delay in appointment of Authority Engineer and delay in obtaining permits for procurement of borrow earth. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20210416_SPK_AE_067_EOT request with Delay analysis.pdf | Six laning of Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V -EOT recommendation by the Authority for a period of 112 days not agreeable to the EPC Contractor — Request for considering EOT as discussed during the Review Meetings- reg | We are writing to express our concerns regarding the EOT recommendation by the Authority for a period of 112 days, which is not agreeable to the EPC Contractor. We request that the EOT be considered as discussed during the Review Meetings. The project involves six laning of the Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km 71+015 to km 107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase-V. We have referenced several documents and meetings in support of our request, and we hope for a favorable consideration. | FALSE | real_data
Borrow area | Contractor's Obligations | Moreover it should be noted that reasons submitted by the contractor for delay, the works, such appointment of AE and the procurement of borrow earth, is the prime responsibility of the Contactor. He has to apply for such permits before the Appointed Date, but unfortunately, these permits applied very late by the Contractor. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/20200827_AE_SPK_394_Delay in achieving of Project Milestones I and II.pdf | Delay in achieving of Project Milestones I and II - Reg | Dear Sir, In reference to the above-mentioned subject and Contractor letter refereed at (12) cited above, we would like to submit the following para wise reply: 1. Having gone through your disagreement with the approved for 112 days vide above said reference was reviewed and our comments was communicated through Ref. No.6. However, your contention for 324 vide above said No.4 by mentioning the points such as 1. Delay in handing over of ROW, 2. Delay in shifting of utilities, 3. Delay in Appointment of Authority Engineer 4. Delay in appointment of Proof & Safety Consultant & 5. Delay in procurement of Borrow earth was already addressed in our EoT recommendations letter. Hence, we stand by our earlier observations and reiterating the same issue is unprofitable. Further your request for 324 days and justifying yourself based on the above same grounds can’t be accepted. More ever, it should be noted that reasons submitted by the Contractor for delay, are nowhere concern with the delay in the works, such appointment of AE and the procurement of borrow earth, is the prime responsibility of the Contactor. He has to apply for such permits before the Appointed Date, but unfortunately, these permits applied very late by the Contractor. 2. The Extension of Time justifying for Mile Stone -1 based on the above said/suitable grounds was recommended vide C.C. CL. No. 10.5.1. & 2. Hence any delay in the Works effected due to the above reasons is already compensated in the EOT. However, mixing the same with WHOLE WORKS according Schedule “J” Point 6 is not accepted. This should also be noted that the progress of works is not appreciable even as on date. So, Contractor requested to please expedite the work progress instead of finding the reasons of delay. 3. Same as Point No.2 4. We reiterate that the approval of EoT for 112 days from the Competent Authority based on our recommendations and their own assessment. However, your disagreement on the same issue with the Authority is noted. 5. Same as point No.4. 6. Your contention for availability of land is deviating from the Joint Memorandum signed by both the parties. This issue was already addressed in the Point No.1. However, considering the balance in shifting of electrical utilities the EoT was recommended. But your contention to delay in achieving the Mile Stone due to non-shifting total electrical utilities is not acceptable. The AE do not agree the affected length as mentioned by the Contractor, however in case Contractor feels that encumbrances are not allowing him to proceed with the works, then Contractor may discuss with the Authority for the length not handed over in the Memorandum signed between the parties in light of Article 8 Right of Way of the Contract Agreement. 7. At no point of time the Authority Engineer has agreed to your contention of 324 days EoT. The AE opinion has been submitted while processing the EOT request. Presenting your grievances will not be accepted as approval of your contention for 324 days. It is requested to such one side conclusions shall not be accepted and they are beyond the good industry practice. Noted, but as mentioned in our letter as referenced No.9 and as on date the Project Mile Stone -3 has also lapsed where in which your stage payment certification should be 60% against which you achieved only 14.38%. This clear cut indicates in lack of progress at with in the available land itself. The delay in progress with specific points has already intimated to you vide our letter No’s SAICPL/Kar-Wal/TL/NH-48/TN/02B//71/2020/361, 367 & 380 Dated 10th July 2020, 23 July and 07th August 2020 respectively. Hence once again it is asked to mobilize your resources to achieve the required progress as per the scheduled completion date. | FALSE | real_data
Borrow area | Contractor's Obligations | Enclosed please find a copy of letter no.2370/MMC.1/2021-2 dated 27.04.2021 issued by the Chief Secretary to Government of Tamilnadu wherein it has been stated that if NHAI applies for quarry lease in their own / borrowed patta lands for bonafide purposes,there is a provision to get lease for three years under rule 19(1) of the Tamil Nadu Minor Mineral Concession Rules,1959 | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210611_PD_AE_1596_Status of permission for Borrow Area.pdf | NHAI - PIU, Kancheepuram — Six Laning of Karaipettai to Walajahpet Section of NH-4 - Granting permission for borrow area permission — Order issued by Government of Tamil Nadu - reg. | Please refer the Regional Officer, NHAI, Chennai, letter cited in reference which is self explanatory. The copy of the letter is enclosed herewith. It is therefore requested to send a compliance report to this office for taking further necessary action. | FALSE | real_data
Borrow area | Contractor's Obligations | The Contractor has taken sincere effort for getting the permission for extraction of borrow earth since from the Appointed Date.But,considering the Contract Clause No.3.17 (a)which reproduced here,"The Contractor shall, at its own cost and expense in addition to and not in derogation of its obligation elswehere set out in this Agreement,(a) make, or cause to be made, necessary applications to the relevant Government Instrumentalities with such particulars and details as may be required for obtaining Applicable Permits set forth in Schedule F."Therefore,on this ground, the Contractor's request for EOT cannot be entertained.However, due to Aadhi Athi Varadhar festival which happens once in 40 years the same shall be considered for Entitlement of EOT.On the same ground,EOT was considered, while proposed the extension of time for Milestone - 1. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210630_AE_PD_14484_Comprehensive EOT proposal.pdf | Extension of Time Comprehensive proposal- Reg. | With reference to the captioned subject and from the above mentioned chronology of correspondences, it can be understood that despite of approving an EoT for a period of 112 days for Mile Stone-1, the Contractor is disagreeing with the approval of the Authority and again highlighted the impediments adversely effected the First Mile Stone as well as other Milestone including the Scheduled Completion Date. The Contractor submitted the comprehensive proposal and requested for an extension of time. | FALSE | real_data
Borrow area | Contractor's Obligations | In view of the above facts,it is submitted that the non-availability of borrow earth in the state adversely affected the work progress since its inception.Further,it is pertinent to note that till now the Contractor facing the difficulty in getting permissions for borrow earth from the concerned department.In this regard it is submitted that Contractor programme for completion of the balance work is also subject to the condition on obtaining the permission for borrow earth from the Government of Tamilnadu at the earliest. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210709_PD_RO_1893_Comprehensive EOT recommendation.pdf | NHAI, PIU, Kancheepuram - Six laning of Karaipettai to Walajahpet section of NH-4 (Km 71/015 to Km 107/091) in the State of Tamil Nadu — Comprehensive Proposal / Revised Extension of Time & Rescheduling of Project Milestones upto 20.12.2022 -— Proposal submitted for approval - Reg. | I submit that, the Authority Engineer vide letter 1* cited above, recommended the Comprehensive Extension of Time Proposal for the period of 398 days i.e upto 13.03.2022 towards completion of the subject project. 2. In this regard, it is submitted that, the Regional Officer, NHAI, Chennai vide letter cited 9'8 above, approved the EoT for a period of 112 days for Milestone-1 against the contractor’s claim of 324 days. However, the contractor vide letter cited 8" above, requested the Authority for considering the EoT for a period of 324 days. 3. In this context, the Contractor was requested to submit the Comprehensive Extension of Time proposal for completion of work and the Contractor vide reference letter cited 4" and 5t above, submitted the Comprehensive EoT Proposal for a period of 678 days i.e., upto 20.12.2022 citing the delays in execution of work due to various reasons such as Covid-19 pandemic, delay in handing over of ROW, delay in Shifting of Utilities / Electrical Towers, delay in Appointment of Authority Engineer, delay in appointment of Proof & Safety Consultant, delay in Procurement of Barrow earth due to Vellore Constituency re-election etc. 4. In this regard, the Authority Engineer vide letter 15' cited above, recommended the Comprehensive Extension of Time Proposal for the period of 398 days i.e upto 13.03.2022 towards completion of the subject project as follows a) Authority Engineer Recommendation: “The AE would like to submit that as provision of Article 10.5.1 stated that “Without prejudice to any other provision of this Agreement for and in respect of Extension of Time, the Contractor shall be entitled to extension of time in the Project Mile Stone is or will be delayed by any of the following, namely: • Delay in providing the Right of Way, Environmental Clearance or Approval of railway Authorities specified in Article 4.1.1. • Any other cause or delay which entitles the Contractor to Extension of Time in accordance with the provisions of this Agreement. In view of the above, pursuant mentioned Article 10.5.1, Article 4.1.6 (a) & (e) of the Contract Agreement, the Authority Engineer opinion are being submitted herewith for further needful; i. Delay due to Force Majeure: Pandemic Coronavirus (COVID-19) As the COVID -19 Pandemic was started and its effect was falling on the project, the Contractor noticed the Authority and the AE through references mentioned as 25, 26 & 27.: In this regard the Contractor claimed total 270 days vide letter No. SPK/ KW/SAIC/ NH-48/2021/069 Dated 19.04.2021 mentioned as ref. No. 46 & 48. However, as per the guidelines issued by the MoRT & H and the Govt. of India, Under Atmanirbhar Bharat Scheme, the Authority Engineer has recommended the EoT under Atmanirbhar Bharat Scheme for a period of 6 months vide letter No. SAICPL/ Kar-IL | FALSE | real_data
Descoping/deletion of works under original scope | Dispute Resolution | Proposed construction at Ch.Km.104+271 may be deleted from scope of enforced contract. | synthetic_template_20250913 | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Provision of Rest Area at Ch. Km. 104/271 - Reg. | With respect to the Contract Agreement, there is a provision of Rest Area at Ch. Km. 104+271 adjacent to the Left Carriageway of the Project Corridor. Please refer Annexure-1 Schedule -C Point No. 2.5 Page No. 163 of the Contract Agreement. However, based on your letter as Referenced No.1 a site inspection was carried out on 15th May 2020 and findings are as follows: 1. According to the Contract provision at Ch. Km. 104+271 a Rest area is to be made i.e. at Katteri village. 2. But there is already a fully functional Rest Area at Ch. Km. 109+250 near Devadanam village in the continuity Package i.e from Wallajahpet to Krishnagiri which is 5 kms away from the proposed Katteri village Rest Area. Further it is lying on the same side of the Project Corridor. Hence considering the proximity distance of 5kms between the proposed and the existing Rest Areas Authority Engineer is opined that proposed construction at Ch. Km. 104+271 may be deleted from scope of enforced Contract, which will be a negative C.O.S. The necessary sketch showing the proposed and existing Rest Areas is being enclosed for your easy understanding. This is for your in-principle approvals. Assuring our best services at all times. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Descoping/deletion of works under original scope | Dispute Resolution | Proposed construction at Ch.Km.104+271 may be deleted from scope of enforced contract. | synthetic_template_20250913 | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Provision of Rest Area at Ch. Km. 104/271 - Reg. | With respect to the Contract Agreement, there is a provision of Rest Area at Ch. Km. 104+271 adjacent to the Left Carriageway of the Project Corridor. Please refer Annexure-1 Schedule -C Point No. 2.5 Page No. 163 of the Contract Agreement. However, based on your letter as Referenced No.1 a site inspection was carried out on 15th May 2020 and findings are as follows: 1. According to the Contract provision at Ch. Km. 104+271 a Rest area is to be made i.e. at Katteri village. 2. But there is already a fully functional Rest Area at Ch. Km. 109+250 near Devadanam village in the continuity Package i.e from Wallajahpet to Krishnagiri which is 5 kms away from the proposed Katteri village Rest Area. Further it is lying on the same side of the Project Corridor. Hence considering the proximity distance of 5kms between the proposed and the existing Rest Areas Authority Engineer is opined that proposed construction at Ch. Km. 104+271 may be deleted from scope of enforced Contract, which will be a negative C.O.S. The necessary sketch showing the proposed and existing Rest Areas is being enclosed for your easy understanding. This is for your in-principle approvals. Assuring our best services at all times. Thank you for your attention to this matter. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Descoping/deletion of works under original scope | Payments | Proposed construction at Ch.Km.104+271 may be deleted from scope of enforced contract. | synthetic_template_20250913 | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Provision of Rest Area at Ch. Km. 104/271 - Reg. | With respect to the Contract Agreement, there is a provision of Rest Area at Ch. Km. 104+271 adjacent to the Left Carriageway of the Project Corridor. Please refer Annexure-1 Schedule -C Point No. 2.5 Page No. 163 of the Contract Agreement. However, based on your letter as Referenced No.1 a site inspection was carried out on 15th May 2020 and findings are as follows: 1. According to the Contract provision at Ch. Km. 104+271 a Rest area is to be made i.e. at Katteri village. 2. But there is already a fully functional Rest Area at Ch. Km. 109+250 near Devadanam village in the continuity Package i.e from Wallajahpet to Krishnagiri which is 5 kms away from the proposed Katteri village Rest Area. Further it is lying on the same side of the Project Corridor. Hence considering the proximity distance of 5kms between the proposed and the existing Rest Areas Authority Engineer is opined that proposed construction at Ch. Km. 104+271 may be deleted from scope of enforced Contract, which will be a negative C.O.S. The necessary sketch showing the proposed and existing Rest Areas is being enclosed for your easy understanding. This is for your in-principle approvals. Assuring our best services at all times. Thank you for your attention to this matter. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Descoping/deletion of works under original scope | Payments | Proposed construction at Ch.Km.104+271 may be deleted from scope of enforced contract. | synthetic_template_20250913 | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Provision of Rest Area at Ch. Km. 104/271 - Reg. | With respect to the Contract Agreement, there is a provision of Rest Area at Ch. Km. 104+271 adjacent to the Left Carriageway of the Project Corridor. Please refer Annexure-1 Schedule -C Point No. 2.5 Page No. 163 of the Contract Agreement. However, based on your letter as Referenced No.1 a site inspection was carried out on 15th May 2020 and findings are as follows: 1. According to the Contract provision at Ch. Km. 104+271 a Rest area is to be made i.e. at Katteri village. 2. But there is already a fully functional Rest Area at Ch. Km. 109+250 near Devadanam village in the continuity Package i.e from Wallajahpet to Krishnagiri which is 5 kms away from the proposed Katteri village Rest Area. Further it is lying on the same side of the Project Corridor. Hence considering the proximity distance of 5kms between the proposed and the existing Rest Areas Authority Engineer is opined that proposed construction at Ch. Km. 104+271 may be deleted from scope of enforced Contract, which will be a negative C.O.S. The necessary sketch showing the proposed and existing Rest Areas is being enclosed for your easy understanding. This is for your in-principle approvals. Assuring our best services at all times. Please confirm receipt of this correspondence. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Descoping/deletion of works under original scope | Change of Scope | Proposed construction at Ch.Km.104+271 may be deleted from scope of enforced contract. | synthetic_template_20250913 | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Provision of Rest Area at Ch. Km. 104/271 - Reg. | With respect to the Contract Agreement, there is a provision of Rest Area at Ch. Km. 104+271 adjacent to the Left Carriageway of the Project Corridor. Please refer Annexure-1 Schedule -C Point No. 2.5 Page No. 163 of the Contract Agreement. However, based on your letter as Referenced No.1 a site inspection was carried out on 15th May 2020 and findings are as follows: 1. According to the Contract provision at Ch. Km. 104+271 a Rest area is to be made i.e. at Katteri village. 2. But there is already a fully functional Rest Area at Ch. Km. 109+250 near Devadanam village in the continuity Package i.e from Wallajahpet to Krishnagiri which is 5 kms away from the proposed Katteri village Rest Area. Further it is lying on the same side of the Project Corridor. Hence considering the proximity distance of 5kms between the proposed and the existing Rest Areas Authority Engineer is opined that proposed construction at Ch. Km. 104+271 may be deleted from scope of enforced Contract, which will be a negative C.O.S. The necessary sketch showing the proposed and existing Rest Areas is being enclosed for your easy understanding. This is for your in-principle approvals. Assuring our best services at all times. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Descoping/deletion of works under original scope | Change of Scope | Proposed construction at Ch.Km.104+271 may be deleted from scope of enforced contract. | synthetic_template_20250913 | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Provision of Rest Area at Ch. Km. 104/271 - Reg. | It is brought to your attention that With respect to the Contract Agreement, there is a provision of Rest Area at Ch. Km. 104+271 adjacent to the Left Carriageway of the Project Corridor. Please refer Annexure-1 Schedule -C Point No. 2.5 Page No. 163 of the Contract Agreement. However, based on your letter as Referenced No.1 a site inspection was carried out on 15th May 2020 and findings are as follows: 1. According to the Contract provision at Ch. Km. 104+271 a Rest area is to be made i.e. at Katteri village. 2. But there is already a fully functional Rest Area at Ch. Km. 109+250 near Devadanam village in the continuity Package i.e from Wallajahpet to Krishnagiri which is 5 kms away from the proposed Katteri village Rest Area. Further it is lying on the same side of the Project Corridor. Hence considering the proximity distance of 5kms between the proposed and the existing Rest Areas Authority Engineer is opined that proposed construction at Ch. Km. 104+271 may be deleted from scope of enforced Contract, which will be a negative C.O.S. The necessary sketch showing the proposed and existing Rest Areas is being enclosed for your easy understanding. This is for your in-principle approvals. Assuring our best services at all times. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Change of scope approval revisit | Payments; Dispute Resolution; Change of Scope; EoT | We hereby requesting the Competent Authority for revisiting the approval of COS works without taking into account the deduction towards discount of 9.66% and issue a revised COS order. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-6/20210904_SPK_CGM_056_COS IN PRINCIPAL Approval Communicated with Deduction of 9.66% in the Cost Estimate - Reg.pdf | Change of Scope Proposal - Change of Scope Approval Communicated with Deduction of 9.66% in the Cost Estimate is outside the purview of the Contract Agreement - Reg | We acknowledge the in-principle approval of Cost estimate towards COS (Change of Scope) works communicated by the PD- PIU Kanchipuram vide ref (3) above and our response is as follows: 1. Clause 13.1.1 of the Contract Agreement states, “The Authority may, notwithstanding anything to the contrary contained in this Agreement, require the Contractor to make modifications / alterations to the works (“Change of Scope”) before the issue of the Completion Certificate either by giving an instruction or by requesting the Contractor to submit a proposal for Change of Scope involving additional cost or reduction in cost. Any such Change of Scope shall be made and valued in accordance with the provisions of this Article 13.” 2. Accordingly, the COS proposal submitted by the Contractor was based on Clause 13.2.3 of the Contract Agreement wherein SOR (2020 - 2021) of Public Works Department, Government of Tamilnadu and MoRTH Standard Data book 2003 was adopted. The same was reviewed by the Authority Engineer and recommended to the Project Director NHAI/Authority. The Regional Officer, NHAI Chennai also acknowledged the Cost Estimate and the same was recommended to NHAI HQ (New Delhi) for in-principle approval. 3. But in the in-principal approval of COS communicated from your end vide ref (3) above, a discount of 9.66% has been deducted in the Total Civil Cost amounting to Rs.3,40,71,496/= (Rupees Three crore forty lakhs seventy-one thousand four hundred and ninety-six) from the Total Civil Cost towards COS of Rs 35,27,06,944/- This deduction is against the provisions of the Contract Agreement. 4. It is worth mentioning that the EPC Contractor has already executed the Black spot rectification works under Change of Scope (COS) and raised invoiced vide IPC and no such deductions were made relating to the above-mentioned discount of 9.66%. 5. We hereby request the Competent Authority for revisiting the approval of COS works without taking into account the deduction towards discount of 9.66% and issue a revised COS order. As original scope of works is also affected at various isolated locations due to delay in approval of COS, the EPC Contractor is facing constraints in completing the original scope of works. It would be highly appreciated if an early response as requested at (5) above is communicated. | FALSE | real_data
Change of scope approval revisit | EoT | We hereby requesting the Competent Authority for revisiting the approval of COS works without taking into account the deduction towards discount of 9.66% and issue a revised COS order. | synthetic_template_20250913 | Change of Scope Proposal - Change of Scope Approval Communicated with Deduction of 9.66% in the Cost Estimate is outside the purview of the Contract Agreement - Reg | It is brought to your attention that We acknowledge the in-principle approval of Cost estimate towards COS (Change of Scope) works communicated by the PD- PIU Kanchipuram vide ref (3) above and our response is as follows: 1. Clause 13.1.1 of the Contract Agreement states, “The Authority may, notwithstanding anything to the contrary contained in this Agreement, require the Contractor to make modifications / alterations to the works (“Change of Scope”) before the issue of the Completion Certificate either by giving an instruction or by requesting the Contractor to submit a proposal for Change of Scope involving additional cost or reduction in cost. Any such Change of Scope shall be made and valued in accordance with the provisions of this Article 13.” 2. Accordingly, the COS proposal submitted by the Contractor was based on Clause 13.2.3 of the Contract Agreement wherein SOR (2020 - 2021) of Public Works Department, Government of Tamilnadu and MoRTH Standard Data book 2003 was adopted. The same was reviewed by the Authority Engineer and recommended to the Project Director NHAI/Authority. The Regional Officer, NHAI Chennai also acknowledged the Cost Estimate and the same was recommended to NHAI HQ (New Delhi) for in-principle approval. 3. But in the in-principal approval of COS communicated from your end vide ref (3) above, a discount of 9.66% has been deducted in the Total Civil Cost amounting to Rs.3,40,71,496/= (Rupees Three crore forty lakhs seventy-one thousand four hundred and ninety-six) from the Total Civil Cost towards COS of Rs 35,27,06,944/- This deduction is against the provisions of the Contract Agreement. 4. It is worth mentioning that the EPC Contractor has already executed the Black spot rectification works under Change of Scope (COS) and raised invoiced vide IPC and no such deductions were made relating to the above-mentioned discount of 9.66%. 5. We hereby request the Competent Authority for revisiting the approval of COS works without taking into account the deduction towards discount of 9.66% and issue a revised COS order. As original scope of works is also affected at various isolated locations due to delay in approval of COS, the EPC Contractor is facing constraints in completing the original scope of works. It would be highly appreciated if an early response as requested at (5) above is communicated. We await your further instructions. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Change of scope approval revisit | EoT | We hereby requesting the Competent Authority for revisiting the approval of COS works without taking into account the deduction towards discount of 9.66% and issue a revised COS order. | synthetic_template_20250913 | Change of Scope Proposal - Change of Scope Approval Communicated with Deduction of 9.66% in the Cost Estimate is outside the purview of the Contract Agreement - Reg | We acknowledge the in-principle approval of Cost estimate towards COS (Change of Scope) works communicated by the PD- PIU Kanchipuram vide ref (3) above and our response is as follows: 1. Clause 13.1.1 of the Contract Agreement states, “The Authority may, notwithstanding anything to the contrary contained in this Agreement, require the Contractor to make modifications / alterations to the works (“Change of Scope”) before the issue of the Completion Certificate either by giving an instruction or by requesting the Contractor to submit a proposal for Change of Scope involving additional cost or reduction in cost. Any such Change of Scope shall be made and valued in accordance with the provisions of this Article 13.” 2. Accordingly, the COS proposal submitted by the Contractor was based on Clause 13.2.3 of the Contract Agreement wherein SOR (2020 - 2021) of Public Works Department, Government of Tamilnadu and MoRTH Standard Data book 2003 was adopted. The same was reviewed by the Authority Engineer and recommended to the Project Director NHAI/Authority. The Regional Officer, NHAI Chennai also acknowledged the Cost Estimate and the same was recommended to NHAI HQ (New Delhi) for in-principle approval. 3. But in the in-principal approval of COS communicated from your end vide ref (3) above, a discount of 9.66% has been deducted in the Total Civil Cost amounting to Rs.3,40,71,496/= (Rupees Three crore forty lakhs seventy-one thousand four hundred and ninety-six) from the Total Civil Cost towards COS of Rs 35,27,06,944/- This deduction is against the provisions of the Contract Agreement. 4. It is worth mentioning that the EPC Contractor has already executed the Black spot rectification works under Change of Scope (COS) and raised invoiced vide IPC and no such deductions were made relating to the above-mentioned discount of 9.66%. 5. We hereby request the Competent Authority for revisiting the approval of COS works without taking into account the deduction towards discount of 9.66% and issue a revised COS order. As original scope of works is also affected at various isolated locations due to delay in approval of COS, the EPC Contractor is facing constraints in completing the original scope of works. It would be highly appreciated if an early response as requested at (5) above is communicated. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Change of scope approval revisit | Dispute Resolution | We hereby requesting the Competent Authority for revisiting the approval of COS works without taking into account the deduction towards discount of 9.66% and issue a revised COS order. | synthetic_template_20250913 | Change of Scope Proposal - Change of Scope Approval Communicated with Deduction of 9.66% in the Cost Estimate is outside the purview of the Contract Agreement - Reg | We acknowledge the in-principle approval of Cost estimate towards COS (Change of Scope) works communicated by the PD- PIU Kanchipuram vide ref (3) above and our response is as follows: 1. Clause 13.1.1 of the Contract Agreement states, “The Authority may, notwithstanding anything to the contrary contained in this Agreement, require the Contractor to make modifications / alterations to the works (“Change of Scope”) before the issue of the Completion Certificate either by giving an instruction or by requesting the Contractor to submit a proposal for Change of Scope involving additional cost or reduction in cost. Any such Change of Scope shall be made and valued in accordance with the provisions of this Article 13.” 2. Accordingly, the COS proposal submitted by the Contractor was based on Clause 13.2.3 of the Contract Agreement wherein SOR (2020 - 2021) of Public Works Department, Government of Tamilnadu and MoRTH Standard Data book 2003 was adopted. The same was reviewed by the Authority Engineer and recommended to the Project Director NHAI/Authority. The Regional Officer, NHAI Chennai also acknowledged the Cost Estimate and the same was recommended to NHAI HQ (New Delhi) for in-principle approval. 3. But in the in-principal approval of COS communicated from your end vide ref (3) above, a discount of 9.66% has been deducted in the Total Civil Cost amounting to Rs.3,40,71,496/= (Rupees Three crore forty lakhs seventy-one thousand four hundred and ninety-six) from the Total Civil Cost towards COS of Rs 35,27,06,944/- This deduction is against the provisions of the Contract Agreement. 4. It is worth mentioning that the EPC Contractor has already executed the Black spot rectification works under Change of Scope (COS) and raised invoiced vide IPC and no such deductions were made relating to the above-mentioned discount of 9.66%. 5. We hereby request the Competent Authority for revisiting the approval of COS works without taking into account the deduction towards discount of 9.66% and issue a revised COS order. As original scope of works is also affected at various isolated locations due to delay in approval of COS, the EPC Contractor is facing constraints in completing the original scope of works. It would be highly appreciated if an early response as requested at (5) above is communicated. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Change of scope approval revisit | Dispute Resolution | We hereby requesting the Competent Authority for revisiting the approval of COS works without taking into account the deduction towards discount of 9.66% and issue a revised COS order. | synthetic_template_20250913 | Change of Scope Proposal - Change of Scope Approval Communicated with Deduction of 9.66% in the Cost Estimate is outside the purview of the Contract Agreement - Reg | We hereby confirm that We acknowledge the in-principle approval of Cost estimate towards COS (Change of Scope) works communicated by the PD- PIU Kanchipuram vide ref (3) above and our response is as follows: 1. Clause 13.1.1 of the Contract Agreement states, “The Authority may, notwithstanding anything to the contrary contained in this Agreement, require the Contractor to make modifications / alterations to the works (“Change of Scope”) before the issue of the Completion Certificate either by giving an instruction or by requesting the Contractor to submit a proposal for Change of Scope involving additional cost or reduction in cost. Any such Change of Scope shall be made and valued in accordance with the provisions of this Article 13.” 2. Accordingly, the COS proposal submitted by the Contractor was based on Clause 13.2.3 of the Contract Agreement wherein SOR (2020 - 2021) of Public Works Department, Government of Tamilnadu and MoRTH Standard Data book 2003 was adopted. The same was reviewed by the Authority Engineer and recommended to the Project Director NHAI/Authority. The Regional Officer, NHAI Chennai also acknowledged the Cost Estimate and the same was recommended to NHAI HQ (New Delhi) for in-principle approval. 3. But in the in-principal approval of COS communicated from your end vide ref (3) above, a discount of 9.66% has been deducted in the Total Civil Cost amounting to Rs.3,40,71,496/= (Rupees Three crore forty lakhs seventy-one thousand four hundred and ninety-six) from the Total Civil Cost towards COS of Rs 35,27,06,944/- This deduction is against the provisions of the Contract Agreement. 4. It is worth mentioning that the EPC Contractor has already executed the Black spot rectification works under Change of Scope (COS) and raised invoiced vide IPC and no such deductions were made relating to the above-mentioned discount of 9.66%. 5. We hereby request the Competent Authority for revisiting the approval of COS works without taking into account the deduction towards discount of 9.66% and issue a revised COS order. As original scope of works is also affected at various isolated locations due to delay in approval of COS, the EPC Contractor is facing constraints in completing the original scope of works. It would be highly appreciated if an early response as requested at (5) above is communicated. Please confirm receipt of this correspondence. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Change of scope approval revisit | Payments | We hereby requesting the Competent Authority for revisiting the approval of COS works without taking into account the deduction towards discount of 9.66% and issue a revised COS order. | synthetic_template_20250913 | Change of Scope Proposal - Change of Scope Approval Communicated with Deduction of 9.66% in the Cost Estimate is outside the purview of the Contract Agreement - Reg | We acknowledge the in-principle approval of Cost estimate towards COS (Change of Scope) works communicated by the PD- PIU Kanchipuram vide ref (3) above and our response is as follows: 1. Clause 13.1.1 of the Contract Agreement states, “The Authority may, notwithstanding anything to the contrary contained in this Agreement, require the Contractor to make modifications / alterations to the works (“Change of Scope”) before the issue of the Completion Certificate either by giving an instruction or by requesting the Contractor to submit a proposal for Change of Scope involving additional cost or reduction in cost. Any such Change of Scope shall be made and valued in accordance with the provisions of this Article 13.” 2. Accordingly, the COS proposal submitted by the Contractor was based on Clause 13.2.3 of the Contract Agreement wherein SOR (2020 - 2021) of Public Works Department, Government of Tamilnadu and MoRTH Standard Data book 2003 was adopted. The same was reviewed by the Authority Engineer and recommended to the Project Director NHAI/Authority. The Regional Officer, NHAI Chennai also acknowledged the Cost Estimate and the same was recommended to NHAI HQ (New Delhi) for in-principle approval. 3. But in the in-principal approval of COS communicated from your end vide ref (3) above, a discount of 9.66% has been deducted in the Total Civil Cost amounting to Rs.3,40,71,496/= (Rupees Three crore forty lakhs seventy-one thousand four hundred and ninety-six) from the Total Civil Cost towards COS of Rs 35,27,06,944/- This deduction is against the provisions of the Contract Agreement. 4. It is worth mentioning that the EPC Contractor has already executed the Black spot rectification works under Change of Scope (COS) and raised invoiced vide IPC and no such deductions were made relating to the above-mentioned discount of 9.66%. 5. We hereby request the Competent Authority for revisiting the approval of COS works without taking into account the deduction towards discount of 9.66% and issue a revised COS order. As original scope of works is also affected at various isolated locations due to delay in approval of COS, the EPC Contractor is facing constraints in completing the original scope of works. It would be highly appreciated if an early response as requested at (5) above is communicated. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Change of scope approval revisit | Payments | We hereby requesting the Competent Authority for revisiting the approval of COS works without taking into account the deduction towards discount of 9.66% and issue a revised COS order. | synthetic_template_20250913 | Change of Scope Proposal - Change of Scope Approval Communicated with Deduction of 9.66% in the Cost Estimate is outside the purview of the Contract Agreement - Reg | We hereby confirm that We acknowledge the in-principle approval of Cost estimate towards COS (Change of Scope) works communicated by the PD- PIU Kanchipuram vide ref (3) above and our response is as follows: 1. Clause 13.1.1 of the Contract Agreement states, “The Authority may, notwithstanding anything to the contrary contained in this Agreement, require the Contractor to make modifications / alterations to the works (“Change of Scope”) before the issue of the Completion Certificate either by giving an instruction or by requesting the Contractor to submit a proposal for Change of Scope involving additional cost or reduction in cost. Any such Change of Scope shall be made and valued in accordance with the provisions of this Article 13.” 2. Accordingly, the COS proposal submitted by the Contractor was based on Clause 13.2.3 of the Contract Agreement wherein SOR (2020 - 2021) of Public Works Department, Government of Tamilnadu and MoRTH Standard Data book 2003 was adopted. The same was reviewed by the Authority Engineer and recommended to the Project Director NHAI/Authority. The Regional Officer, NHAI Chennai also acknowledged the Cost Estimate and the same was recommended to NHAI HQ (New Delhi) for in-principle approval. 3. But in the in-principal approval of COS communicated from your end vide ref (3) above, a discount of 9.66% has been deducted in the Total Civil Cost amounting to Rs.3,40,71,496/= (Rupees Three crore forty lakhs seventy-one thousand four hundred and ninety-six) from the Total Civil Cost towards COS of Rs 35,27,06,944/- This deduction is against the provisions of the Contract Agreement. 4. It is worth mentioning that the EPC Contractor has already executed the Black spot rectification works under Change of Scope (COS) and raised invoiced vide IPC and no such deductions were made relating to the above-mentioned discount of 9.66%. 5. We hereby request the Competent Authority for revisiting the approval of COS works without taking into account the deduction towards discount of 9.66% and issue a revised COS order. As original scope of works is also affected at various isolated locations due to delay in approval of COS, the EPC Contractor is facing constraints in completing the original scope of works. It would be highly appreciated if an early response as requested at (5) above is communicated. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Change of scope approval revisit | Change of Scope | We hereby requesting the Competent Authority for revisiting the approval of COS works without taking into account the deduction towards discount of 9.66% and issue a revised COS order. | synthetic_template_20250913 | Change of Scope Proposal - Change of Scope Approval Communicated with Deduction of 9.66% in the Cost Estimate is outside the purview of the Contract Agreement - Reg | We acknowledge the in-principle approval of Cost estimate towards COS (Change of Scope) works communicated by the PD- PIU Kanchipuram vide ref (3) above and our response is as follows: 1. Clause 13.1.1 of the Contract Agreement states, “The Authority may, notwithstanding anything to the contrary contained in this Agreement, require the Contractor to make modifications / alterations to the works (“Change of Scope”) before the issue of the Completion Certificate either by giving an instruction or by requesting the Contractor to submit a proposal for Change of Scope involving additional cost or reduction in cost. Any such Change of Scope shall be made and valued in accordance with the provisions of this Article 13.” 2. Accordingly, the COS proposal submitted by the Contractor was based on Clause 13.2.3 of the Contract Agreement wherein SOR (2020 - 2021) of Public Works Department, Government of Tamilnadu and MoRTH Standard Data book 2003 was adopted. The same was reviewed by the Authority Engineer and recommended to the Project Director NHAI/Authority. The Regional Officer, NHAI Chennai also acknowledged the Cost Estimate and the same was recommended to NHAI HQ (New Delhi) for in-principle approval. 3. But in the in-principal approval of COS communicated from your end vide ref (3) above, a discount of 9.66% has been deducted in the Total Civil Cost amounting to Rs.3,40,71,496/= (Rupees Three crore forty lakhs seventy-one thousand four hundred and ninety-six) from the Total Civil Cost towards COS of Rs 35,27,06,944/- This deduction is against the provisions of the Contract Agreement. 4. It is worth mentioning that the EPC Contractor has already executed the Black spot rectification works under Change of Scope (COS) and raised invoiced vide IPC and no such deductions were made relating to the above-mentioned discount of 9.66%. 5. We hereby request the Competent Authority for revisiting the approval of COS works without taking into account the deduction towards discount of 9.66% and issue a revised COS order. As original scope of works is also affected at various isolated locations due to delay in approval of COS, the EPC Contractor is facing constraints in completing the original scope of works. It would be highly appreciated if an early response as requested at (5) above is communicated. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Delay due to Change of Scope approval | EoT; Payments; Dispute Resolution; Change of Scope | We wish to inform that the same was not scrutinized and recommended by the Engineer even after a period of 43 days | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-6/20230121_SPK_AE_197_Delay in Toll Plaza cost estimate review and recommendation - Request for early COS Approval of Proposed Toll Plaza with 16 lanes at Km.104+981 - Reg..pdf | Delay in Toll Plaza cost estimate review and recommendation - Request for early COS Approval of Proposed Toll Plaza with 16 lanes at Km.104+981 - Reg. | Dear Sir, Vide reference (3) the submissions related to the proposed 16 Nos (8+8) Toll Lanes at Km104+981 have been submitted and as instructed at NHAI RO, Chennai on 29.10.2022 by the Advisor (Tech) NHAI RO office to submit the Cost Estimate for User Fee Plaza with 16 lanes and instructed to get it reviewed at the RO Office at the earliest, for onward recommendation to the NHAI HQ for approval. But with regret we wish to inform that the same was not scrutinized and recommended from your end even after a period of 43 days. The observations on the submitted Drawings has been communicated from your end vide above reference letter (9) after a period of more than a month from our submission. However, the said observations will be incorporated and submitted at the earliest. Due to delay in review of cost estimate from your end, the construction of this new User Fee Plaza within the revised SPCD will become an arduous task and we shall not be held accountable for any delay in this regard. | FALSE | real_data
Delay due to Change of Scope approval | EoT; Payments; Dispute Resolution; Change of Scope | Due to delay in review of cost estimate from your end the construction of this new user fee plaza within the revised SPCD will become an arduous task and we shall not be held accountable for any delay in this regard. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-6/20230121_SPK_AE_197_Delay in Toll Plaza cost estimate review and recommendation - Request for early COS Approval of Proposed Toll Plaza with 16 lanes at Km.104+981 - Reg..pdf | Delay in Toll Plaza cost estimate review and recommendation - Request for early COS Approval of Proposed Toll Plaza with 16 lanes at Km.104+981 - Reg. | Dear Sir, Vide reference (3) the submissions related to the proposed 16 Nos (8+8) Toll Lanes at Km104+981 have been submitted and as instructed at NHAI RO, Chennai on 29.10.2022 by the Advisor (Tech) NHAI RO office to submit the Cost Estimate for User Fee Plaza with 16 lanes and instructed to get it reviewed at the RO Office at the earliest, for onward recommendation to the NHAI HQ for approval. But with regret we wish to inform that the same was not scrutinized and recommended from your end even after a period of 43 days. The observations on the submitted Drawings has been communicated from your end vide above reference letter (9) after a period of more than a month from our submission. However, the said observations will be incorporated and submitted at the earliest. Due to delay in review of cost estimate from your end, the construction of this new User Fee Plaza within the revised SPCD will become an arduous task and we shall not be held accountable for any delay in this regard. | FALSE | real_data
Delay due to Change of Scope approval | EoT; Payments; Dispute Resolution; Change of Scope | The delay in decision / issuance of change of scope notice by Authority Engineer are still ongoing. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-3/18. Application of EOT or revision of milestone dates 14.06.2018.pdf | Application for extension of time/Revision of Mile Stone dates - Reg. | As the construction of project highway/structures could not proceed, as scheduled in the construction programme, submitted vide our letter no RCM PVR JV/MH PWD/2017-18/40, dated 02nd Jun 2018, we requested for the following. Annexure- i. Amendment of Appointment date (Please refer our letter no. RCM PVR JV/MH PWD/2018-19/151, date 30 Jan 2018) Annexure-I ii. Modification of date of milestone(s) by 120 days (Please refer our Letter no. RCM PVR JV/MH PWD/2018-19/165, date 10th Feb 2018) Annexure-III In your reply to our letter dated 10th Feb 2018 stated above, reference has been made to article/clause 10.1.3 We submit that a) as per terms of contract conditions, we submitted the original construction programme vide letter no. RCM PVR JV/MH PWD/2017-18/40, Dated 02nd Jun 2018 and Annexure-I b) the revised programme, as per article 10.1.3, vide letter no. RCM PVR JV/MH PWD/2018-19/235, date 02nd May 2018 guner regarding Appointed Date, in sl no. 3, you have stated that as the Appointed Date is declared, no EOT can be determined. We had a detailed discussion with the Team Leader on 03rd May 2018 and clarified the following. Schedule-A states that the site comprises of PROW width, which is the same as existing ROW, which implies that the land for 50.587 Km is already in possession of Authority. Please refer clause 5.2 (g) Annexure-V On good faith, The Appointed Date was accepted and encumbrances and existing utilities were recorded in Memorandum by Us. The statement is yet to be countersigned by Authority/Authority Engineer (Please refer our letter no. RCM PVR JV/MH PWD/2017-18/71, dated 10th August 2018). On commencement of works, we were intimated by revenue department of Maharashtra state (Tahsildar) that even the land on which the existing road is running is also not registered/alienated as a property/possession of PWD. Kindly refer our letter no. RCM PVR JV/MH PWD/2018-19/151, date 10th Jan 2018(Annexure-II). The reason for acceptance of Appointed Date was only good faith and the ground reality, when enlightened to Authority, the Authority commenced action for acquisition of entire land width. Kindly refer clause 5.2(h) regarding the commitment of Authority which is a warranty given by Authority Annexure-VI(a,b) The scope of the project {21.a) states that construction, as specified in schedule B & C. will conform to schedule D the technical specification. In order to achieve 80 Kmph in plain terrain & 40 kmph in hilly terrain (reference schedule B of 2.2 page 174) all the kinks, sharp Curves require geometric improvements. Hence, when the horizontal alignment gets changed/improved. deviating from the existing center line, such shifting of center line, results in additional land width requirement. Annexure-VII The assumption and decision of Authority/DPR consultants to procure land for major realignment (only for 5.35 Km) is absurd due to the reasons explained above. You have rightly stated in sl. No 4 referring to article 10.5.2/10.5.1 regarding the entitlement of extension of time by the contractor which is applicable as the works were affected and the Mile Stone could not be achieved. The details of programme of work achieved quantities etc are regularly furnished in all MPR's. The deficit in financial progress is also reflected in the S-Curve forming part of MPR. We reproduce the summary here under: SI.No. Targeted - Achieved Up to Sep 4.37 - 4.35 Oct 8.98 - 8.295 Nov 16.44 - 11.491 Dec 25.9 - 14.691 Jan 33.65 - 21.002 Feb 44.29 - 24.322 March 54.45 - 34.270 Please refer page 15 of MPR wherein a tabulation showing the affected length stretches are given in detail (copy enclosed all MPR) enable a proper evaluation of the time lost. | FALSE | real_data
Delay due to Change of Scope approval | Change of Scope | Delay in approval of COS is the second major reason | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/5. Reply to request for expediting slow process of works 06.12.2018.pdf | Reply to request for expediting Slow Progress of works — Reg. | Respected Sir, This is with reference to the above subject and your above referred letter requesting to expedite the progress of works. We wish to draw your kind attention to our letters ref (2) and (3) above, through which we had submitted a detailed analysis of the delay events and their impact on progress. So far determination of EOT is awaited. We also request your kind attention to our letter to the EE, ref (4) above, requesting to issue COS notice for additional utility ducts. As you are aware, the pending land acquisition is the first of the major reasons for stoppage of work at various locations / various stages. Delay in approval of COS is the second major reason, apart from other delay events, for not being able to proceed with unobstructed work fronts. We request you to look into the above issues and resolve at an early date, which will enhance the progress at site. | FALSE | real_data
Delay due to Change of Scope approval | EoT; Payments; Dispute Resolution; Change of Scope | A total length of 34.35 Km was affected due to pending COS decisions/orders. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/7. Status of Work Front Available 26.12.2018.pdf | Status of work front available — Reg. | Respected Sir, This is with reference to your letter #(1) above regarding the status of work front available, wherein it was mentioned that a length of 41.075 Km was available for work. In this regard, please refer to our letter ref (7) above requesting extension of time & revision of milestones. A total length of 34.35 Km was affected due to pending COS decisions/orders. Please refer to letters (2) to (6) & (8) above regarding structures identified under COS. A total of 269 structures are approved by the AE for Change of Scope. You will appreciate the fact that, despite our repeated requests, COS orders for these structures are still pending. Authority and Authority’s Engineer categorically specified not to take up any COS works until COS orders issued. In addition to this, we continue to get affected by the perennial land acquisition issues, as the property owners have obstructed execution of works. The details are explained in our letter ref (7) above. Apropos to the above, we wish to mention you that, after accounting for all the encroachments and encumbrances as on date, we are able to execute works at very few locations which covers a length of around 22.237 Kms. | FALSE | real_data
Delay due to Change of Scope approval | EoT; Payments; Dispute Resolution; Change of Scope | From the above. if is clear that pending COS orders/decisions & LA problems are the reasons for slow progress of works- Even our existing resources are being subjected to ungainful deployment, due to jack of work fronts, as already intimated in our letter ref (2} above. At this juncture. mobilizing additional resources wi51 only add to the huge financial loss already incurred by us. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/10. Regarding slow progress of work 31.01.2019.pdf | Regarding Slow progress of Work | This is with reference to your letter ref (1) above, regarding slow progress of work, wherein you have instructed us to mobilise additional resources in order to complete the works within the stipulated time. We invite your kind attention to our letter ref (3) above; we have clearly mentioned that works in 34.35 Km of the project are held up due to pending COS orders/decisions. Further, we have also mentioned that works are also hampered due to Land Acquisition (LA) problems at various stretches. From the above, it is clear that pending COS orders/decisions & LA problems are the reasons for slow progress of works. Even our existing resources are being subjected to unfruitful deployment, due to lack of work fronts, as already intimated in our letter ref (2) above. At this juncture, mobilising additional resources will only add to the huge financial loss already incurred by us. In view of the above, we request you to pursue the Authority on issuing COS orders and handing over balance ROW, free of encroachments and encumbrances. | FALSE | real_data
Intimation of Change in law | Payments | Change in Law circular bearing No.3.3.26/2022 dated 23-11-2022 clarifying applicability of GST in EPC Contracts. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-6/20221124_AE_SPK_1195_Clarification regarding calculation of GST against change in rates from 18.07.2022 on the activity of construction of road in case of EPC projects under Change in Law.pdf | Clarification regarding calculation of GST against change in rates from 18.07.2022 on the activity of construction of road in case of EPC projects under Change in Law -Reg. | Please find enclosed herewith a Circular bearing No. 3.3.26/2022 dated 23 November 2022 stated as Ref. No. 1 from NHAI clarifying the applicability of GST on EPC Contracts. Hence it is hereby asked to submit the upcoming IPC’s duly following GST calculations accordingly. This is for your kind information and necessary actions. | FALSE | real_data
Intimation of Change in law | Payments | The Change in GST Rate from 12% to 18% on the work contracts falls under the change in Law | synthetic_template_20250913 | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajapet from km 71.015 to107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode —Change in law pursuant to Clause 19.17 of the Agreement — Notice of changes in GST rate on Works Contract from 12% to 18% w.e.f 18th July 2022- Reg. | Please note that In reference to the subject matter and Contractor Letter No. SPK/ NHAI/ PD/ NH-48/ 2022/ 023 Dated 22.07.2022 vide which Contractor submitted request to consider change in GST rates from 12% to 18% under “Clause 19.17 Change in law” of Contract Agreement. As per the meeting of GST Council, held on 28'-29' June 2022, in which considerable changes in percentage for GST imposed on Goods & Construction work of Roads, Bridges, Railway, Metro etc. made. In this regard it is submitted that as per provision of Contract Agreement Article No. 19.17 & as defined in Article 28(Definition), which states that: Definition: - “Change in Law” means the occurrence of any of the following after the Base date: (a) the enactment of any new Indian law; (b) the repeal, modification or re-enactment of any existing Indian law; (c) the commencement of any Indian law which has not entered in to effect until the Base Date; (d) a change in the interpretation or application of any Indian law by a judgement of a court of record which has become final, conclusive and binding, as compared to such interception or application by a court of record prior to the Base Date. Change in Law 19.17.1, 19.17.1 If a result of Change in Law, the Contractor suffers any additional costs in the execution of the Works or in relation to the performance of its other obligation under this agreement, the Contractor shall, within 15 (fifteen) days from the date it becomes reasonably aware of such addition in cost, notify the Authority with a copy to the Authority's Engineer of such additional cost due to change in Law. 19.17.2 If a result of Change in Law, the Contractor benefits from any reduction in costs for the execution of this Agreement or in the accordance with the provision of this Agreement, either Party shall, within 15 (fifteen) days from the date it becomes reasonably aware of such reduction in cost, notify the other party with a copy to the Authority's Engineer of such reduction in cost due to Change in Law. In view of the above provision, the change in GST Rate from 12% to 18% on the work contracts falls under Change in Law as per definition given under (b) “the repeal, modification of re-enactment of any existing Indian law; Accordingly, Contractor initiated to the Authority under the provision Contract Article No. 19.17.1 of the CA. The Contractor needs to submit the documents under the implication of this change to the Authority under the provisional time mentioned in the Contract Agreement for further review of this case as per the provisions of C.A. Thank you for your attention to this matter. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Intimation of Change in law | Payments | The Change in GST Rate from 12% to 18% on the work contracts falls under the change in Law | synthetic_template_20250913 | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajapet from km 71.015 to107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode —Change in law pursuant to Clause 19.17 of the Agreement — Notice of changes in GST rate on Works Contract from 12% to 18% w.e.f 18th July 2022- Reg. | In reference to the subject matter and Contractor Letter No. SPK/ NHAI/ PD/ NH-48/ 2022/ 023 Dated 22.07.2022 vide which Contractor submitted request to consider change in GST rates from 12% to 18% under “Clause 19.17 Change in law” of Contract Agreement. As per the meeting of GST Council, held on 28'-29' June 2022, in which considerable changes in percentage for GST imposed on Goods & Construction work of Roads, Bridges, Railway, Metro etc. made. In this regard it is submitted that as per provision of Contract Agreement Article No. 19.17 & as defined in Article 28(Definition), which states that: Definition: - “Change in Law” means the occurrence of any of the following after the Base date: (a) the enactment of any new Indian law; (b) the repeal, modification or re-enactment of any existing Indian law; (c) the commencement of any Indian law which has not entered in to effect until the Base Date; (d) a change in the interpretation or application of any Indian law by a judgement of a court of record which has become final, conclusive and binding, as compared to such interception or application by a court of record prior to the Base Date. Change in Law 19.17.1, 19.17.1 If a result of Change in Law, the Contractor suffers any additional costs in the execution of the Works or in relation to the performance of its other obligation under this agreement, the Contractor shall, within 15 (fifteen) days from the date it becomes reasonably aware of such addition in cost, notify the Authority with a copy to the Authority's Engineer of such additional cost due to change in Law. 19.17.2 If a result of Change in Law, the Contractor benefits from any reduction in costs for the execution of this Agreement or in the accordance with the provision of this Agreement, either Party shall, within 15 (fifteen) days from the date it becomes reasonably aware of such reduction in cost, notify the other party with a copy to the Authority's Engineer of such reduction in cost due to Change in Law. In view of the above provision, the change in GST Rate from 12% to 18% on the work contracts falls under Change in Law as per definition given under (b) “the repeal, modification of re-enactment of any existing Indian law; Accordingly, Contractor initiated to the Authority under the provision Contract Article No. 19.17.1 of the CA. The Contractor needs to submit the documents under the implication of this change to the Authority under the provisional time mentioned in the Contract Agreement for further review of this case as per the provisions of C.A. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Intimation of Change in law | Payments | Change in Law circular bearing No.3.3.26/2022 dated 23-11-2022 clarifying applicability of GST in EPC Contracts. | synthetic_template_20250913 | Clarification regarding calculation of GST against change in rates from 18.07.2022 on the activity of construction of road in case of EPC projects under Change in Law -Reg. | Please find enclosed herewith a Circular bearing No. 3.3.26/2022 dated 23 November 2022 stated as Ref. No. 1 from NHAI clarifying the applicability of GST on EPC Contracts. Hence it is hereby asked to submit the upcoming IPC’s duly following GST calculations accordingly. This is for your kind information and necessary actions. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Intimation of Change in law | Payments | Change in Law circular bearing No.3.3.26/2022 dated 23-11-2022 clarifying applicability of GST in EPC Contracts. | synthetic_template_20250913 | Clarification regarding calculation of GST against change in rates from 18.07.2022 on the activity of construction of road in case of EPC projects under Change in Law -Reg. | Please find enclosed herewith a Circular bearing No. 3.3.26/2022 dated 23 November 2022 stated as Ref. No. 1 from NHAI clarifying the applicability of GST on EPC Contracts. Hence it is hereby asked to submit the upcoming IPC’s duly following GST calculations accordingly. This is for your kind information and necessary actions. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Intimation of Change in law | Payments | The Change in GST Rate from 12% to 18% on the work contracts falls under the change in Law | synthetic_template_20250913 | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajapet from km 71.015 to107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode —Change in law pursuant to Clause 19.17 of the Agreement — Notice of changes in GST rate on Works Contract from 12% to 18% w.e.f 18th July 2022- Reg. | In reference to the subject matter and Contractor Letter No. SPK/ NHAI/ PD/ NH-48/ 2022/ 023 Dated 22.07.2022 vide which Contractor submitted request to consider change in GST rates from 12% to 18% under “Clause 19.17 Change in law” of Contract Agreement. As per the meeting of GST Council, held on 28'-29' June 2022, in which considerable changes in percentage for GST imposed on Goods & Construction work of Roads, Bridges, Railway, Metro etc. made. In this regard it is submitted that as per provision of Contract Agreement Article No. 19.17 & as defined in Article 28(Definition), which states that: Definition: - “Change in Law” means the occurrence of any of the following after the Base date: (a) the enactment of any new Indian law; (b) the repeal, modification or re-enactment of any existing Indian law; (c) the commencement of any Indian law which has not entered in to effect until the Base Date; (d) a change in the interpretation or application of any Indian law by a judgement of a court of record which has become final, conclusive and binding, as compared to such interception or application by a court of record prior to the Base Date. Change in Law 19.17.1, 19.17.1 If a result of Change in Law, the Contractor suffers any additional costs in the execution of the Works or in relation to the performance of its other obligation under this agreement, the Contractor shall, within 15 (fifteen) days from the date it becomes reasonably aware of such addition in cost, notify the Authority with a copy to the Authority's Engineer of such additional cost due to change in Law. 19.17.2 If a result of Change in Law, the Contractor benefits from any reduction in costs for the execution of this Agreement or in the accordance with the provision of this Agreement, either Party shall, within 15 (fifteen) days from the date it becomes reasonably aware of such reduction in cost, notify the other party with a copy to the Authority's Engineer of such reduction in cost due to Change in Law. In view of the above provision, the change in GST Rate from 12% to 18% on the work contracts falls under Change in Law as per definition given under (b) “the repeal, modification of re-enactment of any existing Indian law; Accordingly, Contractor initiated to the Authority under the provision Contract Article No. 19.17.1 of the CA. The Contractor needs to submit the documents under the implication of this change to the Authority under the provisional time mentioned in the Contract Agreement for further review of this case as per the provisions of C.A. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Change in law reimbursement | Payments | Under the circumstances, we hereby kindly request you to reimburse us a sum of Rs.73,83,512/- towards GST Tax paid (as per Table 1 Rs.73,83,512/-) and Rs.20,04,065/- towards interest payable for the delayed payment of above GST thereby total of GST and Taxes paid was amounting to Rs.93,87,577/- being the amount paid to the Government by ourselves on your behalf at the earliest. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-6/20230121_SPK_AE_049_Change in Law pursuant to Clause 19.17 of CA Notice of changes in GST rate on Works Contract from 12% to 18% w.e.f 18th July 2022 - Reimbursement of additional 6% GST requested - Reg..pdf | Six Laning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km.71+015 (Existing Km 71+000) to Km 107+091 (Existing Km 107+068) on EPC Mode in the state of Tamil Nadu under NHDP Phase-V - Change in Law pursuant to Clause 19.17 of CA: Notice of changes in GST rate on Works Contract from 12% to 18% wef 18th July 2022 - Reimbursement of additional 6% GST requested - Reg. | This is w.r.t payment towards increase of GST from 12% to 18% w.e.f 18th July 2022 on works contract which has been notified from our end under Change in law Clause 19.17 of the Contract Agreement vide ref (2) above and the same was recommended in principle by the Authority Engineer vide ref (3) above to the Authority. The following payments towards increase in GST are yet to be released by the Authority: (i) Vide letter No Letter No. SPK/KW/SAIC/NH-48/2022/169 - Dt - 22.11.2022 — the EPC Contractor had submitted Auditor Certificate for GST (CGST & SGST) along with paid certificate towards SPS-24 and Requested for Reimbursement of 6% towards Additional Paid GST @ 6 % for an amount of Rs.34,29,025 /-Rupees Thirty-Four Lakhs Twenty-Nine Thousand and twenty-five only). (ii) Vide letter No Letter No. SPK/KW/SAIC/NH-48/2022/189 - Dt — 30.12.2022 — the EPC Contractor had submitted Auditor Certificate for GST (CGST & SGST) along with paid certificate towards SPS - 25 and requested for reimbursement of 6% towards Additional Paid GST @ 6 % to reimburse the GST @ 6% for an amount of Rs.25,92,679/- (Rupees Twenty-Five Lakhs Ninety-Two Thousand and Six hundred and Seventy-Nine only) The Paid Certificates as listed above has been verified by the Authority’s Engineer and has recommended for payment vide their letters cited at (5) & (6) which has also been uploaded in the NHAI DATA Lake for payment procedures. On follow up with the FARO, NHAI RO Office, Chennai it has been informed that the payment towards additional GST @ 6 % requires the necessary approvals of the concerned Regional Officer. In view of the above it is kindly requested to recommend the above payments to the Regional Officer for necessary approval and subsequent reimbursement of the same. | FALSE | real_data
Change in law reimbursement | Payments | We request you to recommend the additional impact to Authority for his sanction and disbursement of the compensation of additional cost incurred, which was unforeseen, at the time of bidding. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/6. Implementation of CGST Act,2017-standard operating procedure-change in law clause 19.17, 33 Cr 13.12.2018.pdf | Rehabilitation and Up-gradation of Paithan (Pategaon) — Mungi — Hadgaon - Bodhegaon- Ladjalgaon —- Ghogaspargaon — Phulsangvi — Ukhandachakla — Dahiwandi - Shirur to 2-Lane with paved shoulder (Project Length 55.937 Km) on EPC basis in the state of Maharashtra (Package ¦ — 56 KM) — Implementation of CGST Act, 2017 - Standard operating procedure - change in law Clause 19.17, 33 Crores - Reg | Please refer our letter, 2 cited above, notifying the impact of GST under change in law. As per the instruction received from Government of India Ministry of Road Transport and Highway dated 19th November 2018, we have calculated the extra cost impact, due to implementation of new GST Act 2017. We are submitting the detailed cost impact of new GST Act 2017 for your review and approvals, as per the procedure mentioned in the reference (1) stated above. We request you to recommend the additional impact to Authority for his sanction and disbursement of the compensation of additional cost incurred, which was unforeseen, at the time of bidding. | FALSE | real_data
Change in law reimbursement | Payments | Further to the letters above, please find enclosed herewith the certificate issued by our chartered accountant M/S VASG & Associates Chartered Accountants on the additional liability due to change in law, duly quantified / assessed | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/12. GST-Change in law-certification by chartered accountants 26.02.2019.pdf | Rehabilitation and Up-gradation of Paithan (Pategaon) —- Mungi —- Hadgaon — Bodhegaon- Ladjaigaon - Ghogaspargaon = Phulsangvi = Ukhandachakia = Dahiwandi — Shirur to 2-Lane with paved shoulder (Project Length 55.937 Km) on EPC basis in the state of Maharashtra (Package ¦ - 56 KM) -— GST - Change in Law - certification by Chartered Accountants — Reg. | Further to the letters above, please find enclosed herewith the certificate issued by our chartered accountant M/S VASG & Associates Chartered Accountants on the additional liability due to change in law, duly quantified / assessed We now request you to recommend to the Authority for release of the additional cost incurred, periodically, as per article 19.17 of the contract agreement. | FALSE | real_data
Change in law reimbursement | Payments | The Recovery of the additional permit and seinorage fees constitutes as a change in law as per clause 19.17 of the contract agreement. An additional sum amount of Rs 6,69,96,1851- (Six Crores Sixty Nine Lakhs Ninety Six Thousand One Hundred and Ninety Five Only) has been recovered till date and the same is yet to be reimbursed. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-2/5. 20240601_291_Cont_AE_Release of Excess Seinorage Fee and Permit Fee-Reg.pdf | Release of Excess Seinorage Fee and Permit Fee- Reg. | The Mines & Geological Department, Government of Telangana revised the seinorge fee of the Rough Stone used for construction and introduced a permit fee from 01.04.2022 by government Orders No. 18 — pertaining to Revision of Sinorage Fee and Government Orders No.21 — pertaining to levy of permit fee. The revised fees are tabulated below. SI. Type of Royalties Rate before Rate after No. Revision per Cum 1 Seinorage for Rough Stone 75 97.5 2 DMF 22.5 29.25 3 SMET 1.5 1.95 4 Permit FEE 0 78 Following the revision of the seinorage fee and introduction of permit fee by the Telangana Government Mines & Geology Department from 01.04.2022, The office of the Authority has been recovering the revised royalty fees from the IPC Bills. The Recovery of the additional permit and seinorage fees constitutes as a change in law as per clause 1917 of the contract agreement and should be reimbursed to the contractor. An additional sum amount of Rs 6,69,96,185 /- (Six Crores Sixty Nine Lakhs Ninety Six Thousand One Hundred and Ninety Five Only) has been recovered till date and the same is yet to be reimbursed. Details of the same are enclosed for your kind perusal and necessary action please. | FALSE | real_data
Descoping of works under original scope | Payments; Dispute Resolution; Change of Scope | Accordingly, the EPC Contractor is hereby requesting for descoping of the Toll plaza/User fee Plaza as per Clause 2.1 Schedule-C and Schedule-H (Page 188). | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-6/20231124_SPK_AE_311_Request to Descope Toll User Fee Plaza to be constructed as per Clause 2.1 Schedule-C and Schedule - H (Page 188) - Reg..pdf | Request to Descope Toll /User Fee Plaza to be constructed as per Clause 2.1 Schedule-C and Schedule - H (Page 188) - Reg. | 1. Pursuant to Clause 2.1 as per Schedule - C of the Contract Agreement the existing Toll Plaza shall be modified/widened to 24 lanes Toll Plaza including other construction of other facilities as per specification mentioned in Scheduled-D. A weightage of 4.14 % is provided in Schedule H of Contract Agreement amounting to Rs.22,08,13,814/- for construction of Toll Plaza including CC pavement, Barrier, High mast Lighting and overhead Sign Boards has been provisioned. 2. As per NHAI/Policy Guidelines/Management of Plaza/2021 Policy Circular No 17.5.82 dated 24.05.2021 issued by the Authority/NHAI and based on the guidelines, the EPC Contractor finalised the layout for the Toll Plaza with 8+8 lanes (Skew) without any land acquisition and submitted the Cost Estimate proposal vide ref (2) as requested by the Authority Engineer, which was reviewed by the Authority Engineer and forwarded to the Authority vide letter cited at (3) above. 3. Further the EPC contractor would like to highlight the following below: > BCE Package - Bangalore - Chennai Expressway - 4packages of Bangalore Chennai Expressway, Hon’ble Minister of Road Transport & Highways, Government of India on 07.09.2023 directed to expedite works and complete by Feb 2024.(Refer.NHAI/11013/267/2021/ROChennai/3044 dated 30.10.2023). Therefore, the existing Toll Plaza on Karaipettai-Walajapet Stretch will suffice to cater the balance meagre traffic since the number of lanes at the Toll plaza has been derived for the forecasted traffic in Design year (10years). The forecast traffic is converted to Peak Hour Peak Direction (PHPD) traffic to derive the number of Toll lanes as below: - Total Tollable Traffic in the Year 2022 (Base Year Traffic) is 29389 - Total Tollable Traffic in the Year 2022 (Opening Year Traffic) 29389 - Total Tollable Traffic in the Year 2031 - A (10 Years Traffic) 45591 - Peak Hour Factor-B is 10% - Direction Split-Percentage of vehicles moving in both Directions-C is 50% - Therefore, Peak Hour Per Direction (AxBxC) per direction is 2280 - Service RateNumber of Lanes in one directionToll capacity of Individual Lane (ETC/FastTag) 400Veh/Hr - Number of Vehicles Allowed to cross ETC lanes 2400 - Capacity Assessment for both direction (For 10years) -12 Therefore, the Finalised Total No of Lanes per Direction is 6 Nos i.e 6+6(12 lanes) (Reference AE letter No.883 dated 17.02.2022) without considering the traffic diverted on to the BCE (Bangalore - Chennai Expressway). Once BCE is open to traffic, there will be substantial reduction in the traffic along our project highway as the road users travelling from Chennai and heading towards Bangalore would prefer to use BCE corridor as its seamless and fully access controlled. Accordingly, the existing 5+5 lane at Toll Plaza (Chennasamudram) will be able to cater the remaining Tollable Traffic in future. > GPS Tagging - GPS-based Toll collection systems likely to replace existing toll plazas in the next 6 months as per Hon’ble Minister of Road Transport & Highways, Government of India (Mar 2023) in view of these upgraded facility to be implemented by NHAI /MoRTH in coming years upgrading the current Toll Plaza (Chennasamudram) from existing 5+5 lanes to 8+8 lanes may be unnecessary or infructuous expenditure. > As Policy Guidelines for Toll Plaza issued by the Authority /NHAI on 24.05.2021 and based on the guidelines, the EPC Contractor finalised the layout for the Toll Plaza with 8+8 lanes (Skew) without any land acquisition and submitted the Cost Estimate proposal as requested by the Authority Engineer, which was reviewed and forwarded to the Authority vide letter cited at (3) above; however further communication or recommendation in this regard has not been received till date from the Authority /NHAI. 4. Accordingly, the EPC Contractor is hereby requesting for descoping of the Toll Plaza /User Fee Plaza to be constructed as per Clause 2.1 Schedule-C and Schedule-H (Page 188) which is now to be proposed as COS (CHANGE OF SCOPE) taking into consideration as above para to avoid the unnecessary or infructuous expenditure to Authority. | FALSE | real_data
Descoping of works under original scope | Dispute Resolution | The computation of cost estimate for negative scope of shall be carried out in the following manner, The above said pipe culvert at Km.103+473 could not be identified at site. | synthetic_template_20250913 | Requisition for De-scoping of Hume Pipe Culverts 2 +1 Total (3Nos) as per Schedule - B which is not existing on ground at project site — Reg. | Dear Sir, With reference to the above subject, the Authority Engineer had communicated to the Authority that the following Hume Pipe Culverts are missing based on the site verification. The requirement at the project site is being submitted for your kind information and further advice. The details of the pipe culverts are as follows: (i) Clause 6.13 (b) of Schedule-B (Page 143): S1.No Exiting ¦ Proposed Existing ¦ Proposed Existing Proposed Chainage ¦ Chainage ¦ Structure ¦ Structure Span Arrangement Arrangement 33 84+099 84+117 HPC HPC 1 Row of 1 Row of 34 844+115 844133 HPC ¦ HPC 0.90m Dia 1.20m Dia Further to the above missing Hume Pipe Culverts, one more Pipe Culvert missing is as listed as below: (ii) Clause 10(a) of Schedule-A (Page 125) S1.No Exiting Proposed Type Width Dia Chainage Chainage ¦ 59 103+450 103+461 ¦ Pipe Culvert 2x2 lane 1 Row of 0.60m Dia (iii) Clause 6.13 (a) of Schedule-B (Page 142): Sl. ¦ Exiting Proposed ¦ Existing Proposed ¦ Proposed Span Remarks No ¦ Chainage ¦ Chainage ¦ Structure ¦ Structure ¦ Arrangement 10 ¦ 103+450 ¦ 103+473 HPC HPC 1 Row of 1.2m ¦ Reconstruction ¦ Dia with Pipe Culvert The above said Pipe Culvert at Km.103+473 could not be identified at site and the same is also submitted for de-scoping along with the above 2 Nos of Hume Pipe Culverts. This is for information that joint site verification at the above location and the facts communicated above are justified. Some photographs at the above-mentioned location of Km.103+473 are herewith attached for reference. The computation of cost estimate for negative scope of work shall be carried out in the following manner: (i) Hume Pipe Culverts at Km.84+117 & Km.84+133 - 1.2m diameter Pipe laying in the widening portion. (ii) Hume Pipe Culverts at Km.103+473 — Reconstruction of pipe culvert with 1.2m dia for the entire barrel length. We hereby request the Authority Engineer to intimate and remind the Authority for further necessary action. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Descoping of works under original scope | Dispute Resolution | Accordingly, the EPC Contractor is hereby requesting for descoping of the Toll plaza/User fee Plaza as per Clause 2.1 Schedule-C and Schedule-H (Page 188). | synthetic_template_20250913 | Request to Descope Toll /User Fee Plaza to be constructed as per Clause 2.1 Schedule-C and Schedule - H (Page 188) - Reg. | We hereby confirm that 1. Pursuant to Clause 2.1 as per Schedule - C of the Contract Agreement the existing Toll Plaza shall be modified/widened to 24 lanes Toll Plaza including other construction of other facilities as per specification mentioned in Scheduled-D. A weightage of 4.14 % is provided in Schedule H of Contract Agreement amounting to Rs.22,08,13,814/- for construction of Toll Plaza including CC pavement, Barrier, High mast Lighting and overhead Sign Boards has been provisioned. 2. As per NHAI/Policy Guidelines/Management of Plaza/2021 Policy Circular No 17.5.82 dated 24.05.2021 issued by the Authority/NHAI and based on the guidelines, the EPC Contractor finalised the layout for the Toll Plaza with 8+8 lanes (Skew) without any land acquisition and submitted the Cost Estimate proposal vide ref (2) as requested by the Authority Engineer, which was reviewed by the Authority Engineer and forwarded to the Authority vide letter cited at (3) above. 3. Further the EPC contractor would like to highlight the following below: > BCE Package - Bangalore - Chennai Expressway - 4packages of Bangalore Chennai Expressway, Hon’ble Minister of Road Transport & Highways, Government of India on 07.09.2023 directed to expedite works and complete by Feb 2024.(Refer.NHAI/11013/267/2021/ROChennai/3044 dated 30.10.2023). Therefore, the existing Toll Plaza on Karaipettai-Walajapet Stretch will suffice to cater the balance meagre traffic since the number of lanes at the Toll plaza has been derived for the forecasted traffic in Design year (10years). The forecast traffic is converted to Peak Hour Peak Direction (PHPD) traffic to derive the number of Toll lanes as below: - Total Tollable Traffic in the Year 2022 (Base Year Traffic) is 29389 - Total Tollable Traffic in the Year 2022 (Opening Year Traffic) 29389 - Total Tollable Traffic in the Year 2031 - A (10 Years Traffic) 45591 - Peak Hour Factor-B is 10% - Direction Split-Percentage of vehicles moving in both Directions-C is 50% - Therefore, Peak Hour Per Direction (AxBxC) per direction is 2280 - Service RateNumber of Lanes in one directionToll capacity of Individual Lane (ETC/FastTag) 400Veh/Hr - Number of Vehicles Allowed to cross ETC lanes 2400 - Capacity Assessment for both direction (For 10years) -12 Therefore, the Finalised Total No of Lanes per Direction is 6 Nos i.e 6+6(12 lanes) (Reference AE letter No.883 dated 17.02.2022) without considering the traffic diverted on to the BCE (Bangalore - Chennai Expressway). Once BCE is open to traffic, there will be substantial reduction in the traffic along our project highway as the road users travelling from Chennai and heading towards Bangalore would prefer to use BCE corridor as its seamless and fully access controlled. Accordingly, the existing 5+5 lane at Toll Plaza (Chennasamudram) will be able to cater the remaining Tollable Traffic in future. > GPS Tagging - GPS-based Toll collection systems likely to replace existing toll plazas in the next 6 months as per Hon’ble Minister of Road Transport & Highways, Government of India (Mar 2023) in view of these upgraded facility to be implemented by NHAI /MoRTH in coming years upgrading the current Toll Plaza (Chennasamudram) from existing 5+5 lanes to 8+8 lanes may be unnecessary or infructuous expenditure. > As Policy Guidelines for Toll Plaza issued by the Authority /NHAI on 24.05.2021 and based on the guidelines, the EPC Contractor finalised the layout for the Toll Plaza with 8+8 lanes (Skew) without any land acquisition and submitted the Cost Estimate proposal as requested by the Authority Engineer, which was reviewed and forwarded to the Authority vide letter cited at (3) above; however further communication or recommendation in this regard has not been received till date from the Authority /NHAI. 4. Accordingly, the EPC Contractor is hereby requesting for descoping of the Toll Plaza /User Fee Plaza to be constructed as per Clause 2.1 Schedule-C and Schedule-H (Page 188) which is now to be proposed as COS (CHANGE OF SCOPE) taking into consideration as above para to avoid the unnecessary or infructuous expenditure to Authority. Thank you for your attention to this matter. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Descoping of works under original scope | Payments | Accordingly, the EPC Contractor is hereby requesting for descoping of the Toll plaza/User fee Plaza as per Clause 2.1 Schedule-C and Schedule-H (Page 188). | synthetic_template_20250913 | Request to Descope Toll /User Fee Plaza to be constructed as per Clause 2.1 Schedule-C and Schedule - H (Page 188) - Reg. | We would like to inform you that 1. Pursuant to Clause 2.1 as per Schedule - C of the Contract Agreement the existing Toll Plaza shall be modified/widened to 24 lanes Toll Plaza including other construction of other facilities as per specification mentioned in Scheduled-D. A weightage of 4.14 % is provided in Schedule H of Contract Agreement amounting to Rs.22,08,13,814/- for construction of Toll Plaza including CC pavement, Barrier, High mast Lighting and overhead Sign Boards has been provisioned. 2. As per NHAI/Policy Guidelines/Management of Plaza/2021 Policy Circular No 17.5.82 dated 24.05.2021 issued by the Authority/NHAI and based on the guidelines, the EPC Contractor finalised the layout for the Toll Plaza with 8+8 lanes (Skew) without any land acquisition and submitted the Cost Estimate proposal vide ref (2) as requested by the Authority Engineer, which was reviewed by the Authority Engineer and forwarded to the Authority vide letter cited at (3) above. 3. Further the EPC contractor would like to highlight the following below: > BCE Package - Bangalore - Chennai Expressway - 4packages of Bangalore Chennai Expressway, Hon’ble Minister of Road Transport & Highways, Government of India on 07.09.2023 directed to expedite works and complete by Feb 2024.(Refer.NHAI/11013/267/2021/ROChennai/3044 dated 30.10.2023). Therefore, the existing Toll Plaza on Karaipettai-Walajapet Stretch will suffice to cater the balance meagre traffic since the number of lanes at the Toll plaza has been derived for the forecasted traffic in Design year (10years). The forecast traffic is converted to Peak Hour Peak Direction (PHPD) traffic to derive the number of Toll lanes as below: - Total Tollable Traffic in the Year 2022 (Base Year Traffic) is 29389 - Total Tollable Traffic in the Year 2022 (Opening Year Traffic) 29389 - Total Tollable Traffic in the Year 2031 - A (10 Years Traffic) 45591 - Peak Hour Factor-B is 10% - Direction Split-Percentage of vehicles moving in both Directions-C is 50% - Therefore, Peak Hour Per Direction (AxBxC) per direction is 2280 - Service RateNumber of Lanes in one directionToll capacity of Individual Lane (ETC/FastTag) 400Veh/Hr - Number of Vehicles Allowed to cross ETC lanes 2400 - Capacity Assessment for both direction (For 10years) -12 Therefore, the Finalised Total No of Lanes per Direction is 6 Nos i.e 6+6(12 lanes) (Reference AE letter No.883 dated 17.02.2022) without considering the traffic diverted on to the BCE (Bangalore - Chennai Expressway). Once BCE is open to traffic, there will be substantial reduction in the traffic along our project highway as the road users travelling from Chennai and heading towards Bangalore would prefer to use BCE corridor as its seamless and fully access controlled. Accordingly, the existing 5+5 lane at Toll Plaza (Chennasamudram) will be able to cater the remaining Tollable Traffic in future. > GPS Tagging - GPS-based Toll collection systems likely to replace existing toll plazas in the next 6 months as per Hon’ble Minister of Road Transport & Highways, Government of India (Mar 2023) in view of these upgraded facility to be implemented by NHAI /MoRTH in coming years upgrading the current Toll Plaza (Chennasamudram) from existing 5+5 lanes to 8+8 lanes may be unnecessary or infructuous expenditure. > As Policy Guidelines for Toll Plaza issued by the Authority /NHAI on 24.05.2021 and based on the guidelines, the EPC Contractor finalised the layout for the Toll Plaza with 8+8 lanes (Skew) without any land acquisition and submitted the Cost Estimate proposal as requested by the Authority Engineer, which was reviewed and forwarded to the Authority vide letter cited at (3) above; however further communication or recommendation in this regard has not been received till date from the Authority /NHAI. 4. Accordingly, the EPC Contractor is hereby requesting for descoping of the Toll Plaza /User Fee Plaza to be constructed as per Clause 2.1 Schedule-C and Schedule-H (Page 188) which is now to be proposed as COS (CHANGE OF SCOPE) taking into consideration as above para to avoid the unnecessary or infructuous expenditure to Authority. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Descoping of works under original scope | Payments | The computation of cost estimate for negative scope of shall be carried out in the following manner, The above said pipe culvert at Km.103+473 could not be identified at site. | synthetic_template_20250913 | Requisition for De-scoping of Hume Pipe Culverts 2 +1 Total (3Nos) as per Schedule - B which is not existing on ground at project site — Reg. | Dear Sir, With reference to the above subject, the Authority Engineer had communicated to the Authority that the following Hume Pipe Culverts are missing based on the site verification. The requirement at the project site is being submitted for your kind information and further advice. The details of the pipe culverts are as follows: (i) Clause 6.13 (b) of Schedule-B (Page 143): S1.No Exiting ¦ Proposed Existing ¦ Proposed Existing Proposed Chainage ¦ Chainage ¦ Structure ¦ Structure Span Arrangement Arrangement 33 84+099 84+117 HPC HPC 1 Row of 1 Row of 34 844+115 844133 HPC ¦ HPC 0.90m Dia 1.20m Dia Further to the above missing Hume Pipe Culverts, one more Pipe Culvert missing is as listed as below: (ii) Clause 10(a) of Schedule-A (Page 125) S1.No Exiting Proposed Type Width Dia Chainage Chainage ¦ 59 103+450 103+461 ¦ Pipe Culvert 2x2 lane 1 Row of 0.60m Dia (iii) Clause 6.13 (a) of Schedule-B (Page 142): Sl. ¦ Exiting Proposed ¦ Existing Proposed ¦ Proposed Span Remarks No ¦ Chainage ¦ Chainage ¦ Structure ¦ Structure ¦ Arrangement 10 ¦ 103+450 ¦ 103+473 HPC HPC 1 Row of 1.2m ¦ Reconstruction ¦ Dia with Pipe Culvert The above said Pipe Culvert at Km.103+473 could not be identified at site and the same is also submitted for de-scoping along with the above 2 Nos of Hume Pipe Culverts. This is for information that joint site verification at the above location and the facts communicated above are justified. Some photographs at the above-mentioned location of Km.103+473 are herewith attached for reference. The computation of cost estimate for negative scope of work shall be carried out in the following manner: (i) Hume Pipe Culverts at Km.84+117 & Km.84+133 - 1.2m diameter Pipe laying in the widening portion. (ii) Hume Pipe Culverts at Km.103+473 — Reconstruction of pipe culvert with 1.2m dia for the entire barrel length. We hereby request the Authority Engineer to intimate and remind the Authority for further necessary action. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Descoping of works under original scope | Change of Scope | The computation of cost estimate for negative scope of shall be carried out in the following manner, The above said pipe culvert at Km.103+473 could not be identified at site. | synthetic_template_20250913 | Requisition for De-scoping of Hume Pipe Culverts 2 +1 Total (3Nos) as per Schedule - B which is not existing on ground at project site — Reg. | Dear Sir, With reference to the above subject, the Authority Engineer had communicated to the Authority that the following Hume Pipe Culverts are missing based on the site verification. The requirement at the project site is being submitted for your kind information and further advice. The details of the pipe culverts are as follows: (i) Clause 6.13 (b) of Schedule-B (Page 143): S1.No Exiting ¦ Proposed Existing ¦ Proposed Existing Proposed Chainage ¦ Chainage ¦ Structure ¦ Structure Span Arrangement Arrangement 33 84+099 84+117 HPC HPC 1 Row of 1 Row of 34 844+115 844133 HPC ¦ HPC 0.90m Dia 1.20m Dia Further to the above missing Hume Pipe Culverts, one more Pipe Culvert missing is as listed as below: (ii) Clause 10(a) of Schedule-A (Page 125) S1.No Exiting Proposed Type Width Dia Chainage Chainage ¦ 59 103+450 103+461 ¦ Pipe Culvert 2x2 lane 1 Row of 0.60m Dia (iii) Clause 6.13 (a) of Schedule-B (Page 142): Sl. ¦ Exiting Proposed ¦ Existing Proposed ¦ Proposed Span Remarks No ¦ Chainage ¦ Chainage ¦ Structure ¦ Structure ¦ Arrangement 10 ¦ 103+450 ¦ 103+473 HPC HPC 1 Row of 1.2m ¦ Reconstruction ¦ Dia with Pipe Culvert The above said Pipe Culvert at Km.103+473 could not be identified at site and the same is also submitted for de-scoping along with the above 2 Nos of Hume Pipe Culverts. This is for information that joint site verification at the above location and the facts communicated above are justified. Some photographs at the above-mentioned location of Km.103+473 are herewith attached for reference. The computation of cost estimate for negative scope of work shall be carried out in the following manner: (i) Hume Pipe Culverts at Km.84+117 & Km.84+133 - 1.2m diameter Pipe laying in the widening portion. (ii) Hume Pipe Culverts at Km.103+473 — Reconstruction of pipe culvert with 1.2m dia for the entire barrel length. We hereby request the Authority Engineer to intimate and remind the Authority for further necessary action. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Descoping of works under original scope | Change of Scope | The computation of cost estimate for negative scope of shall be carried out in the following manner, The above said pipe culvert at Km.103+473 could not be identified at site. | synthetic_template_20250913 | Requisition for De-scoping of Hume Pipe Culverts 2 +1 Total (3Nos) as per Schedule - B which is not existing on ground at project site — Reg. | Dear Sir, With reference to the above subject, the Authority Engineer had communicated to the Authority that the following Hume Pipe Culverts are missing based on the site verification. The requirement at the project site is being submitted for your kind information and further advice. The details of the pipe culverts are as follows: (i) Clause 6.13 (b) of Schedule-B (Page 143): S1.No Exiting ¦ Proposed Existing ¦ Proposed Existing Proposed Chainage ¦ Chainage ¦ Structure ¦ Structure Span Arrangement Arrangement 33 84+099 84+117 HPC HPC 1 Row of 1 Row of 34 844+115 844133 HPC ¦ HPC 0.90m Dia 1.20m Dia Further to the above missing Hume Pipe Culverts, one more Pipe Culvert missing is as listed as below: (ii) Clause 10(a) of Schedule-A (Page 125) S1.No Exiting Proposed Type Width Dia Chainage Chainage ¦ 59 103+450 103+461 ¦ Pipe Culvert 2x2 lane 1 Row of 0.60m Dia (iii) Clause 6.13 (a) of Schedule-B (Page 142): Sl. ¦ Exiting Proposed ¦ Existing Proposed ¦ Proposed Span Remarks No ¦ Chainage ¦ Chainage ¦ Structure ¦ Structure ¦ Arrangement 10 ¦ 103+450 ¦ 103+473 HPC HPC 1 Row of 1.2m ¦ Reconstruction ¦ Dia with Pipe Culvert The above said Pipe Culvert at Km.103+473 could not be identified at site and the same is also submitted for de-scoping along with the above 2 Nos of Hume Pipe Culverts. This is for information that joint site verification at the above location and the facts communicated above are justified. Some photographs at the above-mentioned location of Km.103+473 are herewith attached for reference. The computation of cost estimate for negative scope of work shall be carried out in the following manner: (i) Hume Pipe Culverts at Km.84+117 & Km.84+133 - 1.2m diameter Pipe laying in the widening portion. (ii) Hume Pipe Culverts at Km.103+473 — Reconstruction of pipe culvert with 1.2m dia for the entire barrel length. We hereby request the Authority Engineer to intimate and remind the Authority for further necessary action. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Stoppage of Works by locals/public | EoT; Authority's Obligations | We would like to bring to your kind attention that works on A2 side approach of LVUP@ Km.79/860 - COS location has been stopped by locals on 31.07.2024. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-6/20240802_SPK_PD_098_Brief Stoppage of works at A2 side approach of LVUP at Km.79860 - COS Location – Intimation of the same.pdf | Six laning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km. 71+015 (Existing km 71+000) to Km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - Brief Stoppage of works at A2 side approach of LVUP at Km.79/860 - COS Location - Intimation of the same - Reg. | 1. We would like to bring to your kind attention that works on A2 side approach of LVUP at Km.79/860 - COS Location has been stopped by locals on 31.07.2024 while RE wall approach works were in progress between Km 80+070 to Km 80+100. 2. The local people insisted for construction of LVUP at originally proposed location viz. Thiruppukuzhi junction (Km.80+060) and also demanded that the present access from crossroad to Thirupukuzhi temple, School and Ration Shops shall not be closed/blocked by way of RE wall construction activities. Necessary photographs are herewith enclosed as Annexure 1. 3. We immediately intimated this incident to the nearby Police Station and police officials also came to the site. The police officials also spoke to local people, and it was agreed that as a stop gap solution, the excavated portion will be backfilled and access shall be restored by temporarily leaving a gap of around 30m near Thirupukuzhi junction. Now the EPC Contractor is proceeding with balance approach works on A2 side. 4. As suggested by the Authority, we made sincere attempts to resolve the issue on our own and could succeed partially. We will continue our liasoning with police officials/local people for complete resolving of this issue. 5. District Collector, Kancheepuram vide letter No 0043 dated 27.04.2024 has also replied to the Project Director PIU Kancheepuram that consent has been accorded towards changing the location for Construction of LVUP from Thiruputkuzhi (Km80+060) to Musaravakkam Junction (Km 76+860) which will be helpful in convincing the local people. In the meanwhile, as such finally the gap of around 30m near Thirupukuzhi junction has to be taken up, we also request your good self to apprise this situation to District Administration, Kanchipuram for their kind intervention and provide necessary support & cooperation to us as per clause 4.1.6 (e) of the Contract Agreement for successful implementation of the Project Highway. | FALSE | real_data
Stoppage of Works by locals/public | EoT; Authority's Obligations | Stoppage of works by Land owners. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-3/10. Obstruction to work 11.08.2017.pdf | Obstruction to work — reg. | In the letter referred above, we have intimated a few incidents of stoppage of works by Land owners. As the work fronts available are insufficient to the needs of the earth work units and as we intend to do the work contiguously, the aforesaid issues may kindly be resolved on priority. We therefore request you to depute your suitable representative to site, for the initial period, in order to resolve the issue then-and-there, for execution of the works uninterruptedly. | FALSE | real_data
Stoppage of Works by locals/public | EoT; Authority's Obligations | Though we have started or attempted to commence works at some of the above locations, our works are being stopped by local villagers claiming that the Compensation towards land acquisition is still due. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/2. Encroachements & Encumbrances in the ROW 11.10.2018.pdf | Encroachments & Encumbrances in the ROW -Reg. | With reference to above subject & letters, we would like to bring to your kind notice that the progress of work continues to suffer the ramifications of presence of Encroachments & Encumbrances in the ROW. Please refer to your letter ref (2) above wherein it was intimated that ROW to the tune of 90.44% was available for execution, enclosing Schedule-A of the Agreement. However, when we subsequently visited the Site we had encountered numerous encroachments & encumbrances and thus realized the fact that the available ROW was far less than 90.44%. Hence, we have submitted an Appendix containing the encroachments & encumbrances, vide letter ref (3) above for your joint verification and signing. The same was also communicated in our Extension of Time (EOT) letters ref (8) & (13) above. Further, through various letters referred above, we have intimated to the Authority & Authority Engineer as and when we had faced obstructions to the progress of work due to encroachments & encumbrances. We are once again enlisting below the locations which are not comprehensive, where we are unable to progress with the works even today along with the reasons. | FALSE | real_data
Stoppage of Works by locals/public | EoT; Authority's Obligations | We have so far been attempting to execute the works, by interacting with the property owners, throughout the project corridor. However, we have been stopped at sub grade top level also in nearly 20km length of the 39.713 km completed. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/8. Stoppage of works by local Villagers 04.01.2019.pdf | Rehabilitation and Up-gradation of Paithan (Pategaon) — Mungi - Hadgaon - Bodhegaon- Ladjalgaon - Ghogaspargaon - Phulsangvi — Ukhandachakla — Dahiwandi — Shirur to 2-Lane with paved shoulder (Project Length 55.937 Km) on EPC basis in the state of Maharashtra (Package ¦ — 56 KM) - Stoppage of Works by local villagers — Reg. | We have so far been attempting to execute the works, by interacting with the property owners, throughout the project corridor. However, we have been stopped at sub grade top level also in nearly 20km length of the 39.713 km completed. Please find enclosed a statement & strip chart showing : (a) Land acquisition problem, (b) Realignment stretches ( 5.35 km),(c) built up area ( 12.59km),(d) works completed up to PQC (BHS), (e€) works in progress PQC,DLC,GSB. We will be highly obliged, if this criticality is highlighted by the Authority Engineer to the Authority. | FALSE | real_data
Stoppage of Works by locals/public | EoT; Authority's Obligations | This is to bring to your kind notice that the construction of drain works has been stopped from Km 106+190 to Km 106+650 (RHS) by the local people from Thenkadapanthangal village (photographs enclosed) for want of increase in size of drain width to 3.0 m in lieu of 1.5m. We kindly request you to take up this issue with the District Administration and provide necessary support in resolving the issue as per Clause 4.1.6 (e) of the Contract Agreement. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/2023103_SPK_PD_067_Disruption of works by local people of Thenkadapanthangal Village for demand in “Increase in Drain width to 3.0m instead of 1.5m as per CA.pdf | Disruption of works by local people of Thenkadapanthangal Village for demand in “Increase in Drain width to 3.0m instead of 1.5m as per CA”— Works hampered from Km.106+190 to Km 106+650 (RHS) - Reg. | 1. This is to bring to your kind notice that the construction of drain works has been stopped from Km.106+190 to Km.106+650(RHS) by the local people from Thenkadapanthangal village (Photographs enclosed) for want of increase in size of drain width to 3.0m in lieu of 1.5m. The locals also informed that they will permit construction works only if the width of drain is increased to 3.0 m for the above mentioned length of 460m. 2. The reason stated by the villagers is that the adjacent water course coming from nearby source that flows across Minor Bridge at Km.106+677, will overflow towards the village side and that overflowing water should be allowed to flow in the drain otherwise the water will enter into their houses. 3. This is for information that already a length of 160m of storm water drain with width of 2.5m in lieu of 1.5m from Km.98+214 to Km.98+374 (160m) on LHS for diversion of the storm water into the PWD canal has been constructed for which the additional amount incurred up to Rs.28,49,564/- by the EPC Contractor is still pending for reimbursement with the Authority (Refer our letter No. SPK/KW/SAIC/NH-48/2022/185 dated 19.12.2022) 4. We kindly request you to take up this issue with the District Administration and provide necessary support in resolving the issue as per Clause 4.1.6 (e) of the Contract Agreement. | FALSE | real_data
Stoppage of Works by locals/public | EoT; Authority's Obligations | The farmers adjacent to the existing culvert on either side demanding for new CD work and they have stopped our construction activities | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-2/4. 20240223_238_Cont_AE_Representation of GP to construct BC at Km 9+280.pdf | Representation from Gram Panchayat to construct CD work @ Ch: 9+280 - Reg. | With reference to the above subject, we would like to bring to your kind notice that we have received representation form Gram Panchayat (copy enclosed) addressed to the Executive Engineer to construct a culvert at Ch:9+280. An existing stone masonry culvert with 3 vents of 1m (photographs enclosed) was there at the said location and the same is mentioned in schedule — A of CA which is not covered in schedule — B. The existing culvert has to be removed/ dismantled to proceed with the construction activities as this was not in the scope of work. The farmers adjacent to the existing culvert on either side demanding for new CD work and they have stopped our construction activities. In this context, we request your good self to take up the matter with Authority and resolve the issue at the earliest. Thanking & assuring our best services always, Encl: As Mentioned Above. CC: 1. The Executive Engineer, (R&B), NH Division, Siddipet. | FALSE | real_data
Descoping of a work from the scope of additional works under COS | Payments; EoT; Dispute Resolution; Change of Scope | SPK AND Co.. , the issue was discussed at CUP location. It has been instructed by the Regional Officer NHAI Chennai to stop the CUP at Km.84/032 works and instructed us to restore the excavated portion and complete it with the required layers so that the RHS carriageway is restored back and traffic will be diverted as normal. Also, it was informed that this COS (CUP at Km.84/032) will be descoped from the scope of additional works. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-6/20240802_SPK_AE_408_CUP at Km.84032 – Works stopped by locals – Restoration of Excavated Portion and Opening to Traffic on the RHS – Intimation of the same.pdf | Six laning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km. 71+015 (Existing km 71+000) to Km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - CUP at Km.84/032 —- Works stopped by locals - Restoration of Excavated Portion and Opening to Traffic on the RHS - Intimation of the same - Reg. | 1. The EPC Contractor had started the construction of Cattle Underpass (CUP) at kKm.84+032 under positive COS after carrying out traffic diversion as per the traffic diversion plan. 2. The excavation for the CUP commenced on RHS side of the Project Highway on 25.07.2024 and excavation up to Subgrade top of the existing road was completed for part width of CUP. 3. But on 26.07.2024, local people along with Damal Panchayath President came to CUP location and stopped us from executing further works. They demanded construction of Vehicular Underpass for cross movement of vehicles in lieu of the CUP under positive change of scope. 4. Further during the site inspection on 27.07.2024 by the Regional Officer NHAI Chennai along with the Project Director, Team Leader of AE, Project Manager of SPK AND Co.., the issue was discussed at CUP location. It has been instructed by the Regional Officer NHAI Chennai to stop the CUP at Km.84/032 works and instructed us to restore the excavated portion and complete it with the required layers so that the RHS carriageway is restored back and traffic will be diverted as normal. Also, it was informed that this COS (CUP at Km.84/032) will be descoped from the scope of additional works. 5. This is for information that the restoration works have been completed on 31.07.2024 and the MCW traffic coming from Bangalore which was diverted on LHS from Km.83+920 to Km.84+250 is now plying as normal on the RHS carriageway. Photographs enclosed for your reference as Annexure 1. 6. The EPC Contractor had incurred additional expenses (i) By engaging man power and machinery towards the traffic diversion and restoration of diverted traffic (ii) Excavation for the construction of CUP up to original subgrade level and replacing it back with the same crust viz. Subgrade, GSB, WMM DBM and BC and restoration of centre median kerbs. This additional expenditure is being worked out and will be submitted at the earliest. This may please be scrutinised and recommended for payment to the Authority. This is for your information and further necessary action. | FALSE | real_data
Descoping of a work from the scope of additional works under COS | EoT | SPK AND Co.. , the issue was discussed at CUP location. It has been instructed by the Regional Officer NHAI Chennai to stop the CUP at Km.84/032 works and instructed us to restore the excavated portion and complete it with the required layers so that the RHS carriageway is restored back and traffic will be diverted as normal. Also, it was informed that this COS (CUP at Km.84/032) will be descoped from the scope of additional works. | synthetic_template_20250913 | Six laning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km. 71+015 (Existing km 71+000) to Km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - CUP at Km.84/032 —- Works stopped by locals - Restoration of Excavated Portion and Opening to Traffic on the RHS - Intimation of the same - Reg. | 1. The EPC Contractor had started the construction of Cattle Underpass (CUP) at kKm.84+032 under positive COS after carrying out traffic diversion as per the traffic diversion plan. 2. The excavation for the CUP commenced on RHS side of the Project Highway on 25.07.2024 and excavation up to Subgrade top of the existing road was completed for part width of CUP. 3. But on 26.07.2024, local people along with Damal Panchayath President came to CUP location and stopped us from executing further works. They demanded construction of Vehicular Underpass for cross movement of vehicles in lieu of the CUP under positive change of scope. 4. Further during the site inspection on 27.07.2024 by the Regional Officer NHAI Chennai along with the Project Director, Team Leader of AE, Project Manager of SPK AND Co.., the issue was discussed at CUP location. It has been instructed by the Regional Officer NHAI Chennai to stop the CUP at Km.84/032 works and instructed us to restore the excavated portion and complete it with the required layers so that the RHS carriageway is restored back and traffic will be diverted as normal. Also, it was informed that this COS (CUP at Km.84/032) will be descoped from the scope of additional works. 5. This is for information that the restoration works have been completed on 31.07.2024 and the MCW traffic coming from Bangalore which was diverted on LHS from Km.83+920 to Km.84+250 is now plying as normal on the RHS carriageway. Photographs enclosed for your reference as Annexure 1. 6. The EPC Contractor had incurred additional expenses (i) By engaging man power and machinery towards the traffic diversion and restoration of diverted traffic (ii) Excavation for the construction of CUP up to original subgrade level and replacing it back with the same crust viz. Subgrade, GSB, WMM DBM and BC and restoration of centre median kerbs. This additional expenditure is being worked out and will be submitted at the earliest. This may please be scrutinised and recommended for payment to the Authority. This is for your information and further necessary action. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Descoping of a work from the scope of additional works under COS | EoT | SPK AND Co.. , the issue was discussed at CUP location. It has been instructed by the Regional Officer NHAI Chennai to stop the CUP at Km.84/032 works and instructed us to restore the excavated portion and complete it with the required layers so that the RHS carriageway is restored back and traffic will be diverted as normal. Also, it was informed that this COS (CUP at Km.84/032) will be descoped from the scope of additional works. | synthetic_template_20250913 | Six laning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km. 71+015 (Existing km 71+000) to Km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - CUP at Km.84/032 —- Works stopped by locals - Restoration of Excavated Portion and Opening to Traffic on the RHS - Intimation of the same - Reg. | We hereby confirm that 1. The EPC Contractor had started the construction of Cattle Underpass (CUP) at kKm.84+032 under positive COS after carrying out traffic diversion as per the traffic diversion plan. 2. The excavation for the CUP commenced on RHS side of the Project Highway on 25.07.2024 and excavation up to Subgrade top of the existing road was completed for part width of CUP. 3. But on 26.07.2024, local people along with Damal Panchayath President came to CUP location and stopped us from executing further works. They demanded construction of Vehicular Underpass for cross movement of vehicles in lieu of the CUP under positive change of scope. 4. Further during the site inspection on 27.07.2024 by the Regional Officer NHAI Chennai along with the Project Director, Team Leader of AE, Project Manager of SPK AND Co.., the issue was discussed at CUP location. It has been instructed by the Regional Officer NHAI Chennai to stop the CUP at Km.84/032 works and instructed us to restore the excavated portion and complete it with the required layers so that the RHS carriageway is restored back and traffic will be diverted as normal. Also, it was informed that this COS (CUP at Km.84/032) will be descoped from the scope of additional works. 5. This is for information that the restoration works have been completed on 31.07.2024 and the MCW traffic coming from Bangalore which was diverted on LHS from Km.83+920 to Km.84+250 is now plying as normal on the RHS carriageway. Photographs enclosed for your reference as Annexure 1. 6. The EPC Contractor had incurred additional expenses (i) By engaging man power and machinery towards the traffic diversion and restoration of diverted traffic (ii) Excavation for the construction of CUP up to original subgrade level and replacing it back with the same crust viz. Subgrade, GSB, WMM DBM and BC and restoration of centre median kerbs. This additional expenditure is being worked out and will be submitted at the earliest. This may please be scrutinised and recommended for payment to the Authority. This is for your information and further necessary action. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Descoping of a work from the scope of additional works under COS | Dispute Resolution | SPK AND Co.. , the issue was discussed at CUP location. It has been instructed by the Regional Officer NHAI Chennai to stop the CUP at Km.84/032 works and instructed us to restore the excavated portion and complete it with the required layers so that the RHS carriageway is restored back and traffic will be diverted as normal. Also, it was informed that this COS (CUP at Km.84/032) will be descoped from the scope of additional works. | synthetic_template_20250913 | Six laning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km. 71+015 (Existing km 71+000) to Km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - CUP at Km.84/032 —- Works stopped by locals - Restoration of Excavated Portion and Opening to Traffic on the RHS - Intimation of the same - Reg. | 1. The EPC Contractor had started the construction of Cattle Underpass (CUP) at kKm.84+032 under positive COS after carrying out traffic diversion as per the traffic diversion plan. 2. The excavation for the CUP commenced on RHS side of the Project Highway on 25.07.2024 and excavation up to Subgrade top of the existing road was completed for part width of CUP. 3. But on 26.07.2024, local people along with Damal Panchayath President came to CUP location and stopped us from executing further works. They demanded construction of Vehicular Underpass for cross movement of vehicles in lieu of the CUP under positive change of scope. 4. Further during the site inspection on 27.07.2024 by the Regional Officer NHAI Chennai along with the Project Director, Team Leader of AE, Project Manager of SPK AND Co.., the issue was discussed at CUP location. It has been instructed by the Regional Officer NHAI Chennai to stop the CUP at Km.84/032 works and instructed us to restore the excavated portion and complete it with the required layers so that the RHS carriageway is restored back and traffic will be diverted as normal. Also, it was informed that this COS (CUP at Km.84/032) will be descoped from the scope of additional works. 5. This is for information that the restoration works have been completed on 31.07.2024 and the MCW traffic coming from Bangalore which was diverted on LHS from Km.83+920 to Km.84+250 is now plying as normal on the RHS carriageway. Photographs enclosed for your reference as Annexure 1. 6. The EPC Contractor had incurred additional expenses (i) By engaging man power and machinery towards the traffic diversion and restoration of diverted traffic (ii) Excavation for the construction of CUP up to original subgrade level and replacing it back with the same crust viz. Subgrade, GSB, WMM DBM and BC and restoration of centre median kerbs. This additional expenditure is being worked out and will be submitted at the earliest. This may please be scrutinised and recommended for payment to the Authority. This is for your information and further necessary action. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Descoping of a work from the scope of additional works under COS | Dispute Resolution | SPK AND Co.. , the issue was discussed at CUP location. It has been instructed by the Regional Officer NHAI Chennai to stop the CUP at Km.84/032 works and instructed us to restore the excavated portion and complete it with the required layers so that the RHS carriageway is restored back and traffic will be diverted as normal. Also, it was informed that this COS (CUP at Km.84/032) will be descoped from the scope of additional works. | synthetic_template_20250913 | Six laning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km. 71+015 (Existing km 71+000) to Km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - CUP at Km.84/032 —- Works stopped by locals - Restoration of Excavated Portion and Opening to Traffic on the RHS - Intimation of the same - Reg. | 1. The EPC Contractor had started the construction of Cattle Underpass (CUP) at kKm.84+032 under positive COS after carrying out traffic diversion as per the traffic diversion plan. 2. The excavation for the CUP commenced on RHS side of the Project Highway on 25.07.2024 and excavation up to Subgrade top of the existing road was completed for part width of CUP. 3. But on 26.07.2024, local people along with Damal Panchayath President came to CUP location and stopped us from executing further works. They demanded construction of Vehicular Underpass for cross movement of vehicles in lieu of the CUP under positive change of scope. 4. Further during the site inspection on 27.07.2024 by the Regional Officer NHAI Chennai along with the Project Director, Team Leader of AE, Project Manager of SPK AND Co.., the issue was discussed at CUP location. It has been instructed by the Regional Officer NHAI Chennai to stop the CUP at Km.84/032 works and instructed us to restore the excavated portion and complete it with the required layers so that the RHS carriageway is restored back and traffic will be diverted as normal. Also, it was informed that this COS (CUP at Km.84/032) will be descoped from the scope of additional works. 5. This is for information that the restoration works have been completed on 31.07.2024 and the MCW traffic coming from Bangalore which was diverted on LHS from Km.83+920 to Km.84+250 is now plying as normal on the RHS carriageway. Photographs enclosed for your reference as Annexure 1. 6. The EPC Contractor had incurred additional expenses (i) By engaging man power and machinery towards the traffic diversion and restoration of diverted traffic (ii) Excavation for the construction of CUP up to original subgrade level and replacing it back with the same crust viz. Subgrade, GSB, WMM DBM and BC and restoration of centre median kerbs. This additional expenditure is being worked out and will be submitted at the earliest. This may please be scrutinised and recommended for payment to the Authority. This is for your information and further necessary action. Thank you for your attention to this matter. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Descoping of a work from the scope of additional works under COS | Payments | SPK AND Co.. , the issue was discussed at CUP location. It has been instructed by the Regional Officer NHAI Chennai to stop the CUP at Km.84/032 works and instructed us to restore the excavated portion and complete it with the required layers so that the RHS carriageway is restored back and traffic will be diverted as normal. Also, it was informed that this COS (CUP at Km.84/032) will be descoped from the scope of additional works. | synthetic_template_20250913 | Six laning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km. 71+015 (Existing km 71+000) to Km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - CUP at Km.84/032 —- Works stopped by locals - Restoration of Excavated Portion and Opening to Traffic on the RHS - Intimation of the same - Reg. | This is to notify you that 1. The EPC Contractor had started the construction of Cattle Underpass (CUP) at kKm.84+032 under positive COS after carrying out traffic diversion as per the traffic diversion plan. 2. The excavation for the CUP commenced on RHS side of the Project Highway on 25.07.2024 and excavation up to Subgrade top of the existing road was completed for part width of CUP. 3. But on 26.07.2024, local people along with Damal Panchayath President came to CUP location and stopped us from executing further works. They demanded construction of Vehicular Underpass for cross movement of vehicles in lieu of the CUP under positive change of scope. 4. Further during the site inspection on 27.07.2024 by the Regional Officer NHAI Chennai along with the Project Director, Team Leader of AE, Project Manager of SPK AND Co.., the issue was discussed at CUP location. It has been instructed by the Regional Officer NHAI Chennai to stop the CUP at Km.84/032 works and instructed us to restore the excavated portion and complete it with the required layers so that the RHS carriageway is restored back and traffic will be diverted as normal. Also, it was informed that this COS (CUP at Km.84/032) will be descoped from the scope of additional works. 5. This is for information that the restoration works have been completed on 31.07.2024 and the MCW traffic coming from Bangalore which was diverted on LHS from Km.83+920 to Km.84+250 is now plying as normal on the RHS carriageway. Photographs enclosed for your reference as Annexure 1. 6. The EPC Contractor had incurred additional expenses (i) By engaging man power and machinery towards the traffic diversion and restoration of diverted traffic (ii) Excavation for the construction of CUP up to original subgrade level and replacing it back with the same crust viz. Subgrade, GSB, WMM DBM and BC and restoration of centre median kerbs. This additional expenditure is being worked out and will be submitted at the earliest. This may please be scrutinised and recommended for payment to the Authority. This is for your information and further necessary action. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Descoping of a work from the scope of additional works under COS | Payments | SPK AND Co.. , the issue was discussed at CUP location. It has been instructed by the Regional Officer NHAI Chennai to stop the CUP at Km.84/032 works and instructed us to restore the excavated portion and complete it with the required layers so that the RHS carriageway is restored back and traffic will be diverted as normal. Also, it was informed that this COS (CUP at Km.84/032) will be descoped from the scope of additional works. | synthetic_template_20250913 | Six laning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km. 71+015 (Existing km 71+000) to Km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - CUP at Km.84/032 —- Works stopped by locals - Restoration of Excavated Portion and Opening to Traffic on the RHS - Intimation of the same - Reg. | 1. The EPC Contractor had started the construction of Cattle Underpass (CUP) at kKm.84+032 under positive COS after carrying out traffic diversion as per the traffic diversion plan. 2. The excavation for the CUP commenced on RHS side of the Project Highway on 25.07.2024 and excavation up to Subgrade top of the existing road was completed for part width of CUP. 3. But on 26.07.2024, local people along with Damal Panchayath President came to CUP location and stopped us from executing further works. They demanded construction of Vehicular Underpass for cross movement of vehicles in lieu of the CUP under positive change of scope. 4. Further during the site inspection on 27.07.2024 by the Regional Officer NHAI Chennai along with the Project Director, Team Leader of AE, Project Manager of SPK AND Co.., the issue was discussed at CUP location. It has been instructed by the Regional Officer NHAI Chennai to stop the CUP at Km.84/032 works and instructed us to restore the excavated portion and complete it with the required layers so that the RHS carriageway is restored back and traffic will be diverted as normal. Also, it was informed that this COS (CUP at Km.84/032) will be descoped from the scope of additional works. 5. This is for information that the restoration works have been completed on 31.07.2024 and the MCW traffic coming from Bangalore which was diverted on LHS from Km.83+920 to Km.84+250 is now plying as normal on the RHS carriageway. Photographs enclosed for your reference as Annexure 1. 6. The EPC Contractor had incurred additional expenses (i) By engaging man power and machinery towards the traffic diversion and restoration of diverted traffic (ii) Excavation for the construction of CUP up to original subgrade level and replacing it back with the same crust viz. Subgrade, GSB, WMM DBM and BC and restoration of centre median kerbs. This additional expenditure is being worked out and will be submitted at the earliest. This may please be scrutinised and recommended for payment to the Authority. This is for your information and further necessary action. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Descoping of a work from the scope of additional works under COS | Change of Scope | SPK AND Co.. , the issue was discussed at CUP location. It has been instructed by the Regional Officer NHAI Chennai to stop the CUP at Km.84/032 works and instructed us to restore the excavated portion and complete it with the required layers so that the RHS carriageway is restored back and traffic will be diverted as normal. Also, it was informed that this COS (CUP at Km.84/032) will be descoped from the scope of additional works. | synthetic_template_20250913 | Six laning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km. 71+015 (Existing km 71+000) to Km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - CUP at Km.84/032 —- Works stopped by locals - Restoration of Excavated Portion and Opening to Traffic on the RHS - Intimation of the same - Reg. | 1. The EPC Contractor had started the construction of Cattle Underpass (CUP) at kKm.84+032 under positive COS after carrying out traffic diversion as per the traffic diversion plan. 2. The excavation for the CUP commenced on RHS side of the Project Highway on 25.07.2024 and excavation up to Subgrade top of the existing road was completed for part width of CUP. 3. But on 26.07.2024, local people along with Damal Panchayath President came to CUP location and stopped us from executing further works. They demanded construction of Vehicular Underpass for cross movement of vehicles in lieu of the CUP under positive change of scope. 4. Further during the site inspection on 27.07.2024 by the Regional Officer NHAI Chennai along with the Project Director, Team Leader of AE, Project Manager of SPK AND Co.., the issue was discussed at CUP location. It has been instructed by the Regional Officer NHAI Chennai to stop the CUP at Km.84/032 works and instructed us to restore the excavated portion and complete it with the required layers so that the RHS carriageway is restored back and traffic will be diverted as normal. Also, it was informed that this COS (CUP at Km.84/032) will be descoped from the scope of additional works. 5. This is for information that the restoration works have been completed on 31.07.2024 and the MCW traffic coming from Bangalore which was diverted on LHS from Km.83+920 to Km.84+250 is now plying as normal on the RHS carriageway. Photographs enclosed for your reference as Annexure 1. 6. The EPC Contractor had incurred additional expenses (i) By engaging man power and machinery towards the traffic diversion and restoration of diverted traffic (ii) Excavation for the construction of CUP up to original subgrade level and replacing it back with the same crust viz. Subgrade, GSB, WMM DBM and BC and restoration of centre median kerbs. This additional expenditure is being worked out and will be submitted at the earliest. This may please be scrutinised and recommended for payment to the Authority. This is for your information and further necessary action. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Topography/Geo-tech survey | Contractor's Obligations | we have mobilized rigs for carrying out soil investigation work of the bridges | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-3/5. Delay in start of work 13.06.2017.pdf | Rehabilitation and Upgradation of Ghogaspargaon-Phulsangvi-Ukhandachakla-Dahiwandi-Shirur-Rakshasbhuvan-Kholayachiwadi-Karegaon-Dongarkini-Chumbli-Patoda-Dighol Road (SH-62) Kharda. From KM 0+000 to KM 56+000 to two lanes with paved shoulders” (Project Length 55.937 KM) on EPC basis in the State of Maharashtra (Package — I) — Delay in start of work | We are planned fo start the execution of the project from 14th June 2017 as intimated to you verbally and as per the construction programme submitted to you to complete the project execution in stipulated period. Based on this, we have submitted initial Plan & Profile for a length of 34 Km, starting from Ch: 0+000 to Ch: 34+000 and also at the same time, we have mobilized rigs for carrying out soil investigation work of the bridges. , So far, we have completed detailed survey including establishment of bench marks for a length of 56 km. We are planning to submit the balance Plan & Profile of 22 Km by this weekend. Initially, we have submitted the Plan & Profile in oe copy for your review. Please go through it and suggest for 5 a modifications if any. (amr aT igre wera PUT ty, we are establishing centre line marking on the existing road and will be completed by s. In mean time, we have placed order to procure the lab equipment required for this project e€ are expecting. the delivery of the material by this weekend and we are establishing the NM temporary laboratory at the camp location and can be utilized for the time being till the camp construction completes. As per the discussions we had earlier with the Department, we are forced to take appointed date as 30.05.17, We are mobilizing our equipment to start preliminary works like Clearing and Grubbing and base compaction of the existing ground making suitable for embankment construction. But you L have given instruction not to start the work due to the various reasons which are known to you. This delay will cause slippage in achievement of milestones & completion of the project. Hence we would like to bring to your notice that, if any delay occurs due to any reason and circumstances which are beyond our control in achieving the milestone would not be considered as a failure from our side. So please permit us to start the work at the earliest. | FALSE | real_data
Topography/Geo-tech survey | Contractor's Obligations | we have mobilized rigs for carrying out soil investigation work of the bridges | synthetic_template_20250913 | Rehabilitation and Upgradation of Ghogaspargaon-Phulsangvi-Ukhandachakla-Dahiwandi-Shirur-Rakshasbhuvan-Kholayachiwadi-Karegaon-Dongarkini-Chumbli-Patoda-Dighol Road (SH-62) Kharda. From KM 0+000 to KM 56+000 to two lanes with paved shoulders” (Project Length 55.937 KM) on EPC basis in the State of Maharashtra (Package — I) — Delay in start of work | We are planned fo start the execution of the project from 14th June 2017 as intimated to you verbally and as per the construction programme submitted to you to complete the project execution in stipulated period. Based on this, we have submitted initial Plan & Profile for a length of 34 Km, starting from Ch: 0+000 to Ch: 34+000 and also at the same time, we have mobilized rigs for carrying out soil investigation work of the bridges. , So far, we have completed detailed survey including establishment of bench marks for a length of 56 km. We are planning to submit the balance Plan & Profile of 22 Km by this weekend. Initially, we have submitted the Plan & Profile in oe copy for your review. Please go through it and suggest for 5 a modifications if any. (amr aT igre wera PUT ty, we are establishing centre line marking on the existing road and will be completed by s. In mean time, we have placed order to procure the lab equipment required for this project e€ are expecting. the delivery of the material by this weekend and we are establishing the NM temporary laboratory at the camp location and can be utilized for the time being till the camp construction completes. As per the discussions we had earlier with the Department, we are forced to take appointed date as 30.05.17, We are mobilizing our equipment to start preliminary works like Clearing and Grubbing and base compaction of the existing ground making suitable for embankment construction. But you L have given instruction not to start the work due to the various reasons which are known to you. This delay will cause slippage in achievement of milestones & completion of the project. Hence we would like to bring to your notice that, if any delay occurs due to any reason and circumstances which are beyond our control in achieving the milestone would not be considered as a failure from our side. So please permit us to start the work at the earliest. Thank you for your attention to this matter. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Topography/Geo-tech survey | Contractor's Obligations | we have mobilized rigs for carrying out soil investigation work of the bridges | synthetic_template_20250913 | Rehabilitation and Upgradation of Ghogaspargaon-Phulsangvi-Ukhandachakla-Dahiwandi-Shirur-Rakshasbhuvan-Kholayachiwadi-Karegaon-Dongarkini-Chumbli-Patoda-Dighol Road (SH-62) Kharda. From KM 0+000 to KM 56+000 to two lanes with paved shoulders” (Project Length 55.937 KM) on EPC basis in the State of Maharashtra (Package — I) — Delay in start of work | We are planned fo start the execution of the project from 14th June 2017 as intimated to you verbally and as per the construction programme submitted to you to complete the project execution in stipulated period. Based on this, we have submitted initial Plan & Profile for a length of 34 Km, starting from Ch: 0+000 to Ch: 34+000 and also at the same time, we have mobilized rigs for carrying out soil investigation work of the bridges. , So far, we have completed detailed survey including establishment of bench marks for a length of 56 km. We are planning to submit the balance Plan & Profile of 22 Km by this weekend. Initially, we have submitted the Plan & Profile in oe copy for your review. Please go through it and suggest for 5 a modifications if any. (amr aT igre wera PUT ty, we are establishing centre line marking on the existing road and will be completed by s. In mean time, we have placed order to procure the lab equipment required for this project e€ are expecting. the delivery of the material by this weekend and we are establishing the NM temporary laboratory at the camp location and can be utilized for the time being till the camp construction completes. As per the discussions we had earlier with the Department, we are forced to take appointed date as 30.05.17, We are mobilizing our equipment to start preliminary works like Clearing and Grubbing and base compaction of the existing ground making suitable for embankment construction. But you L have given instruction not to start the work due to the various reasons which are known to you. This delay will cause slippage in achievement of milestones & completion of the project. Hence we would like to bring to your notice that, if any delay occurs due to any reason and circumstances which are beyond our control in achieving the milestone would not be considered as a failure from our side. So please permit us to start the work at the earliest. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Topography/Geo-tech survey | Contractor's Obligations | we hereby inform you that we are planning to carry out subsoil investigation at Minor bridge locations in the next week for conducting necessary field tests and to collect disturbed and undisturbed soil samples from the bore holes for finalization of bridge designs. | synthetic_template_20250913 | Carrying out subsoil investigations af Minor Bridge locations - Reg | Hence your presence is highly appreciated fo support us in providing the required information This is for your kind information and necessary guidance. Thank you for your attention to this matter. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Topography/Geo-tech survey | Contractor's Obligations | we hereby inform you that we are planning to carry out subsoil investigation at Minor bridge locations in the next week for conducting necessary field tests and to collect disturbed and undisturbed soil samples from the bore holes for finalization of bridge designs. | synthetic_template_20250913 | Carrying out subsoil investigations af Minor Bridge locations - Reg | Hence your presence is highly appreciated fo support us in providing the required information This is for your kind information and necessary guidance. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Topography/Geo-tech survey | Contractor's Obligations | we have mobilized rigs for carrying out soil investigation work of the bridges | synthetic_template_20250913 | Rehabilitation and Upgradation of Ghogaspargaon-Phulsangvi-Ukhandachakla-Dahiwandi-Shirur-Rakshasbhuvan-Kholayachiwadi-Karegaon-Dongarkini-Chumbli-Patoda-Dighol Road (SH-62) Kharda. From KM 0+000 to KM 56+000 to two lanes with paved shoulders” (Project Length 55.937 KM) on EPC basis in the State of Maharashtra (Package — I) — Delay in start of work | We are planned fo start the execution of the project from 14th June 2017 as intimated to you verbally and as per the construction programme submitted to you to complete the project execution in stipulated period. Based on this, we have submitted initial Plan & Profile for a length of 34 Km, starting from Ch: 0+000 to Ch: 34+000 and also at the same time, we have mobilized rigs for carrying out soil investigation work of the bridges. , So far, we have completed detailed survey including establishment of bench marks for a length of 56 km. We are planning to submit the balance Plan & Profile of 22 Km by this weekend. Initially, we have submitted the Plan & Profile in oe copy for your review. Please go through it and suggest for 5 a modifications if any. (amr aT igre wera PUT ty, we are establishing centre line marking on the existing road and will be completed by s. In mean time, we have placed order to procure the lab equipment required for this project e€ are expecting. the delivery of the material by this weekend and we are establishing the NM temporary laboratory at the camp location and can be utilized for the time being till the camp construction completes. As per the discussions we had earlier with the Department, we are forced to take appointed date as 30.05.17, We are mobilizing our equipment to start preliminary works like Clearing and Grubbing and base compaction of the existing ground making suitable for embankment construction. But you L have given instruction not to start the work due to the various reasons which are known to you. This delay will cause slippage in achievement of milestones & completion of the project. Hence we would like to bring to your notice that, if any delay occurs due to any reason and circumstances which are beyond our control in achieving the milestone would not be considered as a failure from our side. So please permit us to start the work at the earliest. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Delay in commencement/starting of work | EoT | This delay will cause slippage in achievement of milestones & completion of the project. | synthetic_template_20250913 | Rehabilitation and Upgradation of Ghogaspargaon-Phulsangvi-Ukhandachakla-Dahiwandi-Shirur-Rakshasbhuvan-Kholayachiwadi-Karegaon-Dongarkini-Chumbli-Patoda-Dighol Road (SH-62) Kharda. From KM 0+000 to KM 56+000 to two lanes with paved shoulders” (Project Length 55.937 KM) on EPC basis in the State of Maharashtra (Package — I) — Delay in start of work | We are planned fo start the execution of the project from 14th June 2017 as intimated to you verbally and as per the construction programme submitted to you to complete the project execution in stipulated period. Based on this, we have submitted initial Plan & Profile for a length of 34 Km, starting from Ch: 0+000 to Ch: 34+000 and also at the same time, we have mobilized rigs for carrying out soil investigation work of the bridges. , So far, we have completed detailed survey including establishment of bench marks for a length of 56 km. We are planning to submit the balance Plan & Profile of 22 Km by this weekend. Initially, we have submitted the Plan & Profile in oe copy for your review. Please go through it and suggest for 5 a modifications if any. (amr aT igre wera PUT ty, we are establishing centre line marking on the existing road and will be completed by s. In mean time, we have placed order to procure the lab equipment required for this project e€ are expecting. the delivery of the material by this weekend and we are establishing the NM temporary laboratory at the camp location and can be utilized for the time being till the camp construction completes. As per the discussions we had earlier with the Department, we are forced to take appointed date as 30.05.17, We are mobilizing our equipment to start preliminary works like Clearing and Grubbing and base compaction of the existing ground making suitable for embankment construction. But you L have given instruction not to start the work due to the various reasons which are known to you. This delay will cause slippage in achievement of milestones & completion of the project. Hence we would like to bring to your notice that, if any delay occurs due to any reason and circumstances which are beyond our control in achieving the milestone would not be considered as a failure from our side. So please permit us to start the work at the earliest. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Delay in commencement/starting of work | EoT | This delay will cause slippage in achievement of milestones & completion of the project. | synthetic_template_20250913 | Rehabilitation and Upgradation of Ghogaspargaon-Phulsangvi-Ukhandachakla-Dahiwandi-Shirur-Rakshasbhuvan-Kholayachiwadi-Karegaon-Dongarkini-Chumbli-Patoda-Dighol Road (SH-62) Kharda. From KM 0+000 to KM 56+000 to two lanes with paved shoulders” (Project Length 55.937 KM) on EPC basis in the State of Maharashtra (Package — I) — Delay in start of work | We are planned fo start the execution of the project from 14th June 2017 as intimated to you verbally and as per the construction programme submitted to you to complete the project execution in stipulated period. Based on this, we have submitted initial Plan & Profile for a length of 34 Km, starting from Ch: 0+000 to Ch: 34+000 and also at the same time, we have mobilized rigs for carrying out soil investigation work of the bridges. , So far, we have completed detailed survey including establishment of bench marks for a length of 56 km. We are planning to submit the balance Plan & Profile of 22 Km by this weekend. Initially, we have submitted the Plan & Profile in oe copy for your review. Please go through it and suggest for 5 a modifications if any. (amr aT igre wera PUT ty, we are establishing centre line marking on the existing road and will be completed by s. In mean time, we have placed order to procure the lab equipment required for this project e€ are expecting. the delivery of the material by this weekend and we are establishing the NM temporary laboratory at the camp location and can be utilized for the time being till the camp construction completes. As per the discussions we had earlier with the Department, we are forced to take appointed date as 30.05.17, We are mobilizing our equipment to start preliminary works like Clearing and Grubbing and base compaction of the existing ground making suitable for embankment construction. But you L have given instruction not to start the work due to the various reasons which are known to you. This delay will cause slippage in achievement of milestones & completion of the project. Hence we would like to bring to your notice that, if any delay occurs due to any reason and circumstances which are beyond our control in achieving the milestone would not be considered as a failure from our side. So please permit us to start the work at the earliest. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Delay in commencement/starting of work | Dispute Resolution | This delay will cause slippage in achievement of milestones & completion of the project. | synthetic_template_20250913 | Rehabilitation and Upgradation of Ghogaspargaon-Phulsangvi-Ukhandachakla-Dahiwandi-Shirur-Rakshasbhuvan-Kholayachiwadi-Karegaon-Dongarkini-Chumbli-Patoda-Dighol Road (SH-62) Kharda. From KM 0+000 to KM 56+000 to two lanes with paved shoulders” (Project Length 55.937 KM) on EPC basis in the State of Maharashtra (Package — I) — Delay in start of work | It is brought to your attention that We are planned fo start the execution of the project from 14th June 2017 as intimated to you verbally and as per the construction programme submitted to you to complete the project execution in stipulated period. Based on this, we have submitted initial Plan & Profile for a length of 34 Km, starting from Ch: 0+000 to Ch: 34+000 and also at the same time, we have mobilized rigs for carrying out soil investigation work of the bridges. , So far, we have completed detailed survey including establishment of bench marks for a length of 56 km. We are planning to submit the balance Plan & Profile of 22 Km by this weekend. Initially, we have submitted the Plan & Profile in oe copy for your review. Please go through it and suggest for 5 a modifications if any. (amr aT igre wera PUT ty, we are establishing centre line marking on the existing road and will be completed by s. In mean time, we have placed order to procure the lab equipment required for this project e€ are expecting. the delivery of the material by this weekend and we are establishing the NM temporary laboratory at the camp location and can be utilized for the time being till the camp construction completes. As per the discussions we had earlier with the Department, we are forced to take appointed date as 30.05.17, We are mobilizing our equipment to start preliminary works like Clearing and Grubbing and base compaction of the existing ground making suitable for embankment construction. But you L have given instruction not to start the work due to the various reasons which are known to you. This delay will cause slippage in achievement of milestones & completion of the project. Hence we would like to bring to your notice that, if any delay occurs due to any reason and circumstances which are beyond our control in achieving the milestone would not be considered as a failure from our side. So please permit us to start the work at the earliest. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Delay in commencement/starting of work | Dispute Resolution | This delay will cause slippage in achievement of milestones & completion of the project. | synthetic_template_20250913 | Rehabilitation and Upgradation of Ghogaspargaon-Phulsangvi-Ukhandachakla-Dahiwandi-Shirur-Rakshasbhuvan-Kholayachiwadi-Karegaon-Dongarkini-Chumbli-Patoda-Dighol Road (SH-62) Kharda. From KM 0+000 to KM 56+000 to two lanes with paved shoulders” (Project Length 55.937 KM) on EPC basis in the State of Maharashtra (Package — I) — Delay in start of work | We are planned fo start the execution of the project from 14th June 2017 as intimated to you verbally and as per the construction programme submitted to you to complete the project execution in stipulated period. Based on this, we have submitted initial Plan & Profile for a length of 34 Km, starting from Ch: 0+000 to Ch: 34+000 and also at the same time, we have mobilized rigs for carrying out soil investigation work of the bridges. , So far, we have completed detailed survey including establishment of bench marks for a length of 56 km. We are planning to submit the balance Plan & Profile of 22 Km by this weekend. Initially, we have submitted the Plan & Profile in oe copy for your review. Please go through it and suggest for 5 a modifications if any. (amr aT igre wera PUT ty, we are establishing centre line marking on the existing road and will be completed by s. In mean time, we have placed order to procure the lab equipment required for this project e€ are expecting. the delivery of the material by this weekend and we are establishing the NM temporary laboratory at the camp location and can be utilized for the time being till the camp construction completes. As per the discussions we had earlier with the Department, we are forced to take appointed date as 30.05.17, We are mobilizing our equipment to start preliminary works like Clearing and Grubbing and base compaction of the existing ground making suitable for embankment construction. But you L have given instruction not to start the work due to the various reasons which are known to you. This delay will cause slippage in achievement of milestones & completion of the project. Hence we would like to bring to your notice that, if any delay occurs due to any reason and circumstances which are beyond our control in achieving the milestone would not be considered as a failure from our side. So please permit us to start the work at the earliest. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Delay in commencement/starting of work | Payments | This delay will cause slippage in achievement of milestones & completion of the project. | synthetic_template_20250913 | Rehabilitation and Upgradation of Ghogaspargaon-Phulsangvi-Ukhandachakla-Dahiwandi-Shirur-Rakshasbhuvan-Kholayachiwadi-Karegaon-Dongarkini-Chumbli-Patoda-Dighol Road (SH-62) Kharda. From KM 0+000 to KM 56+000 to two lanes with paved shoulders” (Project Length 55.937 KM) on EPC basis in the State of Maharashtra (Package — I) — Delay in start of work | We are planned fo start the execution of the project from 14th June 2017 as intimated to you verbally and as per the construction programme submitted to you to complete the project execution in stipulated period. Based on this, we have submitted initial Plan & Profile for a length of 34 Km, starting from Ch: 0+000 to Ch: 34+000 and also at the same time, we have mobilized rigs for carrying out soil investigation work of the bridges. , So far, we have completed detailed survey including establishment of bench marks for a length of 56 km. We are planning to submit the balance Plan & Profile of 22 Km by this weekend. Initially, we have submitted the Plan & Profile in oe copy for your review. Please go through it and suggest for 5 a modifications if any. (amr aT igre wera PUT ty, we are establishing centre line marking on the existing road and will be completed by s. In mean time, we have placed order to procure the lab equipment required for this project e€ are expecting. the delivery of the material by this weekend and we are establishing the NM temporary laboratory at the camp location and can be utilized for the time being till the camp construction completes. As per the discussions we had earlier with the Department, we are forced to take appointed date as 30.05.17, We are mobilizing our equipment to start preliminary works like Clearing and Grubbing and base compaction of the existing ground making suitable for embankment construction. But you L have given instruction not to start the work due to the various reasons which are known to you. This delay will cause slippage in achievement of milestones & completion of the project. Hence we would like to bring to your notice that, if any delay occurs due to any reason and circumstances which are beyond our control in achieving the milestone would not be considered as a failure from our side. So please permit us to start the work at the earliest. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Delay in commencement/starting of work | Payments | This delay will cause slippage in achievement of milestones & completion of the project. | synthetic_template_20250913 | Rehabilitation and Upgradation of Ghogaspargaon-Phulsangvi-Ukhandachakla-Dahiwandi-Shirur-Rakshasbhuvan-Kholayachiwadi-Karegaon-Dongarkini-Chumbli-Patoda-Dighol Road (SH-62) Kharda. From KM 0+000 to KM 56+000 to two lanes with paved shoulders” (Project Length 55.937 KM) on EPC basis in the State of Maharashtra (Package — I) — Delay in start of work | We would like to inform you that We are planned fo start the execution of the project from 14th June 2017 as intimated to you verbally and as per the construction programme submitted to you to complete the project execution in stipulated period. Based on this, we have submitted initial Plan & Profile for a length of 34 Km, starting from Ch: 0+000 to Ch: 34+000 and also at the same time, we have mobilized rigs for carrying out soil investigation work of the bridges. , So far, we have completed detailed survey including establishment of bench marks for a length of 56 km. We are planning to submit the balance Plan & Profile of 22 Km by this weekend. Initially, we have submitted the Plan & Profile in oe copy for your review. Please go through it and suggest for 5 a modifications if any. (amr aT igre wera PUT ty, we are establishing centre line marking on the existing road and will be completed by s. In mean time, we have placed order to procure the lab equipment required for this project e€ are expecting. the delivery of the material by this weekend and we are establishing the NM temporary laboratory at the camp location and can be utilized for the time being till the camp construction completes. As per the discussions we had earlier with the Department, we are forced to take appointed date as 30.05.17, We are mobilizing our equipment to start preliminary works like Clearing and Grubbing and base compaction of the existing ground making suitable for embankment construction. But you L have given instruction not to start the work due to the various reasons which are known to you. This delay will cause slippage in achievement of milestones & completion of the project. Hence we would like to bring to your notice that, if any delay occurs due to any reason and circumstances which are beyond our control in achieving the milestone would not be considered as a failure from our side. So please permit us to start the work at the earliest. We await your further instructions. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Preliminary / preparatory works | Contractor's Obligations | Presently, we are establishing centre line marking on the existing road and will be completed by 25.06.17. Simultaneously we have identified stone quarry at Chainage 30+000 and land for camp was finalized at Chainage 33+000 -and planning to start the camp construction by next week | synthetic_template_20250913 | Rehabilitation and Upgradation of Ghogaspargaon-Phulsangvi-Ukhandachakla-Dahiwandi-Shirur-Rakshasbhuvan-Kholayachiwadi-Karegaon-Dongarkini-Chumbli-Patoda-Dighol Road (SH-62) Kharda. From KM 0+000 to KM 56+000 to two lanes with paved shoulders” (Project Length 55.937 KM) on EPC basis in the State of Maharashtra (Package — I) — Delay in start of work | We are planned fo start the execution of the project from 14th June 2017 as intimated to you verbally and as per the construction programme submitted to you to complete the project execution in stipulated period. Based on this, we have submitted initial Plan & Profile for a length of 34 Km, starting from Ch: 0+000 to Ch: 34+000 and also at the same time, we have mobilized rigs for carrying out soil investigation work of the bridges. , So far, we have completed detailed survey including establishment of bench marks for a length of 56 km. We are planning to submit the balance Plan & Profile of 22 Km by this weekend. Initially, we have submitted the Plan & Profile in oe copy for your review. Please go through it and suggest for 5 a modifications if any. (amr aT igre wera PUT ty, we are establishing centre line marking on the existing road and will be completed by s. In mean time, we have placed order to procure the lab equipment required for this project e€ are expecting. the delivery of the material by this weekend and we are establishing the NM temporary laboratory at the camp location and can be utilized for the time being till the camp construction completes. As per the discussions we had earlier with the Department, we are forced to take appointed date as 30.05.17, We are mobilizing our equipment to start preliminary works like Clearing and Grubbing and base compaction of the existing ground making suitable for embankment construction. But you L have given instruction not to start the work due to the various reasons which are known to you. This delay will cause slippage in achievement of milestones & completion of the project. Hence we would like to bring to your notice that, if any delay occurs due to any reason and circumstances which are beyond our control in achieving the milestone would not be considered as a failure from our side. So please permit us to start the work at the earliest. Thank you for your attention to this matter. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Preliminary / preparatory works | Contractor's Obligations | Presently, we are establishing centre line marking on the existing road and will be completed by 25.06.17. Simultaneously we have identified stone quarry at Chainage 30+000 and land for camp was finalized at Chainage 33+000 -and planning to start the camp construction by next week | synthetic_template_20250913 | Rehabilitation and Upgradation of Ghogaspargaon-Phulsangvi-Ukhandachakla-Dahiwandi-Shirur-Rakshasbhuvan-Kholayachiwadi-Karegaon-Dongarkini-Chumbli-Patoda-Dighol Road (SH-62) Kharda. From KM 0+000 to KM 56+000 to two lanes with paved shoulders” (Project Length 55.937 KM) on EPC basis in the State of Maharashtra (Package — I) — Delay in start of work | We are planned fo start the execution of the project from 14th June 2017 as intimated to you verbally and as per the construction programme submitted to you to complete the project execution in stipulated period. Based on this, we have submitted initial Plan & Profile for a length of 34 Km, starting from Ch: 0+000 to Ch: 34+000 and also at the same time, we have mobilized rigs for carrying out soil investigation work of the bridges. , So far, we have completed detailed survey including establishment of bench marks for a length of 56 km. We are planning to submit the balance Plan & Profile of 22 Km by this weekend. Initially, we have submitted the Plan & Profile in oe copy for your review. Please go through it and suggest for 5 a modifications if any. (amr aT igre wera PUT ty, we are establishing centre line marking on the existing road and will be completed by s. In mean time, we have placed order to procure the lab equipment required for this project e€ are expecting. the delivery of the material by this weekend and we are establishing the NM temporary laboratory at the camp location and can be utilized for the time being till the camp construction completes. As per the discussions we had earlier with the Department, we are forced to take appointed date as 30.05.17, We are mobilizing our equipment to start preliminary works like Clearing and Grubbing and base compaction of the existing ground making suitable for embankment construction. But you L have given instruction not to start the work due to the various reasons which are known to you. This delay will cause slippage in achievement of milestones & completion of the project. Hence we would like to bring to your notice that, if any delay occurs due to any reason and circumstances which are beyond our control in achieving the milestone would not be considered as a failure from our side. So please permit us to start the work at the earliest. Thank you for your attention to this matter. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Preliminary / preparatory works | Contractor's Obligations | Presently, we are establishing centre line marking on the existing road and will be completed by 25.06.17. Simultaneously we have identified stone quarry at Chainage 30+000 and land for camp was finalized at Chainage 33+000 -and planning to start the camp construction by next week | synthetic_template_20250913 | Rehabilitation and Upgradation of Ghogaspargaon-Phulsangvi-Ukhandachakla-Dahiwandi-Shirur-Rakshasbhuvan-Kholayachiwadi-Karegaon-Dongarkini-Chumbli-Patoda-Dighol Road (SH-62) Kharda. From KM 0+000 to KM 56+000 to two lanes with paved shoulders” (Project Length 55.937 KM) on EPC basis in the State of Maharashtra (Package — I) — Delay in start of work | We are planned fo start the execution of the project from 14th June 2017 as intimated to you verbally and as per the construction programme submitted to you to complete the project execution in stipulated period. Based on this, we have submitted initial Plan & Profile for a length of 34 Km, starting from Ch: 0+000 to Ch: 34+000 and also at the same time, we have mobilized rigs for carrying out soil investigation work of the bridges. , So far, we have completed detailed survey including establishment of bench marks for a length of 56 km. We are planning to submit the balance Plan & Profile of 22 Km by this weekend. Initially, we have submitted the Plan & Profile in oe copy for your review. Please go through it and suggest for 5 a modifications if any. (amr aT igre wera PUT ty, we are establishing centre line marking on the existing road and will be completed by s. In mean time, we have placed order to procure the lab equipment required for this project e€ are expecting. the delivery of the material by this weekend and we are establishing the NM temporary laboratory at the camp location and can be utilized for the time being till the camp construction completes. As per the discussions we had earlier with the Department, we are forced to take appointed date as 30.05.17, We are mobilizing our equipment to start preliminary works like Clearing and Grubbing and base compaction of the existing ground making suitable for embankment construction. But you L have given instruction not to start the work due to the various reasons which are known to you. This delay will cause slippage in achievement of milestones & completion of the project. Hence we would like to bring to your notice that, if any delay occurs due to any reason and circumstances which are beyond our control in achieving the milestone would not be considered as a failure from our side. So please permit us to start the work at the earliest. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Preliminary / preparatory works | Contractor's Obligations | Presently, we are establishing centre line marking on the existing road and will be completed by 25.06.17. Simultaneously we have identified stone quarry at Chainage 30+000 and land for camp was finalized at Chainage 33+000 -and planning to start the camp construction by next week | synthetic_template_20250913 | Rehabilitation and Upgradation of Ghogaspargaon-Phulsangvi-Ukhandachakla-Dahiwandi-Shirur-Rakshasbhuvan-Kholayachiwadi-Karegaon-Dongarkini-Chumbli-Patoda-Dighol Road (SH-62) Kharda. From KM 0+000 to KM 56+000 to two lanes with paved shoulders” (Project Length 55.937 KM) on EPC basis in the State of Maharashtra (Package — I) — Delay in start of work | We are planned fo start the execution of the project from 14th June 2017 as intimated to you verbally and as per the construction programme submitted to you to complete the project execution in stipulated period. Based on this, we have submitted initial Plan & Profile for a length of 34 Km, starting from Ch: 0+000 to Ch: 34+000 and also at the same time, we have mobilized rigs for carrying out soil investigation work of the bridges. , So far, we have completed detailed survey including establishment of bench marks for a length of 56 km. We are planning to submit the balance Plan & Profile of 22 Km by this weekend. Initially, we have submitted the Plan & Profile in oe copy for your review. Please go through it and suggest for 5 a modifications if any. (amr aT igre wera PUT ty, we are establishing centre line marking on the existing road and will be completed by s. In mean time, we have placed order to procure the lab equipment required for this project e€ are expecting. the delivery of the material by this weekend and we are establishing the NM temporary laboratory at the camp location and can be utilized for the time being till the camp construction completes. As per the discussions we had earlier with the Department, we are forced to take appointed date as 30.05.17, We are mobilizing our equipment to start preliminary works like Clearing and Grubbing and base compaction of the existing ground making suitable for embankment construction. But you L have given instruction not to start the work due to the various reasons which are known to you. This delay will cause slippage in achievement of milestones & completion of the project. Hence we would like to bring to your notice that, if any delay occurs due to any reason and circumstances which are beyond our control in achieving the milestone would not be considered as a failure from our side. So please permit us to start the work at the earliest. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Preliminary / preparatory works | Contractor's Obligations | Presently, we are establishing centre line marking on the existing road and will be completed by 25.06.17. Simultaneously we have identified stone quarry at Chainage 30+000 and land for camp was finalized at Chainage 33+000 -and planning to start the camp construction by next week | synthetic_template_20250913 | Rehabilitation and Upgradation of Ghogaspargaon-Phulsangvi-Ukhandachakla-Dahiwandi-Shirur-Rakshasbhuvan-Kholayachiwadi-Karegaon-Dongarkini-Chumbli-Patoda-Dighol Road (SH-62) Kharda. From KM 0+000 to KM 56+000 to two lanes with paved shoulders” (Project Length 55.937 KM) on EPC basis in the State of Maharashtra (Package — I) — Delay in start of work | We are planned fo start the execution of the project from 14th June 2017 as intimated to you verbally and as per the construction programme submitted to you to complete the project execution in stipulated period. Based on this, we have submitted initial Plan & Profile for a length of 34 Km, starting from Ch: 0+000 to Ch: 34+000 and also at the same time, we have mobilized rigs for carrying out soil investigation work of the bridges. , So far, we have completed detailed survey including establishment of bench marks for a length of 56 km. We are planning to submit the balance Plan & Profile of 22 Km by this weekend. Initially, we have submitted the Plan & Profile in oe copy for your review. Please go through it and suggest for 5 a modifications if any. (amr aT igre wera PUT ty, we are establishing centre line marking on the existing road and will be completed by s. In mean time, we have placed order to procure the lab equipment required for this project e€ are expecting. the delivery of the material by this weekend and we are establishing the NM temporary laboratory at the camp location and can be utilized for the time being till the camp construction completes. As per the discussions we had earlier with the Department, we are forced to take appointed date as 30.05.17, We are mobilizing our equipment to start preliminary works like Clearing and Grubbing and base compaction of the existing ground making suitable for embankment construction. But you L have given instruction not to start the work due to the various reasons which are known to you. This delay will cause slippage in achievement of milestones & completion of the project. Hence we would like to bring to your notice that, if any delay occurs due to any reason and circumstances which are beyond our control in achieving the milestone would not be considered as a failure from our side. So please permit us to start the work at the earliest. We await your further instructions. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Clearances from Irrigation department for construction of Canal Bridges | Others | The Irrigation department may please be apprised of our construction programme. | synthetic_template_20250913 | Rehabilitation and Up-gradation of Paithan (Pategaon) — Mungi - Hadgaon — Bodhegaon- ~*~ Ladjaigaon — Ghogaspargaon — Phulsangvi — Ukhandachakla ~ Dahiwandi — Shirur to 2-Lane — with paved shoulder (Project Length 55.937 Km) on EPC basis in the state of Maharashtra (Package ¦ - 56 KM) — Cross drainage works in irrigation canals — reg. | Please note that We have submitted our construction programme, under reference cited above, which includes five no’s of minor bridges and existing causeways. As it is obligatory to keep the state irrigation department regarding commencement of works coming under them, we request that the irrigation department may please be apprised of our construction programme. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Clearances from Irrigation department for construction of Canal Bridges | Others | The Irrigation department may please be apprised of our construction programme. | synthetic_template_20250913 | Rehabilitation and Up-gradation of Paithan (Pategaon) — Mungi - Hadgaon — Bodhegaon- ~*~ Ladjaigaon — Ghogaspargaon — Phulsangvi — Ukhandachakla ~ Dahiwandi — Shirur to 2-Lane — with paved shoulder (Project Length 55.937 Km) on EPC basis in the state of Maharashtra (Package ¦ - 56 KM) — Cross drainage works in irrigation canals — reg. | We have submitted our construction programme, under reference cited above, which includes five no’s of minor bridges and existing causeways. As it is obligatory to keep the state irrigation department regarding commencement of works coming under them, we request that the irrigation department may please be apprised of our construction programme. Thank you for your attention to this matter. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Clearances from Irrigation department for construction of Canal Bridges | Others | The Irrigation department may please be apprised of our construction programme. | synthetic_template_20250913 | Rehabilitation and Up-gradation of Paithan (Pategaon) — Mungi - Hadgaon — Bodhegaon- ~*~ Ladjaigaon — Ghogaspargaon — Phulsangvi — Ukhandachakla ~ Dahiwandi — Shirur to 2-Lane — with paved shoulder (Project Length 55.937 Km) on EPC basis in the state of Maharashtra (Package ¦ - 56 KM) — Cross drainage works in irrigation canals — reg. | It is brought to your attention that We have submitted our construction programme, under reference cited above, which includes five no’s of minor bridges and existing causeways. As it is obligatory to keep the state irrigation department regarding commencement of works coming under them, we request that the irrigation department may please be apprised of our construction programme. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Clearances from Irrigation department for construction of Canal Bridges | Others | The Irrigation department may please be apprised of our construction programme. | synthetic_template_20250913 | Rehabilitation and Up-gradation of Paithan (Pategaon) — Mungi - Hadgaon — Bodhegaon- ~*~ Ladjaigaon — Ghogaspargaon — Phulsangvi — Ukhandachakla ~ Dahiwandi — Shirur to 2-Lane — with paved shoulder (Project Length 55.937 Km) on EPC basis in the state of Maharashtra (Package ¦ - 56 KM) — Cross drainage works in irrigation canals — reg. | We have submitted our construction programme, under reference cited above, which includes five no’s of minor bridges and existing causeways. As it is obligatory to keep the state irrigation department regarding commencement of works coming under them, we request that the irrigation department may please be apprised of our construction programme. We appreciate your cooperation in this regard. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Clearances from Irrigation department for construction of Canal Bridges | Others | The Irrigation department may please be apprised of our construction programme. | synthetic_template_20250913 | Rehabilitation and Up-gradation of Paithan (Pategaon) — Mungi - Hadgaon — Bodhegaon- ~*~ Ladjaigaon — Ghogaspargaon — Phulsangvi — Ukhandachakla ~ Dahiwandi — Shirur to 2-Lane — with paved shoulder (Project Length 55.937 Km) on EPC basis in the state of Maharashtra (Package ¦ - 56 KM) — Cross drainage works in irrigation canals — reg. | We hereby confirm that We have submitted our construction programme, under reference cited above, which includes five no’s of minor bridges and existing causeways. As it is obligatory to keep the state irrigation department regarding commencement of works coming under them, we request that the irrigation department may please be apprised of our construction programme. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Handing over of cut tree/ salvaged material to the concerned authority | Contractor's Obligations; Others | we request you to intimate us the relevant authority to handover the material | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-3/11. Heavy wind-damages 23.08.2017.pdf | Heavy wind - damages - Reg. | In the night between 19th & 20th of August, there was heavy wind, followed by rain in the stretch between Km 43 & Km 47. Due to this, a few (8 nos) trees at the edge of ROW fell down on the existing road between Km 43 & Km 45, where we had already commenced construction activity. The trees which fell on the existing road, disrupting the traffic, had to be cut and removed, to enable traffic flow. A few photographs of the cut & stockpiled trees are enclosed. We request you to intimate us the relevant authority to handover the material. | FALSE | real_data
Handing over of cut tree/ salvaged material to the concerned authority | Others | we request you to intimate us the relevant authority to handover the material | synthetic_template_20250913 | Heavy wind - damages - Reg. | In the night between 19th & 20th of August, there was heavy wind, followed by rain in the stretch between Km 43 & Km 47. Due to this, a few (8 nos) trees at the edge of ROW fell down on the existing road between Km 43 & Km 45, where we had already commenced construction activity. The trees which fell on the existing road, disrupting the traffic, had to be cut and removed, to enable traffic flow. A few photographs of the cut & stockpiled trees are enclosed. We request you to intimate us the relevant authority to handover the material. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Handing over of cut tree/ salvaged material to the concerned authority | Contractor's Obligations | we request you to intimate us the relevant authority to handover the material | synthetic_template_20250913 | Heavy wind - damages - Reg. | In the night between 19th & 20th of August, there was heavy wind, followed by rain in the stretch between Km 43 & Km 47. Due to this, a few (8 nos) trees at the edge of ROW fell down on the existing road between Km 43 & Km 45, where we had already commenced construction activity. The trees which fell on the existing road, disrupting the traffic, had to be cut and removed, to enable traffic flow. A few photographs of the cut & stockpiled trees are enclosed. We request you to intimate us the relevant authority to handover the material. Please confirm receipt of this correspondence. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Handing over of cut tree/ salvaged material to the concerned authority | Contractor's Obligations | we request you to intimate us the relevant authority to handover the material | synthetic_template_20250913 | Heavy wind - damages - Reg. | In the night between 19th & 20th of August, there was heavy wind, followed by rain in the stretch between Km 43 & Km 47. Due to this, a few (8 nos) trees at the edge of ROW fell down on the existing road between Km 43 & Km 45, where we had already commenced construction activity. The trees which fell on the existing road, disrupting the traffic, had to be cut and removed, to enable traffic flow. A few photographs of the cut & stockpiled trees are enclosed. We request you to intimate us the relevant authority to handover the material. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Schedule-H Division | Payments | The Contractor requested the Authority for bifurcation of Schedule H for their cash flow purpose. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/20191205_AE_NHAI_188_Minutes of Monthly Progress review meeting Mom-5.pdf | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to 107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Minutes of Monthly Progress review meeting Mom-5 -Reg. | With respect to the above said reference please find enclosed herewith the Minutes of Meeting Numbered as MoM-S held on 29.11.2019. The next meeting will be likely on 27.12.2019 at the Consultants office around 11.00 A.M in Kancheepuram. All the concerned are requested to attend with necessary documents. This is for your information and record. Assuring our best services at all times. | FALSE | real_data
Schedule-H Division | Payments | We are once again requesting for your benign consider our appeal, to amend table 1.3.1 of schedule "H", suitably. | synthetic_template_20250913 | Modification in minimum criteria for payment — Reg. | We have been assigned the work mentioned in the captioned subject and the EPC agreement was signed on 18! April 2017 Schedule “H” of the agreement gives the activity wise, weightage and the table 1.3.1 details (in the last column) the payment procedure. The construction period is 24 months, whereas as per the table, value of the billable payment will be 10% of Bridge works and 5% of road works, when completed. In other words, until the percentage is reached, it is not measurable. We submit to state that we have not availed the mobilization advance and due to this stringent yardstick & payment procedure, the requirement of revolving capital will be to the tune of 3 /4 months turnover, considering the minimum criteria requirement of varies key activities. M/S RCM Infrastructure lid. -P V Ramanaiah & Co. JV As this payment procedure will lead to cash flow constraints, we request that a) monthly bills of all completed works may be paid, without any percentage limitations. (OR) b) reduce the percentage which is stated as 5% to 1% and which is stated as 10% to 2%. This will enable advance procurement actions smoothly and also timely completion of the project. We are once again requesting for your benign consideration of our appeal, to amend table 1.3.1 of schedule “H”, suitably. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Schedule-H Division | Payments | We are once again requesting for your benign consider our appeal, to amend table 1.3.1 of schedule "H", suitably. | synthetic_template_20250913 | Modification in minimum criteria for payment — Reg. | Please note that We have been assigned the work mentioned in the captioned subject and the EPC agreement was signed on 18! April 2017 Schedule “H” of the agreement gives the activity wise, weightage and the table 1.3.1 details (in the last column) the payment procedure. The construction period is 24 months, whereas as per the table, value of the billable payment will be 10% of Bridge works and 5% of road works, when completed. In other words, until the percentage is reached, it is not measurable. We submit to state that we have not availed the mobilization advance and due to this stringent yardstick & payment procedure, the requirement of revolving capital will be to the tune of 3 /4 months turnover, considering the minimum criteria requirement of varies key activities. M/S RCM Infrastructure lid. -P V Ramanaiah & Co. JV As this payment procedure will lead to cash flow constraints, we request that a) monthly bills of all completed works may be paid, without any percentage limitations. (OR) b) reduce the percentage which is stated as 5% to 1% and which is stated as 10% to 2%. This will enable advance procurement actions smoothly and also timely completion of the project. We are once again requesting for your benign consideration of our appeal, to amend table 1.3.1 of schedule “H”, suitably. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Schedule-H Division | Payments | We are once again requesting for your benign consider our appeal, to amend table 1.3.1 of schedule "H", suitably. | synthetic_template_20250913 | Modification in minimum criteria for payment — Reg. | We have been assigned the work mentioned in the captioned subject and the EPC agreement was signed on 18! April 2017 Schedule “H” of the agreement gives the activity wise, weightage and the table 1.3.1 details (in the last column) the payment procedure. The construction period is 24 months, whereas as per the table, value of the billable payment will be 10% of Bridge works and 5% of road works, when completed. In other words, until the percentage is reached, it is not measurable. We submit to state that we have not availed the mobilization advance and due to this stringent yardstick & payment procedure, the requirement of revolving capital will be to the tune of 3 /4 months turnover, considering the minimum criteria requirement of varies key activities. M/S RCM Infrastructure lid. -P V Ramanaiah & Co. JV As this payment procedure will lead to cash flow constraints, we request that a) monthly bills of all completed works may be paid, without any percentage limitations. (OR) b) reduce the percentage which is stated as 5% to 1% and which is stated as 10% to 2%. This will enable advance procurement actions smoothly and also timely completion of the project. We are once again requesting for your benign consideration of our appeal, to amend table 1.3.1 of schedule “H”, suitably. Please confirm receipt of this correspondence. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Schedule-H Division | Payments | We are once again requesting for your benign consider our appeal, to amend table 1.3.1 of schedule "H", suitably. | synthetic_template_20250913 | Modification in minimum criteria for payment — Reg. | We have been assigned the work mentioned in the captioned subject and the EPC agreement was signed on 18! April 2017 Schedule “H” of the agreement gives the activity wise, weightage and the table 1.3.1 details (in the last column) the payment procedure. The construction period is 24 months, whereas as per the table, value of the billable payment will be 10% of Bridge works and 5% of road works, when completed. In other words, until the percentage is reached, it is not measurable. We submit to state that we have not availed the mobilization advance and due to this stringent yardstick & payment procedure, the requirement of revolving capital will be to the tune of 3 /4 months turnover, considering the minimum criteria requirement of varies key activities. M/S RCM Infrastructure lid. -P V Ramanaiah & Co. JV As this payment procedure will lead to cash flow constraints, we request that a) monthly bills of all completed works may be paid, without any percentage limitations. (OR) b) reduce the percentage which is stated as 5% to 1% and which is stated as 10% to 2%. This will enable advance procurement actions smoothly and also timely completion of the project. We are once again requesting for your benign consideration of our appeal, to amend table 1.3.1 of schedule “H”, suitably. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Schedule-H Division | Payments | The Contractor requested the Authority for bifurcation of Schedule H for their cash flow purpose. | synthetic_template_20250913 | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to 107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Minutes of Monthly Progress review meeting Mom-5 -Reg. | Kindly be informed that With respect to the above said reference please find enclosed herewith the Minutes of Meeting Numbered as MoM-S held on 29.11.2019. The next meeting will be likely on 27.12.2019 at the Consultants office around 11.00 A.M in Kancheepuram. All the concerned are requested to attend with necessary documents. This is for your information and record. Assuring our best services at all times. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Pending approvals | EoT | In the absence of above approvals, we are-not able to take up high value items, without which achievement of Milestone — I is not practically possible. | synthetic_template_20250913 | Rehabilitation and Up-gradation of Paithan (Pategaon) — Mungi — Hadgaon - Bodhegaon- Ladjalgaon — Ghogaspargaon — Phulsangvi — Ukhandachakla — Dahiwandi - —_ Shirur to 2-Lane with paved shoulder (Project Length 55.937 Km) on EPC basis in the state ~ of Maharashtra (Package ¦- 56 KM) - Approvals pending — Reg. | We hereby confirm that Respected Sir,\n\nVide our letter referred above, we submitted the correspondence of the past - fill then. Though Authority was kind enough to accord approval on a few key matters, we await approval of Authority Engineer on the following matters\n\ni. 2row pipe culverts drawing\nii. Method statement\niii. Drain in built-up area — drawings\niv. Toe wall with PCC (up to 3m height) drawing\nv. GSB for full formation width to serve as drainage layer(as per pre bid meetings page no 085 Of volume-ll of contract agreement}\n\nIn the absence of above approvals, we are_not able to take up high value items, without which achievement of Milestone — ¦ is not practically possible.\n\nHence, we request you to accord your approval on top priority in the aforesaid matters.\n\n | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Pending approvals | EoT | In the absence of above approvals, we are-not able to take up high value items, without which achievement of Milestone — I is not practically possible. | synthetic_template_20250913 | Rehabilitation and Up-gradation of Paithan (Pategaon) — Mungi — Hadgaon - Bodhegaon- Ladjalgaon — Ghogaspargaon — Phulsangvi — Ukhandachakla — Dahiwandi - —_ Shirur to 2-Lane with paved shoulder (Project Length 55.937 Km) on EPC basis in the state ~ of Maharashtra (Package ¦- 56 KM) - Approvals pending — Reg. | This is to notify you that Respected Sir,\n\nVide our letter referred above, we submitted the correspondence of the past - fill then. Though Authority was kind enough to accord approval on a few key matters, we await approval of Authority Engineer on the following matters\n\ni. 2row pipe culverts drawing\nii. Method statement\niii. Drain in built-up area — drawings\niv. Toe wall with PCC (up to 3m height) drawing\nv. GSB for full formation width to serve as drainage layer(as per pre bid meetings page no 085 Of volume-ll of contract agreement}\n\nIn the absence of above approvals, we are_not able to take up high value items, without which achievement of Milestone — ¦ is not practically possible.\n\nHence, we request you to accord your approval on top priority in the aforesaid matters.\n\n | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Pending approvals | Payments | In the absence of above approvals, we are-not able to take up high value items, without which achievement of Milestone — I is not practically possible. | synthetic_template_20250913 | Rehabilitation and Up-gradation of Paithan (Pategaon) — Mungi — Hadgaon - Bodhegaon- Ladjalgaon — Ghogaspargaon — Phulsangvi — Ukhandachakla — Dahiwandi - —_ Shirur to 2-Lane with paved shoulder (Project Length 55.937 Km) on EPC basis in the state ~ of Maharashtra (Package ¦- 56 KM) - Approvals pending — Reg. | This is to notify you that Respected Sir,\n\nVide our letter referred above, we submitted the correspondence of the past - fill then. Though Authority was kind enough to accord approval on a few key matters, we await approval of Authority Engineer on the following matters\n\ni. 2row pipe culverts drawing\nii. Method statement\niii. Drain in built-up area — drawings\niv. Toe wall with PCC (up to 3m height) drawing\nv. GSB for full formation width to serve as drainage layer(as per pre bid meetings page no 085 Of volume-ll of contract agreement}\n\nIn the absence of above approvals, we are_not able to take up high value items, without which achievement of Milestone — ¦ is not practically possible.\n\nHence, we request you to accord your approval on top priority in the aforesaid matters.\n\n We appreciate your cooperation in this regard. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Pending approvals | Payments | In the absence of above approvals, we are-not able to take up high value items, without which achievement of Milestone — I is not practically possible. | synthetic_template_20250913 | Rehabilitation and Up-gradation of Paithan (Pategaon) — Mungi — Hadgaon - Bodhegaon- Ladjalgaon — Ghogaspargaon — Phulsangvi — Ukhandachakla — Dahiwandi - —_ Shirur to 2-Lane with paved shoulder (Project Length 55.937 Km) on EPC basis in the state ~ of Maharashtra (Package ¦- 56 KM) - Approvals pending — Reg. | Respected Sir,\n\nVide our letter referred above, we submitted the correspondence of the past - fill then. Though Authority was kind enough to accord approval on a few key matters, we await approval of Authority Engineer on the following matters\n\ni. 2row pipe culverts drawing\nii. Method statement\niii. Drain in built-up area — drawings\niv. Toe wall with PCC (up to 3m height) drawing\nv. GSB for full formation width to serve as drainage layer(as per pre bid meetings page no 085 Of volume-ll of contract agreement}\n\nIn the absence of above approvals, we are_not able to take up high value items, without which achievement of Milestone — ¦ is not practically possible.\n\nHence, we request you to accord your approval on top priority in the aforesaid matters.\n\n | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Pending approvals | Others | In the absence of above approvals, we are-not able to take up high value items, without which achievement of Milestone — I is not practically possible. | synthetic_template_20250913 | Rehabilitation and Up-gradation of Paithan (Pategaon) — Mungi — Hadgaon - Bodhegaon- Ladjalgaon — Ghogaspargaon — Phulsangvi — Ukhandachakla — Dahiwandi - —_ Shirur to 2-Lane with paved shoulder (Project Length 55.937 Km) on EPC basis in the state ~ of Maharashtra (Package ¦- 56 KM) - Approvals pending — Reg. | We hereby confirm that Respected Sir,\n\nVide our letter referred above, we submitted the correspondence of the past - fill then. Though Authority was kind enough to accord approval on a few key matters, we await approval of Authority Engineer on the following matters\n\ni. 2row pipe culverts drawing\nii. Method statement\niii. Drain in built-up area — drawings\niv. Toe wall with PCC (up to 3m height) drawing\nv. GSB for full formation width to serve as drainage layer(as per pre bid meetings page no 085 Of volume-ll of contract agreement}\n\nIn the absence of above approvals, we are_not able to take up high value items, without which achievement of Milestone — ¦ is not practically possible.\n\nHence, we request you to accord your approval on top priority in the aforesaid matters.\n\n Please confirm receipt of this correspondence. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Pending approvals | Others | In the absence of above approvals, we are-not able to take up high value items, without which achievement of Milestone — I is not practically possible. | synthetic_template_20250913 | Rehabilitation and Up-gradation of Paithan (Pategaon) — Mungi — Hadgaon - Bodhegaon- Ladjalgaon — Ghogaspargaon — Phulsangvi — Ukhandachakla — Dahiwandi - —_ Shirur to 2-Lane with paved shoulder (Project Length 55.937 Km) on EPC basis in the state ~ of Maharashtra (Package ¦- 56 KM) - Approvals pending — Reg. | We would like to inform you that Respected Sir,\n\nVide our letter referred above, we submitted the correspondence of the past - fill then. Though Authority was kind enough to accord approval on a few key matters, we await approval of Authority Engineer on the following matters\n\ni. 2row pipe culverts drawing\nii. Method statement\niii. Drain in built-up area — drawings\niv. Toe wall with PCC (up to 3m height) drawing\nv. GSB for full formation width to serve as drainage layer(as per pre bid meetings page no 085 Of volume-ll of contract agreement}\n\nIn the absence of above approvals, we are_not able to take up high value items, without which achievement of Milestone — ¦ is not practically possible.\n\nHence, we request you to accord your approval on top priority in the aforesaid matters.\n\n | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Stage Payments Statements | Contractor's Obligations; Authority's Obligations; Payments | we request you to immediately recommend for release 90% of claimed amount and process the bill there after. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-3/14. Part payment of IPC-02 03.01.2018.pdf | Part payment of Interim payment certificate (IPC-2) — Reg. | We have submitted the Second IPC vide reference above for certification. We understand that it is under process and the review of already approved drawings is also on going. As you're aware that, we have not availed mobilization advance and machinery advance, and this is a good working season for high value items such as DLC, PQC are to be executed as per the construction programme know. These activities are cost-intensive and hence we require sufficient cash flow hence, we request you to immediately recommend for release 90% of claimed amount and process the bill there after. | FALSE | real_data
Stage Payments Statements | Contractor's Obligations; Authority's Obligations; Payments | It was requested that the Contractors / Concessionaires are requested to use the portal to communicate with the respective stakeholders, seek various approvals, submit stage payment bills with supporting details and upload their letters. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/20200422_NHAI_SPK_795_Uploading data in datalake software.pdf | NHAI, PIU, Kancheepuram - Go Live of project Management Software and Data Lake Portal w.e.f 25th April 2020 - Reg. | I wish to inform that the Chief General Manager (T/ IT), NHAI, New Delhi informed that it has been decided by the Competent Authority that with effect from 25th April 2020, all project related communications, approvals and correspondences between Contractor/ Concessionaires, AE /IE & PD/RO/HQ will be done through the Project management Software/ Data Lake Portal only. Further it was requested that the Contractors/ Concessionaire are requested to use the Portal to communicate with the respective stakeholders, seek various approvals, submit stage payment bills with supporting details and upload their letters. Similarly AEs/IEs are requested to use the portal for communicating various approvals to Contractors/ Concessionaires and taking up cases with PDs/Ros/HQ NHAI. The copy of the Circular is enclosed herewith. 2. The Project Management Software, user manual & video tutorial, help desk can be accessed by using the following: Weblink:http://13/232.225.151/NHAI or http://datalake.nhai.gov.in/nhai Helpdesk: Mr. Mihir/Mr Tanveer at 722786077 & Mr Santhosh 7905054486 Helpdesk email ID: pmshelpdesk@nhai.org 3. In view of the above it is requested to use the Project Management Software for all project related communications, approvals etc. | FALSE | real_data
Stage Payments Statements | Contractor's Obligations; Authority's Obligations; Payments | In continuation to our earlier letter stated as Ref.No.1 and based on Schedule "J" point 2 & 3 of Contract document it is to ask you to submit the "Stage Payment Statement" for further necessary action. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/20200624_AE_SPK_343_Milestone I & II_Submission of Stage Payment Statement.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode ~— Implementation of Mile Stone -1 & 2 - Reg. | In continuation to our earlier letter stated as Ref. No.1 and based on SCHEDULE “J” point 2 & 3 of Contract Document it is to ask you to submit the “Stage Payment Statement” for further necessary action. | FALSE | real_data
Stage Payments Statements | Authority's Obligations | In continuation to our earlier letter stated as Ref.No.1 and based on Schedule "J" point 2 & 3 of Contract document it is to ask you to submit the "Stage Payment Statement" for further necessary action. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode ~— Implementation of Mile Stone -1 & 2 - Reg. | In continuation to our earlier letter stated as Ref. No.1 and based on SCHEDULE “J” point 2 & 3 of Contract Document it is to ask you to submit the “Stage Payment Statement” for further necessary action. We await your further instructions. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Stage Payments Statements | Authority's Obligations | we request you to immediately recommend for release 90% of claimed amount and process the bill there after. | synthetic_template_20250913 | Part payment of Interim payment certificate (IPC-2) — Reg. | We have submitted the Second IPC vide reference above for certification. We understand that it is under process and the review of already approved drawings is also on going. As you're aware that, we have not availed mobilization advance and machinery advance, and this is a good working season for high value items such as DLC, PQC are to be executed as per the construction programme know. These activities are cost-intensive and hence we require sufficient cash flow hence, we request you to immediately recommend for release 90% of claimed amount and process the bill there after. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Stage Payments Statements | Payments | In continuation to our earlier letter stated as Ref.No.1 and based on Schedule "J" point 2 & 3 of Contract document it is to ask you to submit the "Stage Payment Statement" for further necessary action. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode ~— Implementation of Mile Stone -1 & 2 - Reg. | Please note that In continuation to our earlier letter stated as Ref. No.1 and based on SCHEDULE “J” point 2 & 3 of Contract Document it is to ask you to submit the “Stage Payment Statement” for further necessary action. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Stage Payments Statements | Payments | In continuation to our earlier letter stated as Ref.No.1 and based on Schedule "J" point 2 & 3 of Contract document it is to ask you to submit the "Stage Payment Statement" for further necessary action. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode ~— Implementation of Mile Stone -1 & 2 - Reg. | We hereby confirm that In continuation to our earlier letter stated as Ref. No.1 and based on SCHEDULE “J” point 2 & 3 of Contract Document it is to ask you to submit the “Stage Payment Statement” for further necessary action. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Stage Payments Statements | Contractor's Obligations | In continuation to our earlier letter stated as Ref.No.1 and based on Schedule "J" point 2 & 3 of Contract document it is to ask you to submit the "Stage Payment Statement" for further necessary action. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode ~— Implementation of Mile Stone -1 & 2 - Reg. | Kindly be informed that In continuation to our earlier letter stated as Ref. No.1 and based on SCHEDULE “J” point 2 & 3 of Contract Document it is to ask you to submit the “Stage Payment Statement” for further necessary action. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Change of scope due to realignment | Change of Scope; Dispute Resolution; EoT; Payments | 1. We have been instructed by Authority to change the alignment, which being a major deviation, forms change of scope. 2. we are entitled for all additional expenses/costs arising out of this variation, by Authority. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-3/16. Submission of realignment proposal between Km 12+700 & 13+500 05.05.2018.pdf | Submission of Re-alignment proposal between Km 12+700 and 13+500 — Reg. | We have for reference your letter cited above and clarify as follows: The PCL / ROW Coordinates are already furnished. The GAD with 2 spans, for skewed Minor Bridge, will be submitted separately. We have been instructed by Authority to change the alignment, which being a major deviation, forms change of scope. The conditions on the length of the bridge /span, stipulated in Contract agreement, are applicable for the bridge, which was inspected before bidding. The particular clause requires the bidder to study the ground condition and to do a survey, to decide the span as stated in schedule B (or otherwise) and quote the rates accordingly. The subject, location is in the re-alignment suggested by Authority after signing of the agreement, by both the parties which could not be foreseen by any bidder. So, no bidder could have speculated / imagined such location or a skew bridge to consider this additional cost as incidental. Hence we are entitled for all additional expenses / costs arising out of this variation, by Authority. | FALSE | real_data
Change of scope due to realignment | EoT | 1. We have been instructed by Authority to change the alignment, which being a major deviation, forms change of scope. 2. we are entitled for all additional expenses/costs arising out of this variation, by Authority. | synthetic_template_20250913 | Submission of Re-alignment proposal between Km 12+700 and 13+500 — Reg. | We have for reference your letter cited above and clarify as follows: The PCL / ROW Coordinates are already furnished. The GAD with 2 spans, for skewed Minor Bridge, will be submitted separately. We have been instructed by Authority to change the alignment, which being a major deviation, forms change of scope. The conditions on the length of the bridge /span, stipulated in Contract agreement, are applicable for the bridge, which was inspected before bidding. The particular clause requires the bidder to study the ground condition and to do a survey, to decide the span as stated in schedule B (or otherwise) and quote the rates accordingly. The subject, location is in the re-alignment suggested by Authority after signing of the agreement, by both the parties which could not be foreseen by any bidder. So, no bidder could have speculated / imagined such location or a skew bridge to consider this additional cost as incidental. Hence we are entitled for all additional expenses / costs arising out of this variation, by Authority. We await your further instructions. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Change of scope due to realignment | EoT | 1. We have been instructed by Authority to change the alignment, which being a major deviation, forms change of scope. 2. we are entitled for all additional expenses/costs arising out of this variation, by Authority. | synthetic_template_20250913 | Submission of Re-alignment proposal between Km 12+700 and 13+500 — Reg. | Kindly be informed that We have for reference your letter cited above and clarify as follows: The PCL / ROW Coordinates are already furnished. The GAD with 2 spans, for skewed Minor Bridge, will be submitted separately. We have been instructed by Authority to change the alignment, which being a major deviation, forms change of scope. The conditions on the length of the bridge /span, stipulated in Contract agreement, are applicable for the bridge, which was inspected before bidding. The particular clause requires the bidder to study the ground condition and to do a survey, to decide the span as stated in schedule B (or otherwise) and quote the rates accordingly. The subject, location is in the re-alignment suggested by Authority after signing of the agreement, by both the parties which could not be foreseen by any bidder. So, no bidder could have speculated / imagined such location or a skew bridge to consider this additional cost as incidental. Hence we are entitled for all additional expenses / costs arising out of this variation, by Authority. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Change of scope due to realignment | Change of Scope | 1. We have been instructed by Authority to change the alignment, which being a major deviation, forms change of scope. 2. we are entitled for all additional expenses/costs arising out of this variation, by Authority. | synthetic_template_20250913 | Submission of Re-alignment proposal between Km 12+700 and 13+500 — Reg. | We have for reference your letter cited above and clarify as follows: The PCL / ROW Coordinates are already furnished. The GAD with 2 spans, for skewed Minor Bridge, will be submitted separately. We have been instructed by Authority to change the alignment, which being a major deviation, forms change of scope. The conditions on the length of the bridge /span, stipulated in Contract agreement, are applicable for the bridge, which was inspected before bidding. The particular clause requires the bidder to study the ground condition and to do a survey, to decide the span as stated in schedule B (or otherwise) and quote the rates accordingly. The subject, location is in the re-alignment suggested by Authority after signing of the agreement, by both the parties which could not be foreseen by any bidder. So, no bidder could have speculated / imagined such location or a skew bridge to consider this additional cost as incidental. Hence we are entitled for all additional expenses / costs arising out of this variation, by Authority. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Change of scope due to realignment | Change of Scope | 1. We have been instructed by Authority to change the alignment, which being a major deviation, forms change of scope. 2. we are entitled for all additional expenses/costs arising out of this variation, by Authority. | synthetic_template_20250913 | Submission of Re-alignment proposal between Km 12+700 and 13+500 — Reg. | This is to notify you that We have for reference your letter cited above and clarify as follows: The PCL / ROW Coordinates are already furnished. The GAD with 2 spans, for skewed Minor Bridge, will be submitted separately. We have been instructed by Authority to change the alignment, which being a major deviation, forms change of scope. The conditions on the length of the bridge /span, stipulated in Contract agreement, are applicable for the bridge, which was inspected before bidding. The particular clause requires the bidder to study the ground condition and to do a survey, to decide the span as stated in schedule B (or otherwise) and quote the rates accordingly. The subject, location is in the re-alignment suggested by Authority after signing of the agreement, by both the parties which could not be foreseen by any bidder. So, no bidder could have speculated / imagined such location or a skew bridge to consider this additional cost as incidental. Hence we are entitled for all additional expenses / costs arising out of this variation, by Authority. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Change of scope due to realignment | Payments | 1. We have been instructed by Authority to change the alignment, which being a major deviation, forms change of scope. 2. we are entitled for all additional expenses/costs arising out of this variation, by Authority. | synthetic_template_20250913 | Submission of Re-alignment proposal between Km 12+700 and 13+500 — Reg. | We have for reference your letter cited above and clarify as follows: The PCL / ROW Coordinates are already furnished. The GAD with 2 spans, for skewed Minor Bridge, will be submitted separately. We have been instructed by Authority to change the alignment, which being a major deviation, forms change of scope. The conditions on the length of the bridge /span, stipulated in Contract agreement, are applicable for the bridge, which was inspected before bidding. The particular clause requires the bidder to study the ground condition and to do a survey, to decide the span as stated in schedule B (or otherwise) and quote the rates accordingly. The subject, location is in the re-alignment suggested by Authority after signing of the agreement, by both the parties which could not be foreseen by any bidder. So, no bidder could have speculated / imagined such location or a skew bridge to consider this additional cost as incidental. Hence we are entitled for all additional expenses / costs arising out of this variation, by Authority. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Change of scope due to realignment | Payments | 1. We have been instructed by Authority to change the alignment, which being a major deviation, forms change of scope. 2. we are entitled for all additional expenses/costs arising out of this variation, by Authority. | synthetic_template_20250913 | Submission of Re-alignment proposal between Km 12+700 and 13+500 — Reg. | We have for reference your letter cited above and clarify as follows: The PCL / ROW Coordinates are already furnished. The GAD with 2 spans, for skewed Minor Bridge, will be submitted separately. We have been instructed by Authority to change the alignment, which being a major deviation, forms change of scope. The conditions on the length of the bridge /span, stipulated in Contract agreement, are applicable for the bridge, which was inspected before bidding. The particular clause requires the bidder to study the ground condition and to do a survey, to decide the span as stated in schedule B (or otherwise) and quote the rates accordingly. The subject, location is in the re-alignment suggested by Authority after signing of the agreement, by both the parties which could not be foreseen by any bidder. So, no bidder could have speculated / imagined such location or a skew bridge to consider this additional cost as incidental. Hence we are entitled for all additional expenses / costs arising out of this variation, by Authority. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Change of scope due to realignment | Dispute Resolution | 1. We have been instructed by Authority to change the alignment, which being a major deviation, forms change of scope. 2. we are entitled for all additional expenses/costs arising out of this variation, by Authority. | synthetic_template_20250913 | Submission of Re-alignment proposal between Km 12+700 and 13+500 — Reg. | We have for reference your letter cited above and clarify as follows: The PCL / ROW Coordinates are already furnished. The GAD with 2 spans, for skewed Minor Bridge, will be submitted separately. We have been instructed by Authority to change the alignment, which being a major deviation, forms change of scope. The conditions on the length of the bridge /span, stipulated in Contract agreement, are applicable for the bridge, which was inspected before bidding. The particular clause requires the bidder to study the ground condition and to do a survey, to decide the span as stated in schedule B (or otherwise) and quote the rates accordingly. The subject, location is in the re-alignment suggested by Authority after signing of the agreement, by both the parties which could not be foreseen by any bidder. So, no bidder could have speculated / imagined such location or a skew bridge to consider this additional cost as incidental. Hence we are entitled for all additional expenses / costs arising out of this variation, by Authority. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Providing and maintaining highway patrol, ambulance, emergency medical services and cranes etc. for safe operation of the Highway | Contractor's Obligations; Dispute Resolution; Change of Scope | In view of the above and as per Article 2.1(a), Schedule-C, Sl.No.2.7,2.8,2.9 & 2.10 and as per Article 10.4.1, it is requested you to take necessary action for deploying the Highway Patrol, Ambulance, Emergency Medical Services and Cranes immediately. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/Lot-12/010_ 06072019_Maintanance of Highway Patrol, Ambulance, Cranes etc.,.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode. Maintenance of Highway Patrol, Ambulance, Cranes etc., — reg. | This is in reference to the vide cited reference letter (1), the Authority has requested the Contractor to mobilize the Highway Patrol, Ambulance, Emergency Medical Services and Cranes. We reiterate the Article quoted by the Authority once again below for your ready reference, i, As per Article 2. 1(a), - the scope of the project includes construction of highway on the site set forth in Schedule — A and as specified in Schedule — B together with provision of Project Facilities as specified in Schedule — C and in conformity with the specifications and standards set forth in Schedule — D. ii. As per Schedule — C, Annexure — I — Project facility for Six laning, vide item No. 2.7, 2.8, 2.9 & 2.10 the Contractor has to maintain Highway Patrol, Ambulances, Emergency Medical Services and Cranes covering the entire project Highway. Further as per Clause 10.4 Maintenance during Construction period, the Contractor shall at all times be responsible for ensuring safe operation of the Project Highway. In this regard, it is informed that Article 10.4.1 states that”......For the avoidance of doubt, it is agreed that the Contractor shall at all times be responsible for ensuring safe operation of the Project Highway” Further article 10.4.2 states that “ Notwithstanding anything to the contrary contained in this Agreement, in the event of default by the Contractor in discharging the obligations specified in clause 10.4.1 above, the Authority shall get these maintenance works done as recommended by the Authority’s Engineer to avoid public inconvenience at the risk at the risk and cost of the Contractor in order to keep the road in traffic worthy condition.” Providing Highway Patrol, Ambulance, Emergency Medical Services and Cranes etc. are required for the safe operation of the Highway. Also the Authority has informed, during the inspection on 04.07.2019, it is noticed that the Contractor has not been mobilized the Highway Patrol, Ambulances, Emergency Medical Services and Cranes so far. In view of the above and as per Article 2.1(a), Schedule — C, SI. No. 2.7, 2.8, 2.9 & 2.10 and as per Article 10.4.1, it is requested you to take necessary action for deploying the Highway Patrol, Ambulance, Emergency Medical Services and Cranes immediately. This is for your information and necessary action please. | FALSE | real_data
Providing and maintaining highway patrol, ambulance, emergency medical services and cranes etc. for safe operation of the Highway | Dispute Resolution | In view of the above and as per Article 2.1(a), Schedule-C, Sl.No.2.7,2.8,2.9 & 2.10 and as per Article 10.4.1, it is requested you to take necessary action for deploying the Highway Patrol, Ambulance, Emergency Medical Services and Cranes immediately. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode. Maintenance of Highway Patrol, Ambulance, Cranes etc., — reg. | This is in reference to the vide cited reference letter (1), the Authority has requested the Contractor to mobilize the Highway Patrol, Ambulance, Emergency Medical Services and Cranes. We reiterate the Article quoted by the Authority once again below for your ready reference, i, As per Article 2. 1(a), - the scope of the project includes construction of highway on the site set forth in Schedule — A and as specified in Schedule — B together with provision of Project Facilities as specified in Schedule — C and in conformity with the specifications and standards set forth in Schedule — D. ii. As per Schedule — C, Annexure — I — Project facility for Six laning, vide item No. 2.7, 2.8, 2.9 & 2.10 the Contractor has to maintain Highway Patrol, Ambulances, Emergency Medical Services and Cranes covering the entire project Highway. Further as per Clause 10.4 Maintenance during Construction period, the Contractor shall at all times be responsible for ensuring safe operation of the Project Highway. In this regard, it is informed that Article 10.4.1 states that”......For the avoidance of doubt, it is agreed that the Contractor shall at all times be responsible for ensuring safe operation of the Project Highway” Further article 10.4.2 states that “ Notwithstanding anything to the contrary contained in this Agreement, in the event of default by the Contractor in discharging the obligations specified in clause 10.4.1 above, the Authority shall get these maintenance works done as recommended by the Authority’s Engineer to avoid public inconvenience at the risk at the risk and cost of the Contractor in order to keep the road in traffic worthy condition.” Providing Highway Patrol, Ambulance, Emergency Medical Services and Cranes etc. are required for the safe operation of the Highway. Also the Authority has informed, during the inspection on 04.07.2019, it is noticed that the Contractor has not been mobilized the Highway Patrol, Ambulances, Emergency Medical Services and Cranes so far. In view of the above and as per Article 2.1(a), Schedule — C, SI. No. 2.7, 2.8, 2.9 & 2.10 and as per Article 10.4.1, it is requested you to take necessary action for deploying the Highway Patrol, Ambulance, Emergency Medical Services and Cranes immediately. This is for your information and necessary action please. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Providing and maintaining highway patrol, ambulance, emergency medical services and cranes etc. for safe operation of the Highway | Dispute Resolution | In view of the above and as per Article 2.1(a), Schedule-C, Sl.No.2.7,2.8,2.9 & 2.10 and as per Article 10.4.1, it is requested you to take necessary action for deploying the Highway Patrol, Ambulance, Emergency Medical Services and Cranes immediately. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode. Maintenance of Highway Patrol, Ambulance, Cranes etc., — reg. | This is in reference to the vide cited reference letter (1), the Authority has requested the Contractor to mobilize the Highway Patrol, Ambulance, Emergency Medical Services and Cranes. We reiterate the Article quoted by the Authority once again below for your ready reference, i, As per Article 2. 1(a), - the scope of the project includes construction of highway on the site set forth in Schedule — A and as specified in Schedule — B together with provision of Project Facilities as specified in Schedule — C and in conformity with the specifications and standards set forth in Schedule — D. ii. As per Schedule — C, Annexure — I — Project facility for Six laning, vide item No. 2.7, 2.8, 2.9 & 2.10 the Contractor has to maintain Highway Patrol, Ambulances, Emergency Medical Services and Cranes covering the entire project Highway. Further as per Clause 10.4 Maintenance during Construction period, the Contractor shall at all times be responsible for ensuring safe operation of the Project Highway. In this regard, it is informed that Article 10.4.1 states that”......For the avoidance of doubt, it is agreed that the Contractor shall at all times be responsible for ensuring safe operation of the Project Highway” Further article 10.4.2 states that “ Notwithstanding anything to the contrary contained in this Agreement, in the event of default by the Contractor in discharging the obligations specified in clause 10.4.1 above, the Authority shall get these maintenance works done as recommended by the Authority’s Engineer to avoid public inconvenience at the risk at the risk and cost of the Contractor in order to keep the road in traffic worthy condition.” Providing Highway Patrol, Ambulance, Emergency Medical Services and Cranes etc. are required for the safe operation of the Highway. Also the Authority has informed, during the inspection on 04.07.2019, it is noticed that the Contractor has not been mobilized the Highway Patrol, Ambulances, Emergency Medical Services and Cranes so far. In view of the above and as per Article 2.1(a), Schedule — C, SI. No. 2.7, 2.8, 2.9 & 2.10 and as per Article 10.4.1, it is requested you to take necessary action for deploying the Highway Patrol, Ambulance, Emergency Medical Services and Cranes immediately. This is for your information and necessary action please. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Providing and maintaining highway patrol, ambulance, emergency medical services and cranes etc. for safe operation of the Highway | Change of Scope | In view of the above, it is requested the Contractor may be requested to take necessary action for the deploying the Highway Patrol, Ambulance, Emergency Medical Services and Cranes as per Article 2.1(a), Schedule-C, Sl.No.2.7,2.8,2.9 & 2.10 and as per Article 10.4.1 immediately. | synthetic_template_20250913 | NHAI — PIU, Kancheepuram - Six laning of Karaipattai - Walajahpet Section of NH-4 from Km 71/015 to Km 107/091 in the State of Tamil Nadu under NHDP Phase V under EPC mode - M/s. SPK & CO — Scope of the Project - Maintenance of Highway Patrol, Ambulance, Cranes etc - reg. | Kindly be informed that Vide reference 2nd cited above, wherein the Contractor was requested to submit the action taken report on achievements of the stretch during construction period. Further vide reference 1st cited above, the Contractor was once again requested to mobilize the Highway Patrol, Ambulance, Emergency Medical Services and Cranes duly mentioning the following: i. As per Article 2.1(a), - the scope of the project includes construction of highway on the site set forth in Schedule - A and as specified in Schedule — B together with the provision of Project Facilities as specified in Schedule — C and in conformity with the specifications and standards set forth in Schedule — D. ii. As per Schedule — C, Annexure — I — Project facility for six laning, vide item No.2.7, 2.8, 2.9 & 2.10 the Contractor has to maintain Highway Patrol, Ambulances, Emergency Medical Services and Cranes covering the entire project Highway. Further as per Clause 10.4 — Maintenance during construction period the Contractor shall at all times be responsible for ensuring safe operation of the Project Highway. 3: In this regard, it is informed that article 10.4.1 states that “..... For the avoidance of doubt, it is agreed that the Contractor shall at all times be responsible for ensuring safe operation of the Project Highway”. Further article 10.4.2 states that “Notwithstanding anything to the contrary contained in this Agreement, in the event of default by the Contractor in discharging the obligations specified in Clause 10.4.1 above, the Authority shall get these maintenance works done as recommended by the Authority’s Engineer to avoid public inconvenience at the risk and cost of the Contractor in order to keep the road in traffic worthy condition.” Providing Highway Patrol, Ambulance, Emergency Medical Services and Cranes etc are required for the safe operation of the Highway. 4. During the inspection on 04.07.2019, it is noticed that the Contractor had not been mobilized the Highway Patrol, Ambulances, Emergency Medical Services and Cranes so far. The copy of references are enclosed herewith. 5. In view of the above, it is requested the Contractor may be requested to take necessary action for the deploying the Highway Patrol, Ambulance, Emergency Medical Services and Cranes as per article 2.1(a), Schedule C, S1.No.2.7, 2.8, 2.9 & 2.10 and as per article 10.4.1 immediately. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Providing and maintaining highway patrol, ambulance, emergency medical services and cranes etc. for safe operation of the Highway | Change of Scope | In view of the above and as per Article 2.1(a), Schedule-C, Sl.No.2.7,2.8,2.9 & 2.10 and as per Article 10.4.1, it is requested you to take necessary action for deploying the Highway Patrol, Ambulance, Emergency Medical Services and Cranes immediately. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode. Maintenance of Highway Patrol, Ambulance, Cranes etc., — reg. | This is in reference to the vide cited reference letter (1), the Authority has requested the Contractor to mobilize the Highway Patrol, Ambulance, Emergency Medical Services and Cranes. We reiterate the Article quoted by the Authority once again below for your ready reference, i, As per Article 2. 1(a), - the scope of the project includes construction of highway on the site set forth in Schedule — A and as specified in Schedule — B together with provision of Project Facilities as specified in Schedule — C and in conformity with the specifications and standards set forth in Schedule — D. ii. As per Schedule — C, Annexure — I — Project facility for Six laning, vide item No. 2.7, 2.8, 2.9 & 2.10 the Contractor has to maintain Highway Patrol, Ambulances, Emergency Medical Services and Cranes covering the entire project Highway. Further as per Clause 10.4 Maintenance during Construction period, the Contractor shall at all times be responsible for ensuring safe operation of the Project Highway. In this regard, it is informed that Article 10.4.1 states that”......For the avoidance of doubt, it is agreed that the Contractor shall at all times be responsible for ensuring safe operation of the Project Highway” Further article 10.4.2 states that “ Notwithstanding anything to the contrary contained in this Agreement, in the event of default by the Contractor in discharging the obligations specified in clause 10.4.1 above, the Authority shall get these maintenance works done as recommended by the Authority’s Engineer to avoid public inconvenience at the risk at the risk and cost of the Contractor in order to keep the road in traffic worthy condition.” Providing Highway Patrol, Ambulance, Emergency Medical Services and Cranes etc. are required for the safe operation of the Highway. Also the Authority has informed, during the inspection on 04.07.2019, it is noticed that the Contractor has not been mobilized the Highway Patrol, Ambulances, Emergency Medical Services and Cranes so far. In view of the above and as per Article 2.1(a), Schedule — C, SI. No. 2.7, 2.8, 2.9 & 2.10 and as per Article 10.4.1, it is requested you to take necessary action for deploying the Highway Patrol, Ambulance, Emergency Medical Services and Cranes immediately. This is for your information and necessary action please. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Providing and maintaining highway patrol, ambulance, emergency medical services and cranes etc. for safe operation of the Highway | Contractor's Obligations | In view of the above and as per Article 2.1(a), Schedule-C, Sl.No.2.7,2.8,2.9 & 2.10 and as per Article 10.4.1, it is requested you to take necessary action for deploying the Highway Patrol, Ambulance, Emergency Medical Services and Cranes immediately. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode. Maintenance of Highway Patrol, Ambulance, Cranes etc., — reg. | We would like to inform you that This is in reference to the vide cited reference letter (1), the Authority has requested the Contractor to mobilize the Highway Patrol, Ambulance, Emergency Medical Services and Cranes. We reiterate the Article quoted by the Authority once again below for your ready reference, i, As per Article 2. 1(a), - the scope of the project includes construction of highway on the site set forth in Schedule — A and as specified in Schedule — B together with provision of Project Facilities as specified in Schedule — C and in conformity with the specifications and standards set forth in Schedule — D. ii. As per Schedule — C, Annexure — I — Project facility for Six laning, vide item No. 2.7, 2.8, 2.9 & 2.10 the Contractor has to maintain Highway Patrol, Ambulances, Emergency Medical Services and Cranes covering the entire project Highway. Further as per Clause 10.4 Maintenance during Construction period, the Contractor shall at all times be responsible for ensuring safe operation of the Project Highway. In this regard, it is informed that Article 10.4.1 states that”......For the avoidance of doubt, it is agreed that the Contractor shall at all times be responsible for ensuring safe operation of the Project Highway” Further article 10.4.2 states that “ Notwithstanding anything to the contrary contained in this Agreement, in the event of default by the Contractor in discharging the obligations specified in clause 10.4.1 above, the Authority shall get these maintenance works done as recommended by the Authority’s Engineer to avoid public inconvenience at the risk at the risk and cost of the Contractor in order to keep the road in traffic worthy condition.” Providing Highway Patrol, Ambulance, Emergency Medical Services and Cranes etc. are required for the safe operation of the Highway. Also the Authority has informed, during the inspection on 04.07.2019, it is noticed that the Contractor has not been mobilized the Highway Patrol, Ambulances, Emergency Medical Services and Cranes so far. In view of the above and as per Article 2.1(a), Schedule — C, SI. No. 2.7, 2.8, 2.9 & 2.10 and as per Article 10.4.1, it is requested you to take necessary action for deploying the Highway Patrol, Ambulance, Emergency Medical Services and Cranes immediately. This is for your information and necessary action please. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Providing and maintaining highway patrol, ambulance, emergency medical services and cranes etc. for safe operation of the Highway | Contractor's Obligations | In view of the above and as per Article 2.1(a), Schedule-C, Sl.No.2.7,2.8,2.9 & 2.10 and as per Article 10.4.1, it is requested you to take necessary action for deploying the Highway Patrol, Ambulance, Emergency Medical Services and Cranes immediately. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode. Maintenance of Highway Patrol, Ambulance, Cranes etc., — reg. | It is brought to your attention that This is in reference to the vide cited reference letter (1), the Authority has requested the Contractor to mobilize the Highway Patrol, Ambulance, Emergency Medical Services and Cranes. We reiterate the Article quoted by the Authority once again below for your ready reference, i, As per Article 2. 1(a), - the scope of the project includes construction of highway on the site set forth in Schedule — A and as specified in Schedule — B together with provision of Project Facilities as specified in Schedule — C and in conformity with the specifications and standards set forth in Schedule — D. ii. As per Schedule — C, Annexure — I — Project facility for Six laning, vide item No. 2.7, 2.8, 2.9 & 2.10 the Contractor has to maintain Highway Patrol, Ambulances, Emergency Medical Services and Cranes covering the entire project Highway. Further as per Clause 10.4 Maintenance during Construction period, the Contractor shall at all times be responsible for ensuring safe operation of the Project Highway. In this regard, it is informed that Article 10.4.1 states that”......For the avoidance of doubt, it is agreed that the Contractor shall at all times be responsible for ensuring safe operation of the Project Highway” Further article 10.4.2 states that “ Notwithstanding anything to the contrary contained in this Agreement, in the event of default by the Contractor in discharging the obligations specified in clause 10.4.1 above, the Authority shall get these maintenance works done as recommended by the Authority’s Engineer to avoid public inconvenience at the risk at the risk and cost of the Contractor in order to keep the road in traffic worthy condition.” Providing Highway Patrol, Ambulance, Emergency Medical Services and Cranes etc. are required for the safe operation of the Highway. Also the Authority has informed, during the inspection on 04.07.2019, it is noticed that the Contractor has not been mobilized the Highway Patrol, Ambulances, Emergency Medical Services and Cranes so far. In view of the above and as per Article 2.1(a), Schedule — C, SI. No. 2.7, 2.8, 2.9 & 2.10 and as per Article 10.4.1, it is requested you to take necessary action for deploying the Highway Patrol, Ambulance, Emergency Medical Services and Cranes immediately. This is for your information and necessary action please. We look forward to your response. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Maintenance of diversion road/ existing road | Contractor's Obligations | Considering the Contract Agreement Clause No.10.4 you have been asked t take up necessary steps for effective maintenance and for smooth flow of traffic on the project Highway. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/Lot-12/065-09082019_Maintenance of Highway.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode. Maintenance of Highway - Reg | Please find enclosed herewith a communication bearing No. NHAI/11036/4/2019/PIU. Kanchee/1856 dated 5th August 2019 received from PD PIU NHAI Kancheepuram (Marked to yourself also) relating to a tragic incident in NHAI Project Road because of improper maintenance of the user road. In view of the above and considering the Contract Agreement Clause No. 10.4 you have been asked to take up necessary steps for effective maintenance and for smooth flow of traffic on the project Highway. | FALSE | real_data
Maintenance of diversion road/ existing road | Contractor's Obligations | You are hereby once again asked to complete the rectification works of POT Holes and make the Carriageway a smooth motorable on top priority. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/Lot-12/20201210_AE_SPK_494_Maintenance during Construction Contract Article 10.4.1 & 2.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode - Maintenance during Construction Contract Article 10.4.1 & 2 - Reg. | In continuation to the above said Ref. No.3 please find enclosed herewith the Hon'ble Division Bench of the High Court of Madras order restricting the NHAI to collect the toll to 50% of the actual amount in both the toll booths at Maduravoyal and Kaveripakkam, considering the condition/non-maintenance of the road from Maduravoal to Ranipet. Hence based on the above you are hereby once again asked to complete the rectification works of POT Holes and make the Carriageway a smooth motorable on top priority. Your early and immediate action will pave the way for submission of compliance on the subject to the Hon’ble High Court Bench well in time. This is for your information and necessary immediate action. | FALSE | real_data
Maintenance of diversion road/ existing road | Contractor's Obligations | Considering the present road condition you are hereby asked to expedite the steps already taken by you to provide a smooth riding surface to the road users ASAP. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/Lot-12/20201211_AE_SPK_495_Maintenance during Construction Contract Article 10.4.1 & 2..pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode -Maintenance during Construction Contract Article 10.4.1 & 2.- Reg. | In continuation to the above said references please find enclosed herewith a communication bearing No. NHAI/11015/233/2019/RO/Chennai/3545 dated 11 December 2020 from RO Chennai expressing his concern and apprehending about the likely consequences based on the Hon'ble Court Verdict and Media Reports about the maintenance of the Project Corridor from Ch. Km. 71+015 to 107+091. You aware that the same issue was addressed to you in the previous occasions as well. Hence based on the above and considering the present road condition you are hereby asked to expedite the steps already taken by you, to provide a smooth riding surface to the road users ASAP. | FALSE | real_data
Maintenance of diversion road/ existing road | Contractor's Obligations | You are therefore directed to maintain the road as per the above contract stipulation. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/Lot-12/20201211_RO_SPK_3545_Maintenance of existing road stretches.pdf | NHAI, RO Chennai - PIU, Kancheepuram - Six Laning of Karaipettai - Walajahpet section of NH-4 (New NH-48) from Km.71/015 to Km.107/091 in the state of Tamil Nadu under NHDP Phase-V (Pkg-l) - Maintenance of existing road stretches - Directions of Hon’ble High Court of Madras to reduce the user-fee by 50% - Reg. | Kindly refer to the media reports and Hon’ble High Court of Madras order dated 09.12.2020 on the deplorable condition of NH-4, that also belong to your stretch. The Hon’ble High Court has ordered for reduction of user-fee by 50% till the damages are repaired as per the IRC standards. 2. In this regard, reference is invited to Clause 10.4 of the Contract Agreement, which is reproduced below; “10.4.1.During the construction period, the Contractor shall maintain, at its cost, the existing lanes(s) of the Project Highway so that the traffic worthiness and safety thereof are at no time materially inferior as compared to their condition 10 (ten) days prior to the date of this Agreement, and shall undertake the necessary repair and maintenance works for this purpose; provided that the Contractor may, at its cost, interrupt and divert the flow of traffic if such interruption and diversion is necessary for the efficient progress of Works and conforms to Good Industry Practice; provided further that such interruption and diversion shall be undertaken by the Contractor only with the prior written approval of the Authority’s Engineer "Y, a) shall not be unreasonably withheld. For the avoidance of doubt, it is agreed that the Contractor shall at all times be responsible for ensuring safe operation of the Project Highway. It is further agreed that in the event the Project includes construction of a bypass or tunnel and realignment of the existing carriageway, the Contractor shall maintain the existing highway in such sections until the new Works are open to traffic. 3. From the above, it is amply clear that the existing road is to be maintained by you in traffic worthy condition for safe operation. You are, therefore, directed to maintain the road as per the above contract stipulation. In case any fine / reduction in toll is to be borne by NHAI on account of your failure in maintaining the road, the same shall have to be necessarily charged to you. 4, It is, therefore requested that you may take all necessary action to avoid recurrence of such incident. | FALSE | real_data
Maintenance of diversion road/ existing road | Contractor's Obligations | Through the above said ref No's 8,9 & 10 and on several occasions, it is hereby asked to attend the filling of POT Holes in project stretch due to recent Cyclones followed by incessant rains and make road traffic worthy | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/Lot-12/20201217_AE_SPK_499-Maintenance of the existing road as per the Article 10.4 of the Contract Agreement.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode — Maintenance of the existing road as per the Article 10.4 of the Contract Agreement — Reg. | Through the above said Ref. No’s 8, 9 & 10 and on several occasions, it is hereby asked to attend the filling of POT Holes formed in Project stretch due to recent Cyclones followed by incessant rains and make road traffic worthy vide Article no.10.4. But due to lack of improper efforts from your end the corrective action of “Filling of Pot holes” got delayed. This has sought the intervention of Hon’ble Court on a Sue Moto and formed a Court Order restricting the NHAI to reduce the user fee rates at the Chennasamudram Toll Plaza to 50% of the actual charges. The same was informed to yourself vide Ref. No. 1 by the Project director PIU Kancheepuram. Further in the same communication while accepting the Hon’ble Court Order the Competent Authority from NHAI approved to collect the Toll at Chennasamudram Toll Plaza to 50% of the user-fee with a direction to fix the responsibility and recover the money loss on your head of account. Accordingly, the same is endorsed by this office and communicated. This is for your information and necessary action please. | FALSE | real_data
Maintenance of diversion road/ existing road | Contractor's Obligations | The Authority has asked the Contractor to fill up the potholes also to make the road safe for users | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/089_31082019_Minutes of Monthly Progress review meeting.pdf | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to 107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Minutes of Monthly Progress review meeting -Reg. | With respect to the above said reference please find enclosed herewith the minutes of meeting MoM -2 held on 27.08.2019. The venue and date for the next meeting will be intimated in due course of time. This is for your information and record. | FALSE | real_data
Maintenance of diversion road/ existing road | Contractor's Obligations | The Authority has asked the Contractor to attend the POT holes which are formed due to the recent heavy rains and similarly clear the bushes at median locations to make the road safe for users. The Contractor informed that the pot holes formed will be attended shortly. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/20191205_AE_NHAI_188_Minutes of Monthly Progress review meeting Mom-5.pdf | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to 107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Minutes of Monthly Progress review meeting Mom-5 -Reg. | With respect to the above said reference please find enclosed herewith the Minutes of Meeting Numbered as MoM-S held on 29.11.2019. The next meeting will be likely on 27.12.2019 at the Consultants office around 11.00 A.M in Kancheepuram. All the concerned are requested to attend with necessary documents. This is for your information and record. Assuring our best services at all times. | FALSE | real_data
Maintenance of diversion road/ existing road | Contractor's Obligations | All potholes are filled, and road repairs are conducted regularly. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-2/12. 20240728_564_Cont_AE_Progress of works.pdf | Rehabilitation and Upgradation of Satana to Mangrul (Chandwad) Section of NH 752 G Design Ch. KM 64+000 to KM 1014140 Two Lane with Paved Shoulder / Four Lane Configuration in the state of Maharashtra on EPC Mode. Reg. Progress of works. | We refer to your letter at ref. 2, wherein you have conveyed your observations on the progress of works in the above-mentioned project stretch. In this regard, please find our para-wise reply below: 1. Slow Progress of works It is mentioned in your letter that the work front of 11.4 Km from Km.64+000 to 75+400 is available to us. This is contrary to the actual site condition, the land available for works as on date is only 8.52 Km. The details of unavailable stretches are as follows: a) Km 65+000 to 66+490 (1.490 km) - Satana Market: Full width of the Right of Way (ROW) is not available as the encroachments have not been removed. Despite several meetings held with the Satana Tehsildar, Local MLA and the public, in the presence of the Authority and Authority’s Engineer (AE), the issue remains unresolved even as on date. b) Km 66+520 to 66+600 (LHS), 67+560 to 67+650 (LHS), 71+930 to 72+000 (LHS): Land Acquisition at the above locations is not yet completed by the Authority even as on date. c) Km 68+780 to 68+830 (LHS): Encroachments have not been removed, specifically a temple, which has not been removed by the Authority. d) Km 74+100 to 74+700 & 74+900 to 75+400 - Thengode-Lohner Market: Full width of the ROW is not available at these locations as the encroachments have not been removed even as on date. The status of completed works in the available stretch of 8.52 km is as below: ° PQC (Pavement Quality Concrete): 2.3 km (LHS) ° DLC (Dry Lean Concrete): 3.70 km (LHS) ° GSB (Granular Sub-base): 4.1 km (LHS) ° Subgrade: 4.6 km (LHS) ° Subgrade widening on RHS: km 69+000 to 74+600, i.e., 5.6 km. The works of minor bridges at Km. 67+710 and 68+800 could not be started due to the pending land acquisition issues which are yet to be cleared. Though the construction of Minor Bridge at km 71+910 was commenced in the last month, the same got halted due to heavy rains. To avoid idling, the manpower was shifted to other works and was again remobilized to the structure on 27.07.2024 and the work was resumed. The work on the slab drains at km 70+050 and km 70+100 is in progress and will be completed within a month. We assure you that all pipe culvert works from km 64+000 to 75+000 will be completed within a month. For the four-lane portion from km 64+000 to km 64+800, the scope of new Jersey-type divider is only of 590 meters, for which the PCC work is completed, balance work is in progress and will be completed at the earliest. The terminal slab work on one half of km 94+420 (RHS) is pending and will be completed after diversion of traffic movement onto LHS. 2. Shifting of Utilities Regarding shifting of Electrical Utilities, we wish to submit that the estimate approvals for shifting the utilities were accorded by the Competent Authority for Chandwad section in the month of May’24 and for Deola and Satana sections in the Month of June’24. Despite the delayed approvals from the authorities, we have completed the works for Chandwad section, and the works of Deola and Satana sections were started as soon as we have received the approvals, and the works are in progress. | FALSE | real_data
Maintenance of existing project highway with overlay | Dispute Resolution | Project Director PIU, Kancheepuram inspected the Project site on 22.12.2020 and instructed to maintain the Project Highway to Standards and specifications by overlaying Bituminous Courses as per specifications and laying the BC to standards to full width | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode - Maintenance of Project Highway by Overlaying with 30mm thick BC - Reg. | Dear Sir, In view of above-mentioned subject and letters, it is of grave concern and apprehension about the probable consequence, arising out of the Hon'ble High Court verdict, and media report and pouring in of complaints by the road users of the above stretch regarding the maintenance and upkeep of the project corridor to standards and specification from Ch. 71+015 to Ch. 107+091. Specially, when Authority is collecting the Toll from the road users. In this regard, the Authority Engineer requested verbally and written instruction issued vide above referred letter. Subsequently, the Regional Officer, NHAI Chennai and Project Director PIU, Kancheepuram inspected the Project site on 22.12.2020 and instructed to maintain the Project Highway to standards and specifications by overlaying Bituminous Courses as per specifications and laying the BC to standards to full width so as to cover all the potholes to avoid bumpy rides with proper ramping/easing so as to provide a smooth and safe ride without any deficiency. This would help in regaining the lost ground on repute of the Authority. It would therefore be in the interest of the Contractor to immediately take-up the repair work as advised. Enclosed herewith are the stretches, which requires the overlay works. Further to above, your kind attention is also being drawn to on the following Contractual Provisions; Clause 10.4.1 of the Contract, which stated that “During the Construction Period, the Contractor shall maintain, at its cost, the existing lane(s) of the Project Highway so that the traffic worthiness and safety thereof are at no time materially inferior as compared to their condition 10 (ten) days prior to the date of this Agreement, and shall undertake the necessary repair and maintenance works for this purpose; provided that the Contractor may, at its cost, interrupt and divert the flow of traffic if such interruption and diversion is necessary is necessary for the efficient progress of works and conforms to Good Industry Practice; provided further the such interruption and diversion shall be undertaken by the Contractor only with the prior written approval of the Authority's Engineer which approval shall not be unreasonably withheld. For the avoidance of doubt, it is agreed that the Contractor shall at all times be responsible for ensuring safe operation of the Project Highway. It is further agreed that in the event the Project includes construction of a bypass or tunnel and realignment of the existing carriageway, the Contractor shall maintain the existing highway in such sections until the new works are open to traffic.” Clause 10.4.2, which stated that “Notwithstanding anything to the contrary contained in this Agreement, in the event of default by the Contractor in discharging the obligations specified in Clause 10.4.1 above, the Authority shall get these maintenance works done as recommended by the Authority’s Engineer to avoid public inconvenience at the risk and cost of the Contractor in order to keep the road in traffic worthy condition.” In view of above, the EPC Contractor is advised to attend to the repair work as per the instructions of the Authority Given vide reference first cited and to carry out the work on war footing basis and submit the compliance report on daily basis. Any lapses in the aforesaid works shall be reviewed as per the provisions of the Contract Agreement. This letter is issued for your needful and necessary compliance. Thank you for your attention to this matter. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Maintenance of existing project highway with overlay | Dispute Resolution | Project Director PIU, Kancheepuram inspected the Project site on 22.12.2020 and instructed to maintain the Project Highway to Standards and specifications by overlaying Bituminous Courses as per specifications and laying the BC to standards to full width | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode - Maintenance of Project Highway by Overlaying with 30mm thick BC - Reg. | Kindly be informed that Dear Sir, In view of above-mentioned subject and letters, it is of grave concern and apprehension about the probable consequence, arising out of the Hon'ble High Court verdict, and media report and pouring in of complaints by the road users of the above stretch regarding the maintenance and upkeep of the project corridor to standards and specification from Ch. 71+015 to Ch. 107+091. Specially, when Authority is collecting the Toll from the road users. In this regard, the Authority Engineer requested verbally and written instruction issued vide above referred letter. Subsequently, the Regional Officer, NHAI Chennai and Project Director PIU, Kancheepuram inspected the Project site on 22.12.2020 and instructed to maintain the Project Highway to standards and specifications by overlaying Bituminous Courses as per specifications and laying the BC to standards to full width so as to cover all the potholes to avoid bumpy rides with proper ramping/easing so as to provide a smooth and safe ride without any deficiency. This would help in regaining the lost ground on repute of the Authority. It would therefore be in the interest of the Contractor to immediately take-up the repair work as advised. Enclosed herewith are the stretches, which requires the overlay works. Further to above, your kind attention is also being drawn to on the following Contractual Provisions; Clause 10.4.1 of the Contract, which stated that “During the Construction Period, the Contractor shall maintain, at its cost, the existing lane(s) of the Project Highway so that the traffic worthiness and safety thereof are at no time materially inferior as compared to their condition 10 (ten) days prior to the date of this Agreement, and shall undertake the necessary repair and maintenance works for this purpose; provided that the Contractor may, at its cost, interrupt and divert the flow of traffic if such interruption and diversion is necessary is necessary for the efficient progress of works and conforms to Good Industry Practice; provided further the such interruption and diversion shall be undertaken by the Contractor only with the prior written approval of the Authority's Engineer which approval shall not be unreasonably withheld. For the avoidance of doubt, it is agreed that the Contractor shall at all times be responsible for ensuring safe operation of the Project Highway. It is further agreed that in the event the Project includes construction of a bypass or tunnel and realignment of the existing carriageway, the Contractor shall maintain the existing highway in such sections until the new works are open to traffic.” Clause 10.4.2, which stated that “Notwithstanding anything to the contrary contained in this Agreement, in the event of default by the Contractor in discharging the obligations specified in Clause 10.4.1 above, the Authority shall get these maintenance works done as recommended by the Authority’s Engineer to avoid public inconvenience at the risk and cost of the Contractor in order to keep the road in traffic worthy condition.” In view of above, the EPC Contractor is advised to attend to the repair work as per the instructions of the Authority Given vide reference first cited and to carry out the work on war footing basis and submit the compliance report on daily basis. Any lapses in the aforesaid works shall be reviewed as per the provisions of the Contract Agreement. This letter is issued for your needful and necessary compliance. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Maintenance of existing project highway with overlay | Change of Scope | Project Director PIU, Kancheepuram inspected the Project site on 22.12.2020 and instructed to maintain the Project Highway to Standards and specifications by overlaying Bituminous Courses as per specifications and laying the BC to standards to full width | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode - Maintenance of Project Highway by Overlaying with 30mm thick BC - Reg. | Dear Sir, In view of above-mentioned subject and letters, it is of grave concern and apprehension about the probable consequence, arising out of the Hon'ble High Court verdict, and media report and pouring in of complaints by the road users of the above stretch regarding the maintenance and upkeep of the project corridor to standards and specification from Ch. 71+015 to Ch. 107+091. Specially, when Authority is collecting the Toll from the road users. In this regard, the Authority Engineer requested verbally and written instruction issued vide above referred letter. Subsequently, the Regional Officer, NHAI Chennai and Project Director PIU, Kancheepuram inspected the Project site on 22.12.2020 and instructed to maintain the Project Highway to standards and specifications by overlaying Bituminous Courses as per specifications and laying the BC to standards to full width so as to cover all the potholes to avoid bumpy rides with proper ramping/easing so as to provide a smooth and safe ride without any deficiency. This would help in regaining the lost ground on repute of the Authority. It would therefore be in the interest of the Contractor to immediately take-up the repair work as advised. Enclosed herewith are the stretches, which requires the overlay works. Further to above, your kind attention is also being drawn to on the following Contractual Provisions; Clause 10.4.1 of the Contract, which stated that “During the Construction Period, the Contractor shall maintain, at its cost, the existing lane(s) of the Project Highway so that the traffic worthiness and safety thereof are at no time materially inferior as compared to their condition 10 (ten) days prior to the date of this Agreement, and shall undertake the necessary repair and maintenance works for this purpose; provided that the Contractor may, at its cost, interrupt and divert the flow of traffic if such interruption and diversion is necessary is necessary for the efficient progress of works and conforms to Good Industry Practice; provided further the such interruption and diversion shall be undertaken by the Contractor only with the prior written approval of the Authority's Engineer which approval shall not be unreasonably withheld. For the avoidance of doubt, it is agreed that the Contractor shall at all times be responsible for ensuring safe operation of the Project Highway. It is further agreed that in the event the Project includes construction of a bypass or tunnel and realignment of the existing carriageway, the Contractor shall maintain the existing highway in such sections until the new works are open to traffic.” Clause 10.4.2, which stated that “Notwithstanding anything to the contrary contained in this Agreement, in the event of default by the Contractor in discharging the obligations specified in Clause 10.4.1 above, the Authority shall get these maintenance works done as recommended by the Authority’s Engineer to avoid public inconvenience at the risk and cost of the Contractor in order to keep the road in traffic worthy condition.” In view of above, the EPC Contractor is advised to attend to the repair work as per the instructions of the Authority Given vide reference first cited and to carry out the work on war footing basis and submit the compliance report on daily basis. Any lapses in the aforesaid works shall be reviewed as per the provisions of the Contract Agreement. This letter is issued for your needful and necessary compliance. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Maintenance of existing project highway with overlay | Change of Scope | Project Director PIU, Kancheepuram inspected the Project site on 22.12.2020 and instructed to maintain the Project Highway to Standards and specifications by overlaying Bituminous Courses as per specifications and laying the BC to standards to full width | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode - Maintenance of Project Highway by Overlaying with 30mm thick BC - Reg. | It is brought to your attention that Dear Sir, In view of above-mentioned subject and letters, it is of grave concern and apprehension about the probable consequence, arising out of the Hon'ble High Court verdict, and media report and pouring in of complaints by the road users of the above stretch regarding the maintenance and upkeep of the project corridor to standards and specification from Ch. 71+015 to Ch. 107+091. Specially, when Authority is collecting the Toll from the road users. In this regard, the Authority Engineer requested verbally and written instruction issued vide above referred letter. Subsequently, the Regional Officer, NHAI Chennai and Project Director PIU, Kancheepuram inspected the Project site on 22.12.2020 and instructed to maintain the Project Highway to standards and specifications by overlaying Bituminous Courses as per specifications and laying the BC to standards to full width so as to cover all the potholes to avoid bumpy rides with proper ramping/easing so as to provide a smooth and safe ride without any deficiency. This would help in regaining the lost ground on repute of the Authority. It would therefore be in the interest of the Contractor to immediately take-up the repair work as advised. Enclosed herewith are the stretches, which requires the overlay works. Further to above, your kind attention is also being drawn to on the following Contractual Provisions; Clause 10.4.1 of the Contract, which stated that “During the Construction Period, the Contractor shall maintain, at its cost, the existing lane(s) of the Project Highway so that the traffic worthiness and safety thereof are at no time materially inferior as compared to their condition 10 (ten) days prior to the date of this Agreement, and shall undertake the necessary repair and maintenance works for this purpose; provided that the Contractor may, at its cost, interrupt and divert the flow of traffic if such interruption and diversion is necessary is necessary for the efficient progress of works and conforms to Good Industry Practice; provided further the such interruption and diversion shall be undertaken by the Contractor only with the prior written approval of the Authority's Engineer which approval shall not be unreasonably withheld. For the avoidance of doubt, it is agreed that the Contractor shall at all times be responsible for ensuring safe operation of the Project Highway. It is further agreed that in the event the Project includes construction of a bypass or tunnel and realignment of the existing carriageway, the Contractor shall maintain the existing highway in such sections until the new works are open to traffic.” Clause 10.4.2, which stated that “Notwithstanding anything to the contrary contained in this Agreement, in the event of default by the Contractor in discharging the obligations specified in Clause 10.4.1 above, the Authority shall get these maintenance works done as recommended by the Authority’s Engineer to avoid public inconvenience at the risk and cost of the Contractor in order to keep the road in traffic worthy condition.” In view of above, the EPC Contractor is advised to attend to the repair work as per the instructions of the Authority Given vide reference first cited and to carry out the work on war footing basis and submit the compliance report on daily basis. Any lapses in the aforesaid works shall be reviewed as per the provisions of the Contract Agreement. This letter is issued for your needful and necessary compliance. Please confirm receipt of this correspondence. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Maintenance of existing project highway with overlay | Contractor's Obligations | Project Director PIU, Kancheepuram inspected the Project site on 22.12.2020 and instructed to maintain the Project Highway to Standards and specifications by overlaying Bituminous Courses as per specifications and laying the BC to standards to full width | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode - Maintenance of Project Highway by Overlaying with 30mm thick BC - Reg. | Dear Sir, In view of above-mentioned subject and letters, it is of grave concern and apprehension about the probable consequence, arising out of the Hon'ble High Court verdict, and media report and pouring in of complaints by the road users of the above stretch regarding the maintenance and upkeep of the project corridor to standards and specification from Ch. 71+015 to Ch. 107+091. Specially, when Authority is collecting the Toll from the road users. In this regard, the Authority Engineer requested verbally and written instruction issued vide above referred letter. Subsequently, the Regional Officer, NHAI Chennai and Project Director PIU, Kancheepuram inspected the Project site on 22.12.2020 and instructed to maintain the Project Highway to standards and specifications by overlaying Bituminous Courses as per specifications and laying the BC to standards to full width so as to cover all the potholes to avoid bumpy rides with proper ramping/easing so as to provide a smooth and safe ride without any deficiency. This would help in regaining the lost ground on repute of the Authority. It would therefore be in the interest of the Contractor to immediately take-up the repair work as advised. Enclosed herewith are the stretches, which requires the overlay works. Further to above, your kind attention is also being drawn to on the following Contractual Provisions; Clause 10.4.1 of the Contract, which stated that “During the Construction Period, the Contractor shall maintain, at its cost, the existing lane(s) of the Project Highway so that the traffic worthiness and safety thereof are at no time materially inferior as compared to their condition 10 (ten) days prior to the date of this Agreement, and shall undertake the necessary repair and maintenance works for this purpose; provided that the Contractor may, at its cost, interrupt and divert the flow of traffic if such interruption and diversion is necessary is necessary for the efficient progress of works and conforms to Good Industry Practice; provided further the such interruption and diversion shall be undertaken by the Contractor only with the prior written approval of the Authority's Engineer which approval shall not be unreasonably withheld. For the avoidance of doubt, it is agreed that the Contractor shall at all times be responsible for ensuring safe operation of the Project Highway. It is further agreed that in the event the Project includes construction of a bypass or tunnel and realignment of the existing carriageway, the Contractor shall maintain the existing highway in such sections until the new works are open to traffic.” Clause 10.4.2, which stated that “Notwithstanding anything to the contrary contained in this Agreement, in the event of default by the Contractor in discharging the obligations specified in Clause 10.4.1 above, the Authority shall get these maintenance works done as recommended by the Authority’s Engineer to avoid public inconvenience at the risk and cost of the Contractor in order to keep the road in traffic worthy condition.” In view of above, the EPC Contractor is advised to attend to the repair work as per the instructions of the Authority Given vide reference first cited and to carry out the work on war footing basis and submit the compliance report on daily basis. Any lapses in the aforesaid works shall be reviewed as per the provisions of the Contract Agreement. This letter is issued for your needful and necessary compliance. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Maintenance of existing project highway with overlay | Contractor's Obligations | Project Director PIU, Kancheepuram inspected the Project site on 22.12.2020 and instructed to maintain the Project Highway to Standards and specifications by overlaying Bituminous Courses as per specifications and laying the BC to standards to full width | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode - Maintenance of Project Highway by Overlaying with 30mm thick BC - Reg. | This is to notify you that Dear Sir, In view of above-mentioned subject and letters, it is of grave concern and apprehension about the probable consequence, arising out of the Hon'ble High Court verdict, and media report and pouring in of complaints by the road users of the above stretch regarding the maintenance and upkeep of the project corridor to standards and specification from Ch. 71+015 to Ch. 107+091. Specially, when Authority is collecting the Toll from the road users. In this regard, the Authority Engineer requested verbally and written instruction issued vide above referred letter. Subsequently, the Regional Officer, NHAI Chennai and Project Director PIU, Kancheepuram inspected the Project site on 22.12.2020 and instructed to maintain the Project Highway to standards and specifications by overlaying Bituminous Courses as per specifications and laying the BC to standards to full width so as to cover all the potholes to avoid bumpy rides with proper ramping/easing so as to provide a smooth and safe ride without any deficiency. This would help in regaining the lost ground on repute of the Authority. It would therefore be in the interest of the Contractor to immediately take-up the repair work as advised. Enclosed herewith are the stretches, which requires the overlay works. Further to above, your kind attention is also being drawn to on the following Contractual Provisions; Clause 10.4.1 of the Contract, which stated that “During the Construction Period, the Contractor shall maintain, at its cost, the existing lane(s) of the Project Highway so that the traffic worthiness and safety thereof are at no time materially inferior as compared to their condition 10 (ten) days prior to the date of this Agreement, and shall undertake the necessary repair and maintenance works for this purpose; provided that the Contractor may, at its cost, interrupt and divert the flow of traffic if such interruption and diversion is necessary is necessary for the efficient progress of works and conforms to Good Industry Practice; provided further the such interruption and diversion shall be undertaken by the Contractor only with the prior written approval of the Authority's Engineer which approval shall not be unreasonably withheld. For the avoidance of doubt, it is agreed that the Contractor shall at all times be responsible for ensuring safe operation of the Project Highway. It is further agreed that in the event the Project includes construction of a bypass or tunnel and realignment of the existing carriageway, the Contractor shall maintain the existing highway in such sections until the new works are open to traffic.” Clause 10.4.2, which stated that “Notwithstanding anything to the contrary contained in this Agreement, in the event of default by the Contractor in discharging the obligations specified in Clause 10.4.1 above, the Authority shall get these maintenance works done as recommended by the Authority’s Engineer to avoid public inconvenience at the risk and cost of the Contractor in order to keep the road in traffic worthy condition.” In view of above, the EPC Contractor is advised to attend to the repair work as per the instructions of the Authority Given vide reference first cited and to carry out the work on war footing basis and submit the compliance report on daily basis. Any lapses in the aforesaid works shall be reviewed as per the provisions of the Contract Agreement. This letter is issued for your needful and necessary compliance. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Occurrence of Force Majeure event | EoT; Dispute Resolution | Indirect Political event on 10 Sep 2018 | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/1. Indirect political event on 10th Sep 2018 11.09.2018.pdf | Rehabilitation and Up-gradation of Paithan (Pategaon) - Mungi — Hadgaon — Bodhegaon- : Ladjalgaon - Ghogaspargaon — Phulsangvi - Ukhandachakla — Dahiwandi - Shirur to 2-Lane with paved shoulder (Project Length 55.937 Km) on EPC basis in the state of Maharashtra (Package ¦ ~ 56 KM) = Indirect Political event on 10 September 2018 ~ Reg. | Respected Sir, With reference to above mentioned subject and reference we would like to bring to your kind notice that Congress party called for a BHARAT BANDH on 20th July 2018 against rising fuel price. We are herewith attaching the Newspaper cuttings highlighting the issue of BHARAT BANDH on 20th July 2018 against rising fuel price for your reference and record. We are also bringing to your kind notice that the progress of the Work was hampered yesterday. This is for your kind information and record. | FALSE | real_data
Occurrence of Force Majeure event | EoT | Indirect Political event on 10 Sep 2018 | synthetic_template_20250913 | Rehabilitation and Up-gradation of Paithan (Pategaon) - Mungi — Hadgaon — Bodhegaon- : Ladjalgaon - Ghogaspargaon — Phulsangvi - Ukhandachakla — Dahiwandi - Shirur to 2-Lane with paved shoulder (Project Length 55.937 Km) on EPC basis in the state of Maharashtra (Package ¦ ~ 56 KM) = Indirect Political event on 10 September 2018 ~ Reg. | Respected Sir, With reference to above mentioned subject and reference we would like to bring to your kind notice that Congress party called for a BHARAT BANDH on 20th July 2018 against rising fuel price. We are herewith attaching the Newspaper cuttings highlighting the issue of BHARAT BANDH on 20th July 2018 against rising fuel price for your reference and record. We are also bringing to your kind notice that the progress of the Work was hampered yesterday. This is for your kind information and record. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Occurrence of Force Majeure event | Dispute Resolution | Indirect Political event on 10 Sep 2018 | synthetic_template_20250913 | Rehabilitation and Up-gradation of Paithan (Pategaon) - Mungi — Hadgaon — Bodhegaon- : Ladjalgaon - Ghogaspargaon — Phulsangvi - Ukhandachakla — Dahiwandi - Shirur to 2-Lane with paved shoulder (Project Length 55.937 Km) on EPC basis in the state of Maharashtra (Package ¦ ~ 56 KM) = Indirect Political event on 10 September 2018 ~ Reg. | Respected Sir, With reference to above mentioned subject and reference we would like to bring to your kind notice that Congress party called for a BHARAT BANDH on 20th July 2018 against rising fuel price. We are herewith attaching the Newspaper cuttings highlighting the issue of BHARAT BANDH on 20th July 2018 against rising fuel price for your reference and record. We are also bringing to your kind notice that the progress of the Work was hampered yesterday. This is for your kind information and record. We await your further instructions. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Occurrence of Force Majeure event | Dispute Resolution | Indirect Political event on 10 Sep 2018 | synthetic_template_20250913 | Rehabilitation and Up-gradation of Paithan (Pategaon) - Mungi — Hadgaon — Bodhegaon- : Ladjalgaon - Ghogaspargaon — Phulsangvi - Ukhandachakla — Dahiwandi - Shirur to 2-Lane with paved shoulder (Project Length 55.937 Km) on EPC basis in the state of Maharashtra (Package ¦ ~ 56 KM) = Indirect Political event on 10 September 2018 ~ Reg. | Respected Sir, With reference to above mentioned subject and reference we would like to bring to your kind notice that Congress party called for a BHARAT BANDH on 20th July 2018 against rising fuel price. We are herewith attaching the Newspaper cuttings highlighting the issue of BHARAT BANDH on 20th July 2018 against rising fuel price for your reference and record. We are also bringing to your kind notice that the progress of the Work was hampered yesterday. This is for your kind information and record. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Right of way | EoT | we have intimated to the Authority & Authority Engineer as and when we had faced obstructions to the progress of work due to encroachments & encumbrances. | synthetic_template_20250913 | Encroachments & Encumbrances in the ROW -Reg. | It is brought to your attention that With reference to above subject & letters, we would like to bring to your kind notice that the progress of work continues to suffer the ramifications of presence of Encroachments & Encumbrances in the ROW. Please refer to your letter ref (2) above wherein it was intimated that ROW to the tune of 90.44% was available for execution, enclosing Schedule-A of the Agreement. However, when we subsequently visited the Site we had encountered numerous encroachments & encumbrances and thus realized the fact that the available ROW was far less than 90.44%. Hence, we have submitted an Appendix containing the encroachments & encumbrances, vide letter ref (3) above for your joint verification and signing. The same was also communicated in our Extension of Time (EOT) letters ref (8) & (13) above. Further, through various letters referred above, we have intimated to the Authority & Authority Engineer as and when we had faced obstructions to the progress of work due to encroachments & encumbrances. We are once again enlisting below the locations which are not comprehensive, where we are unable to progress with the works even today along with the reasons. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Right of way | EoT | we have intimated to the Authority & Authority Engineer as and when we had faced obstructions to the progress of work due to encroachments & encumbrances. | synthetic_template_20250913 | Encroachments & Encumbrances in the ROW -Reg. | With reference to above subject & letters, we would like to bring to your kind notice that the progress of work continues to suffer the ramifications of presence of Encroachments & Encumbrances in the ROW. Please refer to your letter ref (2) above wherein it was intimated that ROW to the tune of 90.44% was available for execution, enclosing Schedule-A of the Agreement. However, when we subsequently visited the Site we had encountered numerous encroachments & encumbrances and thus realized the fact that the available ROW was far less than 90.44%. Hence, we have submitted an Appendix containing the encroachments & encumbrances, vide letter ref (3) above for your joint verification and signing. The same was also communicated in our Extension of Time (EOT) letters ref (8) & (13) above. Further, through various letters referred above, we have intimated to the Authority & Authority Engineer as and when we had faced obstructions to the progress of work due to encroachments & encumbrances. We are once again enlisting below the locations which are not comprehensive, where we are unable to progress with the works even today along with the reasons. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Right of way | Dispute Resolution | we have intimated to the Authority & Authority Engineer as and when we had faced obstructions to the progress of work due to encroachments & encumbrances. | synthetic_template_20250913 | Encroachments & Encumbrances in the ROW -Reg. | It is brought to your attention that With reference to above subject & letters, we would like to bring to your kind notice that the progress of work continues to suffer the ramifications of presence of Encroachments & Encumbrances in the ROW. Please refer to your letter ref (2) above wherein it was intimated that ROW to the tune of 90.44% was available for execution, enclosing Schedule-A of the Agreement. However, when we subsequently visited the Site we had encountered numerous encroachments & encumbrances and thus realized the fact that the available ROW was far less than 90.44%. Hence, we have submitted an Appendix containing the encroachments & encumbrances, vide letter ref (3) above for your joint verification and signing. The same was also communicated in our Extension of Time (EOT) letters ref (8) & (13) above. Further, through various letters referred above, we have intimated to the Authority & Authority Engineer as and when we had faced obstructions to the progress of work due to encroachments & encumbrances. We are once again enlisting below the locations which are not comprehensive, where we are unable to progress with the works even today along with the reasons. Thank you for your attention to this matter. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Right of way | Dispute Resolution | we have intimated to the Authority & Authority Engineer as and when we had faced obstructions to the progress of work due to encroachments & encumbrances. | synthetic_template_20250913 | Encroachments & Encumbrances in the ROW -Reg. | With reference to above subject & letters, we would like to bring to your kind notice that the progress of work continues to suffer the ramifications of presence of Encroachments & Encumbrances in the ROW. Please refer to your letter ref (2) above wherein it was intimated that ROW to the tune of 90.44% was available for execution, enclosing Schedule-A of the Agreement. However, when we subsequently visited the Site we had encountered numerous encroachments & encumbrances and thus realized the fact that the available ROW was far less than 90.44%. Hence, we have submitted an Appendix containing the encroachments & encumbrances, vide letter ref (3) above for your joint verification and signing. The same was also communicated in our Extension of Time (EOT) letters ref (8) & (13) above. Further, through various letters referred above, we have intimated to the Authority & Authority Engineer as and when we had faced obstructions to the progress of work due to encroachments & encumbrances. We are once again enlisting below the locations which are not comprehensive, where we are unable to progress with the works even today along with the reasons. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Right of way | Authority's Obligations | we have intimated to the Authority & Authority Engineer as and when we had faced obstructions to the progress of work due to encroachments & encumbrances. | synthetic_template_20250913 | Encroachments & Encumbrances in the ROW -Reg. | With reference to above subject & letters, we would like to bring to your kind notice that the progress of work continues to suffer the ramifications of presence of Encroachments & Encumbrances in the ROW. Please refer to your letter ref (2) above wherein it was intimated that ROW to the tune of 90.44% was available for execution, enclosing Schedule-A of the Agreement. However, when we subsequently visited the Site we had encountered numerous encroachments & encumbrances and thus realized the fact that the available ROW was far less than 90.44%. Hence, we have submitted an Appendix containing the encroachments & encumbrances, vide letter ref (3) above for your joint verification and signing. The same was also communicated in our Extension of Time (EOT) letters ref (8) & (13) above. Further, through various letters referred above, we have intimated to the Authority & Authority Engineer as and when we had faced obstructions to the progress of work due to encroachments & encumbrances. We are once again enlisting below the locations which are not comprehensive, where we are unable to progress with the works even today along with the reasons. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Right of way | Authority's Obligations | we have intimated to the Authority & Authority Engineer as and when we had faced obstructions to the progress of work due to encroachments & encumbrances. | synthetic_template_20250913 | Encroachments & Encumbrances in the ROW -Reg. | It is brought to your attention that With reference to above subject & letters, we would like to bring to your kind notice that the progress of work continues to suffer the ramifications of presence of Encroachments & Encumbrances in the ROW. Please refer to your letter ref (2) above wherein it was intimated that ROW to the tune of 90.44% was available for execution, enclosing Schedule-A of the Agreement. However, when we subsequently visited the Site we had encountered numerous encroachments & encumbrances and thus realized the fact that the available ROW was far less than 90.44%. Hence, we have submitted an Appendix containing the encroachments & encumbrances, vide letter ref (3) above for your joint verification and signing. The same was also communicated in our Extension of Time (EOT) letters ref (8) & (13) above. Further, through various letters referred above, we have intimated to the Authority & Authority Engineer as and when we had faced obstructions to the progress of work due to encroachments & encumbrances. We are once again enlisting below the locations which are not comprehensive, where we are unable to progress with the works even today along with the reasons. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Under utilisation / idling of resources | Payments; EoT; Dispute Resolution | We have sufficient resources but they are not gainfully deployed so far. Please refer our letter RCM PVR JV/MH PWD/2018-19/406 date 04th January 2019 on availability of work front & land acquisition status also. The reasons stated above, has led to erosion of revolving capital. we will summaries the losses & submit the comprehensive report, when 90% land is made available, | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/9. Un-gainful Deployement of Resources 28.01.2019.pdf | Rehabilitation and Up-gradation of Paithan (Pategaon) — Mungi - Hadgaon - Bodhegaon- Ladjalgaon ~ Ghogaspargaon ~ Phulsangvi - Ukhandachakla ~ Dahiwandi — Shirur to 2-Lane with paved shoulder (Project Length 55.937 Km) on EPC basis in the state of Maharashtra (Package I - 56 KM) - Un-gainful Deployment of Resources - Reg. | Please refer our revised programme submitted in vide letter no RCM PVR JV/MH PWD/2018-19/235 dated 02 May 2018 which revised & resubmitted recently vide letter no RCM PVR JV/MH PWD/2018-19/402/A dated 29 December 2018. As you are aware, the stretches we programmed to work are not available even today due to non acquisition of land. Further the area/work fronts which were made available by property owners at our request, was also withdrawn by them, since the compensation was not paid in time. Kindly refer our application for revision of milestone dates RCM PVR JV/MH PWD/2018-19/374 dated 17 November 2018 which details elaborately the reasons under relevant clauses of contract agreement. We have sufficient resources but they are not gainfully deployed so far. Please refer our letter RCM PVR JV/MH PWD/2018-19/406 date 04 January 2019 on availability of work front & land acquisition status also. The reasons stated above, has led to erosion of revolving capital. We will summarise the losses & submit the Comprehensive report, when 90% land is made available. | FALSE | real_data
Under utilisation / idling of resources | Payments; EoT; Dispute Resolution | From the above. if is clear that pending COS orders/decisions & LA problems are the reasons for slow progress of works- Even our existing resources are being subjected to ungainful deployment, due to jack of work fronts, as already intimated in our letter ref (2} above. At this juncture. mobilising additional resources with only add to the huge financial loss already incurred by us. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/10. Regarding slow progress of work 31.01.2019.pdf | Regarding Slow progress of Work | This is with reference to your letter ref (1) above, regarding slow progress of work, wherein you have instructed us to mobilise additional resources in order to complete the works within the stipulated time. We invite your kind attention to our letter ref (3) above; we have clearly mentioned that works in 34.35 Km of the project are held up due to pending COS orders/decisions. Further, we have also mentioned that works are also hampered due to Land Acquisition (LA) problems at various stretches. From the above, it is clear that pending COS orders/decisions & LA problems are the reasons for slow progress of works. Even our existing resources are being subjected to unfruitful deployment, due to lack of work fronts, as already intimated in our letter ref (2) above. At this juncture, mobilising additional resources will only add to the huge financial loss already incurred by us. In view of the above, we request you to pursue the Authority on issuing COS orders and handing over balance ROW, free of encroachments and encumbrances. | FALSE | real_data
Under utilisation / idling of resources | Payments; EoT; Dispute Resolution | As intimated earlier, we have been facing financial losses due to idling of resources and simultaneously incurring fixed and renewing costs. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/19. Intention to issue cure period notice 02.11.2019.pdf | Intention to issue Cure Period Notice to the Authority under clause 23.2.1 for temporary demobilization | This is regarding non-availability of encroachment and encumbrance free Right of Way (ROW) along the project highway, regarding which we wish to mention the following: 1. Subsequent to the signing of EPC Agreement dated 18.04.2017 the Appointed Date was fixed on 02.06.2017 and was communicated through Authority's letter no. 1190. It was mentioned in the letter that requirements under Clause 8.2 and obligations under 4.1.3(a), Annex II of Schedule-A are fulfilled by the Authority. 2. However, when we actually mobilised to site, we realised that the Obligations are not fulfilled by the Authority, in terms of the provisions relating to ROW and Appointed Date cited above. We noticed that there is no clarity even on the existing ROW widths. 3. We had submitted the Memorandum / Appendix through our letter no. 71 dated 10th Aug 2017, which indicates that the vacant access and ROW have not been granted at certain locations. Despite several requests, joint site inspection was not done and till date duly countersigned copy of the Memorandum / Appendix prepared by us is not returned till to date. 4. We have been reporting the lack of ROW through our Monthly Progress Reports every month, in addition among various letters on the subject. It is pertinent to mention that even as on date, not a single kilometre/ hectare of additional land has been acquired by the Authority under this project. However, we had convinced the local public and could get some progress in the project due to our efforts. 5. The dispute regarding land acquisition still continues among landowners, Authority and Revenue Authority (CALA). 6. There are realignments in the project for a length of 5.350 Kms, the land acquisition of which is not yet taken up where in there are no ROW boundaries and which area can be acquired directly. Two minor bridges are held up in the realignments. 7. As mentioned in Authority’s and AE's EOT recommendations, Gazette notification for land acquisition was issued on 31st December 2018, after a lapse of 18 months from appointed date. 8. It is also mentioned in your letter no. 78 dated 02.03.2019, that the EOT duration determined was subject to the condition that the ROW for the affected reaches will be handed over to the Contractor by 31.03.2019 and all the hindrances/obstructions will also be removed by 31.03.2019. 9. However, even till date, no further land has been handed over by the Authority we regret to maintain that even the existing ROW width is disputed between land owners concerned Authority. In addition the Acquisition was to be mobilized: the area of ACQUISITION FOR DIFFERENT Land owners is a single survey numbers. Some of them in this case having different survey numbers. 10. As intimated earlier, we have been facing financial losses due to idling of resources and simultaneously incurring fixed and renewing costs. In view of the above, we intend to issue a Notice to the Authority under clause 23.2.1 of the Contract to cure their material default in handing over of ROW which has a huge material adverse effect on our works. We once again request you to pursue with the Authority in expediting handing over of the balance ROW as soon as possible. Due to the above breach of the obligations by the Authority in terms of land handing over, a situation has arisen wherein we have no option other than temporarily demobilizing from site, to avoid further financial loss to us. We shall remobilize upon intimation from you / Authority regarding the availability of balance ROW. | FALSE | real_data
Under utilisation / idling of resources | EoT | From the above. if is clear that pending COS orders/decisions & LA problems are the reasons for slow progress of works- Even our existing resources are being subjected to ungainful deployment, due to jack of work fronts, as already intimated in our letter ref (2} above. At this juncture. mobilising additional resources with only add to the huge financial loss already incurred by us. | synthetic_template_20250913 | Regarding Slow progress of Work | We hereby confirm that This is with reference to your letter ref (1) above, regarding slow progress of work, wherein you have instructed us to mobilise additional resources in order to complete the works within the stipulated time. We invite your kind attention to our letter ref (3) above; we have clearly mentioned that works in 34.35 Km of the project are held up due to pending COS orders/decisions. Further, we have also mentioned that works are also hampered due to Land Acquisition (LA) problems at various stretches. From the above, it is clear that pending COS orders/decisions & LA problems are the reasons for slow progress of works. Even our existing resources are being subjected to unfruitful deployment, due to lack of work fronts, as already intimated in our letter ref (2) above. At this juncture, mobilising additional resources will only add to the huge financial loss already incurred by us. In view of the above, we request you to pursue the Authority on issuing COS orders and handing over balance ROW, free of encroachments and encumbrances. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Under utilisation / idling of resources | EoT | From the above. if is clear that pending COS orders/decisions & LA problems are the reasons for slow progress of works- Even our existing resources are being subjected to ungainful deployment, due to jack of work fronts, as already intimated in our letter ref (2} above. At this juncture. mobilising additional resources with only add to the huge financial loss already incurred by us. | synthetic_template_20250913 | Regarding Slow progress of Work | This is with reference to your letter ref (1) above, regarding slow progress of work, wherein you have instructed us to mobilise additional resources in order to complete the works within the stipulated time. We invite your kind attention to our letter ref (3) above; we have clearly mentioned that works in 34.35 Km of the project are held up due to pending COS orders/decisions. Further, we have also mentioned that works are also hampered due to Land Acquisition (LA) problems at various stretches. From the above, it is clear that pending COS orders/decisions & LA problems are the reasons for slow progress of works. Even our existing resources are being subjected to unfruitful deployment, due to lack of work fronts, as already intimated in our letter ref (2) above. At this juncture, mobilising additional resources will only add to the huge financial loss already incurred by us. In view of the above, we request you to pursue the Authority on issuing COS orders and handing over balance ROW, free of encroachments and encumbrances. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Under utilisation / idling of resources | Dispute Resolution | As intimated earlier, we have been facing financial losses due to idling of resources and simultaneously incurring fixed and renewing costs. | synthetic_template_20250913 | Intention to issue Cure Period Notice to the Authority under clause 23.2.1 for temporary demobilization | This is regarding non-availability of encroachment and encumbrance free Right of Way (ROW) along the project highway, regarding which we wish to mention the following: 1. Subsequent to the signing of EPC Agreement dated 18.04.2017 the Appointed Date was fixed on 02.06.2017 and was communicated through Authority's letter no. 1190. It was mentioned in the letter that requirements under Clause 8.2 and obligations under 4.1.3(a), Annex II of Schedule-A are fulfilled by the Authority. 2. However, when we actually mobilised to site, we realised that the Obligations are not fulfilled by the Authority, in terms of the provisions relating to ROW and Appointed Date cited above. We noticed that there is no clarity even on the existing ROW widths. 3. We had submitted the Memorandum / Appendix through our letter no. 71 dated 10th Aug 2017, which indicates that the vacant access and ROW have not been granted at certain locations. Despite several requests, joint site inspection was not done and till date duly countersigned copy of the Memorandum / Appendix prepared by us is not returned till to date. 4. We have been reporting the lack of ROW through our Monthly Progress Reports every month, in addition among various letters on the subject. It is pertinent to mention that even as on date, not a single kilometre/ hectare of additional land has been acquired by the Authority under this project. However, we had convinced the local public and could get some progress in the project due to our efforts. 5. The dispute regarding land acquisition still continues among landowners, Authority and Revenue Authority (CALA). 6. There are realignments in the project for a length of 5.350 Kms, the land acquisition of which is not yet taken up where in there are no ROW boundaries and which area can be acquired directly. Two minor bridges are held up in the realignments. 7. As mentioned in Authority’s and AE's EOT recommendations, Gazette notification for land acquisition was issued on 31st December 2018, after a lapse of 18 months from appointed date. 8. It is also mentioned in your letter no. 78 dated 02.03.2019, that the EOT duration determined was subject to the condition that the ROW for the affected reaches will be handed over to the Contractor by 31.03.2019 and all the hindrances/obstructions will also be removed by 31.03.2019. 9. However, even till date, no further land has been handed over by the Authority we regret to maintain that even the existing ROW width is disputed between land owners concerned Authority. In addition the Acquisition was to be mobilized: the area of ACQUISITION FOR DIFFERENT Land owners is a single survey numbers. Some of them in this case having different survey numbers. 10. As intimated earlier, we have been facing financial losses due to idling of resources and simultaneously incurring fixed and renewing costs. In view of the above, we intend to issue a Notice to the Authority under clause 23.2.1 of the Contract to cure their material default in handing over of ROW which has a huge material adverse effect on our works. We once again request you to pursue with the Authority in expediting handing over of the balance ROW as soon as possible. Due to the above breach of the obligations by the Authority in terms of land handing over, a situation has arisen wherein we have no option other than temporarily demobilizing from site, to avoid further financial loss to us. We shall remobilize upon intimation from you / Authority regarding the availability of balance ROW. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Under utilisation / idling of resources | Dispute Resolution | From the above. if is clear that pending COS orders/decisions & LA problems are the reasons for slow progress of works- Even our existing resources are being subjected to ungainful deployment, due to jack of work fronts, as already intimated in our letter ref (2} above. At this juncture. mobilising additional resources with only add to the huge financial loss already incurred by us. | synthetic_template_20250913 | Regarding Slow progress of Work | This is with reference to your letter ref (1) above, regarding slow progress of work, wherein you have instructed us to mobilise additional resources in order to complete the works within the stipulated time. We invite your kind attention to our letter ref (3) above; we have clearly mentioned that works in 34.35 Km of the project are held up due to pending COS orders/decisions. Further, we have also mentioned that works are also hampered due to Land Acquisition (LA) problems at various stretches. From the above, it is clear that pending COS orders/decisions & LA problems are the reasons for slow progress of works. Even our existing resources are being subjected to unfruitful deployment, due to lack of work fronts, as already intimated in our letter ref (2) above. At this juncture, mobilising additional resources will only add to the huge financial loss already incurred by us. In view of the above, we request you to pursue the Authority on issuing COS orders and handing over balance ROW, free of encroachments and encumbrances. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Under utilisation / idling of resources | Payments | We have sufficient resources but they are not gainfully deployed so far. Please refer our letter RCM PVR JV/MH PWD/2018-19/406 date 04th January 2019 on availability of work front & land acquisition status also. The reasons stated above, has led to erosion of revolving capital. we will summaries the losses & submit the comprehensive report, when 90% land is made available, | synthetic_template_20250913 | Rehabilitation and Up-gradation of Paithan (Pategaon) — Mungi - Hadgaon - Bodhegaon- Ladjalgaon ~ Ghogaspargaon ~ Phulsangvi - Ukhandachakla ~ Dahiwandi — Shirur to 2-Lane with paved shoulder (Project Length 55.937 Km) on EPC basis in the state of Maharashtra (Package I - 56 KM) - Un-gainful Deployment of Resources - Reg. | Please note that Please refer our revised programme submitted in vide letter no RCM PVR JV/MH PWD/2018-19/235 dated 02 May 2018 which revised & resubmitted recently vide letter no RCM PVR JV/MH PWD/2018-19/402/A dated 29 December 2018. As you are aware, the stretches we programmed to work are not available even today due to non acquisition of land. Further the area/work fronts which were made available by property owners at our request, was also withdrawn by them, since the compensation was not paid in time. Kindly refer our application for revision of milestone dates RCM PVR JV/MH PWD/2018-19/374 dated 17 November 2018 which details elaborately the reasons under relevant clauses of contract agreement. We have sufficient resources but they are not gainfully deployed so far. Please refer our letter RCM PVR JV/MH PWD/2018-19/406 date 04 January 2019 on availability of work front & land acquisition status also. The reasons stated above, has led to erosion of revolving capital. We will summarise the losses & submit the Comprehensive report, when 90% land is made available. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Mobilisation of additional resources | Payments; Dispute Resolution | This is with reference to your *ester ref (1 J above, regarding slow progress of work. wherein you have instructed us to mobilise additional resources in order to complete the works within the stipulated time | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/10. Regarding slow progress of work 31.01.2019.pdf | Regarding Slow progress of Work | This is with reference to your letter ref (1) above, regarding slow progress of work, wherein you have instructed us to mobilise additional resources in order to complete the works within the stipulated time. We invite your kind attention to our letter ref (3) above; we have clearly mentioned that works in 34.35 Km of the project are held up due to pending COS orders/decisions. Further, we have also mentioned that works are also hampered due to Land Acquisition (LA) problems at various stretches. From the above, it is clear that pending COS orders/decisions & LA problems are the reasons for slow progress of works. Even our existing resources are being subjected to unfruitful deployment, due to lack of work fronts, as already intimated in our letter ref (2) above. At this juncture, mobilising additional resources will only add to the huge financial loss already incurred by us. In view of the above, we request you to pursue the Authority on issuing COS orders and handing over balance ROW, free of encroachments and encumbrances. | FALSE | real_data
Mobilisation of additional resources | Dispute Resolution | This is with reference to your *ester ref (1 J above, regarding slow progress of work. wherein you have instructed us to mobilise additional resources in order to complete the works within the stipulated time | synthetic_template_20250913 | Regarding Slow progress of Work | This is with reference to your letter ref (1) above, regarding slow progress of work, wherein you have instructed us to mobilise additional resources in order to complete the works within the stipulated time. We invite your kind attention to our letter ref (3) above; we have clearly mentioned that works in 34.35 Km of the project are held up due to pending COS orders/decisions. Further, we have also mentioned that works are also hampered due to Land Acquisition (LA) problems at various stretches. From the above, it is clear that pending COS orders/decisions & LA problems are the reasons for slow progress of works. Even our existing resources are being subjected to unfruitful deployment, due to lack of work fronts, as already intimated in our letter ref (2) above. At this juncture, mobilising additional resources will only add to the huge financial loss already incurred by us. In view of the above, we request you to pursue the Authority on issuing COS orders and handing over balance ROW, free of encroachments and encumbrances. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Mobilisation of additional resources | Payments | This is with reference to your *ester ref (1 J above, regarding slow progress of work. wherein you have instructed us to mobilise additional resources in order to complete the works within the stipulated time | synthetic_template_20250913 | Regarding Slow progress of Work | This is with reference to your letter ref (1) above, regarding slow progress of work, wherein you have instructed us to mobilise additional resources in order to complete the works within the stipulated time. We invite your kind attention to our letter ref (3) above; we have clearly mentioned that works in 34.35 Km of the project are held up due to pending COS orders/decisions. Further, we have also mentioned that works are also hampered due to Land Acquisition (LA) problems at various stretches. From the above, it is clear that pending COS orders/decisions & LA problems are the reasons for slow progress of works. Even our existing resources are being subjected to unfruitful deployment, due to lack of work fronts, as already intimated in our letter ref (2) above. At this juncture, mobilising additional resources will only add to the huge financial loss already incurred by us. In view of the above, we request you to pursue the Authority on issuing COS orders and handing over balance ROW, free of encroachments and encumbrances. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Mobilisation of additional resources | Payments | This is with reference to your *ester ref (1 J above, regarding slow progress of work. wherein you have instructed us to mobilise additional resources in order to complete the works within the stipulated time | synthetic_template_20250913 | Regarding Slow progress of Work | This is with reference to your letter ref (1) above, regarding slow progress of work, wherein you have instructed us to mobilise additional resources in order to complete the works within the stipulated time. We invite your kind attention to our letter ref (3) above; we have clearly mentioned that works in 34.35 Km of the project are held up due to pending COS orders/decisions. Further, we have also mentioned that works are also hampered due to Land Acquisition (LA) problems at various stretches. From the above, it is clear that pending COS orders/decisions & LA problems are the reasons for slow progress of works. Even our existing resources are being subjected to unfruitful deployment, due to lack of work fronts, as already intimated in our letter ref (2) above. At this juncture, mobilising additional resources will only add to the huge financial loss already incurred by us. In view of the above, we request you to pursue the Authority on issuing COS orders and handing over balance ROW, free of encroachments and encumbrances. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Intimation of Occurrence of Force majeure Events | EoT; Dispute Resolution | Pursuant to Clause 21.5.1 we are notifying this as Force Majeure due to adverse weather conditions mentioned under Clause 21.2 (a) of the EPC Agreement. However, as this is a continuing event, we cannot yet conclude the estimated duration and the cost impact, it will have on us. Once the situation ceases, we shall intimate you of the cost & time impact due to the Force Majeure event. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/14. Notice of Force Majeure adverse weather condition 18.03.2019.pdf | Notice of Force Majeure under Clause 21.2 (a) and (f) - Adverse weather conditions - Acute shortage of Water | In continuation to our letter referred above, we wish to mention that the shortage of water continues as this area is facing draught. The ground water table had gone down in the last year itself due to poor rainfall. This year the total failure of monsoon in the area we are working, has lowered further the water table. Almost all the open wells and bore wells have dried up between Km 20 & 56. There is acute shortage of drinking water. Under these circumstances, we are executing the works by purchasing water from various sources far away, distancing between Km 50 & 65, since November 2018. Pursuant to Clause 21.5.1 we are notifying this as Force Majeure due to adverse weather conditions mentioned under Clause 21.2 (a) of the EPC Agreement. However, as this is a continuing event, we cannot yet conclude the estimated duration and the cost impact, it will have on us. Once the situation ceases, we shall intimate you of the cost & time impact due to the Force Majeure event. | FALSE | real_data
Intimation of Occurrence of Force majeure Events | EoT; Dispute Resolution | We already notified the above event of out break of COVID 19 as Force Majeure event vide ref (3) cited above. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/23_30042020_Extension of lockdown till 17.05.2020.pdf | Six laning of Karaipettai to Walajahpet Section of NH-4 (New NH-48) - Force Majeure Event due to outbreak of Covid 19 - Lockdown imposed by Government of India from 24.03.2020 to 03.05.2020 - Further extension of lockdown till 17.05.2020 - Intimation of the same - Reg. | Dear Sir, This is in continuation of our letter under ref (14) cited above wherein we requested your good self to obtain permission from District Administration for commencing the construction activities with available men and machinery. The Ministry of Home Affairs vide ref (13) cited above made certain inclusion on the consolidated revised guidelines issued already vide ref (6) cited above. This allowed the movement of migrant persons under Sub clause (iv) under Clause 17 on movement of persons by road. Copy of the above mentioned order relating to movement of migrant labourers is herewith enclosed as Annexure 1. Accordingly, the state administration across the country started making arrangements for bringing back the stranded migrant labourers to their respective states. Further request was also made by various chief ministers across the country to arrange rail transport for facilitating movement of migrant labourers which has also been acknowledged by the Government of India. The above mentioned movement of migrant labourers to their respective states would result in further delay of kick-starting the already stalled activities at the project site since 1st week of March 2020. Further, the Ministry of Home Affairs vide its order under ref (13) cited above extended the lockdown for a further period of 14 days from 04.05.2020.Based on the risk profile criteria, various districts across the country divided into three zones - Red, Orange and Green respectively. Red zones or hotspot districts are the ones where the prevalence of COVID 19 is more taking into account total number of active cases, doubling rate of confirmed cases, extent of testing and surveillance feedback. Copy of the above mentioned notification along with Red zone districts in Tamilnadu is herewith enclosed as Annexure 2.Irrespective of the zones, all passenger movement by rail or road or air has been prohibited except for security purposes or for purposes as permitted by Ministry of Home Affairs. Our project highway traverses through Kanhceepuram and Ranipet districts both declared as Red zone or hotspot districts by Ministry of Health and Family welfare, Government of India. Though construction activities are permitted in rural areas under point no.7 (ii) ( c ),we shall be in a position to commence full-fledged construction activities only after the return of migrant labourers. | FALSE | real_data
Intimation of Occurrence of Force majeure Events | EoT | We already notified the above event of out break of COVID 19 as Force Majeure event vide ref (3) cited above. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/26_19052020_ Extension of lockdown till 31.05.2020.pdf | Six laning of Karaipettai to Walajahpet Section of NH-4 (New NH-48) - Force, Majeure Event due to outbreak of Covid 19 - Lockdown imposed by Government of India from 24.03.2020 to 03.05.2020 extended till 17.05.2020 - Further extension of lockdown till 31.05.2020 - Intimation of the same - Reg. | After obtaining necessary approval from the District Administration, the EPC Contractor in the interest of completion of the Project Highway took proactive measures to bring back the labourers / operators from different districts within the State by arranging transportation. Accordingly, activities with available local manpower have been commenced at site and works are progressing. As communicated in our earlier correspondences, the return of migrant labourers to the Project Highway is yet to happen and this would result in further delay of kick-starting the already stalled activities which were executed by the migrant labourers. It is pertinent to mention that the State Government is making all arrangements for movement of migrant labourers to their respective states and several special trains are also arranged for their movement. Further, the Ministry of Home Affairs vide its order under ref (18) cited above extended the lockdown for a further period till 31.05.2020. Our Project Highway traverses through Kancheepuram and Ranipet districts where prevalence of Covid 19 cases are on the rise and these are the two out of twelve districts where Tamil Nadu Government has not allowed any further relaxations during this Lockdown 4.0. We already notified the above event of outbreak of Covid 19 as Force Majeure Event vide ref (3) cited above. The impact of time and cost during the lockdown period and also the subsequent re mobilizing period etc till things get completely normal with no restrictions, would be assessed and submitted in due course of time. This is for your information and further necessary action. | FALSE | real_data
Intimation of Occurrence of Force majeure Events | EoT; Dispute Resolution | We already notified the above event of outbreak of Covid 19 as Force Majeure Event vide ref (3) cited above. The impact of time and cost during the lockdown period and also the subsequent re mobilizing period etc. till things get completely normal with no restrictions, would be assessed and submitted in due course of time. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/26_19052020_ Extension of lockdown till 31.05.2020.pdf | Six laning of Karaipettai to Walajahpet Section of NH-4 (New NH-48) - Force, Majeure Event due to outbreak of Covid 19 - Lockdown imposed by Government of India from 24.03.2020 to 03.05.2020 extended till 17.05.2020 - Further extension of lockdown till 31.05.2020 - Intimation of the same - Reg. | After obtaining necessary approval from the District Administration, the EPC Contractor in the interest of completion of the Project Highway took proactive measures to bring back the labourers / operators from different districts within the State by arranging transportation. Accordingly, activities with available local manpower have been commenced at site and works are progressing. As communicated in our earlier correspondences, the return of migrant labourers to the Project Highway is yet to happen and this would result in further delay of kick-starting the already stalled activities which were executed by the migrant labourers. It is pertinent to mention that the State Government is making all arrangements for movement of migrant labourers to their respective states and several special trains are also arranged for their movement. Further, the Ministry of Home Affairs vide its order under ref (18) cited above extended the lockdown for a further period till 31.05.2020. Our Project Highway traverses through Kancheepuram and Ranipet districts where prevalence of Covid 19 cases are on the rise and these are the two out of twelve districts where Tamil Nadu Government has not allowed any further relaxations during this Lockdown 4.0. We already notified the above event of outbreak of Covid 19 as Force Majeure Event vide ref (3) cited above. The impact of time and cost during the lockdown period and also the subsequent re mobilizing period etc till things get completely normal with no restrictions, would be assessed and submitted in due course of time. This is for your information and further necessary action. | FALSE | real_data
Intimation of Occurrence of Force majeure Events | EoT; Dispute Resolution | We also notified the above as Force Majeure event in accordance with the provision of Article 21,2(a), 21.5.2 of the EPC Agreement vide ref (4) cited above. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20200402_SPK_AE_054_Works standstill due to of outbreak of Corona virus.pdf | Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km.71+015 (Existing Km 71/000) to Km 107+091 (Existing Km 107/068) on EPC Mode in the state of Tamil Nadu under NHDP Phase-V - Progress review by Member (Technical) on 04.03.2020 - Works standstill due to of outbreak of Corona virus — Reg. | Dear Sir, It has been directed by the Member (Technical) during project review meeting on 04.03.2020 to demonstrate substantial progress in the months of March and April. A target of 2.5% per month was fixed. The EPC Contractor worked on continuous basis in order to achieve the targets as directed by the Member (Technical) during the review meeting. Accordingly, SR works for commencement of structure at Km.85+874 completed and diversion of main carriage way traffic into the service road was also planned. But unfortunately due to outbreak of Corona Virus (COVID - 19), the entire construction activities were halted since 22.03.2020. The district administration with the aid of police personnel curbed the movements of our trucks and other construction equipments in order to prevent the spread of this novel virus. Further, on 17th March 2020, the Government of India issued an advisory urging to all residing in India to take social distancing, quarantine, etc., measures as a strategy for implementation till 31st Mar 2020. Due to this serious outbreak of the virus, the labour force and technical manpower deployed in our project site got panicked and many of them have left the project site to their native places fearing getting infected with the said virus. Also, several cases are reported across the country, where people who are suspected to have come in contact with the virus, escaped from the quarantines and hospitals and therefore under such situation, the labourers/construction machinery operators deployed at our project site are finding it difficult to move out of their base camp and report to the site for duty. In continuation to this advisory, Govt. of India declared complete lockdown from 24th March 2020 and necessary orders under Disaster Management Act 2005 have been passed by Ministry of Home Affairs. We also notified the above as Force Majeure event in accordance with the provision of Article 21.2(a), 21.5.2 of the EPC Agreement vide ref (4) cited above. Hence, we would like to submit that we shall not be in a position to achieve rate of progress as discussed during the meeting held on 04.03.2020 due to extraordinary kind of situation prevailing in the country as detailed above. We shall make all out efforts in enhancing the progress of works after reviewing the ground situation post lifting of lockdown on 15.04.2020. | FALSE | real_data
Intimation of Occurrence of Force majeure Events | EoT; Dispute Resolution | We already notified the above event of out break of COVID 19 as Force Majeure event vide ref (3) cited above. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20200620_SPK_NHAI_85_Lockdown imposed from 19.06.2020 to 30.06.2020.pdf | Six laning of Karaipettai to Walajahpet Section of NH-4 (New NH-48) - Force Majeure Event due to outbreak of Covid 19 - Lockdown imposed by Government of India from 24.03.2020 to 03.05.2020 extended till 31.05.2020 - Lockdown announced by TN Government from 19.06.2020 to 30.06.2020 in Chennai, Chengalpattu, Kanchipuram and Thiruvallur districts due to alarming increase of COVID 19 cases - Intimation of the same - reg | Dear Sir, Since the COVID 19 cases are alarmingly increasing, the Tamil Nadu Government ordered to enforce complete lockdown under Disaster Management Act 2005, for 12 days from 19.06.2020 to 30.06.2020 in Greater Chennai Police Commissionarate areas in Thiruvallur, Chengalpet and Kanchipuram Districts. Copy of the above-mentioned order is herewith enclosed as Annexure 1. Our Project Highway traverses through Kancheepuram and Ranipet districts where prevalence of Covid 19 cases are on the rise due to which there are restrictions in the movement of our scarcely available work force and Machineries. It is pertinent to mention that the TN Police is restricting the traffic movements by placing barricades along the Project Highway at Ch.85+875 where PCC laid for construction of VUP - Ch.85+869. Further construction of VUP couldn’t be proceeded due to placing of barricades by the police as mentioned above. As communicated in our earlier correspondences, the return of migrant labourers to the Project Highway is yet to happen and this would result in further delay of kick-starting the already stalled activities which were executed by the migrant labourers. It is pertinent to mention that the State Government is making all arrangements for movement of migrant labourers to their respective states and several Shramik special trains are also arranged for their movement. We already notified the above event of outbreak of Covid 19 as Force Majeure Event vide ref (3) cited above. The impact of time and cost during the lockdown period and the subsequent re mobilizing period etc till things get completely normal with no restrictions, would be assessed and submitted in due course of time. This is for your information and further necessary action. | FALSE | real_data
Intimation of Occurrence of Force majeure Events | EoT; Dispute Resolution | The progress was badly hampered due to outbreak of Pandemic COVID-19 and the Contractor notified the same as Force Majeure event in accordance with the provision of Article 21 of the Contract Agreement vide letter under ref (12) cited above. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20201119_SPK_AE_160_Contractor failure in achieving mile stone 1,2,&3.pdf | Six laning of Karaipcttai to Walajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - Contractor’s failure in achieving Project Mile Stone 1,2 & 3 applying of Damages vide Contract Article No. 10.3.2 & 10.3.3 - Reply made -Reg. | We are in receipt of your letter ref (26) cited above, our reply for the same is as follows: 1. The Contract Agreement for this Project was executed on 15.10.2018. The Appointed Date was fixed as 11.02.2019 and the same was communicated vide ref (2) cited above. 2. The Appointed date was declared as 11.02.2019 by the Authority taking into account the land handed over in terms of the available area without taking into consideration, the requirement of the Contract provision as per Clause 4.1.3 (a) of the EPC agreement which talks about the handing over of land only in terms of length of the Project Highway. The memorandum and appendix prepared in terms of area gave a deceptive / false picture about the availability of vacant access. Taking into consideration all the encumbrances, hindrances, utilities etc. the vacant access available on the appointed date declared was worked out and it was less than 90% and hence requested the Authority vide letter under ref (3) cited above for modification of the appointed date on which 90% of encumbrance free land would be made available to the Contractor. 3. The Authority in its response vide ref (4) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. 4. The EPC contractor vide ref (5) cited above in reply reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that the impacted length due to encroachments and encumbrances was 12.18 km which accounted to 33.77% of the project length. The workable length available to the contractor was only 66.23% of the project length. The EPC contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of encumbrance / encroachment / obstruction. | FALSE | real_data
Intimation of Occurrence of Force majeure Events | EoT; Dispute Resolution | In view of the above, the Contractor hereby notifies under Article 21 of the Contract Agreement that the restrictions/guidelines imposed by the Central Government and different State Governments like partial lock down, night curfew, following social distancing, producing negative Covid test reports are affecting the works progress under force majeure events. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20210415_SPK_PD_029_Regarding Spread of second wave of covid 19.pdf | Six laning of Karaipettai to Walajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V — Regarding spread of Second wave of “Covid 19”- Government restrictions and its effect on the Project — Notification of Force Majeure as per Article-21 of the Contract Agreement - Reg. | 1. With reference to the above subject, it is to inform that there is an outbreak of second wave of COVID-19 in India which has made the situation worst again. In this regard, looking to the severity of impact in various states, the Government of India and State Government have again taken some necessary steps of imposing restrictions like partial lockdown, night curfew, following social distancing, producing negative COVID-19 test report, etc. varying from state to state to contain spread of Pandemic and to combat the effects among the people. 2. The measures taken by different states to contain spread of pandemic have resulted in partial disruption of supply chain and elopement of Skilled and Unskilled labour in the fear of possibility of complete lockdown. The repatriation of labours due to fear and scare for the present situation are affecting the progress of work. Consequently, there is shortage of skilled labour resulting in slow pace of the project progress. Further, the guidelines to follow social distancing continues to remain in effect due to which the Contractor is compelled to work with minimum staff and labour so as to adhere to the same. 3. Hence it is pertinent to mention that there are guidelines issued by State Governments to present negative COVID-19 test report while crossing state borders due to which supply chain management has severely disrupted for major materials like Cement, Steel, Bitumen, etc. This has slowed down the production, procurement, and transportation of major materials at site which has badly affected desired pace of work progress. | FALSE | real_data
Intimation of Occurrence of Force majeure Events | EoT; Dispute Resolution | Vide ref (22) above the EPC Contractor notified the out break of second wave of COVID 19 as Force Majeure Event pursuant to Article 21 of the Contract Agreement. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20210607_SPK_PD_48_Update on FM event as on 06062021.pdf | Six laning of Karaipettai to Walajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V” — Regarding spread of Second wave of “Covid 19”- Government restrictions and its effect on the Project -Update on Force Majeure Event - Lockdown extended till 14/06/2021 with relaxations —Reg. | Vide ref (22) above the EPC Contractor notified the outbreak of Second wave of COVID 19 as Force Majeure Event pursuant to Article 21 of the Contract Agreement. | FALSE | real_data
Intimation of Occurrence of Force majeure Events | EoT; Dispute Resolution | Vide ref (22) above the EPC Contractor notified the out break of second wave of COVID 19 as Force Majeure Event pursuant to Article 21 of the Contract Agreement. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20210712_SPK_PD_050_Update on Force Majeure Event as on 11.07.2021.pdf | Six laning of Karaipettai to Walajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V” — Regarding spread of Second wave of “Covid 19”- Government restrictions and its effect on the Project -Update on Force Majeure Event - Lockdown extended till 19/07/2021 with further relaxations — Reg. | Vide ref (22) above the EPC Contractor notified the outbreak of Second wave of COVID-19 as Force Majeure Event pursuant to Article-21 of the Contract Agreement. The second wave of COVID-19 Pandemic in the country is more severe than the first wave of the Pandemic. The total active cases in the country as on 12/07/2021 is 4,50,899 and in last 24 hours fresh cases reported are 37,154. The second wave of the COVID-19 Pandemic is very severe which once again compelled the Government instrumentalities to impose strict restrictions to contain the spread of the second wave. Restrictions like partial lockdown, full lockdown in the weekends, micro containment, night curfew, COVID-19 appropriate behaviour, social distancing, mandatory RT-PCR test report, Sec 11 under Cr.PC are already in force depending upon the severity in different parts of the Country. | FALSE | real_data
Intimation of Occurrence of Force majeure Events | EoT; Dispute Resolution | Hence, as per the above provision and also this COVID 19 considered by the Central Government as epidemic (as per MHA order dated 24.03.2020) & respective State Governments is a Non - Political Force Majeure Event. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210617_AE_PD_14354_Extension on account of COVID 19 for a period of 6 months.pdf | Extension of time on account of COVID-19 Pandemic-Reg. | In regard to the above mentioned letters and subject, it is submitted that Contractor vide letter no.006 dated 25.03.2020 had intimated regarding the Covid-19 as a Force Majeure Event and requested the extension of time for 270 days due to Covid-19 vide letter No 073 dated 07.05.2020. The Contractor vide letter No. 073 dated 07.05.2020 submitted that; a) The progress of the work was badly hampered due to the outbreak of Covid-19 pandemic and same has been considered as Force Majeure Event as per Article 21 of the Contract Agreement. b) Disruption in supply chain management, which affected the availability of spare parts of the production units like plants and construction machinery which hampered the production of material and construction of work at site due to restriction imposed on movement coupled with deficient inventory levels with manufacturer's warehouses. c) The contractor was adhered to various restrictions imposed by the Statutory Authorities. d) Due to the lockdown and pandemic effect, the Project was reeling under severe shortage of workforce. All the trains and other transportation mode were suspended too. e) Absence of most of the Contractor's staff, workers, subcontractors and labourers due to uncertainty of COVID-19 situation. Assembling of people was not permitted as per the Government notification. f) For transiting between the districts, e-passes were issued by the Govt of Tamil Nadu but these e-passes were only attributed for attending death ceremony, marriage ceremony and health issues. g) Reduced output levels owing to observing stringent safety norms and need to practice social distancing on the construction site as the disease is very fatal and spreading at a higher rate. The above submitted proposal was reviewed by the Authority Engineer for 270 days Extension of Time for Project Milestones & Schedule Completion Date on the ground of COVID-19 pandemic in light of various policy guidelines issued under the Atmanirbhar Bharat Policy and the following is being submitted for ready reference and further needful, please; The Authority Engineer would like to bring kind attention on the project specific dates; The Contract Signing Date ; 15/10/2018 Length of the Project : 36.076 Km Project Cost : INR 533,36,67,000 Appointed Date : 11/02/2019 Construction Period : 730 days from Appointed Date EOT given in MS -I : 112 days for Milestone Stone - I Further to the above, AE would like to submit the provision of Contract Agreement and Atmnirbhar Bharat Policy Guidelines for ready reference, please. 1. Relevant Provisions of CA on Force Majeure: a. Classification of Force Majeure: As per clause 21.1, “As used in this Agreement, the expression “Force Majeure” or “Force Majeure Event” shall, mean occurrence in India of any or all of Non-Political Event, Indirect Political Event and Political Event, as defined in Clauses 21.2, 21.3 and 21.4 respectively, if it affects the performance by the Party claiming the benefit of Force Majeure (the “Affected Party”) of its obligations under this Agreement and which act or event (a) is beyond the reasonable control of the Affected Party, and (b) the Affected Party could not have prevented or overcome by exercise of due diligence and following Good Industry Practice, and (c) has Material Adverse Effect on the Affected Party.” | FALSE | real_data
Intimation of Occurrence of Force majeure Events | EoT; Dispute Resolution | In this regard, it is requested to submit your comments on the above notification of Force Majeure Event submitted by the Contractor as per the provisions of agreement. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210616_PD_AE_1629_Request for comments from AE on FM event.pdf | NHAI, PIU, Kancheepuram - Six laning of Karaipettai to Walajahpet section of NH-4 (Km 71/015 to Km 107/091) in the State of Tamil Nadu — Notification of Force Majeure submitted by the Contractor —- Comments Requested. | This has reference to the letters cited above, wherein the Contractor M/s. S.P.K & Co notifies Article 21 of the Contract Agreement at an outbreak of second wave of COVID-19, that the restrictions / guidelines imposed by the Central Government and different State Governments like full/partial lockdown, night curfew, following social distancing, e-passes, producing negative Covid test reports are affecting the work progress under Force Majeure events. In this regard, it is requested to submit your comments on the above Notification of Force Majeure event submitted by the Contractor as per the provisions of agreement. Encl: Copy of reference (1) to (4) | FALSE | real_data
Additional cost / compensation | Payments; Dispute Resolution | We place on record that this is a strange phenomena not foreseen at the time of bidding and has resulted in additional cost to us. The details / costing is being summarized, for submission later. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/11. Acute shortage of water 23.02.2019.pdf | Rehabilitation and Up-gradation of Paithan (Pategaon) - Mungi - Hadgaoen - Bodhegaon- Ladjalgaon — Ghogaspargaon ~ Phulsangvi ~ Ukhandachakla - Dahiwandi - Shirur to 2-Lane with paved shoulder (Project Length 55.937 Km) on EPC basis in the state of Maharashtra (Package ¦ - 56 KM) - Acute shortage of water-Reg. | The execution of road works, particularly concrete roads needs huge quantity of water before, during and after concreting. Further, in earth work, road maintenance, washing plant etc also the consumption is high. The ground water table had gone down in the last year itself due to poor rainfall. This year the total failure of monsoon in where we are working, has further lowered the water table. Almost all the open wells and bore wells have dried up between km 20 & 56. There is acute shortage of drinking water. This part of Maharashtra is drought area now. We submit to state that under these circumstances, we are executing the works by purchasing water from various sources far away, distancing between 50km to 65 km, since November 2018. We place on record that this is a strange phenomena not foreseen at the time of bidding and has resulted in additional cost to us. The details / costing is being summarized, for submission later. | FALSE | real_data
Additional cost / compensation | Dispute Resolution | We place on record that this is a strange phenomena not foreseen at the time of bidding and has resulted in additional cost to us. The details / costing is being summarized, for submission later. | synthetic_template_20250913 | Rehabilitation and Up-gradation of Paithan (Pategaon) - Mungi - Hadgaoen - Bodhegaon- Ladjalgaon — Ghogaspargaon ~ Phulsangvi ~ Ukhandachakla - Dahiwandi - Shirur to 2-Lane with paved shoulder (Project Length 55.937 Km) on EPC basis in the state of Maharashtra (Package ¦ - 56 KM) - Acute shortage of water-Reg. | The execution of road works, particularly concrete roads needs huge quantity of water before, during and after concreting. Further, in earth work, road maintenance, washing plant etc also the consumption is high. The ground water table had gone down in the last year itself due to poor rainfall. This year the total failure of monsoon in where we are working, has further lowered the water table. Almost all the open wells and bore wells have dried up between km 20 & 56. There is acute shortage of drinking water. This part of Maharashtra is drought area now. We submit to state that under these circumstances, we are executing the works by purchasing water from various sources far away, distancing between 50km to 65 km, since November 2018. We place on record that this is a strange phenomena not foreseen at the time of bidding and has resulted in additional cost to us. The details / costing is being summarized, for submission later. We await your further instructions. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Additional cost / compensation | Payments | We place on record that this is a strange phenomena not foreseen at the time of bidding and has resulted in additional cost to us. The details / costing is being summarized, for submission later. | synthetic_template_20250913 | Rehabilitation and Up-gradation of Paithan (Pategaon) - Mungi - Hadgaoen - Bodhegaon- Ladjalgaon — Ghogaspargaon ~ Phulsangvi ~ Ukhandachakla - Dahiwandi - Shirur to 2-Lane with paved shoulder (Project Length 55.937 Km) on EPC basis in the state of Maharashtra (Package ¦ - 56 KM) - Acute shortage of water-Reg. | The execution of road works, particularly concrete roads needs huge quantity of water before, during and after concreting. Further, in earth work, road maintenance, washing plant etc also the consumption is high. The ground water table had gone down in the last year itself due to poor rainfall. This year the total failure of monsoon in where we are working, has further lowered the water table. Almost all the open wells and bore wells have dried up between km 20 & 56. There is acute shortage of drinking water. This part of Maharashtra is drought area now. We submit to state that under these circumstances, we are executing the works by purchasing water from various sources far away, distancing between 50km to 65 km, since November 2018. We place on record that this is a strange phenomena not foreseen at the time of bidding and has resulted in additional cost to us. The details / costing is being summarized, for submission later. We await your further instructions. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Additional cost / compensation | Payments | We place on record that this is a strange phenomena not foreseen at the time of bidding and has resulted in additional cost to us. The details / costing is being summarized, for submission later. | synthetic_template_20250913 | Rehabilitation and Up-gradation of Paithan (Pategaon) - Mungi - Hadgaoen - Bodhegaon- Ladjalgaon — Ghogaspargaon ~ Phulsangvi ~ Ukhandachakla - Dahiwandi - Shirur to 2-Lane with paved shoulder (Project Length 55.937 Km) on EPC basis in the state of Maharashtra (Package ¦ - 56 KM) - Acute shortage of water-Reg. | The execution of road works, particularly concrete roads needs huge quantity of water before, during and after concreting. Further, in earth work, road maintenance, washing plant etc also the consumption is high. The ground water table had gone down in the last year itself due to poor rainfall. This year the total failure of monsoon in where we are working, has further lowered the water table. Almost all the open wells and bore wells have dried up between km 20 & 56. There is acute shortage of drinking water. This part of Maharashtra is drought area now. We submit to state that under these circumstances, we are executing the works by purchasing water from various sources far away, distancing between 50km to 65 km, since November 2018. We place on record that this is a strange phenomena not foreseen at the time of bidding and has resulted in additional cost to us. The details / costing is being summarized, for submission later. We await your further instructions. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Payment of Royalty/Seignoirage charges for use of Minor Minerals | Contractor's Obligations; Payments | So please release the deducted amount of royalty fee in our bill (IPC -5) | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/16. Release of Royalty money - reg.pdf | Rehabilitation and Up-gradation of Paithan (Pategaon) - Mungi - Hadgaon - Bodhegaon- Ladjalgaon — Ghogaspargaon — Phulsangvi - Ukhandachakla — Dahiwandi - Shirur to 2-Lane with paved shoulder (Project Length 55.937 Km) on EPC basis in the state of Maharashtra (Package ¦ — 56 KM) — Release of Royalty money -Reg | With respect to above subject we submitting attachment of Royalty deduct from our interim payment certificate (IPC-05), but still now it is not credited in concerned taluka they asking us several time regarding the royalty amount. So please release the deducted amount of royalty fee in our bill (IPC -5). | FALSE | real_data
Payment of Royalty/Seignoirage charges for use of Minor Minerals | Payments | So please release the deducted amount of royalty fee in our bill (IPC -5) | synthetic_template_20250913 | Rehabilitation and Up-gradation of Paithan (Pategaon) - Mungi - Hadgaon - Bodhegaon- Ladjalgaon — Ghogaspargaon — Phulsangvi - Ukhandachakla — Dahiwandi - Shirur to 2-Lane with paved shoulder (Project Length 55.937 Km) on EPC basis in the state of Maharashtra (Package ¦ — 56 KM) — Release of Royalty money -Reg | With respect to above subject we submitting attachment of Royalty deduct from our interim payment certificate (IPC-05), but still now it is not credited in concerned taluka they asking us several time regarding the royalty amount. So please release the deducted amount of royalty fee in our bill (IPC -5). | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Payment of Royalty/Seignoirage charges for use of Minor Minerals | Contractor's Obligations | So please release the deducted amount of royalty fee in our bill (IPC -5) | synthetic_template_20250913 | Rehabilitation and Up-gradation of Paithan (Pategaon) - Mungi - Hadgaon - Bodhegaon- Ladjalgaon — Ghogaspargaon — Phulsangvi - Ukhandachakla — Dahiwandi - Shirur to 2-Lane with paved shoulder (Project Length 55.937 Km) on EPC basis in the state of Maharashtra (Package ¦ — 56 KM) — Release of Royalty money -Reg | Please note that With respect to above subject we submitting attachment of Royalty deduct from our interim payment certificate (IPC-05), but still now it is not credited in concerned taluka they asking us several time regarding the royalty amount. So please release the deducted amount of royalty fee in our bill (IPC -5). We await your further instructions. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Payment of Royalty/Seignoirage charges for use of Minor Minerals | Contractor's Obligations | So please release the deducted amount of royalty fee in our bill (IPC -5) | synthetic_template_20250913 | Rehabilitation and Up-gradation of Paithan (Pategaon) - Mungi - Hadgaon - Bodhegaon- Ladjalgaon — Ghogaspargaon — Phulsangvi - Ukhandachakla — Dahiwandi - Shirur to 2-Lane with paved shoulder (Project Length 55.937 Km) on EPC basis in the state of Maharashtra (Package ¦ — 56 KM) — Release of Royalty money -Reg | With respect to above subject we submitting attachment of Royalty deduct from our interim payment certificate (IPC-05), but still now it is not credited in concerned taluka they asking us several time regarding the royalty amount. So please release the deducted amount of royalty fee in our bill (IPC -5). We look forward to your response. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Cure period Notice | Payments; Dispute Resolution | Intend to issue a Notice to the Authority under Clause 23.2.1 of the Contract to cure their material default | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/19. Intention to issue cure period notice 02.11.2019.pdf | Intention to issue Cure Period Notice to the Authority under clause 23.2.1 for temporary demobilization | This is regarding non-availability of encroachment and encumbrance free Right of Way (ROW) along the project highway, regarding which we wish to mention the following: 1. Subsequent to the signing of EPC Agreement dated 18.04.2017 the Appointed Date was fixed on 02.06.2017 and was communicated through Authority's letter no. 1190. It was mentioned in the letter that requirements under Clause 8.2 and obligations under 4.1.3(a), Annex II of Schedule-A are fulfilled by the Authority. 2. However, when we actually mobilised to site, we realised that the Obligations are not fulfilled by the Authority, in terms of the provisions relating to ROW and Appointed Date cited above. We noticed that there is no clarity even on the existing ROW widths. 3. We had submitted the Memorandum / Appendix through our letter no. 71 dated 10th Aug 2017, which indicates that the vacant access and ROW have not been granted at certain locations. Despite several requests, joint site inspection was not done and till date duly countersigned copy of the Memorandum / Appendix prepared by us is not returned till to date. 4. We have been reporting the lack of ROW through our Monthly Progress Reports every month, in addition among various letters on the subject. It is pertinent to mention that even as on date, not a single kilometre/ hectare of additional land has been acquired by the Authority under this project. However, we had convinced the local public and could get some progress in the project due to our efforts. 5. The dispute regarding land acquisition still continues among landowners, Authority and Revenue Authority (CALA). 6. There are realignments in the project for a length of 5.350 Kms, the land acquisition of which is not yet taken up where in there are no ROW boundaries and which area can be acquired directly. Two minor bridges are held up in the realignments. 7. As mentioned in Authority’s and AE's EOT recommendations, Gazette notification for land acquisition was issued on 31st December 2018, after a lapse of 18 months from appointed date. 8. It is also mentioned in your letter no. 78 dated 02.03.2019, that the EOT duration determined was subject to the condition that the ROW for the affected reaches will be handed over to the Contractor by 31.03.2019 and all the hindrances/obstructions will also be removed by 31.03.2019. 9. However, even till date, no further land has been handed over by the Authority we regret to maintain that even the existing ROW width is disputed between land owners concerned Authority. In addition the Acquisition was to be mobilized: the area of ACQUISITION FOR DIFFERENT Land owners is a single survey numbers. Some of them in this case having different survey numbers. 10. As intimated earlier, we have been facing financial losses due to idling of resources and simultaneously incurring fixed and renewing costs. In view of the above, we intend to issue a Notice to the Authority under clause 23.2.1 of the Contract to cure their material default in handing over of ROW which has a huge material adverse effect on our works. We once again request you to pursue with the Authority in expediting handing over of the balance ROW as soon as possible. Due to the above breach of the obligations by the Authority in terms of land handing over, a situation has arisen wherein we have no option other than temporarily demobilizing from site, to avoid further financial loss to us. We shall remobilize upon intimation from you / Authority regarding the availability of balance ROW. | FALSE | real_data
Cure period Notice | Dispute Resolution | Intend to issue a Notice to the Authority under Clause 23.2.1 of the Contract to cure their material default | synthetic_template_20250913 | Intention to issue Cure Period Notice to the Authority under clause 23.2.1 for temporary demobilization | This is regarding non-availability of encroachment and encumbrance free Right of Way (ROW) along the project highway, regarding which we wish to mention the following: 1. Subsequent to the signing of EPC Agreement dated 18.04.2017 the Appointed Date was fixed on 02.06.2017 and was communicated through Authority's letter no. 1190. It was mentioned in the letter that requirements under Clause 8.2 and obligations under 4.1.3(a), Annex II of Schedule-A are fulfilled by the Authority. 2. However, when we actually mobilised to site, we realised that the Obligations are not fulfilled by the Authority, in terms of the provisions relating to ROW and Appointed Date cited above. We noticed that there is no clarity even on the existing ROW widths. 3. We had submitted the Memorandum / Appendix through our letter no. 71 dated 10th Aug 2017, which indicates that the vacant access and ROW have not been granted at certain locations. Despite several requests, joint site inspection was not done and till date duly countersigned copy of the Memorandum / Appendix prepared by us is not returned till to date. 4. We have been reporting the lack of ROW through our Monthly Progress Reports every month, in addition among various letters on the subject. It is pertinent to mention that even as on date, not a single kilometre/ hectare of additional land has been acquired by the Authority under this project. However, we had convinced the local public and could get some progress in the project due to our efforts. 5. The dispute regarding land acquisition still continues among landowners, Authority and Revenue Authority (CALA). 6. There are realignments in the project for a length of 5.350 Kms, the land acquisition of which is not yet taken up where in there are no ROW boundaries and which area can be acquired directly. Two minor bridges are held up in the realignments. 7. As mentioned in Authority’s and AE's EOT recommendations, Gazette notification for land acquisition was issued on 31st December 2018, after a lapse of 18 months from appointed date. 8. It is also mentioned in your letter no. 78 dated 02.03.2019, that the EOT duration determined was subject to the condition that the ROW for the affected reaches will be handed over to the Contractor by 31.03.2019 and all the hindrances/obstructions will also be removed by 31.03.2019. 9. However, even till date, no further land has been handed over by the Authority we regret to maintain that even the existing ROW width is disputed between land owners concerned Authority. In addition the Acquisition was to be mobilized: the area of ACQUISITION FOR DIFFERENT Land owners is a single survey numbers. Some of them in this case having different survey numbers. 10. As intimated earlier, we have been facing financial losses due to idling of resources and simultaneously incurring fixed and renewing costs. In view of the above, we intend to issue a Notice to the Authority under clause 23.2.1 of the Contract to cure their material default in handing over of ROW which has a huge material adverse effect on our works. We once again request you to pursue with the Authority in expediting handing over of the balance ROW as soon as possible. Due to the above breach of the obligations by the Authority in terms of land handing over, a situation has arisen wherein we have no option other than temporarily demobilizing from site, to avoid further financial loss to us. We shall remobilize upon intimation from you / Authority regarding the availability of balance ROW. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Cure period Notice | Payments | Intend to issue a Notice to the Authority under Clause 23.2.1 of the Contract to cure their material default | synthetic_template_20250913 | Intention to issue Cure Period Notice to the Authority under clause 23.2.1 for temporary demobilization | This is regarding non-availability of encroachment and encumbrance free Right of Way (ROW) along the project highway, regarding which we wish to mention the following: 1. Subsequent to the signing of EPC Agreement dated 18.04.2017 the Appointed Date was fixed on 02.06.2017 and was communicated through Authority's letter no. 1190. It was mentioned in the letter that requirements under Clause 8.2 and obligations under 4.1.3(a), Annex II of Schedule-A are fulfilled by the Authority. 2. However, when we actually mobilised to site, we realised that the Obligations are not fulfilled by the Authority, in terms of the provisions relating to ROW and Appointed Date cited above. We noticed that there is no clarity even on the existing ROW widths. 3. We had submitted the Memorandum / Appendix through our letter no. 71 dated 10th Aug 2017, which indicates that the vacant access and ROW have not been granted at certain locations. Despite several requests, joint site inspection was not done and till date duly countersigned copy of the Memorandum / Appendix prepared by us is not returned till to date. 4. We have been reporting the lack of ROW through our Monthly Progress Reports every month, in addition among various letters on the subject. It is pertinent to mention that even as on date, not a single kilometre/ hectare of additional land has been acquired by the Authority under this project. However, we had convinced the local public and could get some progress in the project due to our efforts. 5. The dispute regarding land acquisition still continues among landowners, Authority and Revenue Authority (CALA). 6. There are realignments in the project for a length of 5.350 Kms, the land acquisition of which is not yet taken up where in there are no ROW boundaries and which area can be acquired directly. Two minor bridges are held up in the realignments. 7. As mentioned in Authority’s and AE's EOT recommendations, Gazette notification for land acquisition was issued on 31st December 2018, after a lapse of 18 months from appointed date. 8. It is also mentioned in your letter no. 78 dated 02.03.2019, that the EOT duration determined was subject to the condition that the ROW for the affected reaches will be handed over to the Contractor by 31.03.2019 and all the hindrances/obstructions will also be removed by 31.03.2019. 9. However, even till date, no further land has been handed over by the Authority we regret to maintain that even the existing ROW width is disputed between land owners concerned Authority. In addition the Acquisition was to be mobilized: the area of ACQUISITION FOR DIFFERENT Land owners is a single survey numbers. Some of them in this case having different survey numbers. 10. As intimated earlier, we have been facing financial losses due to idling of resources and simultaneously incurring fixed and renewing costs. In view of the above, we intend to issue a Notice to the Authority under clause 23.2.1 of the Contract to cure their material default in handing over of ROW which has a huge material adverse effect on our works. We once again request you to pursue with the Authority in expediting handing over of the balance ROW as soon as possible. Due to the above breach of the obligations by the Authority in terms of land handing over, a situation has arisen wherein we have no option other than temporarily demobilizing from site, to avoid further financial loss to us. We shall remobilize upon intimation from you / Authority regarding the availability of balance ROW. We await your further instructions. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Cure period Notice | Payments | Intend to issue a Notice to the Authority under Clause 23.2.1 of the Contract to cure their material default | synthetic_template_20250913 | Intention to issue Cure Period Notice to the Authority under clause 23.2.1 for temporary demobilization | This is regarding non-availability of encroachment and encumbrance free Right of Way (ROW) along the project highway, regarding which we wish to mention the following: 1. Subsequent to the signing of EPC Agreement dated 18.04.2017 the Appointed Date was fixed on 02.06.2017 and was communicated through Authority's letter no. 1190. It was mentioned in the letter that requirements under Clause 8.2 and obligations under 4.1.3(a), Annex II of Schedule-A are fulfilled by the Authority. 2. However, when we actually mobilised to site, we realised that the Obligations are not fulfilled by the Authority, in terms of the provisions relating to ROW and Appointed Date cited above. We noticed that there is no clarity even on the existing ROW widths. 3. We had submitted the Memorandum / Appendix through our letter no. 71 dated 10th Aug 2017, which indicates that the vacant access and ROW have not been granted at certain locations. Despite several requests, joint site inspection was not done and till date duly countersigned copy of the Memorandum / Appendix prepared by us is not returned till to date. 4. We have been reporting the lack of ROW through our Monthly Progress Reports every month, in addition among various letters on the subject. It is pertinent to mention that even as on date, not a single kilometre/ hectare of additional land has been acquired by the Authority under this project. However, we had convinced the local public and could get some progress in the project due to our efforts. 5. The dispute regarding land acquisition still continues among landowners, Authority and Revenue Authority (CALA). 6. There are realignments in the project for a length of 5.350 Kms, the land acquisition of which is not yet taken up where in there are no ROW boundaries and which area can be acquired directly. Two minor bridges are held up in the realignments. 7. As mentioned in Authority’s and AE's EOT recommendations, Gazette notification for land acquisition was issued on 31st December 2018, after a lapse of 18 months from appointed date. 8. It is also mentioned in your letter no. 78 dated 02.03.2019, that the EOT duration determined was subject to the condition that the ROW for the affected reaches will be handed over to the Contractor by 31.03.2019 and all the hindrances/obstructions will also be removed by 31.03.2019. 9. However, even till date, no further land has been handed over by the Authority we regret to maintain that even the existing ROW width is disputed between land owners concerned Authority. In addition the Acquisition was to be mobilized: the area of ACQUISITION FOR DIFFERENT Land owners is a single survey numbers. Some of them in this case having different survey numbers. 10. As intimated earlier, we have been facing financial losses due to idling of resources and simultaneously incurring fixed and renewing costs. In view of the above, we intend to issue a Notice to the Authority under clause 23.2.1 of the Contract to cure their material default in handing over of ROW which has a huge material adverse effect on our works. We once again request you to pursue with the Authority in expediting handing over of the balance ROW as soon as possible. Due to the above breach of the obligations by the Authority in terms of land handing over, a situation has arisen wherein we have no option other than temporarily demobilizing from site, to avoid further financial loss to us. We shall remobilize upon intimation from you / Authority regarding the availability of balance ROW. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Demobilisation and Remobilisation | EoT | losses, the cost of demobilizing and remobilizing would also be attributable to the Authority and will be submitted at an appropriate time. | synthetic_template_20250913 | Intention to issue Cure Period Notice to the Authority under clause 23.2.1 for temporary demobilization | This is regarding non-availability of encroachment and encumbrance free Right of Way (ROW) along the project highway, regarding which we wish to mention the following: 1. Subsequent to the signing of EPC Agreement dated 18.04.2017 the Appointed Date was fixed on 02.06.2017 and was communicated through Authority's letter no. 1190. It was mentioned in the letter that requirements under Clause 8.2 and obligations under 4.1.3(a), Annex II of Schedule-A are fulfilled by the Authority. 2. However, when we actually mobilised to site, we realised that the Obligations are not fulfilled by the Authority, in terms of the provisions relating to ROW and Appointed Date cited above. We noticed that there is no clarity even on the existing ROW widths. 3. We had submitted the Memorandum / Appendix through our letter no. 71 dated 10th Aug 2017, which indicates that the vacant access and ROW have not been granted at certain locations. Despite several requests, joint site inspection was not done and till date duly countersigned copy of the Memorandum / Appendix prepared by us is not returned till to date. 4. We have been reporting the lack of ROW through our Monthly Progress Reports every month, in addition among various letters on the subject. It is pertinent to mention that even as on date, not a single kilometre/ hectare of additional land has been acquired by the Authority under this project. However, we had convinced the local public and could get some progress in the project due to our efforts. 5. The dispute regarding land acquisition still continues among landowners, Authority and Revenue Authority (CALA). 6. There are realignments in the project for a length of 5.350 Kms, the land acquisition of which is not yet taken up where in there are no ROW boundaries and which area can be acquired directly. Two minor bridges are held up in the realignments. 7. As mentioned in Authority’s and AE's EOT recommendations, Gazette notification for land acquisition was issued on 31st December 2018, after a lapse of 18 months from appointed date. 8. It is also mentioned in your letter no. 78 dated 02.03.2019, that the EOT duration determined was subject to the condition that the ROW for the affected reaches will be handed over to the Contractor by 31.03.2019 and all the hindrances/obstructions will also be removed by 31.03.2019. 9. However, even till date, no further land has been handed over by the Authority we regret to maintain that even the existing ROW width is disputed between land owners concerned Authority. In addition the Acquisition was to be mobilized: the area of ACQUISITION FOR DIFFERENT Land owners is a single survey numbers. Some of them in this case having different survey numbers. 10. As intimated earlier, we have been facing financial losses due to idling of resources and simultaneously incurring fixed and renewing costs. In view of the above, we intend to issue a Notice to the Authority under clause 23.2.1 of the Contract to cure their material default in handing over of ROW which has a huge material adverse effect on our works. We once again request you to pursue with the Authority in expediting handing over of the balance ROW as soon as possible. Due to the above breach of the obligations by the Authority in terms of land handing over, a situation has arisen wherein we have no option other than temporarily demobilizing from site, to avoid further financial loss to us. We shall remobilize upon intimation from you / Authority regarding the availability of balance ROW. Thank you for your attention to this matter. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Demobilisation and Remobilisation | EoT | losses, the cost of demobilizing and remobilizing would also be attributable to the Authority and will be submitted at an appropriate time. | synthetic_template_20250913 | Intention to issue Cure Period Notice to the Authority under clause 23.2.1 for temporary demobilization | This is regarding non-availability of encroachment and encumbrance free Right of Way (ROW) along the project highway, regarding which we wish to mention the following: 1. Subsequent to the signing of EPC Agreement dated 18.04.2017 the Appointed Date was fixed on 02.06.2017 and was communicated through Authority's letter no. 1190. It was mentioned in the letter that requirements under Clause 8.2 and obligations under 4.1.3(a), Annex II of Schedule-A are fulfilled by the Authority. 2. However, when we actually mobilised to site, we realised that the Obligations are not fulfilled by the Authority, in terms of the provisions relating to ROW and Appointed Date cited above. We noticed that there is no clarity even on the existing ROW widths. 3. We had submitted the Memorandum / Appendix through our letter no. 71 dated 10th Aug 2017, which indicates that the vacant access and ROW have not been granted at certain locations. Despite several requests, joint site inspection was not done and till date duly countersigned copy of the Memorandum / Appendix prepared by us is not returned till to date. 4. We have been reporting the lack of ROW through our Monthly Progress Reports every month, in addition among various letters on the subject. It is pertinent to mention that even as on date, not a single kilometre/ hectare of additional land has been acquired by the Authority under this project. However, we had convinced the local public and could get some progress in the project due to our efforts. 5. The dispute regarding land acquisition still continues among landowners, Authority and Revenue Authority (CALA). 6. There are realignments in the project for a length of 5.350 Kms, the land acquisition of which is not yet taken up where in there are no ROW boundaries and which area can be acquired directly. Two minor bridges are held up in the realignments. 7. As mentioned in Authority’s and AE's EOT recommendations, Gazette notification for land acquisition was issued on 31st December 2018, after a lapse of 18 months from appointed date. 8. It is also mentioned in your letter no. 78 dated 02.03.2019, that the EOT duration determined was subject to the condition that the ROW for the affected reaches will be handed over to the Contractor by 31.03.2019 and all the hindrances/obstructions will also be removed by 31.03.2019. 9. However, even till date, no further land has been handed over by the Authority we regret to maintain that even the existing ROW width is disputed between land owners concerned Authority. In addition the Acquisition was to be mobilized: the area of ACQUISITION FOR DIFFERENT Land owners is a single survey numbers. Some of them in this case having different survey numbers. 10. As intimated earlier, we have been facing financial losses due to idling of resources and simultaneously incurring fixed and renewing costs. In view of the above, we intend to issue a Notice to the Authority under clause 23.2.1 of the Contract to cure their material default in handing over of ROW which has a huge material adverse effect on our works. We once again request you to pursue with the Authority in expediting handing over of the balance ROW as soon as possible. Due to the above breach of the obligations by the Authority in terms of land handing over, a situation has arisen wherein we have no option other than temporarily demobilizing from site, to avoid further financial loss to us. We shall remobilize upon intimation from you / Authority regarding the availability of balance ROW. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Demobilisation and Remobilisation | Dispute Resolution | losses, the cost of demobilizing and remobilizing would also be attributable to the Authority and will be submitted at an appropriate time. | synthetic_template_20250913 | Intention to issue Cure Period Notice to the Authority under clause 23.2.1 for temporary demobilization | Kindly be informed that This is regarding non-availability of encroachment and encumbrance free Right of Way (ROW) along the project highway, regarding which we wish to mention the following: 1. Subsequent to the signing of EPC Agreement dated 18.04.2017 the Appointed Date was fixed on 02.06.2017 and was communicated through Authority's letter no. 1190. It was mentioned in the letter that requirements under Clause 8.2 and obligations under 4.1.3(a), Annex II of Schedule-A are fulfilled by the Authority. 2. However, when we actually mobilised to site, we realised that the Obligations are not fulfilled by the Authority, in terms of the provisions relating to ROW and Appointed Date cited above. We noticed that there is no clarity even on the existing ROW widths. 3. We had submitted the Memorandum / Appendix through our letter no. 71 dated 10th Aug 2017, which indicates that the vacant access and ROW have not been granted at certain locations. Despite several requests, joint site inspection was not done and till date duly countersigned copy of the Memorandum / Appendix prepared by us is not returned till to date. 4. We have been reporting the lack of ROW through our Monthly Progress Reports every month, in addition among various letters on the subject. It is pertinent to mention that even as on date, not a single kilometre/ hectare of additional land has been acquired by the Authority under this project. However, we had convinced the local public and could get some progress in the project due to our efforts. 5. The dispute regarding land acquisition still continues among landowners, Authority and Revenue Authority (CALA). 6. There are realignments in the project for a length of 5.350 Kms, the land acquisition of which is not yet taken up where in there are no ROW boundaries and which area can be acquired directly. Two minor bridges are held up in the realignments. 7. As mentioned in Authority’s and AE's EOT recommendations, Gazette notification for land acquisition was issued on 31st December 2018, after a lapse of 18 months from appointed date. 8. It is also mentioned in your letter no. 78 dated 02.03.2019, that the EOT duration determined was subject to the condition that the ROW for the affected reaches will be handed over to the Contractor by 31.03.2019 and all the hindrances/obstructions will also be removed by 31.03.2019. 9. However, even till date, no further land has been handed over by the Authority we regret to maintain that even the existing ROW width is disputed between land owners concerned Authority. In addition the Acquisition was to be mobilized: the area of ACQUISITION FOR DIFFERENT Land owners is a single survey numbers. Some of them in this case having different survey numbers. 10. As intimated earlier, we have been facing financial losses due to idling of resources and simultaneously incurring fixed and renewing costs. In view of the above, we intend to issue a Notice to the Authority under clause 23.2.1 of the Contract to cure their material default in handing over of ROW which has a huge material adverse effect on our works. We once again request you to pursue with the Authority in expediting handing over of the balance ROW as soon as possible. Due to the above breach of the obligations by the Authority in terms of land handing over, a situation has arisen wherein we have no option other than temporarily demobilizing from site, to avoid further financial loss to us. We shall remobilize upon intimation from you / Authority regarding the availability of balance ROW. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Demobilisation and Remobilisation | Dispute Resolution | losses, the cost of demobilizing and remobilizing would also be attributable to the Authority and will be submitted at an appropriate time. | synthetic_template_20250913 | Intention to issue Cure Period Notice to the Authority under clause 23.2.1 for temporary demobilization | This is regarding non-availability of encroachment and encumbrance free Right of Way (ROW) along the project highway, regarding which we wish to mention the following: 1. Subsequent to the signing of EPC Agreement dated 18.04.2017 the Appointed Date was fixed on 02.06.2017 and was communicated through Authority's letter no. 1190. It was mentioned in the letter that requirements under Clause 8.2 and obligations under 4.1.3(a), Annex II of Schedule-A are fulfilled by the Authority. 2. However, when we actually mobilised to site, we realised that the Obligations are not fulfilled by the Authority, in terms of the provisions relating to ROW and Appointed Date cited above. We noticed that there is no clarity even on the existing ROW widths. 3. We had submitted the Memorandum / Appendix through our letter no. 71 dated 10th Aug 2017, which indicates that the vacant access and ROW have not been granted at certain locations. Despite several requests, joint site inspection was not done and till date duly countersigned copy of the Memorandum / Appendix prepared by us is not returned till to date. 4. We have been reporting the lack of ROW through our Monthly Progress Reports every month, in addition among various letters on the subject. It is pertinent to mention that even as on date, not a single kilometre/ hectare of additional land has been acquired by the Authority under this project. However, we had convinced the local public and could get some progress in the project due to our efforts. 5. The dispute regarding land acquisition still continues among landowners, Authority and Revenue Authority (CALA). 6. There are realignments in the project for a length of 5.350 Kms, the land acquisition of which is not yet taken up where in there are no ROW boundaries and which area can be acquired directly. Two minor bridges are held up in the realignments. 7. As mentioned in Authority’s and AE's EOT recommendations, Gazette notification for land acquisition was issued on 31st December 2018, after a lapse of 18 months from appointed date. 8. It is also mentioned in your letter no. 78 dated 02.03.2019, that the EOT duration determined was subject to the condition that the ROW for the affected reaches will be handed over to the Contractor by 31.03.2019 and all the hindrances/obstructions will also be removed by 31.03.2019. 9. However, even till date, no further land has been handed over by the Authority we regret to maintain that even the existing ROW width is disputed between land owners concerned Authority. In addition the Acquisition was to be mobilized: the area of ACQUISITION FOR DIFFERENT Land owners is a single survey numbers. Some of them in this case having different survey numbers. 10. As intimated earlier, we have been facing financial losses due to idling of resources and simultaneously incurring fixed and renewing costs. In view of the above, we intend to issue a Notice to the Authority under clause 23.2.1 of the Contract to cure their material default in handing over of ROW which has a huge material adverse effect on our works. We once again request you to pursue with the Authority in expediting handing over of the balance ROW as soon as possible. Due to the above breach of the obligations by the Authority in terms of land handing over, a situation has arisen wherein we have no option other than temporarily demobilizing from site, to avoid further financial loss to us. We shall remobilize upon intimation from you / Authority regarding the availability of balance ROW. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Demobilisation and Remobilisation | Payments | losses, the cost of demobilizing and remobilizing would also be attributable to the Authority and will be submitted at an appropriate time. | synthetic_template_20250913 | Intention to issue Cure Period Notice to the Authority under clause 23.2.1 for temporary demobilization | This is regarding non-availability of encroachment and encumbrance free Right of Way (ROW) along the project highway, regarding which we wish to mention the following: 1. Subsequent to the signing of EPC Agreement dated 18.04.2017 the Appointed Date was fixed on 02.06.2017 and was communicated through Authority's letter no. 1190. It was mentioned in the letter that requirements under Clause 8.2 and obligations under 4.1.3(a), Annex II of Schedule-A are fulfilled by the Authority. 2. However, when we actually mobilised to site, we realised that the Obligations are not fulfilled by the Authority, in terms of the provisions relating to ROW and Appointed Date cited above. We noticed that there is no clarity even on the existing ROW widths. 3. We had submitted the Memorandum / Appendix through our letter no. 71 dated 10th Aug 2017, which indicates that the vacant access and ROW have not been granted at certain locations. Despite several requests, joint site inspection was not done and till date duly countersigned copy of the Memorandum / Appendix prepared by us is not returned till to date. 4. We have been reporting the lack of ROW through our Monthly Progress Reports every month, in addition among various letters on the subject. It is pertinent to mention that even as on date, not a single kilometre/ hectare of additional land has been acquired by the Authority under this project. However, we had convinced the local public and could get some progress in the project due to our efforts. 5. The dispute regarding land acquisition still continues among landowners, Authority and Revenue Authority (CALA). 6. There are realignments in the project for a length of 5.350 Kms, the land acquisition of which is not yet taken up where in there are no ROW boundaries and which area can be acquired directly. Two minor bridges are held up in the realignments. 7. As mentioned in Authority’s and AE's EOT recommendations, Gazette notification for land acquisition was issued on 31st December 2018, after a lapse of 18 months from appointed date. 8. It is also mentioned in your letter no. 78 dated 02.03.2019, that the EOT duration determined was subject to the condition that the ROW for the affected reaches will be handed over to the Contractor by 31.03.2019 and all the hindrances/obstructions will also be removed by 31.03.2019. 9. However, even till date, no further land has been handed over by the Authority we regret to maintain that even the existing ROW width is disputed between land owners concerned Authority. In addition the Acquisition was to be mobilized: the area of ACQUISITION FOR DIFFERENT Land owners is a single survey numbers. Some of them in this case having different survey numbers. 10. As intimated earlier, we have been facing financial losses due to idling of resources and simultaneously incurring fixed and renewing costs. In view of the above, we intend to issue a Notice to the Authority under clause 23.2.1 of the Contract to cure their material default in handing over of ROW which has a huge material adverse effect on our works. We once again request you to pursue with the Authority in expediting handing over of the balance ROW as soon as possible. Due to the above breach of the obligations by the Authority in terms of land handing over, a situation has arisen wherein we have no option other than temporarily demobilizing from site, to avoid further financial loss to us. We shall remobilize upon intimation from you / Authority regarding the availability of balance ROW. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Demobilisation and Remobilisation | Payments | losses, the cost of demobilizing and remobilizing would also be attributable to the Authority and will be submitted at an appropriate time. | synthetic_template_20250913 | Intention to issue Cure Period Notice to the Authority under clause 23.2.1 for temporary demobilization | It is brought to your attention that This is regarding non-availability of encroachment and encumbrance free Right of Way (ROW) along the project highway, regarding which we wish to mention the following: 1. Subsequent to the signing of EPC Agreement dated 18.04.2017 the Appointed Date was fixed on 02.06.2017 and was communicated through Authority's letter no. 1190. It was mentioned in the letter that requirements under Clause 8.2 and obligations under 4.1.3(a), Annex II of Schedule-A are fulfilled by the Authority. 2. However, when we actually mobilised to site, we realised that the Obligations are not fulfilled by the Authority, in terms of the provisions relating to ROW and Appointed Date cited above. We noticed that there is no clarity even on the existing ROW widths. 3. We had submitted the Memorandum / Appendix through our letter no. 71 dated 10th Aug 2017, which indicates that the vacant access and ROW have not been granted at certain locations. Despite several requests, joint site inspection was not done and till date duly countersigned copy of the Memorandum / Appendix prepared by us is not returned till to date. 4. We have been reporting the lack of ROW through our Monthly Progress Reports every month, in addition among various letters on the subject. It is pertinent to mention that even as on date, not a single kilometre/ hectare of additional land has been acquired by the Authority under this project. However, we had convinced the local public and could get some progress in the project due to our efforts. 5. The dispute regarding land acquisition still continues among landowners, Authority and Revenue Authority (CALA). 6. There are realignments in the project for a length of 5.350 Kms, the land acquisition of which is not yet taken up where in there are no ROW boundaries and which area can be acquired directly. Two minor bridges are held up in the realignments. 7. As mentioned in Authority’s and AE's EOT recommendations, Gazette notification for land acquisition was issued on 31st December 2018, after a lapse of 18 months from appointed date. 8. It is also mentioned in your letter no. 78 dated 02.03.2019, that the EOT duration determined was subject to the condition that the ROW for the affected reaches will be handed over to the Contractor by 31.03.2019 and all the hindrances/obstructions will also be removed by 31.03.2019. 9. However, even till date, no further land has been handed over by the Authority we regret to maintain that even the existing ROW width is disputed between land owners concerned Authority. In addition the Acquisition was to be mobilized: the area of ACQUISITION FOR DIFFERENT Land owners is a single survey numbers. Some of them in this case having different survey numbers. 10. As intimated earlier, we have been facing financial losses due to idling of resources and simultaneously incurring fixed and renewing costs. In view of the above, we intend to issue a Notice to the Authority under clause 23.2.1 of the Contract to cure their material default in handing over of ROW which has a huge material adverse effect on our works. We once again request you to pursue with the Authority in expediting handing over of the balance ROW as soon as possible. Due to the above breach of the obligations by the Authority in terms of land handing over, a situation has arisen wherein we have no option other than temporarily demobilizing from site, to avoid further financial loss to us. We shall remobilize upon intimation from you / Authority regarding the availability of balance ROW. Thank you for your attention to this matter. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Request for revisit of EOT determined/approved | EoT; Dispute Resolution | We hereby request the Authority to revisit the EOT determined/approved and communicate 324 days as interim extension of time. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/28_25052020_Request for revisiting the EOT already recommended.pdf | Extension of Time and Rescheduling of Project Milestones - EOT granted for 112 days not acceptable to the EPC contractor ~ Request for revisiting the EOT recommended — Reg. | This is with respect to the Extension of Time(EOT) approved by the Authority for a period of 112 days for Project Milestone I without effecting changes in Scheduled Project Completion Period vide ref (3) cited above.The EPC Contrator disagrees and does not accept the grant of KU’! approval tor 112 days, the reasons for disgreeement of this approval are elaborated in our submission to the Authority Engineer vide ref (4) cited above and copy of the same is herewith enclosed as Annexure 1. It is also submitted that EOT is granted by rescheduling all the Project Milestones and not for a specific Project Milestone pursuant to Clause 6 of Schedule J of the Contract Agreement. We hereby request the Authority to revisit the EOT determined/approved and communicate 324 days as interim Extension of time. | FALSE | real_data
Request for revisit of EOT determined/approved | EoT; Dispute Resolution | We once again request the Authority to reconsider the EOT already recommended and communicate 324 days as interim extension of time at the earliest failing which, the EPC Contractor is left with no other option other than invoking Sub clause 26.1 0f the Concession Agreement. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20200713_SPK_RO_42_Reminder - Request for revisiting the EOT already recommended - Rev2.pdf | Extension of Time and Rescheduling of Project Milestones - EOT granted for 112 days not acceptable to the EPC contractor - Request for revisiting the EOT recommended - Reminder sent - Reg. | 1. This is with respect to the Extension of Time(EOT} approved by the Authority for. a period of 112 days for Project Milestone-I without effecting changes in Scheduled Project Completion Period vide ref (3) cited above.The EPC Contrator disagrees and does not accept the grant of EOT approval for 112 days, the reasons for disgreeement of this approval are elaborated in our submission to the Authority Engineer vide ref (4) cited above. 2. The EPC contractor requested the Authority/NHAI to revisit the EOT determined/approved and communicate 324 days as interim Extension of time vide ref (5) cited above but, we are yet to receive response in this regard. Copy of the same is herewith enclosed as Annexure 1. 3. The Authority is yet to fulfil the obligations relating to handing over of ROW as per Sub Clause 8.2 of the Contract Agreement. Copy of the newspaper publication regarding LA status / notification for acquiring land for the Project Highway (Kanchipuram District} is herewith enclosed as Annexure 2. By not fulfilling the obligations as per the provisions of the Contract Agreement, the Authority committed a material default pursuant to Sub clause 23.2.1 (a) of the Contract Agreement. 4. The electrical pole/Transformer shifting is yet to be completed by the Authority even as on date and following are the Chainages whether shifting is required to be carried out: No.of Transformers In addition to the above, following locations listed below where shifting of High Tension(HT) Towerlines are required to be carried out: No. of HT Towers Status All Material mobilized at site. Due to Lockdown Estimate Approved on 22.02.2020. Electrical Contractor engaged by EPC Contractor on 20.03.2020 for shifting works. Due to Lockdown work yet to be taken-up. Estimate yet to be approved. Estimate yet to be approved. | FALSE | real_data
Request for revisit of EOT determined/approved | EoT; Dispute Resolution | The EPC Contractor requested the Authority Engineer vide letter under ref (14) cited above to revisit the EOT already approved for 112 days by the Authority and consider 324 days as requested by the EPC Contractor. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20201119_SPK_AE_160_Contractor failure in achieving mile stone 1,2,&3.pdf | Six laning of Karaipcttai to Walajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - Contractor’s failure in achieving Project Mile Stone 1,2 & 3 applying of Damages vide Contract Article No. 10.3.2 & 10.3.3 - Reply made -Reg. | We are in receipt of your letter ref (26) cited above, our reply for the same is as follows: 1. The Contract Agreement for this Project was executed on 15.10.2018. The Appointed Date was fixed as 11.02.2019 and the same was communicated vide ref (2) cited above. 2. The Appointed date was declared as 11.02.2019 by the Authority taking into account the land handed over in terms of the available area without taking into consideration, the requirement of the Contract provision as per Clause 4.1.3 (a) of the EPC agreement which talks about the handing over of land only in terms of length of the Project Highway. The memorandum and appendix prepared in terms of area gave a deceptive / false picture about the availability of vacant access. Taking into consideration all the encumbrances, hindrances, utilities etc. the vacant access available on the appointed date declared was worked out and it was less than 90% and hence requested the Authority vide letter under ref (3) cited above for modification of the appointed date on which 90% of encumbrance free land would be made available to the Contractor. 3. The Authority in its response vide ref (4) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. 4. The EPC contractor vide ref (5) cited above in reply reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that the impacted length due to encroachments and encumbrances was 12.18 km which accounted to 33.77% of the project length. The workable length available to the contractor was only 66.23% of the project length. The EPC contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of encumbrance / encroachment / obstruction. | FALSE | real_data
Request for revisit of EOT determined/approved | EoT; Dispute Resolution | Taking into consideration all these encumbrances, hindrances etc. the vacant access available on the appointed date declared was worked out and it was less than 90% and hence the Authority was requested to modify the appointed date on which 90% encumbrance free highway would be made available to the EPC Contractor vide ref(5) cited above. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20210416_SPK_AE_067_EOT request with Delay analysis.pdf | Six laning of Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V -EOT recommendation by the Authority for a period of 112 days not agreeable to the EPC Contractor — Request for considering EOT as discussed during the Review Meetings- reg | We are writing to express our concerns regarding the EOT recommendation by the Authority for a period of 112 days, which is not agreeable to the EPC Contractor. We request that the EOT be considered as discussed during the Review Meetings. The project involves six laning of the Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km 71+015 to km 107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase-V. We have referenced several documents and meetings in support of our request, and we hope for a favorable consideration. | FALSE | real_data
Joint inspection | Appointed Date; Contractor's Obligations; Authority's Obligations | A joint inspection of the project highway took place along with utility shifting contractor on 13.06.2019. It was identified and concluded by the Authority during the inspection that shifting of electrical poles can be taken up only after removal of encumbrances/ obstructions, as land was not available. Utility shifting is also interlinked with removal of encumbrance/ encroachments. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/40_07082019_Rescheduling of Project Milestones – Request for Extension of time.pdf | Rescheduling of Project Milestones - Request for Extension of time - Reg. | The Contract agreement for the above mentioned project was executed on 15.10.2018. The appointed date was fixed as 11.02.2019 and the same was communicated vide ref (3) cited above. The Copy of the same is herewith enclosed as Annexure 1. The Authority in its response vide ref (5) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. The copy of the same is enclosed as Annexure 3. The EPC contractor vide ref (6) cited above reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that still the condition remained the same and dismantling/ removal of structures fouling was not started and shifting of Electric pole and power line also not started. The impacted length due to encroachments and encumbrances was 12.18 Km which accounted to 33.77% of the project highway. The workable length available to the Contractor based on the impacted length was 66.23% of the Project Highway length. The EPC Contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of removal of encumbrance / encroachment / obstruction. The copy of ref (7) is herewith enclosed as Annexure 4. It is almost six months since the declaration of appointed date, removal/ dismantling of structures/encroachments have not been started. Also, the work of shifting of power line and electric pole of LT line and HT lines crossings have not been started yet. The following are some of the key contractual dates and events since the inception of the project to till date: 1. Total length of the project highway: 36.076 Km 2. Date of Signing of agreement: 152018 3. Submission of Performance BG as per Clause 7.1.1 of the Contract Agreement: 262018 4. Target date for preparation of Memorandum as per Clause 8.2.1 of the Contract Agreement: 142018 5. Actual date of signing of Memorandum of land handing over: 112019 6. Declaration of appointed date by the Authority: 112019 7. ROW to be handed over as on appointed date as per Clause 8.2.2 & Annexure II: 35.468 Km | FALSE | real_data
Joint inspection | Contractor's Obligations | It was also emphasized that during the Joint inspection along with the representatives of Authority's Engineer from 14.10.2019 to 24.10.2019, only 62.52% of length of project highway was available and the same was also acknowledged by Authority Engineer (refer EPC Contractor letter vide ref (7) cited above). | synthetic_template_20250913 | Six laning of Karaipcttai to Walajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - Contractor’s failure in achieving Project Mile Stone 1,2 & 3 applying of Damages vide Contract Article No. 10.3.2 & 10.3.3 - Reply made -Reg. | We are in receipt of your letter ref (26) cited above, our reply for the same is as follows: 1. The Contract Agreement for this Project was executed on 15.10.2018. The Appointed Date was fixed as 11.02.2019 and the same was communicated vide ref (2) cited above. 2. The Appointed date was declared as 11.02.2019 by the Authority taking into account the land handed over in terms of the available area without taking into consideration, the requirement of the Contract provision as per Clause 4.1.3 (a) of the EPC agreement which talks about the handing over of land only in terms of length of the Project Highway. The memorandum and appendix prepared in terms of area gave a deceptive / false picture about the availability of vacant access. Taking into consideration all the encumbrances, hindrances, utilities etc. the vacant access available on the appointed date declared was worked out and it was less than 90% and hence requested the Authority vide letter under ref (3) cited above for modification of the appointed date on which 90% of encumbrance free land would be made available to the Contractor. 3. The Authority in its response vide ref (4) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. 4. The EPC contractor vide ref (5) cited above in reply reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that the impacted length due to encroachments and encumbrances was 12.18 km which accounted to 33.77% of the project length. The workable length available to the contractor was only 66.23% of the project length. The EPC contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of encumbrance / encroachment / obstruction. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Joint inspection | Contractor's Obligations | It was also emphasized that during the Joint inspection along with the representatives of Authority's Engineer from 14.10.2019 to 24.10.2019, only 62.52% of length of project highway was available and the same was also acknowledged by Authority Engineer (refer EPC Contractor letter vide ref (7) cited above). | synthetic_template_20250913 | Six laning of Karaipcttai to Walajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - Contractor’s failure in achieving Project Mile Stone 1,2 & 3 applying of Damages vide Contract Article No. 10.3.2 & 10.3.3 - Reply made -Reg. | We are in receipt of your letter ref (26) cited above, our reply for the same is as follows: 1. The Contract Agreement for this Project was executed on 15.10.2018. The Appointed Date was fixed as 11.02.2019 and the same was communicated vide ref (2) cited above. 2. The Appointed date was declared as 11.02.2019 by the Authority taking into account the land handed over in terms of the available area without taking into consideration, the requirement of the Contract provision as per Clause 4.1.3 (a) of the EPC agreement which talks about the handing over of land only in terms of length of the Project Highway. The memorandum and appendix prepared in terms of area gave a deceptive / false picture about the availability of vacant access. Taking into consideration all the encumbrances, hindrances, utilities etc. the vacant access available on the appointed date declared was worked out and it was less than 90% and hence requested the Authority vide letter under ref (3) cited above for modification of the appointed date on which 90% of encumbrance free land would be made available to the Contractor. 3. The Authority in its response vide ref (4) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. 4. The EPC contractor vide ref (5) cited above in reply reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that the impacted length due to encroachments and encumbrances was 12.18 km which accounted to 33.77% of the project length. The workable length available to the contractor was only 66.23% of the project length. The EPC contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of encumbrance / encroachment / obstruction. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Joint inspection | Authority's Obligations | It was also emphasized that during the Joint inspection along with the representatives of Authority's Engineer from 14.10.2019 to 24.10.2019, only 62.52% of length of project highway was available and the same was also acknowledged by Authority Engineer (refer EPC Contractor letter vide ref (7) cited above). | synthetic_template_20250913 | Six laning of Karaipcttai to Walajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - Contractor’s failure in achieving Project Mile Stone 1,2 & 3 applying of Damages vide Contract Article No. 10.3.2 & 10.3.3 - Reply made -Reg. | We are in receipt of your letter ref (26) cited above, our reply for the same is as follows: 1. The Contract Agreement for this Project was executed on 15.10.2018. The Appointed Date was fixed as 11.02.2019 and the same was communicated vide ref (2) cited above. 2. The Appointed date was declared as 11.02.2019 by the Authority taking into account the land handed over in terms of the available area without taking into consideration, the requirement of the Contract provision as per Clause 4.1.3 (a) of the EPC agreement which talks about the handing over of land only in terms of length of the Project Highway. The memorandum and appendix prepared in terms of area gave a deceptive / false picture about the availability of vacant access. Taking into consideration all the encumbrances, hindrances, utilities etc. the vacant access available on the appointed date declared was worked out and it was less than 90% and hence requested the Authority vide letter under ref (3) cited above for modification of the appointed date on which 90% of encumbrance free land would be made available to the Contractor. 3. The Authority in its response vide ref (4) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. 4. The EPC contractor vide ref (5) cited above in reply reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that the impacted length due to encroachments and encumbrances was 12.18 km which accounted to 33.77% of the project length. The workable length available to the contractor was only 66.23% of the project length. The EPC contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of encumbrance / encroachment / obstruction. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Joint inspection | Authority's Obligations | A joint inspection of the project highway took place along with utility shifting contractor on 13.06.2019. It was identified and concluded by the Authority during the inspection that shifting of electrical poles can be taken up only after removal of encumbrances/ obstructions, as land was not available. Utility shifting is also interlinked with removal of encumbrance/ encroachments. | synthetic_template_20250913 | Rescheduling of Project Milestones - Request for Extension of time - Reg. | Please note that The Contract agreement for the above mentioned project was executed on 15.10.2018. The appointed date was fixed as 11.02.2019 and the same was communicated vide ref (3) cited above. The Copy of the same is herewith enclosed as Annexure 1. The Authority in its response vide ref (5) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. The copy of the same is enclosed as Annexure 3. The EPC contractor vide ref (6) cited above reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that still the condition remained the same and dismantling/ removal of structures fouling was not started and shifting of Electric pole and power line also not started. The impacted length due to encroachments and encumbrances was 12.18 Km which accounted to 33.77% of the project highway. The workable length available to the Contractor based on the impacted length was 66.23% of the Project Highway length. The EPC Contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of removal of encumbrance / encroachment / obstruction. The copy of ref (7) is herewith enclosed as Annexure 4. It is almost six months since the declaration of appointed date, removal/ dismantling of structures/encroachments have not been started. Also, the work of shifting of power line and electric pole of LT line and HT lines crossings have not been started yet. The following are some of the key contractual dates and events since the inception of the project to till date: 1. Total length of the project highway: 36.076 Km 2. Date of Signing of agreement: 152018 3. Submission of Performance BG as per Clause 7.1.1 of the Contract Agreement: 262018 4. Target date for preparation of Memorandum as per Clause 8.2.1 of the Contract Agreement: 142018 5. Actual date of signing of Memorandum of land handing over: 112019 6. Declaration of appointed date by the Authority: 112019 7. ROW to be handed over as on appointed date as per Clause 8.2.2 & Annexure II: 35.468 Km | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Joint inspection | Appointed Date | A joint inspection of the project highway took place along with utility shifting contractor on 13.06.2019. It was identified and concluded by the Authority during the inspection that shifting of electrical poles can be taken up only after removal of encumbrances/ obstructions, as land was not available. Utility shifting is also interlinked with removal of encumbrance/ encroachments. | synthetic_template_20250913 | Rescheduling of Project Milestones - Request for Extension of time - Reg. | Please note that The Contract agreement for the above mentioned project was executed on 15.10.2018. The appointed date was fixed as 11.02.2019 and the same was communicated vide ref (3) cited above. The Copy of the same is herewith enclosed as Annexure 1. The Authority in its response vide ref (5) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. The copy of the same is enclosed as Annexure 3. The EPC contractor vide ref (6) cited above reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that still the condition remained the same and dismantling/ removal of structures fouling was not started and shifting of Electric pole and power line also not started. The impacted length due to encroachments and encumbrances was 12.18 Km which accounted to 33.77% of the project highway. The workable length available to the Contractor based on the impacted length was 66.23% of the Project Highway length. The EPC Contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of removal of encumbrance / encroachment / obstruction. The copy of ref (7) is herewith enclosed as Annexure 4. It is almost six months since the declaration of appointed date, removal/ dismantling of structures/encroachments have not been started. Also, the work of shifting of power line and electric pole of LT line and HT lines crossings have not been started yet. The following are some of the key contractual dates and events since the inception of the project to till date: 1. Total length of the project highway: 36.076 Km 2. Date of Signing of agreement: 152018 3. Submission of Performance BG as per Clause 7.1.1 of the Contract Agreement: 262018 4. Target date for preparation of Memorandum as per Clause 8.2.1 of the Contract Agreement: 142018 5. Actual date of signing of Memorandum of land handing over: 112019 6. Declaration of appointed date by the Authority: 112019 7. ROW to be handed over as on appointed date as per Clause 8.2.2 & Annexure II: 35.468 Km | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Joint inspection | Appointed Date | It was also emphasized that during the Joint inspection along with the representatives of Authority's Engineer from 14.10.2019 to 24.10.2019, only 62.52% of length of project highway was available and the same was also acknowledged by Authority Engineer (refer EPC Contractor letter vide ref (7) cited above). | synthetic_template_20250913 | Six laning of Karaipcttai to Walajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - Contractor’s failure in achieving Project Mile Stone 1,2 & 3 applying of Damages vide Contract Article No. 10.3.2 & 10.3.3 - Reply made -Reg. | We are in receipt of your letter ref (26) cited above, our reply for the same is as follows: 1. The Contract Agreement for this Project was executed on 15.10.2018. The Appointed Date was fixed as 11.02.2019 and the same was communicated vide ref (2) cited above. 2. The Appointed date was declared as 11.02.2019 by the Authority taking into account the land handed over in terms of the available area without taking into consideration, the requirement of the Contract provision as per Clause 4.1.3 (a) of the EPC agreement which talks about the handing over of land only in terms of length of the Project Highway. The memorandum and appendix prepared in terms of area gave a deceptive / false picture about the availability of vacant access. Taking into consideration all the encumbrances, hindrances, utilities etc. the vacant access available on the appointed date declared was worked out and it was less than 90% and hence requested the Authority vide letter under ref (3) cited above for modification of the appointed date on which 90% of encumbrance free land would be made available to the Contractor. 3. The Authority in its response vide ref (4) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. 4. The EPC contractor vide ref (5) cited above in reply reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that the impacted length due to encroachments and encumbrances was 12.18 km which accounted to 33.77% of the project length. The workable length available to the contractor was only 66.23% of the project length. The EPC contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of encumbrance / encroachment / obstruction. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Demands by local villagers for additional structures/service road/utility ducts | Change of Scope; EoT; Dispute Resolution; Payments | This is to bring to your kind notice that the construction of drain works has been stopped from Km 106+190 to Km 106+650 (RHS) by the local people from Thenkadapanthangal village (photographs enclosed) for want of increase in size of drain width to 3.0 m in lieu of 1.5m. We kindly request you to take up this issue with the District Administration and provide necessary support in resolving the issue as per Clause 4.1.6 (e) of the Contract Agreement. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/2023103_SPK_PD_067_Disruption of works by local people of Thenkadapanthangal Village for demand in “Increase in Drain width to 3.0m instead of 1.5m as per CA.pdf | Disruption of works by local people of Thenkadapanthangal Village for demand in “Increase in Drain width to 3.0m instead of 1.5m as per CA”— Works hampered from Km.106+190 to Km 106+650 (RHS) - Reg. | 1. This is to bring to your kind notice that the construction of drain works has been stopped from Km.106+190 to Km.106+650(RHS) by the local people from Thenkadapanthangal village (Photographs enclosed) for want of increase in size of drain width to 3.0m in lieu of 1.5m. The locals also informed that they will permit construction works only if the width of drain is increased to 3.0 m for the above mentioned length of 460m. 2. The reason stated by the villagers is that the adjacent water course coming from nearby source that flows across Minor Bridge at Km.106+677, will overflow towards the village side and that overflowing water should be allowed to flow in the drain otherwise the water will enter into their houses. 3. This is for information that already a length of 160m of storm water drain with width of 2.5m in lieu of 1.5m from Km.98+214 to Km.98+374 (160m) on LHS for diversion of the storm water into the PWD canal has been constructed for which the additional amount incurred up to Rs.28,49,564/- by the EPC Contractor is still pending for reimbursement with the Authority (Refer our letter No. SPK/KW/SAIC/NH-48/2022/185 dated 19.12.2022) 4. We kindly request you to take up this issue with the District Administration and provide necessary support in resolving the issue as per Clause 4.1.6 (e) of the Contract Agreement. | FALSE | real_data
Demands by local villagers for additional structures/service road/utility ducts | EoT | This is to bring to your kind notice that the construction of drain works has been stopped from Km 106+190 to Km 106+650 (RHS) by the local people from Thenkadapanthangal village (photographs enclosed) for want of increase in size of drain width to 3.0 m in lieu of 1.5m. We kindly request you to take up this issue with the District Administration and provide necessary support in resolving the issue as per Clause 4.1.6 (e) of the Contract Agreement. | synthetic_template_20250913 | Disruption of works by local people of Thenkadapanthangal Village for demand in “Increase in Drain width to 3.0m instead of 1.5m as per CA”— Works hampered from Km.106+190 to Km 106+650 (RHS) - Reg. | Please note that 1. This is to bring to your kind notice that the construction of drain works has been stopped from Km.106+190 to Km.106+650(RHS) by the local people from Thenkadapanthangal village (Photographs enclosed) for want of increase in size of drain width to 3.0m in lieu of 1.5m. The locals also informed that they will permit construction works only if the width of drain is increased to 3.0 m for the above mentioned length of 460m. 2. The reason stated by the villagers is that the adjacent water course coming from nearby source that flows across Minor Bridge at Km.106+677, will overflow towards the village side and that overflowing water should be allowed to flow in the drain otherwise the water will enter into their houses. 3. This is for information that already a length of 160m of storm water drain with width of 2.5m in lieu of 1.5m from Km.98+214 to Km.98+374 (160m) on LHS for diversion of the storm water into the PWD canal has been constructed for which the additional amount incurred up to Rs.28,49,564/- by the EPC Contractor is still pending for reimbursement with the Authority (Refer our letter No. SPK/KW/SAIC/NH-48/2022/185 dated 19.12.2022) 4. We kindly request you to take up this issue with the District Administration and provide necessary support in resolving the issue as per Clause 4.1.6 (e) of the Contract Agreement. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Demands by local villagers for additional structures/service road/utility ducts | EoT | This is to bring to your kind notice that the construction of drain works has been stopped from Km 106+190 to Km 106+650 (RHS) by the local people from Thenkadapanthangal village (photographs enclosed) for want of increase in size of drain width to 3.0 m in lieu of 1.5m. We kindly request you to take up this issue with the District Administration and provide necessary support in resolving the issue as per Clause 4.1.6 (e) of the Contract Agreement. | synthetic_template_20250913 | Disruption of works by local people of Thenkadapanthangal Village for demand in “Increase in Drain width to 3.0m instead of 1.5m as per CA”— Works hampered from Km.106+190 to Km 106+650 (RHS) - Reg. | We would like to inform you that 1. This is to bring to your kind notice that the construction of drain works has been stopped from Km.106+190 to Km.106+650(RHS) by the local people from Thenkadapanthangal village (Photographs enclosed) for want of increase in size of drain width to 3.0m in lieu of 1.5m. The locals also informed that they will permit construction works only if the width of drain is increased to 3.0 m for the above mentioned length of 460m. 2. The reason stated by the villagers is that the adjacent water course coming from nearby source that flows across Minor Bridge at Km.106+677, will overflow towards the village side and that overflowing water should be allowed to flow in the drain otherwise the water will enter into their houses. 3. This is for information that already a length of 160m of storm water drain with width of 2.5m in lieu of 1.5m from Km.98+214 to Km.98+374 (160m) on LHS for diversion of the storm water into the PWD canal has been constructed for which the additional amount incurred up to Rs.28,49,564/- by the EPC Contractor is still pending for reimbursement with the Authority (Refer our letter No. SPK/KW/SAIC/NH-48/2022/185 dated 19.12.2022) 4. We kindly request you to take up this issue with the District Administration and provide necessary support in resolving the issue as per Clause 4.1.6 (e) of the Contract Agreement. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Demands by local villagers for additional structures/service road/utility ducts | Change of Scope | This is to bring to your kind notice that the construction of drain works has been stopped from Km 106+190 to Km 106+650 (RHS) by the local people from Thenkadapanthangal village (photographs enclosed) for want of increase in size of drain width to 3.0 m in lieu of 1.5m. We kindly request you to take up this issue with the District Administration and provide necessary support in resolving the issue as per Clause 4.1.6 (e) of the Contract Agreement. | synthetic_template_20250913 | Disruption of works by local people of Thenkadapanthangal Village for demand in “Increase in Drain width to 3.0m instead of 1.5m as per CA”— Works hampered from Km.106+190 to Km 106+650 (RHS) - Reg. | 1. This is to bring to your kind notice that the construction of drain works has been stopped from Km.106+190 to Km.106+650(RHS) by the local people from Thenkadapanthangal village (Photographs enclosed) for want of increase in size of drain width to 3.0m in lieu of 1.5m. The locals also informed that they will permit construction works only if the width of drain is increased to 3.0 m for the above mentioned length of 460m. 2. The reason stated by the villagers is that the adjacent water course coming from nearby source that flows across Minor Bridge at Km.106+677, will overflow towards the village side and that overflowing water should be allowed to flow in the drain otherwise the water will enter into their houses. 3. This is for information that already a length of 160m of storm water drain with width of 2.5m in lieu of 1.5m from Km.98+214 to Km.98+374 (160m) on LHS for diversion of the storm water into the PWD canal has been constructed for which the additional amount incurred up to Rs.28,49,564/- by the EPC Contractor is still pending for reimbursement with the Authority (Refer our letter No. SPK/KW/SAIC/NH-48/2022/185 dated 19.12.2022) 4. We kindly request you to take up this issue with the District Administration and provide necessary support in resolving the issue as per Clause 4.1.6 (e) of the Contract Agreement. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Demands by local villagers for additional structures/service road/utility ducts | Change of Scope | This is to bring to your kind notice that the construction of drain works has been stopped from Km 106+190 to Km 106+650 (RHS) by the local people from Thenkadapanthangal village (photographs enclosed) for want of increase in size of drain width to 3.0 m in lieu of 1.5m. We kindly request you to take up this issue with the District Administration and provide necessary support in resolving the issue as per Clause 4.1.6 (e) of the Contract Agreement. | synthetic_template_20250913 | Disruption of works by local people of Thenkadapanthangal Village for demand in “Increase in Drain width to 3.0m instead of 1.5m as per CA”— Works hampered from Km.106+190 to Km 106+650 (RHS) - Reg. | 1. This is to bring to your kind notice that the construction of drain works has been stopped from Km.106+190 to Km.106+650(RHS) by the local people from Thenkadapanthangal village (Photographs enclosed) for want of increase in size of drain width to 3.0m in lieu of 1.5m. The locals also informed that they will permit construction works only if the width of drain is increased to 3.0 m for the above mentioned length of 460m. 2. The reason stated by the villagers is that the adjacent water course coming from nearby source that flows across Minor Bridge at Km.106+677, will overflow towards the village side and that overflowing water should be allowed to flow in the drain otherwise the water will enter into their houses. 3. This is for information that already a length of 160m of storm water drain with width of 2.5m in lieu of 1.5m from Km.98+214 to Km.98+374 (160m) on LHS for diversion of the storm water into the PWD canal has been constructed for which the additional amount incurred up to Rs.28,49,564/- by the EPC Contractor is still pending for reimbursement with the Authority (Refer our letter No. SPK/KW/SAIC/NH-48/2022/185 dated 19.12.2022) 4. We kindly request you to take up this issue with the District Administration and provide necessary support in resolving the issue as per Clause 4.1.6 (e) of the Contract Agreement. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Demands by local villagers for additional structures/service road/utility ducts | Payments | This is to bring to your kind notice that the construction of drain works has been stopped from Km 106+190 to Km 106+650 (RHS) by the local people from Thenkadapanthangal village (photographs enclosed) for want of increase in size of drain width to 3.0 m in lieu of 1.5m. We kindly request you to take up this issue with the District Administration and provide necessary support in resolving the issue as per Clause 4.1.6 (e) of the Contract Agreement. | synthetic_template_20250913 | Disruption of works by local people of Thenkadapanthangal Village for demand in “Increase in Drain width to 3.0m instead of 1.5m as per CA”— Works hampered from Km.106+190 to Km 106+650 (RHS) - Reg. | This is to notify you that 1. This is to bring to your kind notice that the construction of drain works has been stopped from Km.106+190 to Km.106+650(RHS) by the local people from Thenkadapanthangal village (Photographs enclosed) for want of increase in size of drain width to 3.0m in lieu of 1.5m. The locals also informed that they will permit construction works only if the width of drain is increased to 3.0 m for the above mentioned length of 460m. 2. The reason stated by the villagers is that the adjacent water course coming from nearby source that flows across Minor Bridge at Km.106+677, will overflow towards the village side and that overflowing water should be allowed to flow in the drain otherwise the water will enter into their houses. 3. This is for information that already a length of 160m of storm water drain with width of 2.5m in lieu of 1.5m from Km.98+214 to Km.98+374 (160m) on LHS for diversion of the storm water into the PWD canal has been constructed for which the additional amount incurred up to Rs.28,49,564/- by the EPC Contractor is still pending for reimbursement with the Authority (Refer our letter No. SPK/KW/SAIC/NH-48/2022/185 dated 19.12.2022) 4. We kindly request you to take up this issue with the District Administration and provide necessary support in resolving the issue as per Clause 4.1.6 (e) of the Contract Agreement. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Demands by local villagers for additional structures/service road/utility ducts | Payments | This is to bring to your kind notice that the construction of drain works has been stopped from Km 106+190 to Km 106+650 (RHS) by the local people from Thenkadapanthangal village (photographs enclosed) for want of increase in size of drain width to 3.0 m in lieu of 1.5m. We kindly request you to take up this issue with the District Administration and provide necessary support in resolving the issue as per Clause 4.1.6 (e) of the Contract Agreement. | synthetic_template_20250913 | Disruption of works by local people of Thenkadapanthangal Village for demand in “Increase in Drain width to 3.0m instead of 1.5m as per CA”— Works hampered from Km.106+190 to Km 106+650 (RHS) - Reg. | 1. This is to bring to your kind notice that the construction of drain works has been stopped from Km.106+190 to Km.106+650(RHS) by the local people from Thenkadapanthangal village (Photographs enclosed) for want of increase in size of drain width to 3.0m in lieu of 1.5m. The locals also informed that they will permit construction works only if the width of drain is increased to 3.0 m for the above mentioned length of 460m. 2. The reason stated by the villagers is that the adjacent water course coming from nearby source that flows across Minor Bridge at Km.106+677, will overflow towards the village side and that overflowing water should be allowed to flow in the drain otherwise the water will enter into their houses. 3. This is for information that already a length of 160m of storm water drain with width of 2.5m in lieu of 1.5m from Km.98+214 to Km.98+374 (160m) on LHS for diversion of the storm water into the PWD canal has been constructed for which the additional amount incurred up to Rs.28,49,564/- by the EPC Contractor is still pending for reimbursement with the Authority (Refer our letter No. SPK/KW/SAIC/NH-48/2022/185 dated 19.12.2022) 4. We kindly request you to take up this issue with the District Administration and provide necessary support in resolving the issue as per Clause 4.1.6 (e) of the Contract Agreement. We await your further instructions. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Demands by local villagers for additional structures/service road/utility ducts | Dispute Resolution | This is to bring to your kind notice that the construction of drain works has been stopped from Km 106+190 to Km 106+650 (RHS) by the local people from Thenkadapanthangal village (photographs enclosed) for want of increase in size of drain width to 3.0 m in lieu of 1.5m. We kindly request you to take up this issue with the District Administration and provide necessary support in resolving the issue as per Clause 4.1.6 (e) of the Contract Agreement. | synthetic_template_20250913 | Disruption of works by local people of Thenkadapanthangal Village for demand in “Increase in Drain width to 3.0m instead of 1.5m as per CA”— Works hampered from Km.106+190 to Km 106+650 (RHS) - Reg. | We would like to inform you that 1. This is to bring to your kind notice that the construction of drain works has been stopped from Km.106+190 to Km.106+650(RHS) by the local people from Thenkadapanthangal village (Photographs enclosed) for want of increase in size of drain width to 3.0m in lieu of 1.5m. The locals also informed that they will permit construction works only if the width of drain is increased to 3.0 m for the above mentioned length of 460m. 2. The reason stated by the villagers is that the adjacent water course coming from nearby source that flows across Minor Bridge at Km.106+677, will overflow towards the village side and that overflowing water should be allowed to flow in the drain otherwise the water will enter into their houses. 3. This is for information that already a length of 160m of storm water drain with width of 2.5m in lieu of 1.5m from Km.98+214 to Km.98+374 (160m) on LHS for diversion of the storm water into the PWD canal has been constructed for which the additional amount incurred up to Rs.28,49,564/- by the EPC Contractor is still pending for reimbursement with the Authority (Refer our letter No. SPK/KW/SAIC/NH-48/2022/185 dated 19.12.2022) 4. We kindly request you to take up this issue with the District Administration and provide necessary support in resolving the issue as per Clause 4.1.6 (e) of the Contract Agreement. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Progress Review | EoT; Payments; Others | It has been directed by the member (Technical) during project review meeting on 04.03.2020 to demonstrate substantial progress in the months of March and April. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20200402_SPK_AE_054_Works standstill due to of outbreak of Corona virus.pdf | Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km.71+015 (Existing Km 71/000) to Km 107+091 (Existing Km 107/068) on EPC Mode in the state of Tamil Nadu under NHDP Phase-V - Progress review by Member (Technical) on 04.03.2020 - Works standstill due to of outbreak of Corona virus — Reg. | Dear Sir, It has been directed by the Member (Technical) during project review meeting on 04.03.2020 to demonstrate substantial progress in the months of March and April. A target of 2.5% per month was fixed. The EPC Contractor worked on continuous basis in order to achieve the targets as directed by the Member (Technical) during the review meeting. Accordingly, SR works for commencement of structure at Km.85+874 completed and diversion of main carriage way traffic into the service road was also planned. But unfortunately due to outbreak of Corona Virus (COVID - 19), the entire construction activities were halted since 22.03.2020. The district administration with the aid of police personnel curbed the movements of our trucks and other construction equipments in order to prevent the spread of this novel virus. Further, on 17th March 2020, the Government of India issued an advisory urging to all residing in India to take social distancing, quarantine, etc., measures as a strategy for implementation till 31st Mar 2020. Due to this serious outbreak of the virus, the labour force and technical manpower deployed in our project site got panicked and many of them have left the project site to their native places fearing getting infected with the said virus. Also, several cases are reported across the country, where people who are suspected to have come in contact with the virus, escaped from the quarantines and hospitals and therefore under such situation, the labourers/construction machinery operators deployed at our project site are finding it difficult to move out of their base camp and report to the site for duty. In continuation to this advisory, Govt. of India declared complete lockdown from 24th March 2020 and necessary orders under Disaster Management Act 2005 have been passed by Ministry of Home Affairs. We also notified the above as Force Majeure event in accordance with the provision of Article 21.2(a), 21.5.2 of the EPC Agreement vide ref (4) cited above. Hence, we would like to submit that we shall not be in a position to achieve rate of progress as discussed during the meeting held on 04.03.2020 due to extraordinary kind of situation prevailing in the country as detailed above. We shall make all out efforts in enhancing the progress of works after reviewing the ground situation post lifting of lockdown on 15.04.2020. | FALSE | real_data
Progress Review | EoT; Payments; Others | Further, a meeting took place at NHAI HQ on 04.03.2020 and the status of the project was reviewed by Member (Technical) wherein the issues faced by the EPC Contractor relating to non-handing over of ROW, delay in shifting of utilities etc. were briefed. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20201119_SPK_AE_160_Contractor failure in achieving mile stone 1,2,&3.pdf | Six laning of Karaipcttai to Walajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - Contractor’s failure in achieving Project Mile Stone 1,2 & 3 applying of Damages vide Contract Article No. 10.3.2 & 10.3.3 - Reply made -Reg. | We are in receipt of your letter ref (26) cited above, our reply for the same is as follows: 1. The Contract Agreement for this Project was executed on 15.10.2018. The Appointed Date was fixed as 11.02.2019 and the same was communicated vide ref (2) cited above. 2. The Appointed date was declared as 11.02.2019 by the Authority taking into account the land handed over in terms of the available area without taking into consideration, the requirement of the Contract provision as per Clause 4.1.3 (a) of the EPC agreement which talks about the handing over of land only in terms of length of the Project Highway. The memorandum and appendix prepared in terms of area gave a deceptive / false picture about the availability of vacant access. Taking into consideration all the encumbrances, hindrances, utilities etc. the vacant access available on the appointed date declared was worked out and it was less than 90% and hence requested the Authority vide letter under ref (3) cited above for modification of the appointed date on which 90% of encumbrance free land would be made available to the Contractor. 3. The Authority in its response vide ref (4) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. 4. The EPC contractor vide ref (5) cited above in reply reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that the impacted length due to encroachments and encumbrances was 12.18 km which accounted to 33.77% of the project length. The workable length available to the contractor was only 66.23% of the project length. The EPC contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of encumbrance / encroachment / obstruction. | FALSE | real_data
Progress Review | EoT; Payments; Others | Also during the recent site inspection and meeting by the NHAI, GM(T), TN on 18/02/2021 along with the Project Director (PIU) Kancheepuram, Manager (Tech), Team Leader of Authority Engineer, the EPC Contractor was informed to submit a "Comprehensive EOT proposal" for review and recommendation to the Authority Engineer. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20210416_SPK_AE_067_EOT request with Delay analysis.pdf | Six laning of Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V -EOT recommendation by the Authority for a period of 112 days not agreeable to the EPC Contractor — Request for considering EOT as discussed during the Review Meetings- reg | We are writing to express our concerns regarding the EOT recommendation by the Authority for a period of 112 days, which is not agreeable to the EPC Contractor. We request that the EOT be considered as discussed during the Review Meetings. The project involves six laning of the Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km 71+015 to km 107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase-V. We have referenced several documents and meetings in support of our request, and we hope for a favorable consideration. | FALSE | real_data
Progress Review | EoT; Payments; Others | Site progress review meeting | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/082_24082019_Project works review meeting.pdf | Six Lanning of Karaipettai to Walajhapet from km 71.015 to 107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode. —Project works review meeting - Reg. | In continuation to our earlier site progress review meeting of Karaipettai to Walajapet Package Works, it is planned to have a tripartite meeting which includes the Authority, Authority Engineer and the Contractor on 27th Aug 2019 around 11.00 AM in our office. Hence you have been requested to participate. | FALSE | real_data
Progress Review | EoT; Payments; Others | With respect to the above said reference please find enclosed herewith the minutes of meeting MOM -2 held on 27.08.2019. The venue and date for the next meeting will be intimated in due course of time. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/089_31082019_Minutes of Monthly Progress review meeting.pdf | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to 107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Minutes of Monthly Progress review meeting -Reg. | With respect to the above said reference please find enclosed herewith the minutes of meeting MoM -2 held on 27.08.2019. The venue and date for the next meeting will be intimated in due course of time. This is for your information and record. | FALSE | real_data
Progress Review | EoT; Payments; Others | With respect to the above said reference please find enclosed herewith the minutes of meeting MOM -3 held on 25.09.2019. The venue and date for the next meeting will be intimated in due course of time. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/119_01102019_Minutes of Monthly Progress review meeting Mom -3.pdf | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to 107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Minutes of Monthly Progress review meeting Mom -3 -Reg. | With respect to the above said reference please find enclosed herewith the minutes of meeting MoM -3 held on 25.09.2019. The venue and date for the next meeting will be intimated in due course of time. This is for your information and record. Assuring our best services at all times. | FALSE | real_data
Progress Review | EoT; Payments; Others | With respect to the above said reference please find enclosed herewith the Minutes of Meeting Numbered as MoM-4 held on 30.10.2019. The venue and date for the next meeting are scheduled on 27.11.2019 at Consultants office around 11.00 A.M in Kancheepuram. All the concerned are requested to attend with necessary documents. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/162_11112019_Minutes of meeting_MOM 4.pdf | Consultancy services for Authority's Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Minutes of Monthly Progress review meeting Mom-4 -Reg. | With respect to the above said reference please find enclosed herewith the Minutes of Meeting Numbered as MoM-4 held on 30.10.2019. The venue and date for the next meeting are scheduled on 27.11.2019 at Consultants office around 11.00 A.M in Kancheepuram. All the concerned are requested to attend with necessary documents. This is for your information and record. Assuring our best services at all times. | FALSE | real_data
Progress Review | EoT; Payments; Others | Review meeting | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/1237_18062019_Meeting at Chennai RO.pdf | NHAI — PIU, Kancheepuram - Six laning of Karaipettai - Walajahpet Section of NH-48 (Old NH-4) from Km 71/015 to Km 107/091 (36.076 Km) in the State of Tamil Nadu under NHDP Phase V - Discussion - reg | In continuation to this office letter cited above, it has been proposed to conduct review meeting on 21.06.2019 at 03:00 PM at this office on the project stretch of Six laning of Karaipettai — Walajahpet Section of NH-48 (Old NH-4) from Km 71/015 to Km 107/091 (36.076 Km). Hence it is requested to make it convenient to attend the above said discussion. | FALSE | real_data
Progress Review | EoT; Payments; Others | With respect to the above said reference please find enclosed herewith the Meeting of Meeting Numbered as MoM-5 held on 29.11.2019. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/20191205_AE_NHAI_188_Minutes of Monthly Progress review meeting Mom-5.pdf | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to 107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Minutes of Monthly Progress review meeting Mom-5 -Reg. | With respect to the above said reference please find enclosed herewith the Minutes of Meeting Numbered as MoM-S held on 29.11.2019. The next meeting will be likely on 27.12.2019 at the Consultants office around 11.00 A.M in Kancheepuram. All the concerned are requested to attend with necessary documents. This is for your information and record. Assuring our best services at all times. | FALSE | real_data
Progress Review | EoT; Payments; Others | DBM is completed in 13 Km.There are other reaches where DBM can be done.The Contractor was directed to take up the DBM work in such reaches. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20201213_RO_PD_3721_Inspection Report by RO on 22.12.2020.pdf | NHAI Chennai Region - PIU Kancheepuram - Inspection of Maduravoyal - Wallajahpet / Ranipet section of NH-4 by RO-Chennai on 22.12.2020 - Inspection Report forwarded - Reg | Enclosed please find herewith the Report on the Inspection of the project highway carried out by the undersigned on 22.12.2020 for necessary action and to submit the Action Taken Report. | FALSE | real_data
Progress Review | EoT; Payments; Others | Please find enclosed herewith the minutes of meeting numbered as MOM-09 held on 26.02.2021 | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210302_AE_SPK_569-Minutes of Monthly Progress review meeting Mom – 09.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode. - Minutes of Monthly Progress review meeting Mom — 09 — Reg. | With respect to the above said reference please find enclosed herewith the Minutes of Meeting Numbered as MoM - 09 held on 26.02.2021 The next meeting will be likely on 19 March 2021 at Team Leader office around 11.00 A.M in Kancheepuram. All the concerned are requested to attend with necessary documents. This is for your information and record. Assuring our best services at all times. | FALSE | real_data
Delay due to Change of Scope works | EoT; Payments; Dispute Resolution; Change of Scope | Non finalisation of COS proposal by frequently revising the scope has an adverse impact on the progress of works at the approaches of the underpass as we are not able to commence even drain and service road works which has direct impact on the physical and financial progress hampering the milestone achievement. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20201119_SPK_AE_160_Contractor failure in achieving mile stone 1,2,&3.pdf | Six laning of Karaipcttai to Walajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - Contractor’s failure in achieving Project Mile Stone 1,2 & 3 applying of Damages vide Contract Article No. 10.3.2 & 10.3.3 - Reply made -Reg. | We are in receipt of your letter ref (26) cited above, our reply for the same is as follows: 1. The Contract Agreement for this Project was executed on 15.10.2018. The Appointed Date was fixed as 11.02.2019 and the same was communicated vide ref (2) cited above. 2. The Appointed date was declared as 11.02.2019 by the Authority taking into account the land handed over in terms of the available area without taking into consideration, the requirement of the Contract provision as per Clause 4.1.3 (a) of the EPC agreement which talks about the handing over of land only in terms of length of the Project Highway. The memorandum and appendix prepared in terms of area gave a deceptive / false picture about the availability of vacant access. Taking into consideration all the encumbrances, hindrances, utilities etc. the vacant access available on the appointed date declared was worked out and it was less than 90% and hence requested the Authority vide letter under ref (3) cited above for modification of the appointed date on which 90% of encumbrance free land would be made available to the Contractor. 3. The Authority in its response vide ref (4) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. 4. The EPC contractor vide ref (5) cited above in reply reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that the impacted length due to encroachments and encumbrances was 12.18 km which accounted to 33.77% of the project length. The workable length available to the contractor was only 66.23% of the project length. The EPC contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of encumbrance / encroachment / obstruction. | FALSE | real_data
Delay due to Change of Scope works | EoT; Payments; Dispute Resolution; Change of Scope | The EPC Contractor has substantially completed majority of the road works at grade sections where unencumbered land has been provided by the Authority and presently finding it difficult to open up further stretches due to a) non availability of unencumbered land, b) temporary suspension of works due to COS proposals warranted by the Authority pursuant to sub clause 13.1.1 of the Contract Agreement. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20210416_SPK_AE_067_EOT request with Delay analysis.pdf | Six laning of Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V -EOT recommendation by the Authority for a period of 112 days not agreeable to the EPC Contractor — Request for considering EOT as discussed during the Review Meetings- reg | We are writing to express our concerns regarding the EOT recommendation by the Authority for a period of 112 days, which is not agreeable to the EPC Contractor. We request that the EOT be considered as discussed during the Review Meetings. The project involves six laning of the Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km 71+015 to km 107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase-V. We have referenced several documents and meetings in support of our request, and we hope for a favorable consideration. | FALSE | real_data
Delay due to Change of Scope works | EoT | The EPC Contractor has substantially completed majority of the road works at grade sections where unencumbered land has been provided by the Authority and presently finding it difficult to open up further stretches due to a) non availability of unencumbered land, b) temporary suspension of works due to COS proposals warranted by the Authority pursuant to sub clause 13.1.1 of the Contract Agreement. | synthetic_template_20250913 | Six laning of Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V -EOT recommendation by the Authority for a period of 112 days not agreeable to the EPC Contractor — Request for considering EOT as discussed during the Review Meetings- reg | We are writing to express our concerns regarding the EOT recommendation by the Authority for a period of 112 days, which is not agreeable to the EPC Contractor. We request that the EOT be considered as discussed during the Review Meetings. The project involves six laning of the Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km 71+015 to km 107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase-V. We have referenced several documents and meetings in support of our request, and we hope for a favorable consideration. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Delay due to Change of Scope works | EoT | The EPC Contractor has substantially completed majority of the road works at grade sections where unencumbered land has been provided by the Authority and presently finding it difficult to open up further stretches due to a) non availability of unencumbered land, b) temporary suspension of works due to COS proposals warranted by the Authority pursuant to sub clause 13.1.1 of the Contract Agreement. | synthetic_template_20250913 | Six laning of Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V -EOT recommendation by the Authority for a period of 112 days not agreeable to the EPC Contractor — Request for considering EOT as discussed during the Review Meetings- reg | We hereby confirm that We are writing to express our concerns regarding the EOT recommendation by the Authority for a period of 112 days, which is not agreeable to the EPC Contractor. We request that the EOT be considered as discussed during the Review Meetings. The project involves six laning of the Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km 71+015 to km 107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase-V. We have referenced several documents and meetings in support of our request, and we hope for a favorable consideration. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Delay due to Change of Scope works | Dispute Resolution | Non finalisation of COS proposal by frequently revising the scope has an adverse impact on the progress of works at the approaches of the underpass as we are not able to commence even drain and service road works which has direct impact on the physical and financial progress hampering the milestone achievement. | synthetic_template_20250913 | Six laning of Karaipcttai to Walajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - Contractor’s failure in achieving Project Mile Stone 1,2 & 3 applying of Damages vide Contract Article No. 10.3.2 & 10.3.3 - Reply made -Reg. | We are in receipt of your letter ref (26) cited above, our reply for the same is as follows: 1. The Contract Agreement for this Project was executed on 15.10.2018. The Appointed Date was fixed as 11.02.2019 and the same was communicated vide ref (2) cited above. 2. The Appointed date was declared as 11.02.2019 by the Authority taking into account the land handed over in terms of the available area without taking into consideration, the requirement of the Contract provision as per Clause 4.1.3 (a) of the EPC agreement which talks about the handing over of land only in terms of length of the Project Highway. The memorandum and appendix prepared in terms of area gave a deceptive / false picture about the availability of vacant access. Taking into consideration all the encumbrances, hindrances, utilities etc. the vacant access available on the appointed date declared was worked out and it was less than 90% and hence requested the Authority vide letter under ref (3) cited above for modification of the appointed date on which 90% of encumbrance free land would be made available to the Contractor. 3. The Authority in its response vide ref (4) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. 4. The EPC contractor vide ref (5) cited above in reply reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that the impacted length due to encroachments and encumbrances was 12.18 km which accounted to 33.77% of the project length. The workable length available to the contractor was only 66.23% of the project length. The EPC contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of encumbrance / encroachment / obstruction. We await your further instructions. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Delay due to Change of Scope works | Payments | Non finalisation of COS proposal by frequently revising the scope has an adverse impact on the progress of works at the approaches of the underpass as we are not able to commence even drain and service road works which has direct impact on the physical and financial progress hampering the milestone achievement. | synthetic_template_20250913 | Six laning of Karaipcttai to Walajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - Contractor’s failure in achieving Project Mile Stone 1,2 & 3 applying of Damages vide Contract Article No. 10.3.2 & 10.3.3 - Reply made -Reg. | We would like to inform you that We are in receipt of your letter ref (26) cited above, our reply for the same is as follows: 1. The Contract Agreement for this Project was executed on 15.10.2018. The Appointed Date was fixed as 11.02.2019 and the same was communicated vide ref (2) cited above. 2. The Appointed date was declared as 11.02.2019 by the Authority taking into account the land handed over in terms of the available area without taking into consideration, the requirement of the Contract provision as per Clause 4.1.3 (a) of the EPC agreement which talks about the handing over of land only in terms of length of the Project Highway. The memorandum and appendix prepared in terms of area gave a deceptive / false picture about the availability of vacant access. Taking into consideration all the encumbrances, hindrances, utilities etc. the vacant access available on the appointed date declared was worked out and it was less than 90% and hence requested the Authority vide letter under ref (3) cited above for modification of the appointed date on which 90% of encumbrance free land would be made available to the Contractor. 3. The Authority in its response vide ref (4) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. 4. The EPC contractor vide ref (5) cited above in reply reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that the impacted length due to encroachments and encumbrances was 12.18 km which accounted to 33.77% of the project length. The workable length available to the contractor was only 66.23% of the project length. The EPC contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of encumbrance / encroachment / obstruction. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Delay due to Change of Scope works | Payments | The EPC Contractor has substantially completed majority of the road works at grade sections where unencumbered land has been provided by the Authority and presently finding it difficult to open up further stretches due to non availability of unencumbered land, temporary suspension of works due to COS proposals warranted by the Authority pursuant to clause 13.1.1 of the Contract Agreement. | synthetic_template_20250913 | Extension of Time and Rescheduling of Project Milestones - EOT granted for 112 days not acceptable to the EPC contractor - Request for revisiting the EOT recommended - Reminder sent - Reg. | 1. This is with respect to the Extension of Time(EOT} approved by the Authority for. a period of 112 days for Project Milestone-I without effecting changes in Scheduled Project Completion Period vide ref (3) cited above.The EPC Contrator disagrees and does not accept the grant of EOT approval for 112 days, the reasons for disgreeement of this approval are elaborated in our submission to the Authority Engineer vide ref (4) cited above. 2. The EPC contractor requested the Authority/NHAI to revisit the EOT determined/approved and communicate 324 days as interim Extension of time vide ref (5) cited above but, we are yet to receive response in this regard. Copy of the same is herewith enclosed as Annexure 1. 3. The Authority is yet to fulfil the obligations relating to handing over of ROW as per Sub Clause 8.2 of the Contract Agreement. Copy of the newspaper publication regarding LA status / notification for acquiring land for the Project Highway (Kanchipuram District} is herewith enclosed as Annexure 2. By not fulfilling the obligations as per the provisions of the Contract Agreement, the Authority committed a material default pursuant to Sub clause 23.2.1 (a) of the Contract Agreement. 4. The electrical pole/Transformer shifting is yet to be completed by the Authority even as on date and following are the Chainages whether shifting is required to be carried out: No.of Transformers In addition to the above, following locations listed below where shifting of High Tension(HT) Towerlines are required to be carried out: No. of HT Towers Status All Material mobilized at site. Due to Lockdown Estimate Approved on 22.02.2020. Electrical Contractor engaged by EPC Contractor on 20.03.2020 for shifting works. Due to Lockdown work yet to be taken-up. Estimate yet to be approved. Estimate yet to be approved. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Delay due to Change of Scope works | Change of Scope | The EPC Contractor has substantially completed majority of the road works at grade sections where unencumbered land has been provided by the Authority and presently finding it difficult to open up further stretches due to a) non availability of unencumbered land, b) temporary suspension of works due to COS proposals warranted by the Authority pursuant to sub clause 13.1.1 of the Contract Agreement. | synthetic_template_20250913 | Six laning of Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V -EOT recommendation by the Authority for a period of 112 days not agreeable to the EPC Contractor — Request for considering EOT as discussed during the Review Meetings- reg | We are writing to express our concerns regarding the EOT recommendation by the Authority for a period of 112 days, which is not agreeable to the EPC Contractor. We request that the EOT be considered as discussed during the Review Meetings. The project involves six laning of the Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km 71+015 to km 107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase-V. We have referenced several documents and meetings in support of our request, and we hope for a favorable consideration. Please confirm receipt of this correspondence. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Delay due to Change of Scope works | Change of Scope | Non finalisation of COS proposal by frequently revising the scope has an adverse impact on the progress of works at the approaches of the underpass as we are not able to commence even drain and service road works which has direct impact on the physical and financial progress hampering the milestone achievement. | synthetic_template_20250913 | Six laning of Karaipcttai to Walajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - Contractor’s failure in achieving Project Mile Stone 1,2 & 3 applying of Damages vide Contract Article No. 10.3.2 & 10.3.3 - Reply made -Reg. | We are in receipt of your letter ref (26) cited above, our reply for the same is as follows: 1. The Contract Agreement for this Project was executed on 15.10.2018. The Appointed Date was fixed as 11.02.2019 and the same was communicated vide ref (2) cited above. 2. The Appointed date was declared as 11.02.2019 by the Authority taking into account the land handed over in terms of the available area without taking into consideration, the requirement of the Contract provision as per Clause 4.1.3 (a) of the EPC agreement which talks about the handing over of land only in terms of length of the Project Highway. The memorandum and appendix prepared in terms of area gave a deceptive / false picture about the availability of vacant access. Taking into consideration all the encumbrances, hindrances, utilities etc. the vacant access available on the appointed date declared was worked out and it was less than 90% and hence requested the Authority vide letter under ref (3) cited above for modification of the appointed date on which 90% of encumbrance free land would be made available to the Contractor. 3. The Authority in its response vide ref (4) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. 4. The EPC contractor vide ref (5) cited above in reply reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that the impacted length due to encroachments and encumbrances was 12.18 km which accounted to 33.77% of the project length. The workable length available to the contractor was only 66.23% of the project length. The EPC contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of encumbrance / encroachment / obstruction. Thank you for your attention to this matter. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Release of Retention Money | Payments | It is pertinent to mention that the AE after observing the substantial progress made by the EPC Contractor at site has recommended the release of Retention Money vide his Lr. No. 356 dated 09.07.2020 and copy of the same is herewith enclosed as Annexure 4. | synthetic_template_20250913 | Extension of Time and Rescheduling of Project Milestones - EOT granted for 112 days not acceptable to the EPC contractor - Request for revisiting the EOT recommended - Reminder sent - Reg. | 1. This is with respect to the Extension of Time(EOT} approved by the Authority for. a period of 112 days for Project Milestone-I without effecting changes in Scheduled Project Completion Period vide ref (3) cited above.The EPC Contrator disagrees and does not accept the grant of EOT approval for 112 days, the reasons for disgreeement of this approval are elaborated in our submission to the Authority Engineer vide ref (4) cited above. 2. The EPC contractor requested the Authority/NHAI to revisit the EOT determined/approved and communicate 324 days as interim Extension of time vide ref (5) cited above but, we are yet to receive response in this regard. Copy of the same is herewith enclosed as Annexure 1. 3. The Authority is yet to fulfil the obligations relating to handing over of ROW as per Sub Clause 8.2 of the Contract Agreement. Copy of the newspaper publication regarding LA status / notification for acquiring land for the Project Highway (Kanchipuram District} is herewith enclosed as Annexure 2. By not fulfilling the obligations as per the provisions of the Contract Agreement, the Authority committed a material default pursuant to Sub clause 23.2.1 (a) of the Contract Agreement. 4. The electrical pole/Transformer shifting is yet to be completed by the Authority even as on date and following are the Chainages whether shifting is required to be carried out: No.of Transformers In addition to the above, following locations listed below where shifting of High Tension(HT) Towerlines are required to be carried out: No. of HT Towers Status All Material mobilized at site. Due to Lockdown Estimate Approved on 22.02.2020. Electrical Contractor engaged by EPC Contractor on 20.03.2020 for shifting works. Due to Lockdown work yet to be taken-up. Estimate yet to be approved. Estimate yet to be approved. We look forward to your response. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Release of Retention Money | Payments | It is pertinent to mention that the AE after observing the substantial progress made by the EPC Contractor at site has recommended the release of Retention Money vide his Lr. No. 356 dated 09.07.2020 and copy of the same is herewith enclosed as Annexure 4. | synthetic_template_20250913 | Extension of Time and Rescheduling of Project Milestones - EOT granted for 112 days not acceptable to the EPC contractor - Request for revisiting the EOT recommended - Reminder sent - Reg. | 1. This is with respect to the Extension of Time(EOT} approved by the Authority for. a period of 112 days for Project Milestone-I without effecting changes in Scheduled Project Completion Period vide ref (3) cited above.The EPC Contrator disagrees and does not accept the grant of EOT approval for 112 days, the reasons for disgreeement of this approval are elaborated in our submission to the Authority Engineer vide ref (4) cited above. 2. The EPC contractor requested the Authority/NHAI to revisit the EOT determined/approved and communicate 324 days as interim Extension of time vide ref (5) cited above but, we are yet to receive response in this regard. Copy of the same is herewith enclosed as Annexure 1. 3. The Authority is yet to fulfil the obligations relating to handing over of ROW as per Sub Clause 8.2 of the Contract Agreement. Copy of the newspaper publication regarding LA status / notification for acquiring land for the Project Highway (Kanchipuram District} is herewith enclosed as Annexure 2. By not fulfilling the obligations as per the provisions of the Contract Agreement, the Authority committed a material default pursuant to Sub clause 23.2.1 (a) of the Contract Agreement. 4. The electrical pole/Transformer shifting is yet to be completed by the Authority even as on date and following are the Chainages whether shifting is required to be carried out: No.of Transformers In addition to the above, following locations listed below where shifting of High Tension(HT) Towerlines are required to be carried out: No. of HT Towers Status All Material mobilized at site. Due to Lockdown Estimate Approved on 22.02.2020. Electrical Contractor engaged by EPC Contractor on 20.03.2020 for shifting works. Due to Lockdown work yet to be taken-up. Estimate yet to be approved. Estimate yet to be approved. Please confirm receipt of this correspondence. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Release of Retention Money | Payments | It is pertinent to mention that the AE after observing the substantial progress made by the EPC Contractor at site has recommended the release of Retention Money vide his Lr. No. 356 dated 09.07.2020 and copy of the same is herewith enclosed as Annexure 4. | synthetic_template_20250913 | Extension of Time and Rescheduling of Project Milestones - EOT granted for 112 days not acceptable to the EPC contractor - Request for revisiting the EOT recommended - Reminder sent - Reg. | 1. This is with respect to the Extension of Time(EOT} approved by the Authority for. a period of 112 days for Project Milestone-I without effecting changes in Scheduled Project Completion Period vide ref (3) cited above.The EPC Contrator disagrees and does not accept the grant of EOT approval for 112 days, the reasons for disgreeement of this approval are elaborated in our submission to the Authority Engineer vide ref (4) cited above. 2. The EPC contractor requested the Authority/NHAI to revisit the EOT determined/approved and communicate 324 days as interim Extension of time vide ref (5) cited above but, we are yet to receive response in this regard. Copy of the same is herewith enclosed as Annexure 1. 3. The Authority is yet to fulfil the obligations relating to handing over of ROW as per Sub Clause 8.2 of the Contract Agreement. Copy of the newspaper publication regarding LA status / notification for acquiring land for the Project Highway (Kanchipuram District} is herewith enclosed as Annexure 2. By not fulfilling the obligations as per the provisions of the Contract Agreement, the Authority committed a material default pursuant to Sub clause 23.2.1 (a) of the Contract Agreement. 4. The electrical pole/Transformer shifting is yet to be completed by the Authority even as on date and following are the Chainages whether shifting is required to be carried out: No.of Transformers In addition to the above, following locations listed below where shifting of High Tension(HT) Towerlines are required to be carried out: No. of HT Towers Status All Material mobilized at site. Due to Lockdown Estimate Approved on 22.02.2020. Electrical Contractor engaged by EPC Contractor on 20.03.2020 for shifting works. Due to Lockdown work yet to be taken-up. Estimate yet to be approved. Estimate yet to be approved. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Release of Retention Money | Payments | It is pertinent to mention that the AE after observing the substantial progress made by the EPC Contractor at site has recommended the release of Retention Money vide his Lr. No. 356 dated 09.07.2020 and copy of the same is herewith enclosed as Annexure 4. | synthetic_template_20250913 | Extension of Time and Rescheduling of Project Milestones - EOT granted for 112 days not acceptable to the EPC contractor - Request for revisiting the EOT recommended - Reminder sent - Reg. | Please note that 1. This is with respect to the Extension of Time(EOT} approved by the Authority for. a period of 112 days for Project Milestone-I without effecting changes in Scheduled Project Completion Period vide ref (3) cited above.The EPC Contrator disagrees and does not accept the grant of EOT approval for 112 days, the reasons for disgreeement of this approval are elaborated in our submission to the Authority Engineer vide ref (4) cited above. 2. The EPC contractor requested the Authority/NHAI to revisit the EOT determined/approved and communicate 324 days as interim Extension of time vide ref (5) cited above but, we are yet to receive response in this regard. Copy of the same is herewith enclosed as Annexure 1. 3. The Authority is yet to fulfil the obligations relating to handing over of ROW as per Sub Clause 8.2 of the Contract Agreement. Copy of the newspaper publication regarding LA status / notification for acquiring land for the Project Highway (Kanchipuram District} is herewith enclosed as Annexure 2. By not fulfilling the obligations as per the provisions of the Contract Agreement, the Authority committed a material default pursuant to Sub clause 23.2.1 (a) of the Contract Agreement. 4. The electrical pole/Transformer shifting is yet to be completed by the Authority even as on date and following are the Chainages whether shifting is required to be carried out: No.of Transformers In addition to the above, following locations listed below where shifting of High Tension(HT) Towerlines are required to be carried out: No. of HT Towers Status All Material mobilized at site. Due to Lockdown Estimate Approved on 22.02.2020. Electrical Contractor engaged by EPC Contractor on 20.03.2020 for shifting works. Due to Lockdown work yet to be taken-up. Estimate yet to be approved. Estimate yet to be approved. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Release of Retention Money | Payments | It is pertinent to mention that the AE after observing the substantial progress made by the EPC Contractor at site has recommended the release of Retention Money vide his Lr. No. 356 dated 09.07.2020 and copy of the same is herewith enclosed as Annexure 4. | synthetic_template_20250913 | Extension of Time and Rescheduling of Project Milestones - EOT granted for 112 days not acceptable to the EPC contractor - Request for revisiting the EOT recommended - Reminder sent - Reg. | 1. This is with respect to the Extension of Time(EOT} approved by the Authority for. a period of 112 days for Project Milestone-I without effecting changes in Scheduled Project Completion Period vide ref (3) cited above.The EPC Contrator disagrees and does not accept the grant of EOT approval for 112 days, the reasons for disgreeement of this approval are elaborated in our submission to the Authority Engineer vide ref (4) cited above. 2. The EPC contractor requested the Authority/NHAI to revisit the EOT determined/approved and communicate 324 days as interim Extension of time vide ref (5) cited above but, we are yet to receive response in this regard. Copy of the same is herewith enclosed as Annexure 1. 3. The Authority is yet to fulfil the obligations relating to handing over of ROW as per Sub Clause 8.2 of the Contract Agreement. Copy of the newspaper publication regarding LA status / notification for acquiring land for the Project Highway (Kanchipuram District} is herewith enclosed as Annexure 2. By not fulfilling the obligations as per the provisions of the Contract Agreement, the Authority committed a material default pursuant to Sub clause 23.2.1 (a) of the Contract Agreement. 4. The electrical pole/Transformer shifting is yet to be completed by the Authority even as on date and following are the Chainages whether shifting is required to be carried out: No.of Transformers In addition to the above, following locations listed below where shifting of High Tension(HT) Towerlines are required to be carried out: No. of HT Towers Status All Material mobilized at site. Due to Lockdown Estimate Approved on 22.02.2020. Electrical Contractor engaged by EPC Contractor on 20.03.2020 for shifting works. Due to Lockdown work yet to be taken-up. Estimate yet to be approved. Estimate yet to be approved. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
occurrence of cyclones | EoT | Now due to the recent cyclones such as NIVAR & BUREVI, the district had experienced heavy and copious rains and all the above identified borrow locations have been completely filled up with the water. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20210120_005_SPK_RO_Delay in obtaining permission for Borrow area.pdf | Delay in Obtaining Permission of Borrow Earth - Ranipet District - Reg. | Dear Sir, This is with reference to the above said references (2) to (7); we wish to submit that, since from the Appointed Date we have been approaching the Ranipet District administration for obtaining necessary permission for extracting Borrow earth. Correspondences for the same is enclosed as ready reference. Application for extracting borrow earth from the identified Borrow area which were submitted to the district administration are as follows: S.No ¦ Chainage ¦ 1 ¦ 101+310 2 ¦ 101+310 Name of the tank Marutheri Lake Bagaveli Lake Sumaithangi Lake Kaveripakkam Lake However, we wish to inform that. we are awaiting for the necessary permission from the District Collector to date. Now due to the recent cyclones such as NIVAR & BUREVI, the district had experienced heavy and copious rains and all the above identified borrow locations have been completely filled up with water. In this connection, we wish to mention that; widening sections of project road (i.e, 20.77Km.) is in the verge of completion and only balance scope for earthwork is required for approaches of the elevated sections. Due to non-availability of Borrow earth, all Elevated sections (i.e, totalling 13.90Km.) of RE Wall/RE Fill works has come to standstill despite more than 70% of completion of casting of RE panel. Further, delay. in extraction of Borrow earth will lead to delay in achieving the target. In this regard, we kindly request your good-self to intervene and forward our difficulties in obtaining permission of Borrow Earth to the Chief Secretary -— Government of Tamil nadu to issue suitable instructions to the concerned officials to accord permission to extract earth in order to facilitate the EPC Contractor in early completion of Project. This is for your immediate 8& necessary action, please. | FALSE | real_data
occurrence of cyclones | EoT | Now due to the recent cyclones such as NIVAR & BUREVI, the district had experienced heavy and copious rains and all the above identified borrow locations have been completely filled up with the water. | synthetic_template_20250913 | Delay in Obtaining Permission of Borrow Earth - Ranipet District - Reg. | Dear Sir, This is with reference to the above said references (2) to (7); we wish to submit that, since from the Appointed Date we have been approaching the Ranipet District administration for obtaining necessary permission for extracting Borrow earth. Correspondences for the same is enclosed as ready reference. Application for extracting borrow earth from the identified Borrow area which were submitted to the district administration are as follows: S.No ¦ Chainage ¦ 1 ¦ 101+310 2 ¦ 101+310 Name of the tank Marutheri Lake Bagaveli Lake Sumaithangi Lake Kaveripakkam Lake However, we wish to inform that. we are awaiting for the necessary permission from the District Collector to date. Now due to the recent cyclones such as NIVAR & BUREVI, the district had experienced heavy and copious rains and all the above identified borrow locations have been completely filled up with water. In this connection, we wish to mention that; widening sections of project road (i.e, 20.77Km.) is in the verge of completion and only balance scope for earthwork is required for approaches of the elevated sections. Due to non-availability of Borrow earth, all Elevated sections (i.e, totalling 13.90Km.) of RE Wall/RE Fill works has come to standstill despite more than 70% of completion of casting of RE panel. Further, delay. in extraction of Borrow earth will lead to delay in achieving the target. In this regard, we kindly request your good-self to intervene and forward our difficulties in obtaining permission of Borrow Earth to the Chief Secretary -— Government of Tamil nadu to issue suitable instructions to the concerned officials to accord permission to extract earth in order to facilitate the EPC Contractor in early completion of Project. This is for your immediate 8& necessary action, please. We appreciate your cooperation in this regard. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
occurrence of cyclones | EoT | Now due to the recent cyclones such as NIVAR & BUREVI, the district had experienced heavy and copious rains and all the above identified borrow locations have been completely filled up with the water. | synthetic_template_20250913 | Delay in Obtaining Permission of Borrow Earth - Ranipet District - Reg. | Dear Sir, This is with reference to the above said references (2) to (7); we wish to submit that, since from the Appointed Date we have been approaching the Ranipet District administration for obtaining necessary permission for extracting Borrow earth. Correspondences for the same is enclosed as ready reference. Application for extracting borrow earth from the identified Borrow area which were submitted to the district administration are as follows: S.No ¦ Chainage ¦ 1 ¦ 101+310 2 ¦ 101+310 Name of the tank Marutheri Lake Bagaveli Lake Sumaithangi Lake Kaveripakkam Lake However, we wish to inform that. we are awaiting for the necessary permission from the District Collector to date. Now due to the recent cyclones such as NIVAR & BUREVI, the district had experienced heavy and copious rains and all the above identified borrow locations have been completely filled up with water. In this connection, we wish to mention that; widening sections of project road (i.e, 20.77Km.) is in the verge of completion and only balance scope for earthwork is required for approaches of the elevated sections. Due to non-availability of Borrow earth, all Elevated sections (i.e, totalling 13.90Km.) of RE Wall/RE Fill works has come to standstill despite more than 70% of completion of casting of RE panel. Further, delay. in extraction of Borrow earth will lead to delay in achieving the target. In this regard, we kindly request your good-self to intervene and forward our difficulties in obtaining permission of Borrow Earth to the Chief Secretary -— Government of Tamil nadu to issue suitable instructions to the concerned officials to accord permission to extract earth in order to facilitate the EPC Contractor in early completion of Project. This is for your immediate 8& necessary action, please. We appreciate your cooperation in this regard. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
occurrence of cyclones | EoT | Now due to the recent cyclones such as NIVAR & BUREVI, the district had experienced heavy and copious rains and all the above identified borrow locations have been completely filled up with the water. | synthetic_template_20250913 | Delay in Obtaining Permission of Borrow Earth - Ranipet District - Reg. | We hereby confirm that Dear Sir, This is with reference to the above said references (2) to (7); we wish to submit that, since from the Appointed Date we have been approaching the Ranipet District administration for obtaining necessary permission for extracting Borrow earth. Correspondences for the same is enclosed as ready reference. Application for extracting borrow earth from the identified Borrow area which were submitted to the district administration are as follows: S.No ¦ Chainage ¦ 1 ¦ 101+310 2 ¦ 101+310 Name of the tank Marutheri Lake Bagaveli Lake Sumaithangi Lake Kaveripakkam Lake However, we wish to inform that. we are awaiting for the necessary permission from the District Collector to date. Now due to the recent cyclones such as NIVAR & BUREVI, the district had experienced heavy and copious rains and all the above identified borrow locations have been completely filled up with water. In this connection, we wish to mention that; widening sections of project road (i.e, 20.77Km.) is in the verge of completion and only balance scope for earthwork is required for approaches of the elevated sections. Due to non-availability of Borrow earth, all Elevated sections (i.e, totalling 13.90Km.) of RE Wall/RE Fill works has come to standstill despite more than 70% of completion of casting of RE panel. Further, delay. in extraction of Borrow earth will lead to delay in achieving the target. In this regard, we kindly request your good-self to intervene and forward our difficulties in obtaining permission of Borrow Earth to the Chief Secretary -— Government of Tamil nadu to issue suitable instructions to the concerned officials to accord permission to extract earth in order to facilitate the EPC Contractor in early completion of Project. This is for your immediate 8& necessary action, please. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
occurrence of cyclones | EoT | With reference to the above subject, we wish to bring your notice that, due to occurrence of "NIVAR & BUREVI Cyclone" there has been a heavy/continuous rain in Kanchipuram & Ranipet Districts. | synthetic_template_20250913 | Intimation of Stagnation of Water in Identified Borrow Areas — Reg. | With reference to the above subject; we wish to bring your notice that, due to occurrence of “NIVAR & BUREVI Cyclone” there has been a heavy/continuous rain in Kanchipuram & Ranipet Districts. The entire works of the Project Highway have come to standstill owing to non-operation of Borrow area due to unexpected heavy downpour. Since, there has been a complete waterlogging in all the identified Borrow areas of Kanchipuram & Ranipet District, it is not possible to operate the Borrow Areas for a minimum period of 3 months. RE wall back filling for approaches of 3.Nos. of LVUP’s are hampered due to ponding of borrow areas. RE Panels are even stacked at site for commencement of back filling works. Photos showing the stagnation of water in the identified borrow areas of Kanchipuram & Ranipet Districts is enclosed as Annexure - I. This is for your kind information & record, please. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
occurrence of cyclones | EoT | With reference to the above subject, we wish to bring your notice that, due to occurrence of "NIVAR & BUREVI Cyclone" there has been a heavy/continuous rain in Kanchipuram & Ranipet Districts. | synthetic_template_20250913 | Intimation of Stagnation of Water in Identified Borrow Areas — Reg. | This is to notify you that With reference to the above subject; we wish to bring your notice that, due to occurrence of “NIVAR & BUREVI Cyclone” there has been a heavy/continuous rain in Kanchipuram & Ranipet Districts. The entire works of the Project Highway have come to standstill owing to non-operation of Borrow area due to unexpected heavy downpour. Since, there has been a complete waterlogging in all the identified Borrow areas of Kanchipuram & Ranipet District, it is not possible to operate the Borrow Areas for a minimum period of 3 months. RE wall back filling for approaches of 3.Nos. of LVUP’s are hampered due to ponding of borrow areas. RE Panels are even stacked at site for commencement of back filling works. Photos showing the stagnation of water in the identified borrow areas of Kanchipuram & Ranipet Districts is enclosed as Annexure - I. This is for your kind information & record, please. Please confirm receipt of this correspondence. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Submission of additional information/clarifications on Extension of time proposal | EoT; Dispute Resolution | Regarding Extension of Time for Milestone I, it has been asked to submit the details viz.Rainfall data, Evidence on the effect of Aadhi Athi Varadhar Festival & details of permission obtained for the extraction of borrow earth | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/117A_25092019_Request for Supporting details - EOT I received on 26.11.2019.pdf | Entitlement of EoT for Milestone-I — Supporting details -Reg | This is in reference to your above cited letters 1 and 3 regarding Extension of Time for Milestone-—t; it has been asked to submit the following details to evaluate further. 1. Rainfall data along with Weather report and proof of evidence 2. Evidence on the effect of Aadhi Aththi Varadhar Festival with necessary documents 3. Details cf Permission obtained for the extraction of borrow earth This is for your information and necessary action. | FALSE | real_data
Submission of additional information/clarifications on Extension of time proposal | EoT; Dispute Resolution | The delay due to North East Monsoon is recommended by IE restricting to 39 days in the period from 15.10.2019 to 31.12.2019 without mentioning the exact dates for which EOT is to be considered. The aforesaid is necessary for eliminating the period that may overlap in the period recommended for delay due to other reasons. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/20200829_RO_PD_2378_RO Letter regadring EOT.pdf | NHAI, RO Chennai — PIU, Kancheepuram — Six Laning of Sriperumbudur to Karaipettai from Km.37.000 to Km.71.015 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC Mode — Extension of Time & Rescheduling of Project Milestones I & II — Proposal submitted for approval — Reg. | Please refer to your letter cited at (1) under reference submitting therewith a proposal for extension of time and rescheduling of Project Milestones I & I in the subject project. The proposal has been examined and the following are observed: i. In respect of delay due to monsoon the Authority Engineer has recommended for considering the delay due to unexpected and continued rains due to North East Monsoon which prolonged for a period i.e. upto 01° week of January’2020 and has mentioned that the delay can be evaluated from 15.10.2019 to 31.12.2019. In this connection vide your letter dated 19.05.2020 in para 4 (vii) (C) Le. PD’s recommendation it is mentioned that the view of the Authority Engineer’s determination that the Contractor is entitled for the period from 01.07.2019 to 18.09.2019 towards Extension of Time due to delay caused by Monsoon rainfall. The aforesaid is not correct as the AE has not taken into account the Contractor’s quoted reason of South West Monsoon from 03.06.2019 to 15.08.2019 and has only recommended for evaluating the delay due to North East Monsoon. Herein it is also mentioned that as the North East monsoon is the phenomenon experienced by the area of project stretch and already this fact could have been known to the Contractor the justification for considering the aforesaid rains for delay needs to be furnished. il, As could be seen from the summarization of the EOT vide para 5 (ii) (G) the EOT for delay due to North East Monsoon is recommended by IE restricting to 39 days in th= period from 15.10.2019 to 31.12.2019 without mentioning the exact dates for which the EOT is to be considered. The aforesaid is necessary for eliminating the period that may overlap in the period recommended for delay due to other reasons. 2. In view of the above, the proposal is returned for review, compliance and resubmission. | FALSE | real_data
Submission of additional information/clarifications on Extension of time proposal | EoT | Entitlement of EOT for Milestone I, EOT for Milestone - I, Your claim for EOT | synthetic_template_20250913 | Entitlement of EoT for Milestone-!l - Supporting details -Reg | This is in reference to your letter cited 1 above regarding EoT of Milestone -I and subsequent discussion had with your representative on 17.08.2019. The submitted details are not substantiating your claim for EoT and found lacking of supporting particulars. So, you are requested to submit your reasoning specifically based on conditions of Contract Agreement. This is for your information and necessary action. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Submission of additional information/clarifications on Extension of time proposal | EoT | Entitlement of EOT for Milestone I, EOT for Milestone - I, Your claim for EOT | synthetic_template_20250913 | Entitlement of EoT for Milestone-!l - Supporting details -Reg | Please note that This is in reference to your letter cited 1 above regarding EoT of Milestone -I and subsequent discussion had with your representative on 17.08.2019. The submitted details are not substantiating your claim for EoT and found lacking of supporting particulars. So, you are requested to submit your reasoning specifically based on conditions of Contract Agreement. This is for your information and necessary action. Please confirm receipt of this correspondence. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Submission of additional information/clarifications on Extension of time proposal | Dispute Resolution | Regarding Extension of Time for Milestone I, it has been asked to submit the details viz.Rainfall data, Evidence on the effect of Aadhi Athi Varadhar Festival & details of permission obtained for the extraction of borrow earth | synthetic_template_20250913 | Entitlement of EoT for Milestone-I — Supporting details -Reg | This is in reference to your above cited letters 1 and 3 regarding Extension of Time for Milestone-—t; it has been asked to submit the following details to evaluate further. 1. Rainfall data along with Weather report and proof of evidence 2. Evidence on the effect of Aadhi Aththi Varadhar Festival with necessary documents 3. Details cf Permission obtained for the extraction of borrow earth This is for your information and necessary action. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Submission of additional information/clarifications on Extension of time proposal | Dispute Resolution | The delay due to North East Monsoon is recommended by IE restricting to 39 days in the period from 15.10.2019 to 31.12.2019 without mentioning the exact dates for which EOT is to be considered. The aforesaid is necessary for eliminating the period that may overlap in the period recommended for delay due to other reasons. | synthetic_template_20250913 | NHAI, RO Chennai — PIU, Kancheepuram — Six Laning of Sriperumbudur to Karaipettai from Km.37.000 to Km.71.015 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC Mode — Extension of Time & Rescheduling of Project Milestones I & II — Proposal submitted for approval — Reg. | Please note that Please refer to your letter cited at (1) under reference submitting therewith a proposal for extension of time and rescheduling of Project Milestones I & I in the subject project. The proposal has been examined and the following are observed: i. In respect of delay due to monsoon the Authority Engineer has recommended for considering the delay due to unexpected and continued rains due to North East Monsoon which prolonged for a period i.e. upto 01° week of January’2020 and has mentioned that the delay can be evaluated from 15.10.2019 to 31.12.2019. In this connection vide your letter dated 19.05.2020 in para 4 (vii) (C) Le. PD’s recommendation it is mentioned that the view of the Authority Engineer’s determination that the Contractor is entitled for the period from 01.07.2019 to 18.09.2019 towards Extension of Time due to delay caused by Monsoon rainfall. The aforesaid is not correct as the AE has not taken into account the Contractor’s quoted reason of South West Monsoon from 03.06.2019 to 15.08.2019 and has only recommended for evaluating the delay due to North East Monsoon. Herein it is also mentioned that as the North East monsoon is the phenomenon experienced by the area of project stretch and already this fact could have been known to the Contractor the justification for considering the aforesaid rains for delay needs to be furnished. il, As could be seen from the summarization of the EOT vide para 5 (ii) (G) the EOT for delay due to North East Monsoon is recommended by IE restricting to 39 days in th= period from 15.10.2019 to 31.12.2019 without mentioning the exact dates for which the EOT is to be considered. The aforesaid is necessary for eliminating the period that may overlap in the period recommended for delay due to other reasons. 2. In view of the above, the proposal is returned for review, compliance and resubmission. Please confirm receipt of this correspondence. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Permission for extracting soil from minor irrigation tanks and ponds | Others | The Contractor has taken sincere effort for getting Permission for extraction of Borrow earth since from the Appointed Date. But, considering the Contract Clause No. 3.17 (a), which reproduced here, "The Contractor shall, at its own cost and expense, in addition to and not in derogation of its obligation elsewhere set out in this Agreement, (a) make, or cause to be made, necessary applications to the relevant Government Instrumentalities with such particulars and details as may be required for obtaining Applicable Permits set forth in Schedule F. " Therefore, on this ground, Contractor's request for EOT cannot be entertained. However, due to Aadhi Athi Varadhar festival which happens once in 40 years the same shall be considered for Entitlement of EoT. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/189_Rescheduling of Project Milestones - EOT - 1.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under BharatmalaPariyojana on EPC mode — Rescheduling of Project Mile Stone- Request for Extension of Time -Reg. | Having gone through your documents related to Rescheduling of Project Milestone-Request for Extension of Time EoT-1 please find enclosed herewith the Authority Engineers recommendations on the same subject. This is for your information and necessary action. | FALSE | real_data
Permission for extracting soil from minor irrigation tanks and ponds | Others | Executive Engineer, Irrigation Division No.7, Gajwel has requested to instruct the agency to submit the list of vehicles to be used for lifting of Canal spoil before starting the work. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-2/7. 20230926_EE_Cont_permission for lifing of canal spoil.pdf | Widening to 2 lanes with paved shoulders of Medak-Siddipet Section from km. 0.000 to 69.978 of NH-765DG in the State of Telangana under annual plan 2021-22 on EPC Basis Permission proposal for extracting canal spoil from Tail end Distributary of Package 13 at Km 18+000 near Bachurajpalli (V), Nizampet (M), Medak (Dist.) - Permission accorded for lifting of Canal spoil-Regarding. | Please find here with the copy of the reference 24 cited, which is self explanatory, wherein, the Executive Engineer, Irrigation Division No.7, Gajwel has accorded permission for lifting of 6000 Cum of spoil for the above work. While according permission, the Executive Engineer, Irrigation Division No.7, Gajwel has requested to instruct the agency to submit the list of vehicles to be used for lifting of Canal spoil before starting the work. Further requested to recover initial charges and seignorage charges and stated that if any damages occurred to the Canal during the lifting of spoil, the same would be restored before leaving the loading point as per the instructions of the Engineer concerned. The Executive Engineer has also informed that permission is valid for 10 days from the date of permission. That is upto 30.09.2023. In view of the above, it is requested take suitable safety measures to avoid any damages to the Canals as desired by Irrigation Department. You are requested to conduct test on the soil and ensure that results are satisfying as per the Contract Agreement before use of material. | FALSE | real_data
Permission for extracting soil from minor irrigation tanks and ponds | Others | The Contractor has taken sincere effort for getting Permission for extraction of Borrow earth since from the Appointed Date. But, considering the Contract Clause No. 3.17 (a), which reproduced here, "The Contractor shall, at its own cost and expense, in addition to and not in derogation of its obligation elsewhere set out in this Agreement, (a) make, or cause to be made, necessary applications to the relevant Government Instrumentalities with such particulars and details as may be required for obtaining Applicable Permits set forth in Schedule F. " Therefore, on this ground, Contractor's request for EOT cannot be entertained. However, due to Aadhi Athi Varadhar festival which happens once in 40 years the same shall be considered for Entitlement of EoT. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under BharatmalaPariyojana on EPC mode — Rescheduling of Project Mile Stone- Request for Extension of Time -Reg. | We hereby confirm that Having gone through your documents related to Rescheduling of Project Milestone-Request for Extension of Time EoT-1 please find enclosed herewith the Authority Engineers recommendations on the same subject. This is for your information and necessary action. We look forward to your response. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Permission for extracting soil from minor irrigation tanks and ponds | Others | Executive Engineer, Irrigation Division No.7, Gajwel has requested to instruct the agency to submit the list of vehicles to be used for lifting of Canal spoil before starting the work. | synthetic_template_20250913 | Widening to 2 lanes with paved shoulders of Medak-Siddipet Section from km. 0.000 to 69.978 of NH-765DG in the State of Telangana under annual plan 2021-22 on EPC Basis Permission proposal for extracting canal spoil from Tail end Distributary of Package 13 at Km 18+000 near Bachurajpalli (V), Nizampet (M), Medak (Dist.) - Permission accorded for lifting of Canal spoil-Regarding. | Please find here with the copy of the reference 24 cited, which is self explanatory, wherein, the Executive Engineer, Irrigation Division No.7, Gajwel has accorded permission for lifting of 6000 Cum of spoil for the above work. While according permission, the Executive Engineer, Irrigation Division No.7, Gajwel has requested to instruct the agency to submit the list of vehicles to be used for lifting of Canal spoil before starting the work. Further requested to recover initial charges and seignorage charges and stated that if any damages occurred to the Canal during the lifting of spoil, the same would be restored before leaving the loading point as per the instructions of the Engineer concerned. The Executive Engineer has also informed that permission is valid for 10 days from the date of permission. That is upto 30.09.2023. In view of the above, it is requested take suitable safety measures to avoid any damages to the Canals as desired by Irrigation Department. You are requested to conduct test on the soil and ensure that results are satisfying as per the Contract Agreement before use of material. We await your further instructions. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Permission for extracting soil from minor irrigation tanks and ponds | Others | The Contractor has taken sincere effort for getting Permission for extraction of Borrow earth since from the Appointed Date. But, considering the Contract Clause No. 3.17 (a), which reproduced here, "The Contractor shall, at its own cost and expense, in addition to and not in derogation of its obligation elsewhere set out in this Agreement, (a) make, or cause to be made, necessary applications to the relevant Government Instrumentalities with such particulars and details as may be required for obtaining Applicable Permits set forth in Schedule F. " Therefore, on this ground, Contractor's request for EOT cannot be entertained. However, due to Aadhi Athi Varadhar festival which happens once in 40 years the same shall be considered for Entitlement of EoT. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under BharatmalaPariyojana on EPC mode — Rescheduling of Project Mile Stone- Request for Extension of Time -Reg. | Having gone through your documents related to Rescheduling of Project Milestone-Request for Extension of Time EoT-1 please find enclosed herewith the Authority Engineers recommendations on the same subject. This is for your information and necessary action. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Permission for extracting soil from minor irrigation tanks and ponds | Others | The Contractor has taken sincere effort for getting Permission for extraction of Borrow earth since from the Appointed Date. But, considering the Contract Clause No. 3.17 (a), which reproduced here, "The Contractor shall, at its own cost and expense, in addition to and not in derogation of its obligation elsewhere set out in this Agreement, (a) make, or cause to be made, necessary applications to the relevant Government Instrumentalities with such particulars and details as may be required for obtaining Applicable Permits set forth in Schedule F. " Therefore, on this ground, Contractor's request for EOT cannot be entertained. However, due to Aadhi Athi Varadhar festival which happens once in 40 years the same shall be considered for Entitlement of EoT. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under BharatmalaPariyojana on EPC mode — Rescheduling of Project Mile Stone- Request for Extension of Time -Reg. | Having gone through your documents related to Rescheduling of Project Milestone-Request for Extension of Time EoT-1 please find enclosed herewith the Authority Engineers recommendations on the same subject. This is for your information and necessary action. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Permission for extracting soil from minor irrigation tanks and ponds | Others | The Contractor has taken sincere effort for getting Permission for extraction of Borrow earth since from the Appointed Date. But, considering the Contract Clause No. 3.17 (a), which reproduced here, "The Contractor shall, at its own cost and expense, in addition to and not in derogation of its obligation elsewhere set out in this Agreement, (a) make, or cause to be made, necessary applications to the relevant Government Instrumentalities with such particulars and details as may be required for obtaining Applicable Permits set forth in Schedule F. " Therefore, on this ground, Contractor's request for EOT cannot be entertained. However, due to Aadhi Athi Varadhar festival which happens once in 40 years the same shall be considered for Entitlement of EoT. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under BharatmalaPariyojana on EPC mode — Rescheduling of Project Mile Stone- Request for Extension of Time -Reg. | Having gone through your documents related to Rescheduling of Project Milestone-Request for Extension of Time EoT-1 please find enclosed herewith the Authority Engineers recommendations on the same subject. This is for your information and necessary action. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Design & Drawings of Highways & Structures | Contractor's Obligations | By copy of this letter, concerned local self-government bodies are being requested to depute their Engineer for site inspection. It is requested to arrange joint inspection in consultation with the Engineers of local self-government bodies. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/20200723_NHAI_TEL&IE_ 605_Drainage Adequacy and effectiveness.pdf | Design, Construction, Development, Finance, Operation & Maintenance of 6-laning of Vadakkenchery to Thrissur (km 240.000 to 270.000) section of NH-544 (old No.47) on DBFOT(Toll) basis - Under construction project - Drainage systems: Adequacy & Effectiveness - reg. | Please refer to this office e-mail dated 09.07.2020 & 13.07.2020 communicating therewith NHAI policy guidelines regarding drainage systems: adequacy & effectiveness for compliance. In continuation to above, it is requested to inspect the site along with Engineers of concerned local panchayat / municipal / corporation bodies duly following the guidelines defined for under construction projects and submit drainage plan to this office, which will be reviewed by the Drainage Expert being identified by PIU / Regional Office. By copy of this letter, concerned local self-government bodies are being requested to depute their Engineer for site inspection. It is requested to arrange joint inspection in consultation with the Engineers of local self-government bodies. The drainage plan / report shall be submitted to this office latest by 31.07.2020. | FALSE | real_data
Design & Drawings of Highways & Structures | Contractor's Obligations | With reference to above, vide your letter under ref. 2 above you have submitted drawings for Miscellaneous Items. The same has been reviewed and approval is hereby communicated for the Miscellaneous Items drawing mentioned below. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-2/8. 20240202_40B_AE_Cont_Approval of Drawings for Miscellaneous items.pdf | Widening to 2 Lane with paved shoulders of Medak - Siddipet section from Km 0/000 to Km 69/978 of NH-765DG in the state of Telangana under Annual plan 2021-22 on EPC Basis Submission of drawings for Miscellaneous Items - Approval- Reg. | With reference to above, vide your letter under ref. 2 above you have submitted drawings for Miscellaneous Items. The same has been reviewed and approval is hereby communicated for the Miscellaneous Items drawing mentioned below. 1. Pedestrian Guard Rail 2. Kilometre, 5" Kilometre & Hectometre Stones 3. Metal beam Crash Barrier No review/approval and/or observation of the Authority’s Engineer and/or its failure to review/approval and/or convey its observations on any Drawings shall relieve the Contractor of its obligations and liabilities under the Agreement in any manner nor shall the Authority’s Engineer or the Authority be liable for the same in any manner; and if errors, omissions, ambiguities, inconsistencies, inadequacies or other defects are found in the drawings, they and the construction works shall be corrected at the Contractor’s cost, notwithstanding any approval. All precautions viz., safety during construction, diversion of traffic shall be ensured by the Contractor during execution. | FALSE | real_data
Design & Drawings of Highways & Structures | Contractor's Obligations | Please find enclosed herewith the comments / observations of Drainage Expert Mr.R.Nagarajan on the drainage works being carried out in the project. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode — Inspection report of Drainage Expert - Reg | In continuation to the above said references please find enclosed herewith the comments/observations of Drainage Expert Mr. R. Nagarajan on the drainage works being carried out in the Project. Hence it is hereby asked to submit your compliance to the same in consultation with the Design Director for onward processing of the same. This is for your information and necessary immediate action. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Design & Drawings of Highways & Structures | Contractor's Obligations | By copy of this letter, concerned local self-government bodies are being requested to depute their Engineer for site inspection. It is requested to arrange joint inspection in consultation with the Engineers of local self-government bodies. | synthetic_template_20250913 | Design, Construction, Development, Finance, Operation & Maintenance of 6-laning of Vadakkenchery to Thrissur (km 240.000 to 270.000) section of NH-544 (old No.47) on DBFOT(Toll) basis - Under construction project - Drainage systems: Adequacy & Effectiveness - reg. | Please refer to this office e-mail dated 09.07.2020 & 13.07.2020 communicating therewith NHAI policy guidelines regarding drainage systems: adequacy & effectiveness for compliance. In continuation to above, it is requested to inspect the site along with Engineers of concerned local panchayat / municipal / corporation bodies duly following the guidelines defined for under construction projects and submit drainage plan to this office, which will be reviewed by the Drainage Expert being identified by PIU / Regional Office. By copy of this letter, concerned local self-government bodies are being requested to depute their Engineer for site inspection. It is requested to arrange joint inspection in consultation with the Engineers of local self-government bodies. The drainage plan / report shall be submitted to this office latest by 31.07.2020. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Design & Drawings of Highways & Structures | Contractor's Obligations | By copy of this letter, concerned local self-government bodies are being requested to depute their Engineer for site inspection. It is requested to arrange joint inspection in consultation with the Engineers of local self-government bodies. | synthetic_template_20250913 | Design, Construction, Development, Finance, Operation & Maintenance of 6-laning of Vadakkenchery to Thrissur (km 240.000 to 270.000) section of NH-544 (old No.47) on DBFOT(Toll) basis - Under construction project - Drainage systems: Adequacy & Effectiveness - reg. | Please refer to this office e-mail dated 09.07.2020 & 13.07.2020 communicating therewith NHAI policy guidelines regarding drainage systems: adequacy & effectiveness for compliance. In continuation to above, it is requested to inspect the site along with Engineers of concerned local panchayat / municipal / corporation bodies duly following the guidelines defined for under construction projects and submit drainage plan to this office, which will be reviewed by the Drainage Expert being identified by PIU / Regional Office. By copy of this letter, concerned local self-government bodies are being requested to depute their Engineer for site inspection. It is requested to arrange joint inspection in consultation with the Engineers of local self-government bodies. The drainage plan / report shall be submitted to this office latest by 31.07.2020. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Design & Drawings of Highways & Structures | Contractor's Obligations | By copy of this letter, concerned local self-government bodies are being requested to depute their Engineer for site inspection. It is requested to arrange joint inspection in consultation with the Engineers of local self-government bodies. | synthetic_template_20250913 | Design, Construction, Development, Finance, Operation & Maintenance of 6-laning of Vadakkenchery to Thrissur (km 240.000 to 270.000) section of NH-544 (old No.47) on DBFOT(Toll) basis - Under construction project - Drainage systems: Adequacy & Effectiveness - reg. | Please refer to this office e-mail dated 09.07.2020 & 13.07.2020 communicating therewith NHAI policy guidelines regarding drainage systems: adequacy & effectiveness for compliance. In continuation to above, it is requested to inspect the site along with Engineers of concerned local panchayat / municipal / corporation bodies duly following the guidelines defined for under construction projects and submit drainage plan to this office, which will be reviewed by the Drainage Expert being identified by PIU / Regional Office. By copy of this letter, concerned local self-government bodies are being requested to depute their Engineer for site inspection. It is requested to arrange joint inspection in consultation with the Engineers of local self-government bodies. The drainage plan / report shall be submitted to this office latest by 31.07.2020. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Design & Drawings of Highways & Structures | Contractor's Obligations | By copy of this letter, concerned local self-government bodies are being requested to depute their Engineer for site inspection. It is requested to arrange joint inspection in consultation with the Engineers of local self-government bodies. | synthetic_template_20250913 | Design, Construction, Development, Finance, Operation & Maintenance of 6-laning of Vadakkenchery to Thrissur (km 240.000 to 270.000) section of NH-544 (old No.47) on DBFOT(Toll) basis - Under construction project - Drainage systems: Adequacy & Effectiveness - reg. | Please refer to this office e-mail dated 09.07.2020 & 13.07.2020 communicating therewith NHAI policy guidelines regarding drainage systems: adequacy & effectiveness for compliance. In continuation to above, it is requested to inspect the site along with Engineers of concerned local panchayat / municipal / corporation bodies duly following the guidelines defined for under construction projects and submit drainage plan to this office, which will be reviewed by the Drainage Expert being identified by PIU / Regional Office. By copy of this letter, concerned local self-government bodies are being requested to depute their Engineer for site inspection. It is requested to arrange joint inspection in consultation with the Engineers of local self-government bodies. The drainage plan / report shall be submitted to this office latest by 31.07.2020. We look forward to your response. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Safety measures during construction | Contractor's Obligations | Conractor informed that they are attending all the locations and further it will be improved. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210302_AE_SPK_569-Minutes of Monthly Progress review meeting Mom – 09.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode. - Minutes of Monthly Progress review meeting Mom — 09 — Reg. | With respect to the above said reference please find enclosed herewith the Minutes of Meeting Numbered as MoM - 09 held on 26.02.2021 The next meeting will be likely on 19 March 2021 at Team Leader office around 11.00 A.M in Kancheepuram. All the concerned are requested to attend with necessary documents. This is for your information and record. Assuring our best services at all times. | FALSE | real_data
Safety measures during construction | Contractor's Obligations | Consultant has asked to improve the safety provisions at site | synthetic_template_20250913 | Consultancy services for Authority's Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode - Minutes of Monthly Progress review meeting Mom — 08 — Reg. | With respect to the above said reference please find enclosed herewith the Minutes of Meeting Numbered as MoM - 08 held on 21.11.2020 The next meeting will be likely on 23.12.2020 at the Consultants office around 11.00 A.M in Kancheepuram. All the concerned are requested to attend with necessary documents. This is for your information and record. Assuring our best services at all times. We look forward to your response. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Safety measures during construction | Contractor's Obligations | Consultant has asked to improve the safety provisions at site | synthetic_template_20250913 | Consultancy services for Authority's Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode - Minutes of Monthly Progress review meeting Mom — 08 — Reg. | With respect to the above said reference please find enclosed herewith the Minutes of Meeting Numbered as MoM - 08 held on 21.11.2020 The next meeting will be likely on 23.12.2020 at the Consultants office around 11.00 A.M in Kancheepuram. All the concerned are requested to attend with necessary documents. This is for your information and record. Assuring our best services at all times. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Safety measures during construction | Contractor's Obligations | Consultant has asked to improve the safety provisions at site | synthetic_template_20250913 | Consultancy services for Authority's Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode - Minutes of Monthly Progress review meeting Mom — 08 — Reg. | With respect to the above said reference please find enclosed herewith the Minutes of Meeting Numbered as MoM - 08 held on 21.11.2020 The next meeting will be likely on 23.12.2020 at the Consultants office around 11.00 A.M in Kancheepuram. All the concerned are requested to attend with necessary documents. This is for your information and record. Assuring our best services at all times. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Safety measures during construction | Contractor's Obligations | Conractor informed that they are attending all the locations and further it will be improved. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode. - Minutes of Monthly Progress review meeting Mom — 09 — Reg. | With respect to the above said reference please find enclosed herewith the Minutes of Meeting Numbered as MoM - 09 held on 26.02.2021 The next meeting will be likely on 19 March 2021 at Team Leader office around 11.00 A.M in Kancheepuram. All the concerned are requested to attend with necessary documents. This is for your information and record. Assuring our best services at all times. We appreciate your cooperation in this regard. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Safety measures during construction | Contractor's Obligations | Conractor informed that they are attending all the locations and further it will be improved. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode. - Minutes of Monthly Progress review meeting Mom — 09 — Reg. | With respect to the above said reference please find enclosed herewith the Minutes of Meeting Numbered as MoM - 09 held on 26.02.2021 The next meeting will be likely on 19 March 2021 at Team Leader office around 11.00 A.M in Kancheepuram. All the concerned are requested to attend with necessary documents. This is for your information and record. Assuring our best services at all times. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Occurrence of cyclones | EoT | An EOT of 10 days can be considered on account of NIVAR and BURVI cyclones | synthetic_template_20250913 | Extension of Time Comprehensive proposal- Reg. | With reference to the captioned subject and from the above mentioned chronology of correspondences, it can be understood that despite of approving an EoT for a period of 112 days for Mile Stone-1, the Contractor is disagreeing with the approval of the Authority and again highlighted the impediments adversely effected the First Mile Stone as well as other Milestone including the Scheduled Completion Date. The Contractor submitted the comprehensive proposal and requested for an extension of time. Please confirm receipt of this correspondence. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Occurrence of cyclones | EoT | An EOT of 10 days can be considered on account of NIVAR and BURVI cyclones | synthetic_template_20250913 | Extension of Time Comprehensive proposal- Reg. | With reference to the captioned subject and from the above mentioned chronology of correspondences, it can be understood that despite of approving an EoT for a period of 112 days for Mile Stone-1, the Contractor is disagreeing with the approval of the Authority and again highlighted the impediments adversely effected the First Mile Stone as well as other Milestone including the Scheduled Completion Date. The Contractor submitted the comprehensive proposal and requested for an extension of time. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Occurrence of cyclones | EoT | An EOT of 10 days can be considered on account of NIVAR and BURVI cyclones | synthetic_template_20250913 | Extension of Time Comprehensive proposal- Reg. | With reference to the captioned subject and from the above mentioned chronology of correspondences, it can be understood that despite of approving an EoT for a period of 112 days for Mile Stone-1, the Contractor is disagreeing with the approval of the Authority and again highlighted the impediments adversely effected the First Mile Stone as well as other Milestone including the Scheduled Completion Date. The Contractor submitted the comprehensive proposal and requested for an extension of time. Thank you for your attention to this matter. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Occurrence of cyclones | EoT | An EOT of 10 days can be considered on account of NIVAR and BURVI cyclones | synthetic_template_20250913 | Extension of Time Comprehensive proposal- Reg. | With reference to the captioned subject and from the above mentioned chronology of correspondences, it can be understood that despite of approving an EoT for a period of 112 days for Mile Stone-1, the Contractor is disagreeing with the approval of the Authority and again highlighted the impediments adversely effected the First Mile Stone as well as other Milestone including the Scheduled Completion Date. The Contractor submitted the comprehensive proposal and requested for an extension of time. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Occurrence of cyclones | EoT | An EOT of 10 days can be considered on account of NIVAR and BURVI cyclones | synthetic_template_20250913 | Extension of Time Comprehensive proposal- Reg. | With reference to the captioned subject and from the above mentioned chronology of correspondences, it can be understood that despite of approving an EoT for a period of 112 days for Mile Stone-1, the Contractor is disagreeing with the approval of the Authority and again highlighted the impediments adversely effected the First Mile Stone as well as other Milestone including the Scheduled Completion Date. The Contractor submitted the comprehensive proposal and requested for an extension of time. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Clearances from Forest Department | Authority's Obligations | From Ch. 90+818 to Ch. 93+380, we have been unable to proceed due to the non-clearance of forest land. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-2/14. 20240624_543_Cont_AE_Request for Relaxation in Schedule H.pdf | Request for Relaxation in Schedule H Due to Non-Availability of Workfront Caused by ROW Issues | We would like to bring to your attention the current status and challenges we are facing in our ongoing project. As per the details mentioned above, we have successfully completed the work in full width from Ch. 94+000 to Ch. 101+000, covering a total of 7 kilometers out of the 37.14 kilometers. However, we are currently encountering significant obstacles that are hindering our progress: 1. Local Farmer Land Dispute: From Ch. 75+400 to Ch. 90+818, there has been an ongoing dispute with local farmers for the past four months. 2. Forest Land Non-Clearance: From Ch. 90+818 to Ch. 93+380, we have been unable to proceed due to the non-clearance of forest land since the appointed date of 15.05.2023. These issues have severely limited our available work front to only 12.28 kilometers out of the total 37.14 kilometers. Within this 12.28 kilometers, 3.80 kilometers are in built-up areas where encroachments have not been removed, further restricting our ability to proceed at full capacity. Consequently, our work in these sections is progressing slowly and in a fragmented manner. Thus, we have only 8.48 kilometers of stretch where we can execute the work with full machinery and manpower. As per Schedule H, Clause No. 1.3, a minimum length of 5 kilometers is required for stage payment eligibility. While we meet this criterion with the available 8.48 kilometers, the overall progress and financial flow of the project are significantly affected due to the aforementioned hindrances. We kindly request your assistance in resolving the land dispute with the local farmers and expediting the clearance of the forest land to ensure our project progresses smoothly. Additionally, we seek a relaxation in the requirements stipulated in Schedule H to support our financial needs. This relaxation will enable us to maintain the project's timeline and ensure timely completion. Thank you for your understanding and cooperation. | FALSE | real_data
Clearances from Forest Department | Authority's Obligations | From Ch. 90+818 to Ch. 93+380, we have been unable to proceed due to the non-clearance of forest land. | synthetic_template_20250913 | Request for Relaxation in Schedule H Due to Non-Availability of Workfront Caused by ROW Issues | We would like to bring to your attention the current status and challenges we are facing in our ongoing project. As per the details mentioned above, we have successfully completed the work in full width from Ch. 94+000 to Ch. 101+000, covering a total of 7 kilometers out of the 37.14 kilometers. However, we are currently encountering significant obstacles that are hindering our progress: 1. Local Farmer Land Dispute: From Ch. 75+400 to Ch. 90+818, there has been an ongoing dispute with local farmers for the past four months. 2. Forest Land Non-Clearance: From Ch. 90+818 to Ch. 93+380, we have been unable to proceed due to the non-clearance of forest land since the appointed date of 15.05.2023. These issues have severely limited our available work front to only 12.28 kilometers out of the total 37.14 kilometers. Within this 12.28 kilometers, 3.80 kilometers are in built-up areas where encroachments have not been removed, further restricting our ability to proceed at full capacity. Consequently, our work in these sections is progressing slowly and in a fragmented manner. Thus, we have only 8.48 kilometers of stretch where we can execute the work with full machinery and manpower. As per Schedule H, Clause No. 1.3, a minimum length of 5 kilometers is required for stage payment eligibility. While we meet this criterion with the available 8.48 kilometers, the overall progress and financial flow of the project are significantly affected due to the aforementioned hindrances. We kindly request your assistance in resolving the land dispute with the local farmers and expediting the clearance of the forest land to ensure our project progresses smoothly. Additionally, we seek a relaxation in the requirements stipulated in Schedule H to support our financial needs. This relaxation will enable us to maintain the project's timeline and ensure timely completion. Thank you for your understanding and cooperation. We appreciate your cooperation in this regard. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Clearances from Forest Department | Authority's Obligations | Clearance from the Forest department. | synthetic_template_20250913 | Notice under clause 10.5.(V)- Accumulated delays till 30" November 2023 - Reg. | We refer to the above letters, wherein we have intimated the Authority about the following issues/Bottlenecks prevailing in the project which are hampering the progress of the works: 1. Handing over of the Balance land. 2. Clearance from the Forest department. 3. GAD Approval from the Railway Authorities. However, the issues are yet to be cleared and hence the same continue to hamper the progress. In this regard, pursuant to clause 10.5.(V) of the EPC Contract agreement, we herewith submit the accumulated delays as on 30" November 2023. SLMI — DMCPL (JV) (A Joint Venture of M/s. SLMI Infra Projects Private Limited & M/s. Dwarakamai Constructions Pvt. Ltd.) H.No.1223, Street No.5, Tarnaka, Secunderabad — 500017. Accumulated delays Till 30-Nov-2023. Description of Delay Events From the above the total accumulated delay as on 30.11.2023 is 303 days. Handing over of ROW/Construction Zone on at least 90% of the total length of the Project Highway Still Continuing. Handing over of the balance Land (to be handed over in 150 days) Still Continuing. Clearance from Forest Department Still Continuing. GAD Approval from Railway Authorities ~ Owing to the above delays, we may not be able to achieve Milestone-II which is due in April’24. It may please be noted that we may run out of work fronts and our resources may become idle as all the available work fronts are already being tackled. In view of the above, we request your office to pursue with the Authority to clear the issues at the earliest and provide hindrance free work fronts over the entire length of the Project Highway. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Clearances from Forest Department | Authority's Obligations | From Ch. 90+818 to Ch. 93+380, we have been unable to proceed due to the non-clearance of forest land. | synthetic_template_20250913 | Request for Relaxation in Schedule H Due to Non-Availability of Workfront Caused by ROW Issues | Please note that We would like to bring to your attention the current status and challenges we are facing in our ongoing project. As per the details mentioned above, we have successfully completed the work in full width from Ch. 94+000 to Ch. 101+000, covering a total of 7 kilometers out of the 37.14 kilometers. However, we are currently encountering significant obstacles that are hindering our progress: 1. Local Farmer Land Dispute: From Ch. 75+400 to Ch. 90+818, there has been an ongoing dispute with local farmers for the past four months. 2. Forest Land Non-Clearance: From Ch. 90+818 to Ch. 93+380, we have been unable to proceed due to the non-clearance of forest land since the appointed date of 15.05.2023. These issues have severely limited our available work front to only 12.28 kilometers out of the total 37.14 kilometers. Within this 12.28 kilometers, 3.80 kilometers are in built-up areas where encroachments have not been removed, further restricting our ability to proceed at full capacity. Consequently, our work in these sections is progressing slowly and in a fragmented manner. Thus, we have only 8.48 kilometers of stretch where we can execute the work with full machinery and manpower. As per Schedule H, Clause No. 1.3, a minimum length of 5 kilometers is required for stage payment eligibility. While we meet this criterion with the available 8.48 kilometers, the overall progress and financial flow of the project are significantly affected due to the aforementioned hindrances. We kindly request your assistance in resolving the land dispute with the local farmers and expediting the clearance of the forest land to ensure our project progresses smoothly. Additionally, we seek a relaxation in the requirements stipulated in Schedule H to support our financial needs. This relaxation will enable us to maintain the project's timeline and ensure timely completion. Thank you for your understanding and cooperation. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Clearances from Forest Department | Authority's Obligations | Clearance from the Forest department. | synthetic_template_20250913 | Notice under clause 10.5.(V)- Accumulated delays till 30" November 2023 - Reg. | It is brought to your attention that We refer to the above letters, wherein we have intimated the Authority about the following issues/Bottlenecks prevailing in the project which are hampering the progress of the works: 1. Handing over of the Balance land. 2. Clearance from the Forest department. 3. GAD Approval from the Railway Authorities. However, the issues are yet to be cleared and hence the same continue to hamper the progress. In this regard, pursuant to clause 10.5.(V) of the EPC Contract agreement, we herewith submit the accumulated delays as on 30" November 2023. SLMI — DMCPL (JV) (A Joint Venture of M/s. SLMI Infra Projects Private Limited & M/s. Dwarakamai Constructions Pvt. Ltd.) H.No.1223, Street No.5, Tarnaka, Secunderabad — 500017. Accumulated delays Till 30-Nov-2023. Description of Delay Events From the above the total accumulated delay as on 30.11.2023 is 303 days. Handing over of ROW/Construction Zone on at least 90% of the total length of the Project Highway Still Continuing. Handing over of the balance Land (to be handed over in 150 days) Still Continuing. Clearance from Forest Department Still Continuing. GAD Approval from Railway Authorities ~ Owing to the above delays, we may not be able to achieve Milestone-II which is due in April’24. It may please be noted that we may run out of work fronts and our resources may become idle as all the available work fronts are already being tackled. In view of the above, we request your office to pursue with the Authority to clear the issues at the earliest and provide hindrance free work fronts over the entire length of the Project Highway. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Clearances from Forest Department | Authority's Obligations | Clearance from the Forest department. | synthetic_template_20250913 | Notice under clause 10.5.(V)- Accumulated delays till 30" November 2023 - Reg. | We refer to the above letters, wherein we have intimated the Authority about the following issues/Bottlenecks prevailing in the project which are hampering the progress of the works: 1. Handing over of the Balance land. 2. Clearance from the Forest department. 3. GAD Approval from the Railway Authorities. However, the issues are yet to be cleared and hence the same continue to hamper the progress. In this regard, pursuant to clause 10.5.(V) of the EPC Contract agreement, we herewith submit the accumulated delays as on 30" November 2023. SLMI — DMCPL (JV) (A Joint Venture of M/s. SLMI Infra Projects Private Limited & M/s. Dwarakamai Constructions Pvt. Ltd.) H.No.1223, Street No.5, Tarnaka, Secunderabad — 500017. Accumulated delays Till 30-Nov-2023. Description of Delay Events From the above the total accumulated delay as on 30.11.2023 is 303 days. Handing over of ROW/Construction Zone on at least 90% of the total length of the Project Highway Still Continuing. Handing over of the balance Land (to be handed over in 150 days) Still Continuing. Clearance from Forest Department Still Continuing. GAD Approval from Railway Authorities ~ Owing to the above delays, we may not be able to achieve Milestone-II which is due in April’24. It may please be noted that we may run out of work fronts and our resources may become idle as all the available work fronts are already being tackled. In view of the above, we request your office to pursue with the Authority to clear the issues at the earliest and provide hindrance free work fronts over the entire length of the Project Highway. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Construction work methodologies | Contractor's Obligations | we are here with submitting the Method Statement for Paver Blocks & Foot Path Chequered Cement Concrete Tiles. | synthetic_template_20250913 | Submission of Method Statement- Reg. | With reference to above cited subject, we are here with submitting the Method Statement for Paver Blocks & Foot Path Chequered Cement Concrete Tiles. We request for your kind perusal & necessary approval please. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Construction work methodologies | Contractor's Obligations | we are here with submitting the Method Statement for Paver Blocks & Foot Path Chequered Cement Concrete Tiles. | synthetic_template_20250913 | Submission of Method Statement- Reg. | With reference to above cited subject, we are here with submitting the Method Statement for Paver Blocks & Foot Path Chequered Cement Concrete Tiles. We request for your kind perusal & necessary approval please. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Construction work methodologies | Contractor's Obligations | we are here with submitting the Method Statement for Paver Blocks & Foot Path Chequered Cement Concrete Tiles. | synthetic_template_20250913 | Submission of Method Statement- Reg. | With reference to above cited subject, we are here with submitting the Method Statement for Paver Blocks & Foot Path Chequered Cement Concrete Tiles. We request for your kind perusal & necessary approval please. We await your further instructions. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Construction work methodologies | Contractor's Obligations | we are here with submitting the Method Statement for Paver Blocks & Foot Path Chequered Cement Concrete Tiles. | synthetic_template_20250913 | Submission of Method Statement- Reg. | With reference to above cited subject, we are here with submitting the Method Statement for Paver Blocks & Foot Path Chequered Cement Concrete Tiles. We request for your kind perusal & necessary approval please. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Construction work methodologies | Contractor's Obligations | we are here with submitting the Method Statement for Paver Blocks & Foot Path Chequered Cement Concrete Tiles. | synthetic_template_20250913 | Submission of Method Statement- Reg. | With reference to above cited subject, we are here with submitting the Method Statement for Paver Blocks & Foot Path Chequered Cement Concrete Tiles. We request for your kind perusal & necessary approval please. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Obstruction/Halt of works by local farmers/ Land owners | Authority's Obligations | From Ch. 75+400 to Ch. 90+818, there has been an ongoing dispute with local farmers for the past four months. | synthetic_template_20250913 | Request for Relaxation in Schedule H Due to Non-Availability of Workfront Caused by ROW Issues | This is to notify you that We would like to bring to your attention the current status and challenges we are facing in our ongoing project. As per the details mentioned above, we have successfully completed the work in full width from Ch. 94+000 to Ch. 101+000, covering a total of 7 kilometers out of the 37.14 kilometers. However, we are currently encountering significant obstacles that are hindering our progress: 1. Local Farmer Land Dispute: From Ch. 75+400 to Ch. 90+818, there has been an ongoing dispute with local farmers for the past four months. 2. Forest Land Non-Clearance: From Ch. 90+818 to Ch. 93+380, we have been unable to proceed due to the non-clearance of forest land since the appointed date of 15.05.2023. These issues have severely limited our available work front to only 12.28 kilometers out of the total 37.14 kilometers. Within this 12.28 kilometers, 3.80 kilometers are in built-up areas where encroachments have not been removed, further restricting our ability to proceed at full capacity. Consequently, our work in these sections is progressing slowly and in a fragmented manner. Thus, we have only 8.48 kilometers of stretch where we can execute the work with full machinery and manpower. As per Schedule H, Clause No. 1.3, a minimum length of 5 kilometers is required for stage payment eligibility. While we meet this criterion with the available 8.48 kilometers, the overall progress and financial flow of the project are significantly affected due to the aforementioned hindrances. We kindly request your assistance in resolving the land dispute with the local farmers and expediting the clearance of the forest land to ensure our project progresses smoothly. Additionally, we seek a relaxation in the requirements stipulated in Schedule H to support our financial needs. This relaxation will enable us to maintain the project's timeline and ensure timely completion. Thank you for your understanding and cooperation. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Obstruction/Halt of works by local farmers/ Land owners | Authority's Obligations | From Ch. 75+400 to Ch. 90+818, there has been an ongoing dispute with local farmers for the past four months. | synthetic_template_20250913 | Request for Relaxation in Schedule H Due to Non-Availability of Workfront Caused by ROW Issues | We would like to bring to your attention the current status and challenges we are facing in our ongoing project. As per the details mentioned above, we have successfully completed the work in full width from Ch. 94+000 to Ch. 101+000, covering a total of 7 kilometers out of the 37.14 kilometers. However, we are currently encountering significant obstacles that are hindering our progress: 1. Local Farmer Land Dispute: From Ch. 75+400 to Ch. 90+818, there has been an ongoing dispute with local farmers for the past four months. 2. Forest Land Non-Clearance: From Ch. 90+818 to Ch. 93+380, we have been unable to proceed due to the non-clearance of forest land since the appointed date of 15.05.2023. These issues have severely limited our available work front to only 12.28 kilometers out of the total 37.14 kilometers. Within this 12.28 kilometers, 3.80 kilometers are in built-up areas where encroachments have not been removed, further restricting our ability to proceed at full capacity. Consequently, our work in these sections is progressing slowly and in a fragmented manner. Thus, we have only 8.48 kilometers of stretch where we can execute the work with full machinery and manpower. As per Schedule H, Clause No. 1.3, a minimum length of 5 kilometers is required for stage payment eligibility. While we meet this criterion with the available 8.48 kilometers, the overall progress and financial flow of the project are significantly affected due to the aforementioned hindrances. We kindly request your assistance in resolving the land dispute with the local farmers and expediting the clearance of the forest land to ensure our project progresses smoothly. Additionally, we seek a relaxation in the requirements stipulated in Schedule H to support our financial needs. This relaxation will enable us to maintain the project's timeline and ensure timely completion. Thank you for your understanding and cooperation. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Obstruction/Halt of works by local farmers/ Land owners | Authority's Obligations | From Ch. 75+400 to Ch. 90+818, there has been an ongoing dispute with local farmers for the past four months. | synthetic_template_20250913 | Request for Relaxation in Schedule H Due to Non-Availability of Workfront Caused by ROW Issues | We would like to inform you that We would like to bring to your attention the current status and challenges we are facing in our ongoing project. As per the details mentioned above, we have successfully completed the work in full width from Ch. 94+000 to Ch. 101+000, covering a total of 7 kilometers out of the 37.14 kilometers. However, we are currently encountering significant obstacles that are hindering our progress: 1. Local Farmer Land Dispute: From Ch. 75+400 to Ch. 90+818, there has been an ongoing dispute with local farmers for the past four months. 2. Forest Land Non-Clearance: From Ch. 90+818 to Ch. 93+380, we have been unable to proceed due to the non-clearance of forest land since the appointed date of 15.05.2023. These issues have severely limited our available work front to only 12.28 kilometers out of the total 37.14 kilometers. Within this 12.28 kilometers, 3.80 kilometers are in built-up areas where encroachments have not been removed, further restricting our ability to proceed at full capacity. Consequently, our work in these sections is progressing slowly and in a fragmented manner. Thus, we have only 8.48 kilometers of stretch where we can execute the work with full machinery and manpower. As per Schedule H, Clause No. 1.3, a minimum length of 5 kilometers is required for stage payment eligibility. While we meet this criterion with the available 8.48 kilometers, the overall progress and financial flow of the project are significantly affected due to the aforementioned hindrances. We kindly request your assistance in resolving the land dispute with the local farmers and expediting the clearance of the forest land to ensure our project progresses smoothly. Additionally, we seek a relaxation in the requirements stipulated in Schedule H to support our financial needs. This relaxation will enable us to maintain the project's timeline and ensure timely completion. Thank you for your understanding and cooperation. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Obstruction/Halt of works by local farmers/ Land owners | Authority's Obligations | From Ch. 75+400 to Ch. 90+818, there has been an ongoing dispute with local farmers for the past four months. | synthetic_template_20250913 | Request for Relaxation in Schedule H Due to Non-Availability of Workfront Caused by ROW Issues | We would like to inform you that We would like to bring to your attention the current status and challenges we are facing in our ongoing project. As per the details mentioned above, we have successfully completed the work in full width from Ch. 94+000 to Ch. 101+000, covering a total of 7 kilometers out of the 37.14 kilometers. However, we are currently encountering significant obstacles that are hindering our progress: 1. Local Farmer Land Dispute: From Ch. 75+400 to Ch. 90+818, there has been an ongoing dispute with local farmers for the past four months. 2. Forest Land Non-Clearance: From Ch. 90+818 to Ch. 93+380, we have been unable to proceed due to the non-clearance of forest land since the appointed date of 15.05.2023. These issues have severely limited our available work front to only 12.28 kilometers out of the total 37.14 kilometers. Within this 12.28 kilometers, 3.80 kilometers are in built-up areas where encroachments have not been removed, further restricting our ability to proceed at full capacity. Consequently, our work in these sections is progressing slowly and in a fragmented manner. Thus, we have only 8.48 kilometers of stretch where we can execute the work with full machinery and manpower. As per Schedule H, Clause No. 1.3, a minimum length of 5 kilometers is required for stage payment eligibility. While we meet this criterion with the available 8.48 kilometers, the overall progress and financial flow of the project are significantly affected due to the aforementioned hindrances. We kindly request your assistance in resolving the land dispute with the local farmers and expediting the clearance of the forest land to ensure our project progresses smoothly. Additionally, we seek a relaxation in the requirements stipulated in Schedule H to support our financial needs. This relaxation will enable us to maintain the project's timeline and ensure timely completion. Thank you for your understanding and cooperation. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Obstruction/Halt of works by local farmers/ Land owners | Authority's Obligations | From Ch. 75+400 to Ch. 90+818, there has been an ongoing dispute with local farmers for the past four months. | synthetic_template_20250913 | Request for Relaxation in Schedule H Due to Non-Availability of Workfront Caused by ROW Issues | We would like to bring to your attention the current status and challenges we are facing in our ongoing project. As per the details mentioned above, we have successfully completed the work in full width from Ch. 94+000 to Ch. 101+000, covering a total of 7 kilometers out of the 37.14 kilometers. However, we are currently encountering significant obstacles that are hindering our progress: 1. Local Farmer Land Dispute: From Ch. 75+400 to Ch. 90+818, there has been an ongoing dispute with local farmers for the past four months. 2. Forest Land Non-Clearance: From Ch. 90+818 to Ch. 93+380, we have been unable to proceed due to the non-clearance of forest land since the appointed date of 15.05.2023. These issues have severely limited our available work front to only 12.28 kilometers out of the total 37.14 kilometers. Within this 12.28 kilometers, 3.80 kilometers are in built-up areas where encroachments have not been removed, further restricting our ability to proceed at full capacity. Consequently, our work in these sections is progressing slowly and in a fragmented manner. Thus, we have only 8.48 kilometers of stretch where we can execute the work with full machinery and manpower. As per Schedule H, Clause No. 1.3, a minimum length of 5 kilometers is required for stage payment eligibility. While we meet this criterion with the available 8.48 kilometers, the overall progress and financial flow of the project are significantly affected due to the aforementioned hindrances. We kindly request your assistance in resolving the land dispute with the local farmers and expediting the clearance of the forest land to ensure our project progresses smoothly. Additionally, we seek a relaxation in the requirements stipulated in Schedule H to support our financial needs. This relaxation will enable us to maintain the project's timeline and ensure timely completion. Thank you for your understanding and cooperation. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Relaxation for schedule-H payment criteria | Payments | Additionally, we seek a relaxation in the requirements stipulated in Schedule H to support our financial needs. | synthetic_template_20250913 | Request for Relaxation in Schedule H Due to Non-Availability of Workfront Caused by ROW Issues | Please note that We would like to bring to your attention the current status and challenges we are facing in our ongoing project. As per the details mentioned above, we have successfully completed the work in full width from Ch. 94+000 to Ch. 101+000, covering a total of 7 kilometers out of the 37.14 kilometers. However, we are currently encountering significant obstacles that are hindering our progress: 1. Local Farmer Land Dispute: From Ch. 75+400 to Ch. 90+818, there has been an ongoing dispute with local farmers for the past four months. 2. Forest Land Non-Clearance: From Ch. 90+818 to Ch. 93+380, we have been unable to proceed due to the non-clearance of forest land since the appointed date of 15.05.2023. These issues have severely limited our available work front to only 12.28 kilometers out of the total 37.14 kilometers. Within this 12.28 kilometers, 3.80 kilometers are in built-up areas where encroachments have not been removed, further restricting our ability to proceed at full capacity. Consequently, our work in these sections is progressing slowly and in a fragmented manner. Thus, we have only 8.48 kilometers of stretch where we can execute the work with full machinery and manpower. As per Schedule H, Clause No. 1.3, a minimum length of 5 kilometers is required for stage payment eligibility. While we meet this criterion with the available 8.48 kilometers, the overall progress and financial flow of the project are significantly affected due to the aforementioned hindrances. We kindly request your assistance in resolving the land dispute with the local farmers and expediting the clearance of the forest land to ensure our project progresses smoothly. Additionally, we seek a relaxation in the requirements stipulated in Schedule H to support our financial needs. This relaxation will enable us to maintain the project's timeline and ensure timely completion. Thank you for your understanding and cooperation. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Relaxation for schedule-H payment criteria | Payments | Additionally, we seek a relaxation in the requirements stipulated in Schedule H to support our financial needs. | synthetic_template_20250913 | Request for Relaxation in Schedule H Due to Non-Availability of Workfront Caused by ROW Issues | We would like to inform you that We would like to bring to your attention the current status and challenges we are facing in our ongoing project. As per the details mentioned above, we have successfully completed the work in full width from Ch. 94+000 to Ch. 101+000, covering a total of 7 kilometers out of the 37.14 kilometers. However, we are currently encountering significant obstacles that are hindering our progress: 1. Local Farmer Land Dispute: From Ch. 75+400 to Ch. 90+818, there has been an ongoing dispute with local farmers for the past four months. 2. Forest Land Non-Clearance: From Ch. 90+818 to Ch. 93+380, we have been unable to proceed due to the non-clearance of forest land since the appointed date of 15.05.2023. These issues have severely limited our available work front to only 12.28 kilometers out of the total 37.14 kilometers. Within this 12.28 kilometers, 3.80 kilometers are in built-up areas where encroachments have not been removed, further restricting our ability to proceed at full capacity. Consequently, our work in these sections is progressing slowly and in a fragmented manner. Thus, we have only 8.48 kilometers of stretch where we can execute the work with full machinery and manpower. As per Schedule H, Clause No. 1.3, a minimum length of 5 kilometers is required for stage payment eligibility. While we meet this criterion with the available 8.48 kilometers, the overall progress and financial flow of the project are significantly affected due to the aforementioned hindrances. We kindly request your assistance in resolving the land dispute with the local farmers and expediting the clearance of the forest land to ensure our project progresses smoothly. Additionally, we seek a relaxation in the requirements stipulated in Schedule H to support our financial needs. This relaxation will enable us to maintain the project's timeline and ensure timely completion. Thank you for your understanding and cooperation. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Relaxation for schedule-H payment criteria | Payments | Additionally, we seek a relaxation in the requirements stipulated in Schedule H to support our financial needs. | synthetic_template_20250913 | Request for Relaxation in Schedule H Due to Non-Availability of Workfront Caused by ROW Issues | We would like to bring to your attention the current status and challenges we are facing in our ongoing project. As per the details mentioned above, we have successfully completed the work in full width from Ch. 94+000 to Ch. 101+000, covering a total of 7 kilometers out of the 37.14 kilometers. However, we are currently encountering significant obstacles that are hindering our progress: 1. Local Farmer Land Dispute: From Ch. 75+400 to Ch. 90+818, there has been an ongoing dispute with local farmers for the past four months. 2. Forest Land Non-Clearance: From Ch. 90+818 to Ch. 93+380, we have been unable to proceed due to the non-clearance of forest land since the appointed date of 15.05.2023. These issues have severely limited our available work front to only 12.28 kilometers out of the total 37.14 kilometers. Within this 12.28 kilometers, 3.80 kilometers are in built-up areas where encroachments have not been removed, further restricting our ability to proceed at full capacity. Consequently, our work in these sections is progressing slowly and in a fragmented manner. Thus, we have only 8.48 kilometers of stretch where we can execute the work with full machinery and manpower. As per Schedule H, Clause No. 1.3, a minimum length of 5 kilometers is required for stage payment eligibility. While we meet this criterion with the available 8.48 kilometers, the overall progress and financial flow of the project are significantly affected due to the aforementioned hindrances. We kindly request your assistance in resolving the land dispute with the local farmers and expediting the clearance of the forest land to ensure our project progresses smoothly. Additionally, we seek a relaxation in the requirements stipulated in Schedule H to support our financial needs. This relaxation will enable us to maintain the project's timeline and ensure timely completion. Thank you for your understanding and cooperation. We await your further instructions. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Relaxation for schedule-H payment criteria | Payments | Additionally, we seek a relaxation in the requirements stipulated in Schedule H to support our financial needs. | synthetic_template_20250913 | Request for Relaxation in Schedule H Due to Non-Availability of Workfront Caused by ROW Issues | We would like to bring to your attention the current status and challenges we are facing in our ongoing project. As per the details mentioned above, we have successfully completed the work in full width from Ch. 94+000 to Ch. 101+000, covering a total of 7 kilometers out of the 37.14 kilometers. However, we are currently encountering significant obstacles that are hindering our progress: 1. Local Farmer Land Dispute: From Ch. 75+400 to Ch. 90+818, there has been an ongoing dispute with local farmers for the past four months. 2. Forest Land Non-Clearance: From Ch. 90+818 to Ch. 93+380, we have been unable to proceed due to the non-clearance of forest land since the appointed date of 15.05.2023. These issues have severely limited our available work front to only 12.28 kilometers out of the total 37.14 kilometers. Within this 12.28 kilometers, 3.80 kilometers are in built-up areas where encroachments have not been removed, further restricting our ability to proceed at full capacity. Consequently, our work in these sections is progressing slowly and in a fragmented manner. Thus, we have only 8.48 kilometers of stretch where we can execute the work with full machinery and manpower. As per Schedule H, Clause No. 1.3, a minimum length of 5 kilometers is required for stage payment eligibility. While we meet this criterion with the available 8.48 kilometers, the overall progress and financial flow of the project are significantly affected due to the aforementioned hindrances. We kindly request your assistance in resolving the land dispute with the local farmers and expediting the clearance of the forest land to ensure our project progresses smoothly. Additionally, we seek a relaxation in the requirements stipulated in Schedule H to support our financial needs. This relaxation will enable us to maintain the project's timeline and ensure timely completion. Thank you for your understanding and cooperation. We appreciate your cooperation in this regard. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Relaxation for schedule-H payment criteria | Payments | Additionally, we seek a relaxation in the requirements stipulated in Schedule H to support our financial needs. | synthetic_template_20250913 | Request for Relaxation in Schedule H Due to Non-Availability of Workfront Caused by ROW Issues | We would like to bring to your attention the current status and challenges we are facing in our ongoing project. As per the details mentioned above, we have successfully completed the work in full width from Ch. 94+000 to Ch. 101+000, covering a total of 7 kilometers out of the 37.14 kilometers. However, we are currently encountering significant obstacles that are hindering our progress: 1. Local Farmer Land Dispute: From Ch. 75+400 to Ch. 90+818, there has been an ongoing dispute with local farmers for the past four months. 2. Forest Land Non-Clearance: From Ch. 90+818 to Ch. 93+380, we have been unable to proceed due to the non-clearance of forest land since the appointed date of 15.05.2023. These issues have severely limited our available work front to only 12.28 kilometers out of the total 37.14 kilometers. Within this 12.28 kilometers, 3.80 kilometers are in built-up areas where encroachments have not been removed, further restricting our ability to proceed at full capacity. Consequently, our work in these sections is progressing slowly and in a fragmented manner. Thus, we have only 8.48 kilometers of stretch where we can execute the work with full machinery and manpower. As per Schedule H, Clause No. 1.3, a minimum length of 5 kilometers is required for stage payment eligibility. While we meet this criterion with the available 8.48 kilometers, the overall progress and financial flow of the project are significantly affected due to the aforementioned hindrances. We kindly request your assistance in resolving the land dispute with the local farmers and expediting the clearance of the forest land to ensure our project progresses smoothly. Additionally, we seek a relaxation in the requirements stipulated in Schedule H to support our financial needs. This relaxation will enable us to maintain the project's timeline and ensure timely completion. Thank you for your understanding and cooperation. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Trial patch | Contractor's Obligations | we are initiating a PQC trial patch at Chainage 94+090 to 94+120. | synthetic_template_20250913 | Intimation for Laying of PQC Trail Patch | With Reference to above mentioned subject and ref letter no.2, we would like to inform you that we have now hereby submitting our revised plan for the location of the PQC trial patch at Chainage 94+090 to 94+120 LHS Side. After completing the PQC trial patch at the specified Chainage and upon receiving a satisfactory result, we will commence the PQC laying from Chainage 94+090 LHS side towards end of project Ch. 101+140km. We would further like to inform you that we are initiating a PQC trial patch at Chainage 94+090 to 94+120. We are hereby giving our Declaration that the PQC trial patch is at our own risk and cost. In the event that the results of the PQC trial patch are deemed unsatisfactory, we will dismantle the entire length of the patch, and all materials will be promptly removed from the site. This is for your kind information and record please. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Trial patch | Contractor's Obligations | we are initiating a PQC trial patch at Chainage 94+090 to 94+120. | synthetic_template_20250913 | Intimation for Laying of PQC Trail Patch | With Reference to above mentioned subject and ref letter no.2, we would like to inform you that we have now hereby submitting our revised plan for the location of the PQC trial patch at Chainage 94+090 to 94+120 LHS Side. After completing the PQC trial patch at the specified Chainage and upon receiving a satisfactory result, we will commence the PQC laying from Chainage 94+090 LHS side towards end of project Ch. 101+140km. We would further like to inform you that we are initiating a PQC trial patch at Chainage 94+090 to 94+120. We are hereby giving our Declaration that the PQC trial patch is at our own risk and cost. In the event that the results of the PQC trial patch are deemed unsatisfactory, we will dismantle the entire length of the patch, and all materials will be promptly removed from the site. This is for your kind information and record please. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Trial patch | Contractor's Obligations | we are initiating a PQC trial patch at Chainage 94+090 to 94+120. | synthetic_template_20250913 | Intimation for Laying of PQC Trail Patch | With Reference to above mentioned subject and ref letter no.2, we would like to inform you that we have now hereby submitting our revised plan for the location of the PQC trial patch at Chainage 94+090 to 94+120 LHS Side. After completing the PQC trial patch at the specified Chainage and upon receiving a satisfactory result, we will commence the PQC laying from Chainage 94+090 LHS side towards end of project Ch. 101+140km. We would further like to inform you that we are initiating a PQC trial patch at Chainage 94+090 to 94+120. We are hereby giving our Declaration that the PQC trial patch is at our own risk and cost. In the event that the results of the PQC trial patch are deemed unsatisfactory, we will dismantle the entire length of the patch, and all materials will be promptly removed from the site. This is for your kind information and record please. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Trial patch | Contractor's Obligations | we are initiating a PQC trial patch at Chainage 94+090 to 94+120. | synthetic_template_20250913 | Intimation for Laying of PQC Trail Patch | With Reference to above mentioned subject and ref letter no.2, we would like to inform you that we have now hereby submitting our revised plan for the location of the PQC trial patch at Chainage 94+090 to 94+120 LHS Side. After completing the PQC trial patch at the specified Chainage and upon receiving a satisfactory result, we will commence the PQC laying from Chainage 94+090 LHS side towards end of project Ch. 101+140km. We would further like to inform you that we are initiating a PQC trial patch at Chainage 94+090 to 94+120. We are hereby giving our Declaration that the PQC trial patch is at our own risk and cost. In the event that the results of the PQC trial patch are deemed unsatisfactory, we will dismantle the entire length of the patch, and all materials will be promptly removed from the site. This is for your kind information and record please. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Trial patch | Contractor's Obligations | we are initiating a PQC trial patch at Chainage 94+090 to 94+120. | synthetic_template_20250913 | Intimation for Laying of PQC Trail Patch | With Reference to above mentioned subject and ref letter no.2, we would like to inform you that we have now hereby submitting our revised plan for the location of the PQC trial patch at Chainage 94+090 to 94+120 LHS Side. After completing the PQC trial patch at the specified Chainage and upon receiving a satisfactory result, we will commence the PQC laying from Chainage 94+090 LHS side towards end of project Ch. 101+140km. We would further like to inform you that we are initiating a PQC trial patch at Chainage 94+090 to 94+120. We are hereby giving our Declaration that the PQC trial patch is at our own risk and cost. In the event that the results of the PQC trial patch are deemed unsatisfactory, we will dismantle the entire length of the patch, and all materials will be promptly removed from the site. This is for your kind information and record please. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Black spots | Change of Scope; EoT | Providing road safety interventions at identified blackspots on ORR to Medak road section of NH-765D from 0+000 to 62+920. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-2/16. 20240625_240_AE_Cont_Road Safety Interventions at Identified Blackspots on ORR to Medak section.pdf | Rehabilitation and Upgradation of Hyderabad Outer Ring Road to Medak section of NH-765D from existing Km 15.970 (Design Km 0.00) to existing Km 78.700 (Design Km 62.92) to Two Lane with paved shoulders / Four Lane in the State of Telangana on EPC Mode. | With reference to 4" cited (copy enclosed) you are hereby notified to undertake the short term road safety measures at identified Black spots on ORR Hyderabad to Medak Road Section of NH-765D from km 0/000 to Km 62/920 in the State of Telangana and submit the compliance report immediately. | FALSE | real_data
Black spots | EoT | Providing road safety interventions at identified blackspots on ORR to Medak road section of NH-765D from 0+000 to 62+920. | synthetic_template_20250913 | Rehabilitation and Upgradation of Hyderabad Outer Ring Road to Medak section of NH-765D from existing Km 15.970 (Design Km 0.00) to existing Km 78.700 (Design Km 62.92) to Two Lane with paved shoulders / Four Lane in the State of Telangana on EPC Mode. | Please note that With reference to 4" cited (copy enclosed) you are hereby notified to undertake the short term road safety measures at identified Black spots on ORR Hyderabad to Medak Road Section of NH-765D from km 0/000 to Km 62/920 in the State of Telangana and submit the compliance report immediately. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Black spots | Change of Scope | Providing road safety interventions at identified blackspots on ORR to Medak road section of NH-765D from 0+000 to 62+920. | synthetic_template_20250913 | Rehabilitation and Upgradation of Hyderabad Outer Ring Road to Medak section of NH-765D from existing Km 15.970 (Design Km 0.00) to existing Km 78.700 (Design Km 62.92) to Two Lane with paved shoulders / Four Lane in the State of Telangana on EPC Mode. | With reference to 4" cited (copy enclosed) you are hereby notified to undertake the short term road safety measures at identified Black spots on ORR Hyderabad to Medak Road Section of NH-765D from km 0/000 to Km 62/920 in the State of Telangana and submit the compliance report immediately. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Black spots | Change of Scope | Providing road safety interventions at identified blackspots on ORR to Medak road section of NH-765D from 0+000 to 62+920. | synthetic_template_20250913 | Rehabilitation and Upgradation of Hyderabad Outer Ring Road to Medak section of NH-765D from existing Km 15.970 (Design Km 0.00) to existing Km 78.700 (Design Km 62.92) to Two Lane with paved shoulders / Four Lane in the State of Telangana on EPC Mode. | With reference to 4" cited (copy enclosed) you are hereby notified to undertake the short term road safety measures at identified Black spots on ORR Hyderabad to Medak Road Section of NH-765D from km 0/000 to Km 62/920 in the State of Telangana and submit the compliance report immediately. We await your further instructions. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Source / vendor / Manufacturer / supplier credential submission and approval | Contractor's Obligations | we are here with submitting the Profile and credentials of lndian Oil Corporation LTD (IOCL) for obtaining Source approval. | synthetic_template_20250913 | Submission of Profile and Credentials for Source approval- Reg. | With reference to above cited subject, we are here with submitting the Profile and credentials of Indian Oil Corporation LTD (IOCL) for obtaining Source approval to procure Bitumen for execution of the Bituminous works in the project. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Source / vendor / Manufacturer / supplier credential submission and approval | Contractor's Obligations | we are here with submitting the Profile and credentials of lndian Oil Corporation LTD (IOCL) for obtaining Source approval. | synthetic_template_20250913 | Submission of Profile and Credentials for Source approval- Reg. | With reference to above cited subject, we are here with submitting the Profile and credentials of Indian Oil Corporation LTD (IOCL) for obtaining Source approval to procure Bitumen for execution of the Bituminous works in the project. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Source / vendor / Manufacturer / supplier credential submission and approval | Contractor's Obligations | we are here with submitting the Profile and credentials of lndian Oil Corporation LTD (IOCL) for obtaining Source approval. | synthetic_template_20250913 | Submission of Profile and Credentials for Source approval- Reg. | With reference to above cited subject, we are here with submitting the Profile and credentials of Indian Oil Corporation LTD (IOCL) for obtaining Source approval to procure Bitumen for execution of the Bituminous works in the project. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Source / vendor / Manufacturer / supplier credential submission and approval | Contractor's Obligations | we are here with submitting the Profile and credentials of lndian Oil Corporation LTD (IOCL) for obtaining Source approval. | synthetic_template_20250913 | Submission of Profile and Credentials for Source approval- Reg. | With reference to above cited subject, we are here with submitting the Profile and credentials of Indian Oil Corporation LTD (IOCL) for obtaining Source approval to procure Bitumen for execution of the Bituminous works in the project. Please confirm receipt of this correspondence. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Source / vendor / Manufacturer / supplier credential submission and approval | Contractor's Obligations | we are here with submitting the Profile and credentials of lndian Oil Corporation LTD (IOCL) for obtaining Source approval. | synthetic_template_20250913 | Submission of Profile and Credentials for Source approval- Reg. | Kindly be informed that With reference to above cited subject, we are here with submitting the Profile and credentials of Indian Oil Corporation LTD (IOCL) for obtaining Source approval to procure Bitumen for execution of the Bituminous works in the project. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Submission of Stage Payment Application | Authority's Obligations | we are herewith submitting 3 hard copies of the "lnterim Payment Certificate (lPC) -8. | synthetic_template_20250913 | Submission of Interim Payment Certificate (IPC) -8 - Reg. | Kindly be informed that With reference to the above subject, pursuant to the clause No. 19.4 of the article.19 of the Contract Agreement, we are herewith submitting 3 hard copies of the “Interim Payment Certificate (IPC) -8” for the period of 1** October 2023 to 2" November 2023 for an amount of Gross Value of work done 20,57,28,679 /- (Rupees Twenty Crores Fifty Seven Lakhs Twenty Eight Thousand Six Hundred and Seventy Nine only) with price adjustment value 20,59,961 /- (Rupees Twenty Lakhs Fifty Nine Thousand Nine Hundred and Sixty One Only) and the Grand total is 20,77,88,640 /- (Rupees Twenty Crores Seventy Seven Lakhs Eighty Eight Thousand Six Hundred and Forty Only) for your kind perusal and necessary recommendation please. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Submission of Stage Payment Application | Authority's Obligations | we are herewith submitting 3 hard copies of the "lnterim Payment Certificate (lPC) -8. | synthetic_template_20250913 | Submission of Interim Payment Certificate (IPC) -8 - Reg. | We would like to inform you that With reference to the above subject, pursuant to the clause No. 19.4 of the article.19 of the Contract Agreement, we are herewith submitting 3 hard copies of the “Interim Payment Certificate (IPC) -8” for the period of 1** October 2023 to 2" November 2023 for an amount of Gross Value of work done 20,57,28,679 /- (Rupees Twenty Crores Fifty Seven Lakhs Twenty Eight Thousand Six Hundred and Seventy Nine only) with price adjustment value 20,59,961 /- (Rupees Twenty Lakhs Fifty Nine Thousand Nine Hundred and Sixty One Only) and the Grand total is 20,77,88,640 /- (Rupees Twenty Crores Seventy Seven Lakhs Eighty Eight Thousand Six Hundred and Forty Only) for your kind perusal and necessary recommendation please. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Submission of Stage Payment Application | Payments | we are herewith submitting 3 hard copies of the "lnterim Payment Certificate (lPC) -8. | synthetic_template_20250913 | Submission of Interim Payment Certificate (IPC) -8 - Reg. | We would like to inform you that With reference to the above subject, pursuant to the clause No. 19.4 of the article.19 of the Contract Agreement, we are herewith submitting 3 hard copies of the “Interim Payment Certificate (IPC) -8” for the period of 1** October 2023 to 2" November 2023 for an amount of Gross Value of work done 20,57,28,679 /- (Rupees Twenty Crores Fifty Seven Lakhs Twenty Eight Thousand Six Hundred and Seventy Nine only) with price adjustment value 20,59,961 /- (Rupees Twenty Lakhs Fifty Nine Thousand Nine Hundred and Sixty One Only) and the Grand total is 20,77,88,640 /- (Rupees Twenty Crores Seventy Seven Lakhs Eighty Eight Thousand Six Hundred and Forty Only) for your kind perusal and necessary recommendation please. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Submission of Stage Payment Application | Payments | we are herewith submitting 3 hard copies of the "lnterim Payment Certificate (lPC) -8. | synthetic_template_20250913 | Submission of Interim Payment Certificate (IPC) -8 - Reg. | We hereby confirm that With reference to the above subject, pursuant to the clause No. 19.4 of the article.19 of the Contract Agreement, we are herewith submitting 3 hard copies of the “Interim Payment Certificate (IPC) -8” for the period of 1** October 2023 to 2" November 2023 for an amount of Gross Value of work done 20,57,28,679 /- (Rupees Twenty Crores Fifty Seven Lakhs Twenty Eight Thousand Six Hundred and Seventy Nine only) with price adjustment value 20,59,961 /- (Rupees Twenty Lakhs Fifty Nine Thousand Nine Hundred and Sixty One Only) and the Grand total is 20,77,88,640 /- (Rupees Twenty Crores Seventy Seven Lakhs Eighty Eight Thousand Six Hundred and Forty Only) for your kind perusal and necessary recommendation please. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Submission of Stage Payment Application | Contractor's Obligations | we are herewith submitting 3 hard copies of the "lnterim Payment Certificate (lPC) -8. | synthetic_template_20250913 | Submission of Interim Payment Certificate (IPC) -8 - Reg. | With reference to the above subject, pursuant to the clause No. 19.4 of the article.19 of the Contract Agreement, we are herewith submitting 3 hard copies of the “Interim Payment Certificate (IPC) -8” for the period of 1** October 2023 to 2" November 2023 for an amount of Gross Value of work done 20,57,28,679 /- (Rupees Twenty Crores Fifty Seven Lakhs Twenty Eight Thousand Six Hundred and Seventy Nine only) with price adjustment value 20,59,961 /- (Rupees Twenty Lakhs Fifty Nine Thousand Nine Hundred and Sixty One Only) and the Grand total is 20,77,88,640 /- (Rupees Twenty Crores Seventy Seven Lakhs Eighty Eight Thousand Six Hundred and Forty Only) for your kind perusal and necessary recommendation please. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0
Submission of Stage Payment Application | Contractor's Obligations | we are herewith submitting 3 hard copies of the "lnterim Payment Certificate (lPC) -8. | synthetic_template_20250913 | Submission of Interim Payment Certificate (IPC) -8 - Reg. | Please note that With reference to the above subject, pursuant to the clause No. 19.4 of the article.19 of the Contract Agreement, we are herewith submitting 3 hard copies of the “Interim Payment Certificate (IPC) -8” for the period of 1** October 2023 to 2" November 2023 for an amount of Gross Value of work done 20,57,28,679 /- (Rupees Twenty Crores Fifty Seven Lakhs Twenty Eight Thousand Six Hundred and Seventy Nine only) with price adjustment value 20,59,961 /- (Rupees Twenty Lakhs Fifty Nine Thousand Nine Hundred and Sixty One Only) and the Grand total is 20,77,88,640 /- (Rupees Twenty Crores Seventy Seven Lakhs Eighty Eight Thousand Six Hundred and Forty Only) for your kind perusal and necessary recommendation please. | TRUE | template_variation | 2025-09-13T12:02:50.677445 | 1.0