## Sheet1
Issue_type | Categories | Category_count | Source
Description of the Issue | Category | 1 | EPC_V3
BG's for Performance Security and Additional Performance Security | Contractor's Obligations | 1 | EPC_V3
Appointment of Design Director | Contractor's Obligations | 1 | EPC_V3
Permission for extracting soil from minor irrigation tanks and ponds | Others | 1 | EPC_V3
Appointment of Safety & Proof Consultants | Contractor's Obligations | 1 | EPC_V3
Submission of 3rd party lab test reports | Contractor's Obligations | 1 | EPC_V3
Video recording of the Project Highway (before inception & during construction) | Contractor's Obligations | 1 | EPC_V3
Handing over of land /Possession of site. | Authority's Obligations | 1 | EPC_V3
QAP, EMP, EHS and Construction Programme | Contractor's Obligations | 1 | EPC_V3
Construction work methodologies | Contractor's Obligations | 1 | EPC_V3
Material test reports for Source Approvals | Contractor's Obligations | 1 | EPC_V3
Mix Designs for Pavement Layers & Structural Concrete | Contractor's Obligations | 1 | EPC_V3
Design & Drawings of Highways & Structures | Contractor's Obligations | 1 | EPC_V3
BG's for Mobilization Advance | Contractor's Obligations | 1 | EPC_V3
Slow Progress of Works | EoT | 1 | EPC_V3
Delay in payment of Supervision Charges to utility departments | Authority's Obligations, EoT | 2 | EPC_V3
Removal of Encumbrances and Encroachments from the ROW | Authority's Obligations, EoT | 2 | EPC_V3
Monthly Progress Reports | Contractor's Obligations | 1 | EPC_V3
Stage Payments Statements | Authority's Obligations, Contractor's Obligations, Payments | 3 | EPC_V3
Non Compliance Reports | Contractor's Obligation, Others | 2 | EPC_V3
Safety measures during construction. | Contractor's Obligations | 1 | EPC_V3
Providing of GAD drawings from Railway Authorities | Authority's Obligations | 1 | EPC_V3
Maintenance of diversion road/ existing road | Contractor's Obligations | 1 | EPC_V3
Schedule-H Division | Payments | 1 | EPC_V3
Change in location of structures as per site requirement | Others, Payments | 2 | EPC_V3
Change in cross section/span arrangement of structures as per site condition | Change of Scope, Dispute Resolution, EoT, Others, Payments | 5 | EPC_V3
Request for Inspection reports, test reports | Others | 1 | EPC_V3
Notices for Achievement/ Non Achievement of Milestones | Dispute Resolution | 1 | EPC_V3
Intimation of Occurrence of Force majeure Events | Dispute Resolution, EoT | 2 | EPC_V3
Occurrence of unprecedent rainfall | EoT | 1 | EPC_V3
Occurrence of unseasonal rainfall | EoT | 1 | EPC_V3
Occurrence of land slides | EoT | 1 | EPC_V3
Occurrence of floods | EoT | 1 | EPC_V3
Strikes/ boycotts/ agitations | EoT | 1 | EPC_V3
Elections in the state | EoT | 1 | EPC_V3
Declaration of Emergency by State/ Central Government | EoT | 1 | EPC_V3
occurrence of cyclones | EoT | 1 | EPC_V3
Outbreak of epidemic or pandemic | EoT | 1 | EPC_V3
Intimation of Change in Law | Payments | 1 | EPC_V3
Change of Scope Proposals | Change of Scope, Dispute Resolution, EoT, Payments | 4 | EPC_V3
Change of scope due to change in structural dimensions | Change of Scope, Dispute Resolution, EoT, Payments | 4 | EPC_V3
change of scope due to local demand for additional structures, service road, utility ducts | Change of Scope, Dispute Resolution, EoT, Payments | 4 | EPC_V3
Change of scope due to heavy rainfall and floods | Change of Scope, Dispute Resolution, EoT, Payments | 4 | EPC_V3
Change of scope due to realignment | Change of Scope, Dispute Resolution, EoT, Payments | 4 | EPC_V3
Change of scope due to redesign | Change of Scope, Dispute Resolution, EoT, Payments | 4 | EPC_V3
Change of scope due to reconstruction of pavement | Change of Scope, Dispute Resolution, EoT, Payments | 4 | EPC_V3
Extension of Time Proposals | Dispute Resolution, EoT | 2 | EPC_V3
Release of Retention Money | Payments | 1 | EPC_V3
Policies during construction period (Workmen's Compensation Policy, CAR, etc.,) | Contractor's Obligations | 1 | EPC_V3
Permissions/licences for use of blasting/explosive materials for roadway excavation | Contractor's Obligations | 1 | EPC_V3
Payment of Royalty/Seignoirage charges for use of Minor Minerals | Contractor's Obligations, Payments | 2 | EPC_V3
Submission of Applicable permits as per Schedule-F | Contractor's Obligations | 1 | EPC_V3
Calibration of Machinery & Equipment present at site | Contractor's Obligations | 1 | EPC_V3
Obstruction/Halt of works by local farmers/ Land owners | Authority's Obligations | 1 | EPC_V3
Delay in payment of certified stage payment amounts | Authority's Obligations, Payments | 2 | EPC_V3
Inadequate Manpower/ staff at site | Contractor's Obligations, Payments | 2 | EPC_V3
Inadequate machinery at site | Contractor's Obligations, Payments | 2 | EPC_V3
Relaxation for schedule-H payment criteria | Payments | 1 | EPC_V3
Clearances from Environmental & Forest Departments | Authority's Obligations | 1 | EPC_V3
Repairs to existing PWD roads | Contractor's Obligations, Payments | 2 | EPC_V3
usage of unapproved materials in the construction works | Others | 1 | EPC_V3
Demands by local villagers for additional structures/service road/utility ducts | Change of Scope, Dispute Resolution, EoT, Payments | 4 | EPC_V3
Clearances from Irrigation department for construction of Canal Bridges | Others | 1 | EPC_V3
High Embankment slope protection works | Contractor's Obligations, Others, Payments | 3 | EPC_V3
Slope protection for Hill Cutting works | Contractor's Obligations, Others, Payments | 3 | EPC_V3
Delay in payment of stage payments | Payments | 1 | EPC_V3
Tests on completion | Contractor's Obligations | 1 | EPC_V3
Punchlist items | Contractor's Obligations | 1 | EPC_V3
Provisional completion certificate | Authority's Obligations | 1 | EPC_V3
Completion certificate | Authority's Obligations | 1 | EPC_V3
Repairs to road furniture during maintenance period | Contractor's Obligations | 1 | EPC_V3
Rectification of defects at toll plaza (Static weigh bridges/ In motion weigh bridges/ ATMS/ HTMS) | Contractor's Obligations | 1 | EPC_V3
Fly ash supply | Contractor's Obligations, EoT, Others, Payments | 4 | EPC_V3
Pond ash supply | EoT, Others, Payments | 3 | EPC_V3
Joint inspection | Appointed Date, Authority's Obligations, Contractor's Obligations | 3 | EPC_V3
Memorandum & Appendix | Appointed Date, Authority's Obligations, Contractor's Obligations | 3 | EPC_V3
Utility shifting | Authority's Obligations, Contractor's Obligation, EoT | 3 | EPC_V3
Declaration of Appointed Date | Appointed Date | 1 | EPC_V3
Contractor's representative | Contractor's Obligations | 1 | EPC_V3
Providing Right of Way as per Schedule A | Authority's Obligations, Dispute Resolution, EoT | 3 | EPC_V3
Model code of conduct | EoT | 1 | EPC_V3
Modification of Appointed Date | Appointed Date, Dispute Resolution, EoT | 3 | EPC_V3
Dismantling of structures | Authority's Obligations, EoT, Payments | 3 | EPC_V3
Authority Engineer | Authority's Obligations | 1 | EPC_V3
Mobilisation of Authority Engineer | Authority's Obligations | 1 | EPC_V3
Submission of Plan & Profile | Contractor's Obligations | 1 | EPC_V3
Submission of Design and Drawings | Contractor's Obligations | 1 | EPC_V3
Providing Right of Way in terms of length of Project Highway | Appointed Date, Authority's Obligations | 2 | EPC_V3
Letter of Award | Authority's Obligations, Others | 2 | EPC_V3
Filing of affidavit | Others | 1 | EPC_V3
Settlement Agreement | Dispute Resolution, EoT, Payments | 3 | EPC_V3
DRB | Dispute Resolution | 1 | EPC_V3
Arbitration | Dispute Resolution | 1 | EPC_V3
Price escalation | EoT, Payments | 2 | EPC_V3
Court's decision | EoT, Others | 2 | EPC_V3
Borrow area | Contractor's Obligations | 1 | EPC_V3
Damages | Dispute Resolution, Payments | 2 | EPC_V3
DLP | Contractor's Obligations | 1 | EPC_V3
Maintenance period | Contractor's Obligations | 1 | EPC_V3
Bonus | Dispute Resolution, EoT, Payments | 3 | EPC_V3
Tree cutting | Authority's Obligations, Contractor's Obligations, EoT | 3 | EPC_V3
Labour License | Contractor's Obligations | 1 | EPC_V3
Change in law reimbursement | Payments | 1 | EPC_V3
Change of Scope Approval/order | Change of Scope, Dispute Resolution, EoT, Payments | 4 | EPC_V3
Change of scope Approval revisit | Change of Scope, Dispute Resolution, EoT, Payments | 4 | EPC_V3
Change of scope request for additional works or works not in the scope | Change of Scope, Dispute Resolution, EoT, Payments | 4 | EPC_V3
Change of scope proposals clarifications | Change of Scope, Dispute Resolution, EoT, Payments | 4 | EPC_V3
Delay due to Change of Scope approval | Change of Scope, Dispute Resolution, EoT, Payments | 4 | EPC_V3
Delay due to Change of Scope works | Change of Scope, Dispute Resolution, EoT, Payments | 4 | EPC_V3
Design & Drawings for COS works | Change of Scope, Dispute Resolution, EoT, Others, Payments | 5 | EPC_V3
Descoping/deletion of works under original scope | Change of Scope, Dispute Resolution, Payments | 3 | EPC_V3
Stoppage of Works by locals/public | Authority's Obligations, EoT | 2 | EPC_V3
Descoping of a work from the scope of additional works under COS | Change of Scope, Dispute Resolution, EoT, Payments | 4 | EPC_V3
Progress Review | EoT, Others, Payments | 3 | EPC_V3
Delay in construction activities | Dispute Resolution, EoT | 2 | EPC_V3
Request for revisit of EOT determined/approved | Dispute Resolution, EoT | 2 | EPC_V3
Submission of additional information/clarifications on Extension of time proposal | Dispute Resolution, EoT | 2 | EPC_V3
Disputing the issue pursuant to Article 26 | Dispute Resolution | 1 | EPC_V3
Right of way | Authority's Obligations, Dispute Resolution, EoT | 3 | EPC_V3
Under utilisation / idling of resources | Dispute Resolution, EoT, Payments | 3 | EPC_V3
Mobilisation of additional resources | Dispute Resolution, Payments | 2 | EPC_V3
Additional cost / compensation | Dispute Resolution, Payments | 2 | EPC_V3
Releasing of pending / outstanding amount | Dispute Resolution, Payments | 2 | EPC_V3
Cure period Notice | Dispute Resolution, Payments | 2 | EPC_V3
Demobilisation and Remobilisation | Dispute Resolution, EoT, Payments | 3 | EPC_V3
Release of Performance security | Dispute Resolution, Payments | 2 | EPC_V3
Topography/Geotech survey | Contractor's Obligations | 1 | EPC_V3
Delay in commencement/starting of work | Dispute Resolution, EoT, Payments | 3 | EPC_V3
Preliminary / preparatory works | Contractor's Obligations | 1 | EPC_V3
Handing over of cut tree/ salvaged material to the concerned authority | Contractor's Obligations, Others | 2 | EPC_V3
Pending approvals | EoT, Others, Payments | 3 | EPC_V3
Trial patch | Contractor's Obligations | 1 | EPC_V3
Black spots | Change of Scope, EoT | 2 | EPC_V3
Source / vendor / Manufacturer / supplier credential submission and approval | Contractor's Obligations | 1 | EPC_V3
Requirement of Additional land | Authority's Obligations | 1 | EPC_V3
Releasing of BG submitted against mobilization advance | Authority's Obligations, Others | 2 | EPC_V3
Delinking impacted length | Authority's Obligations, Dispute Resolution, Payments | 3 | EPC_V3
Contractor's delay in submission of COS Proposals | Change of Scope, Contractor's Obligations, Dispute Resolution | 3 | EPC_V3
Contractor's delay in commencing the COS works | Change of Scope, Contractor's Obligations, Dispute Resolution | 3 | EPC_V3
Rejection of COS request by Authority Engineer/Authority | Change of Scope, Dispute Resolution, EoT, Payments | 4 | EPC_V3
Providing and maintaining highway patrol,ambulance, emergency medical services and cranes etc. for safe operation of the Highway | Change of Scope, Contractor's Obligations, Dispute Resolution | 3 | EPC_V3
Maintenance of existing project highway with overlay | Change of Scope, Contractor's Obligations, Dispute Resolution | 3 | EPC_V3
Deviation of structure location / type/ span at site from the details given in Schedule-A/B | Change of Scope, Dispute Resolution, EoT, Payments | 4 | EPC_V3
Supplementary Agreement / CCIE | Dispute Resolution, EoT, Payments | 3 | EPC_V3
Reimbursement of Maintenance Cost after Scheduled Completion Date | Change of Scope, Dispute Resolution, Payments | 3 | EPC_V3
Action on Petition from locals/public | Others | 1 | EPC_V3
Slow Progress of Works from Contractor | Contractor's Obligations, Dispute Resolution | 2 | EPC_V3
Removal of encroachments after handing over of ROW | Contractor's Obligations, Dispute Resolution, EoT | 3 | EPC_V3
Borrow soil | Contractor's Obligations | 1 | EPC_V3
Borrow Earth | Contractor's Obligations | 1 | EPC_V3
Memorandum | Appointed Date, Authority's Obligations, Contractor's Obligations | 3 | EPC_V3
Joint Memorandum | Appointed Date, Authority's Obligations, Contractor's Obligations | 3 | EPC_V3
Tempoary Land | Contractor's Obligations | 1 | EPC_V3
Site Office | Contractor's Obligations | 1 | EPC_V3
Camp Area | Contractor's Obligations | 1 | EPC_V3
Labour Camp | Contractor's Obligations | 1 | EPC_V3
Bituminous Plant | Contractor's Obligations | 1 | EPC_V3
Concrete Plant | Contractor's Obligations | 1 | EPC_V3
Quarry | Contractor's Obligations | 1 | EPC_V3
Mobilisation Advance | Authority's Obligations, Dispute Resolution, Payments | 3 | EPC_V3
TDS | Authority's Obligations, Dispute Resolution, Payments | 3 | EPC_V3
LOA | Authority's Obligations, Contractor's Obligations | 2 | EPC_V3
Power of Attorney | Contractor's Obligations | 1 | EPC_V3
Signing of Agreement | Authority's Obligations, Contractor's Obligations | 2 | EPC_V3
Legal Opinion | Contractor's Obligations | 1 | EPC_V3
Hydrology report | Contractor's Obligations | 1 | EPC_V3
Termination Notice | Authority's Obligations, Damages, Dispute Resolution, Payments | 4 | EPC_V3
Descoping of works under original scope | Change of Scope, Dispute Resolution, Payments | 3 | CURRENT_ONLY
Safety measures during construction | Contractor's Obligations | 1 | CURRENT_ONLY
BG's for Mobilization Advance | Contractor's Obligations | 1 | CURRENT_ONLY
Approval for Proof Consultant conveyed | Contractor's Obligations | 1 | CURRENT_ONLY
Providing Right of Way in terms of length of Project Highway | Appointed Date, Authority's Obligations | 2 | CURRENT_ONLY
Borrow area | Contractor's Obligations | 1 | CURRENT_ONLY
Clearances from Forest Department | Authority's Obligations | 1 | CURRENT_ONLY
Providing and maintaining highway patrol, ambulance, emergency medical services and cranes etc. for safe operation of the Highway | Change of Scope, Contractor's Obligations, Dispute Resolution | 3 | CURRENT_ONLY
Releasing of pending/ outstanding amount | Dispute Resolution, Payments | 2 | CURRENT_ONLY
Occurrence of Force Majeure event | Dispute Resolution, EoT | 2 | CURRENT_ONLY
Occurrence of cyclones | EoT | 1 | CURRENT_ONLY
Letter of Award issued by the Authority | Authority's Obligations, Others | 2 | CURRENT_ONLY
Change of scope approval revisit | Change of Scope, Dispute Resolution, EoT, Payments | 4 | CURRENT_ONLY
Change of scope Approval revisit | Change of Scope, Dispute Resolution, EoT, Payments | 4 | CURRENT_ONLY
Topography/Geo-tech survey | Contractor's Obligations | 1 | CURRENT_ONLY
Repairs to existing PWD roads | Contractor's Obligations, Payments | 2 | CURRENT_ONLY
change of scope proposal | Change of Scope, Dispute Resolution, EoT, Payments | 4 | CURRENT_ONLY
Submission of Stage Payment Application | Authority's Obligations, Contractor's Obligations, Payments | 3 | CURRENT_ONLY
Occurrence of floods | EoT | 1 | CURRENT_ONLY
Memorandum and Appendix | Appointed Date, Authority's Obligations, Contractor's Obligations | 3 | CURRENT_ONLY
Intimation of Change in law | Payments | 1 | CURRENT_ONLY
Non Compliance Reports | Contractor's Obligations, Others | 2 | CURRENT_ONLY
occurrence of cyclones | EoT | 1 | CURRENT_ONLY
High Embankment slope protection works | Contractor's Obligations, Others, Payments | 3 | CURRENT_ONLY
Labour License | Contractor's Obligations | 1 | CURRENT_ONLY
Preliminary / preparatory works | Contractor's Obligations | 1 | CURRENT_ONLY
Change of scope proposal | Change of Scope, Dispute Resolution, EoT, Payments | 4 | CURRENT_ONLY
Permission for extracting soil from minor irrigation tanks and ponds | Others | 1 | CURRENT_ONLY