## Sheet1
issue_type | category | reference_sentence | source_file | subject | body | is_synthetic | generation_method | generated_date | generator_version
Memorandum & Appendix | Appointed Date, Contractor's Obligations, Authority's Obligations | As the obligations of the authority as per clause 4.1.3 of Agreement is satisfied appointed date to the project may please be communicated at the earliest. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/99_17012019_Submission of Memorandum.pdf | NHAI, PIU - Krishnagiri - Six Laning of Karaipettai to Walajhapet section of NH-4 (New NH-48) from km.71.015 to km.107.091 in the State of Tamil Nadu under NHDP Phase-V under EPC Mode- M/s SPK &Co -Right of Way-Procurement of the site-Submission of Memorandum-Reg. | As per contract agreement clause 8.2-Procurement of the Site, the memorandum containing an inventory of the site including the vacant and unencumbered land, buildings, structures, road works, trees and any other immovable property on or attached to the site is prepared by the contractor and Site Engineer of PIU. As per Appendix to the Memorandum the percent of unencumbered and vacant area is coming out to 94.94% on LHS and 92.37% on RHS and combined on both sides is coming out to 93.66% of NH-4 which is more than 90% as per clause 8.2.3 of contract. As the obligations of the authority as per clause 4.1.3 of Agreement is satisfied appointed date to the project may please be communicated at the earliest. Encl:- Joint Memorandum (2 copies) | FALSE | real_data
Memorandum & Appendix | Appointed Date, Contractor's Obligations, Authority's Obligations | As the obligations of the authority as per clause 4.1.3 of Agreement is satisfied | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/99_17012019_Submission of Memorandum.pdf | NHAI, PIU - Krishnagiri - Six Laning of Karaipettai to Walajhapet section of NH-4 (New NH-48) from km.71.015 to km.107.091 in the State of Tamil Nadu under NHDP Phase-V under EPC Mode- M/s SPK &Co -Right of Way-Procurement of the site-Submission of Memorandum-Reg. | As per contract agreement clause 8.2-Procurement of the Site, the memorandum containing an inventory of the site including the vacant and unencumbered land, buildings, structures, road works, trees and any other immovable property on or attached to the site is prepared by the contractor and Site Engineer of PIU. As per Appendix to the Memorandum the percent of unencumbered and vacant area is coming out to 94.94% on LHS and 92.37% on RHS and combined on both sides is coming out to 93.66% of NH-4 which is more than 90% as per clause 8.2.3 of contract. As the obligations of the authority as per clause 4.1.3 of Agreement is satisfied appointed date to the project may please be communicated at the earliest. Encl:- Joint Memorandum (2 copies) | FALSE | real_data
Memorandum & Appendix | Appointed Date, Contractor's Obligations, Authority's Obligations | Hence, we have submitted an Appendix containing the encroachments & encumbrances, vide letter ref (3) above for your joint verification and signing. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/2. Encroachements & Encumbrances in the ROW 11.10.2018.pdf | Encroachments & Encumbrances in the ROW -Reg. | With reference to above subject & letters, we would like to bring to your kind notice that the progress of work continues to suffer the ramifications of presence of Encroachments & Encumbrances in the ROW. Please refer to your letter ref (2) above wherein it was intimated that ROW to the tune of 90.44% was available for execution, enclosing Schedule-A of the Agreement. However, when we subsequently visited the Site we had encountered numerous encroachments & encumbrances and thus realized the fact that the available ROW was far less than 90.44%. Hence, we have submitted an Appendix containing the encroachments & encumbrances, vide letter ref (3) above for your joint verification and signing. The same was also communicated in our Extension of Time (EOT) letters ref (8) & (13) above. Further, through various letters referred above, we have intimated to the Authority & Authority Engineer as and when we had faced obstructions to the progress of work due to encroachments & encumbrances. We are once again enlisting below the locations which are not comprehensive, where we are unable to progress with the works even today along with the reasons. | FALSE | real_data
Providing of GAD drawings from Railway Authorities | Authority's Obligations | GAD Approval from the Railway Authorities. | synthetic_template_20250913 | Notice under clause 10.5.(V)- Accumulated delays till 30" November 2023 - Reg. | We refer to the above letters, wherein we have intimated the Authority about the following issues/Bottlenecks prevailing in the project which are hampering the progress of the works: 1. Handing over of the Balance land. 2. Clearance from the Forest department. 3. GAD Approval from the Railway Authorities. However, the issues are yet to be cleared and hence the same continue to hamper the progress. In this regard, pursuant to clause 10.5.(V) of the EPC Contract agreement, we herewith submit the accumulated delays as on 30" November 2023. SLMI — DMCPL (JV) (A Joint Venture of M/s. SLMI Infra Projects Private Limited & M/s. Dwarakamai Constructions Pvt. Ltd.) H.No.1223, Street No.5, Tarnaka, Secunderabad — 500017. Accumulated delays Till 30-Nov-2023. Description of Delay Events From the above the total accumulated delay as on 30.11.2023 is 303 days. Handing over of ROW/Construction Zone on at least 90% of the total length of the Project Highway Still Continuing. Handing over of the balance Land (to be handed over in 150 days) Still Continuing. Clearance from Forest Department Still Continuing. GAD Approval from Railway Authorities ~ Owing to the above delays, we may not be able to achieve Milestone-II which is due in April’24. It may please be noted that we may run out of work fronts and our resources may become idle as all the available work fronts are already being tackled. In view of the above, we request your office to pursue with the Authority to clear the issues at the earliest and provide hindrance free work fronts over the entire length of the Project Highway. We await your further instructions. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Providing of GAD drawings from Railway Authorities | Authority's Obligations | Approval of GAD from Railway Authorities to enable the contractor to construct ROBs | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/188_30012019_Procurement of Site Submission of Memorandum.pdf | NHAL, PIU ~ Krishnagiri - Six Laning of (New NH48) from km 71.015 to km 107.0 - Right-of-Way Procurement of the site Submission of Memorandum-Reg. | Kindly refer to the letter 24 cited wherein it is requested to submit joint memorandum signed by the Contractor along, with status of approval of GAD for ROBs, Environmental clearance as per clause 4.13 of Agreement and status of shifting of obstructing utilities and felling of trees as per cl 9.2 & 9.4 of Agreement. 2. The status report is submitted below: (i) Joint Signed copy of the Joint Memorandum submitted by the Contractor vide reference 1 is enclosed as Annexure. (ii) The status of Obligations of the Authority as per Article 4 is as below: (a) The Authority has to give Right of Way to the Contractor no less than 90% of the total length of the Project Highway. Accordingly, as per clause 62 the memorandum containing an inventory is prepared by the Contractor and Authority. As per Appendix to memorandum the percent of unencumbered and vacant area is coming out to 93.65% which is more than 90% as per cl 8.23 of contract and also as per clause 83.2 Schedule-A, Annex-II dates for providing right of way is more than 80% of the total length of the project on appointed date in compliance to clause 10.3 of agreement, hence fulfilled the obligation. (b) Approval of GAD from Railway Authorities to enable the contractor to construct ROBs. One No of 6 lane ROB is existing and only Repair/Rehabilitation is to be carried out no fresh approval of GAD is required from Railways, hence fulfilled the obligation. (c) Environmental clearance is required under cl 4.3 and shall be procured by Authority before issue of LOA. As per MOEF Notification S.O No 2559, 22.8.2013 Environmental clearance is required for the expansion of NHs greater than 100 Km involving additional right of way or land acquisition greater than 40m on existing alignments and 60m on realignments or by passes. In this case the length of project is only 36.076 Km and additional land acquired is less than 40m, hence no clearance is required from MOEF. (d) As per Article 9.2 of Agreement the status of shifting of obstructing Utilities are as below: (i) Balance Electrical Utilities are to be shifted. The subcontractor of the terminated Concessionaire has shifted the Electrical Utilities partially and the authority has decided to shift the balance utilities through the same agency at the old SOR rates. In this regard RO Chennai vide letter No 3921 dt 03.10.2018 has forwarded report to GM(T)-TN NHAI HQ Delhi. Approval is awaited. (ii) Tree cutting is already completed and few left out trees were identified and cutting is under progress. Hence it is requested to communicate appointed date for the project at the earliest. | FALSE | real_data
Clearances from Environmental & Forest Departments | Authority's Obligations | we request your office to kindly arrange for necessary approval from the Forest Department. | synthetic_template_20250913 | Change of location for Flyover @ 72+760 - Reg. | Kindly be informed that We wish to draw your kind attention to our site visit along with RO regarding various issues. As per Schedule-B of the Contract Agreement (CA), a Flyover / Animal Underpass (3v x 25 m) is to be constructed at Km. 72+760 and the stretch falls under Wildlife Zone. The width of the structure is 12m, resting on RCC open foundations and I-girders. The applicable cross-section on the approaches of the flyover as per Schedule-B is TCS-9 for the stretch from Km. 72+350 to Km. 73+290. As per Annex-ll of Schedule-A, the Right of Way (ROW) is 20m between Km 72+460 to Km 73+396. The scope of work includes olf the existing 7m road to 12.9m overall width. The existing road level is 200.399 and the FRL of the proposed structure is 208.685, thus the road top level is increasing by more than 8m at this location. As you are aware, two High Tension (HT) grid lines are crossing the Project Highway at Km. 72+850 and Km 72+940 at a height of 10.2 m and 7.6 m respectively from the existing road top, with FRL of 208.403 and 207.251 respectively. Hence the minimum vertical clearance requirement of 8.5m (5.5m vertical clearance + 3m for Induction) is not being met at these two locations. During the recent Site Visit with RO and your good self, this issue was discussed at site and it Was proposed to shift the Flyover to Km. 72+650. The original ground level at this location is 4m below the existing road top level, i.e., approximately 196.77m. Thus, the structure can be fitted as per the proposed GAD in the CA, simultaneously ensuring the vertical clearance between the ground level and soffit of the structure. In view of the above, we request your office to kindly arrange for necessary approval from the Forest Department, to proceed with construction of the Flyover/Animal Underpass at the revised location at the earliest. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Clearances from Environmental & Forest Departments | Authority's Obligations | we request your office to kindly arrange for necessary approval from the Forest Department. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-1/3. Change in location of flyover @72+760.pdf | Change of location for Flyover @ 72+760 - Reg. | We wish to draw your kind attention to our site visit along with RO regarding various issues. As per Schedule-B of the Contract Agreement (CA), a Flyover / Animal Underpass (3v x 25 m) is to be constructed at Km. 72+760 and the stretch falls under Wildlife Zone. The width of the structure is 12m, resting on RCC open foundations and I-girders. The applicable cross-section on the approaches of the flyover as per Schedule-B is TCS-9 for the stretch from Km. 72+350 to Km. 73+290. As per Annex-ll of Schedule-A, the Right of Way (ROW) is 20m between Km 72+460 to Km 73+396. The scope of work includes olf the existing 7m road to 12.9m overall width. The existing road level is 200.399 and the FRL of the proposed structure is 208.685, thus the road top level is increasing by more than 8m at this location. As you are aware, two High Tension (HT) grid lines are crossing the Project Highway at Km. 72+850 and Km 72+940 at a height of 10.2 m and 7.6 m respectively from the existing road top, with FRL of 208.403 and 207.251 respectively. Hence the minimum vertical clearance requirement of 8.5m (5.5m vertical clearance + 3m for Induction) is not being met at these two locations. During the recent Site Visit with RO and your good self, this issue was discussed at site and it Was proposed to shift the Flyover to Km. 72+650. The original ground level at this location is 4m below the existing road top level, i.e., approximately 196.77m. Thus, the structure can be fitted as per the proposed GAD in the CA, simultaneously ensuring the vertical clearance between the ground level and soffit of the structure. In view of the above, we request your office to kindly arrange for necessary approval from the Forest Department, to proceed with construction of the Flyover/Animal Underpass at the revised location at the earliest. | FALSE | real_data
Utility shifting | Authority's Obligations, Contractor's Obligations, EoT | Further, it is to inform that NH Authority made payment towards supervision charges | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-2/9. 20240423_EE_DE_TSSPDCL_Supervision charges for Electrical shifiting work taken up by Nh agency on 100% trunkey basis.pdf | Widening to 2 Lane with paved shoulders of Medak - Siddipet section from Km 0/000 to Km 69/978 of NH-765DG in the State of Telangana under Annual Plan 2021-2 on EPC Basis - Payment of 2.5% Supervision Charges for Electrical Shifting Works taken up by NH Agency on 100% turnkey basis - Reg. | It is to inform that the subject work was sanctioned by MoRTH, Government of India vide reference 1 cited and electrical shifting works involved in the Project Highway are taken up by the NH Agency M/s SLMI - DMCPL (JV), Hyderabad on 100% turnkey basis and the works are in progress. The Project Highway is targeted to be completed by 30.01.2025. Further, it is to inform that NH Authority made payment towards Supervision Charges @ 2.5% on the estimate cost (Material + Service) for an amount of Rs 18,89,318/- to the Divisional Engineer, Operations, TSSPDCL, Siddipet on 07.06.2023 with UTR number “CNRBR52023060757082752” as per the approval communicated by the Regional Officer, MORTH, Hyderabad vide reference 3 cited. In this regard, it is requested to kindly instruct the concerned to provide necessary LCs to the NH Agency for taking up the electrical shifting works along the Project Highway, as and when required, on priority. We solicit your kind cooperation in this regard. | FALSE | real_data
Utility shifting | Authority's Obligations, Contractor's Obligations, EoT | Hence in view of this, the extension of time cannot be recommended for shifting of utilities at this stage. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/264_18022020_Rescheduling of Project Milestones – Request for Extension of Time.pdf | Rescheduling of Project Milestones — Request for Extension of Time -Reg. | In reference to the above-mentioned subject and Contractor letter No. SPK/KW/SAIC/NH-48/2020/001 dated 29.01.2020 regarding the rescheduling of Project Milestone, in this regard, it is submitted that AE has computed the 176 days for extension of time in Milestones I and II. The same was recommended vide AE letter No. SAICPL/Kar-Wal/H.O./NH-48/TN/2019/10451 dated 30.11.2019 to the Authority for their acceptance and further needful. However, the Contractor submitted his reservations on the computation of the nos. of delay days and requested for rescheduling of Project Milestones for a period of 324 days instead of recommended 176 nos. of days. In this regard, AE is hereby submitted point wise reply of your raised observations for your ready reference and record, please; 4. Modification of Appointed date and Handing Over in % of area. The appointed date was communicated by the Authority letter No. NHAI/PIU.K.giri/NH-4/SPK/PS/2019/972 Dated 03.06.2019. it is also submitted that as per cl 8.2.2 the authority shall provide the Right of Way to the Contractor in respect of all land included in the Appendix by the date specified in Schedule-A for those parts of the site referred to therein, or no later than 90 days of the appointed date for those parts of the site which have not been specified in Schedule-A. It is well evident that the lands specified in Annexure-II, Schedule-A of agreement are available from the day one and as on appointed date, the existing and proposed ROW is same and no parts of the site is mentioned as not available in Schedule-A and joint memorandum signed on 11.01.2019 except for the lands for widening of plaza at Chennasamudram. Hence authority has fulfilled the obligation. This was informed vide Authority letter No. NHAI/PIU.K.giri/NH-4/SPK/PS/2019/972 Dated 03.06.2019. In view of above, the request of the Contractor to modify the appointed date is not eligible as per agreement due to the following reasons (i) As per cl 4.1.3, 8.2.1 & 8.2.2, 8.2.3 — The agreement is signed on 15.10.2018 and the Joint memorandum is signed by both the parties on 30.01.2019 and appointed date is declared for the project on 11.02.2019 to commence the work. (i) The Authority Engineer vide Letter No. SAICPL/Kar-Wal/H.O./NH-48/TN/2019/10451 Dated 30.11.2019. informed that the contractor consciously agreed and signed the Joint memorandum and aware that the unencumbered and the vacant land available after joint inspection is 93.65%. (iii) Further, it is submitted that the Joint memorandum was signed on 11.01.2019 & the appointment date is declared as 11.02.2019. The Contractor has requested the Authority for modifying the Appointment date based on the length of Project Highway handed over, vide letter No. 29/SPK/Kar-Wal/PD/NHAI/ Dated 13.05.2019. On this account and in view of clause 8.3.2 of the Contract Agreement, the Contractor cited reason of land not handed over pursuant to Clause 4.1.3 (a) is not acceptable and cannot be considered for Entitlement for EOT. 2. Assessment of Hindrance length. The assessment of hindrance length is already enumerated in Point No. 01 above. It is to remind the contractor that the Joint memorandum was signed by both the parties on 30.01.2019 as per the provisions of the Contract Agreement. The AE hereby like to reiterate the clause 8.2.1. “The Authority Representative and the Contractor shall, within 30 (thirty) days of the date of this Agreement, inspect the Site and prepare a memorandum containing an inventory of the Site including the vacant and unencumbered land, buildings, structures, road works, trees and any other immovable property on or attached to the Site. Subject to the provisions of Clause 8.2.3, such memorandum shall have appended thereto an appendix (the “Appendix”) specifying in reasonable detail those parts of the Site to which vacant access and Right of Way has not been given to the Contractor. Signing of the memorandum, in two counterparts (each of which shall constitute an original), by the authorized representatives of the Parties shall be deemed to constitute a valid evidence of giving the Right of Way to the Contractor for discharging its obligations under and in accordance with the provisions of this Agreement and for no other purpose whatsoever’. AE would like to further clarify that cl. 8.3.1 last para stating that “For the avoidance of doubt, the Parties expressly agree that the Damages specified hereunder and the Time Extension specified in Clause 10.5 shall be restricted only to failure of the Authority to provide the Right of Way for and in respect of the width of the roadway, its embankment and a parallel working strip at least 3 (three) meters wide”. The width of the roadway can be treated as one side of the road since it is neither mentioned “Total width nor Full width’. Hence the Authority Engineer has done the analysis of Hindrance free length is clear with the above illustrated iteration. | FALSE | real_data
Utility shifting | Authority's Obligations, Contractor's Obligations, EoT | The contractor informed that at 75Km towers were erected and waiting for the LC from the electrical department. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210302_AE_SPK_569-Minutes of Monthly Progress review meeting Mom – 09.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode. - Minutes of Monthly Progress review meeting Mom — 09 — Reg. | With respect to the above said reference please find enclosed herewith the Minutes of Meeting Numbered as MoM - 09 held on 26.02.2021 The next meeting will be likely on 19 March 2021 at Team Leader office around 11.00 A.M in Kancheepuram. All the concerned are requested to attend with necessary documents. This is for your information and record. Assuring our best services at all times. | FALSE | real_data
Utility shifting | Authority's Obligations, Contractor's Obligations, EoT | The Contractor informed that the shifting of electric poles was pending at water logged areas and built up locations. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/20191205_AE_NHAI_188_Minutes of Monthly Progress review meeting Mom-5.pdf | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to 107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Minutes of Monthly Progress review meeting Mom-5 -Reg. | With respect to the above said reference please find enclosed herewith the Minutes of Meeting Numbered as MoM-S held on 29.11.2019. The next meeting will be likely on 27.12.2019 at the Consultants office around 11.00 A.M in Kancheepuram. All the concerned are requested to attend with necessary documents. This is for your information and record. Assuring our best services at all times. | FALSE | real_data
Utility shifting | Authority's Obligations, Contractor's Obligations, EoT | Further the Contract Agreement between the Authority and utility shifting was executed only on 19.07.2019 . It is evident that shifting of utilities was not taken till 19.07.2019, i.e. 158 days from the declaration of Appointed Date by the Authority. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20200129_SPK_AE_001_Reply on Rescheduling of Project Milestone - Request for EoT.pdf | Reply on Rescheduling of Project Milestones — Request for Extension of Time - Reg. | The Authority Engineer vide ref (3) cited above communicated his recommendation on the above captioned subject. The EPC Contractor would like to submit his observations which are as follows: 1. The EPC Contractor vide his letter No. 49 / SPK / Kar - Wal / PD / NHAI dated 17.06.2019 requested the Authority to consider the ROW handed over in terms of length (as per Cl. 4.1.3 and not in terms of area and shift the Appointed Date based on the actual date of removal of encumbrance / encroachment / obstruction for which response is still awaited from the Authority. Further, it is worth mentioning that the AE also reiterated our stand wherein it was mentioned in Authority Engineer recommendation that “It is also worth mentioning that this memorandum was signed based on the % of area of the project ROW, in place of % of length, as mentioned in the Clause 4.1.3 (a).” 2. The assessment of hindrance length by the EPC contractor is correct as irrespective of hindrance available on one side, the same has to be considered for entire six laning width. In this regard it is hereby requested that the definition of ROW as per Article 28 shall be referred for further clarity. Further a working strip of at least 3 m wide shall be available parallel from the toe of the embankment pursuant to Clause 8.3.1 of the Contract Agreement. Authority Engineer has not based on this provision. 3. We totally deny with the observation of the Authority Engineer in not considering delay in handing over of land by the Authority pursuant to 4.1.3 (a) and 8.3.2 of the Contract Agreement. It is worth mentioning that even as on date 90% of encumbrance free land is yet to be handed over which is against the provisions of the Contract Agreement as 90% of land should have been handed over within 30 days of the execution of the agreement as per 4.1.3 (a) i.e on or before 15/11 / 2019. The joint inspection done on 24.10.2019 and on which the Authority Engineer’s representative signed would prove that only 62.51% of length was available on that day. Even today the Authority Engineer may carry out a joint inspection and will find that hardly 70% of the length is available for work front if imparted length is considered. 4. The EPC Contractor is obligated to comply only with the provisions of the Contract Agreement and not bound by any internal circular of the Authority as mentioned in AE recommendation. Hence, we disagree with the contention of the Authority Engineer that the EPC Contractor is not entitled for EOT in light of the circular issued by the Authority dated 16.08.2019. 5. It has been explicitly mentioned in Authority Engineer’s recommendation that shifting of utilities was being taken care by the Authority. Further the Contract Agreement between the Authority and Utility shifting agency was executed only on 19.07.2019. It is evident that shifting of utilities was not taken up till 19.07.2019, i.e 158 days from the declaration of Appointed Date by the Authority. Since the Authority is taking care of utility shifting and the agency appointed by the Authority commenced the works only after 180 days of the Appointed Date, period of 180 days mentioned in Clause 9.2is has no relevance. Hence, we deny with the contention of the Authority Engineer that the Contractor is entitled for time extension only beyond 180 days. The project duration is only 24 months and first 6 months are very crucial for the EPC contractor to progress the works based on his targeted programme. The Authority Engineer is also reiterating our concern wherein it has been mentioned that, ’The shifting of Utilities is important for this project, as the project is a Toll road and considering this, the Contractor submitted Construction Methodology, stating that first service road is to be constructed and after diverting the traffic over there, Main carriageway would be constructed ” . Utility shifting work is also not progressing as the encumbrances have not been removed and space is not made available for relocating the utility. 6. We would like to submit that as per Cl. 6 of Schedule-J , the Extension of Time recommendation is for Scheduled Project Completion Date and not confined to Milestone I. Based on the EOT recommended, all the milestones get automatically rescheduled accordingly. Hence, we do not agree with the contention of the Authority Engineer that the Extension of Time for Project. | FALSE | real_data
Utility shifting | Authority's Obligations, Contractor's Obligations, EoT | The electrical pole/transformer shifting is yet to be completed by the Authority even as on date and the following are the chainages whether shifting is required to be carried out. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20200713_SPK_RO_42_Reminder - Request for revisiting the EOT already recommended - Rev2.pdf | Extension of Time and Rescheduling of Project Milestones - EOT granted for 112 days not acceptable to the EPC contractor - Request for revisiting the EOT recommended - Reminder sent - Reg. | 1. This is with respect to the Extension of Time(EOT} approved by the Authority for. a period of 112 days for Project Milestone-I without effecting changes in Scheduled Project Completion Period vide ref (3) cited above.The EPC Contrator disagrees and does not accept the grant of EOT approval for 112 days, the reasons for disgreeement of this approval are elaborated in our submission to the Authority Engineer vide ref (4) cited above. 2. The EPC contractor requested the Authority/NHAI to revisit the EOT determined/approved and communicate 324 days as interim Extension of time vide ref (5) cited above but, we are yet to receive response in this regard. Copy of the same is herewith enclosed as Annexure 1. 3. The Authority is yet to fulfil the obligations relating to handing over of ROW as per Sub Clause 8.2 of the Contract Agreement. Copy of the newspaper publication regarding LA status / notification for acquiring land for the Project Highway (Kanchipuram District} is herewith enclosed as Annexure 2. By not fulfilling the obligations as per the provisions of the Contract Agreement, the Authority committed a material default pursuant to Sub clause 23.2.1 (a) of the Contract Agreement. 4. The electrical pole/Transformer shifting is yet to be completed by the Authority even as on date and following are the Chainages whether shifting is required to be carried out: No.of Transformers In addition to the above, following locations listed below where shifting of High Tension(HT) Towerlines are required to be carried out: No. of HT Towers Status All Material mobilized at site. Due to Lockdown Estimate Approved on 22.02.2020. Electrical Contractor engaged by EPC Contractor on 20.03.2020 for shifting works. Due to Lockdown work yet to be taken-up. Estimate yet to be approved. Estimate yet to be approved. | FALSE | real_data
Declaration of Appointed Date | Appointed Date | Hence it is requested to communicate appointed date for the project at the earliest | synthetic_template_20250913 | NHAL, PIU ~ Krishnagiri - Six Laning of (New NH48) from km 71.015 to km 107.0 - Right-of-Way Procurement of the site Submission of Memorandum-Reg. | Kindly refer to the letter 24 cited wherein it is requested to submit joint memorandum signed by the Contractor along, with status of approval of GAD for ROBs, Environmental clearance as per clause 4.13 of Agreement and status of shifting of obstructing utilities and felling of trees as per cl 9.2 & 9.4 of Agreement. 2. The status report is submitted below: (i) Joint Signed copy of the Joint Memorandum submitted by the Contractor vide reference 1 is enclosed as Annexure. (ii) The status of Obligations of the Authority as per Article 4 is as below: (a) The Authority has to give Right of Way to the Contractor no less than 90% of the total length of the Project Highway. Accordingly, as per clause 62 the memorandum containing an inventory is prepared by the Contractor and Authority. As per Appendix to memorandum the percent of unencumbered and vacant area is coming out to 93.65% which is more than 90% as per cl 8.23 of contract and also as per clause 83.2 Schedule-A, Annex-II dates for providing right of way is more than 80% of the total length of the project on appointed date in compliance to clause 10.3 of agreement, hence fulfilled the obligation. (b) Approval of GAD from Railway Authorities to enable the contractor to construct ROBs. One No of 6 lane ROB is existing and only Repair/Rehabilitation is to be carried out no fresh approval of GAD is required from Railways, hence fulfilled the obligation. (c) Environmental clearance is required under cl 4.3 and shall be procured by Authority before issue of LOA. As per MOEF Notification S.O No 2559, 22.8.2013 Environmental clearance is required for the expansion of NHs greater than 100 Km involving additional right of way or land acquisition greater than 40m on existing alignments and 60m on realignments or by passes. In this case the length of project is only 36.076 Km and additional land acquired is less than 40m, hence no clearance is required from MOEF. (d) As per Article 9.2 of Agreement the status of shifting of obstructing Utilities are as below: (i) Balance Electrical Utilities are to be shifted. The subcontractor of the terminated Concessionaire has shifted the Electrical Utilities partially and the authority has decided to shift the balance utilities through the same agency at the old SOR rates. In this regard RO Chennai vide letter No 3921 dt 03.10.2018 has forwarded report to GM(T)-TN NHAI HQ Delhi. Approval is awaited. (ii) Tree cutting is already completed and few left out trees were identified and cutting is under progress. Hence it is requested to communicate appointed date for the project at the earliest. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Declaration of Appointed Date | Appointed Date | Regarding declaration of Appointed Date | synthetic_template_20250913 | Six Laning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km. 71+015 to Km 107+091 on EPC Mode in the state of Tamil Nadu under NHDP Phase-V - Regarding declaration of Appointed Date. | This has reference to Joint Memorandum of Site Inventory signed jointly by PD, Krishnagiri and the EPC Contractor submitted vide your letter dated 01.02.2019 in terms of Clause 8.2.1 of Agreement regarding declaration of Appointed Date for the subject Project. By In this context, it is to convey that the Competent Authority has accorded approval to declare the Appointed Date as 11.02.2019, to commence the work. Further, it has also been directed to arrange handing over of balance ROW as per Clause 8.2.2 of Contract Agreement and to ensure that encumbrances due to Tree Cutting, removal of Structures, shifting of Electric Poles and Water Supply Lines etc., don’t hinder the construction of Project. This is for kind information and further necessary action, please. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Submission of Applicable permits as per Schedule-F | Contractor's Obligations | Status of obligations of the Contractor as per Article 3 of Agreement | synthetic_template_20250913 | NHAIL, PIU - Krishnagiri - Six Laning of Karaipettai to Walajhapet section of NH-4 (New NH-48) from km.71.015 to km.107.091 in the State of Tamil Nadu under NHDP Phase-V under EPC Mode- M/s SPK é&Co -Declaration of Appointed Date—Reg. | It is brought to your attention that With reference to the references 2nd & 3rd cited, the competent authority in NHAI vide reference 1st cited has communicated approval to declare appointed date as 11.02.2019 to commence the works. In view of the above, it is requested to submit the action taken on the following issues: (a) Status of obligations of the contractor as per Article 3 of agreement (b) Maintenance of the stretch during construction period as per clause 10.4 of Agreement for which the contractor is responsible for ensuring safe operation of Project Highway. (c) Status of obligations of the Contractor on Design and Construction of the Project Highway as per Article 10 of Agreement. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Submission of Applicable permits as per Schedule-F | Contractor's Obligations | Status of obligations of the Contractor as per Article 3 of Agreement | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/233_11022019_Declaration of Appointed Date.pdf | NHAIL, PIU - Krishnagiri - Six Laning of Karaipettai to Walajhapet section of NH-4 (New NH-48) from km.71.015 to km.107.091 in the State of Tamil Nadu under NHDP Phase-V under EPC Mode- M/s SPK é&Co -Declaration of Appointed Date—Reg. | With reference to the references 2nd & 3rd cited, the competent authority in NHAI vide reference 1st cited has communicated approval to declare appointed date as 11.02.2019 to commence the works. In view of the above, it is requested to submit the action taken on the following issues: (a) Status of obligations of the contractor as per Article 3 of agreement (b) Maintenance of the stretch during construction period as per clause 10.4 of Agreement for which the contractor is responsible for ensuring safe operation of Project Highway. (c) Status of obligations of the Contractor on Design and Construction of the Project Highway as per Article 10 of Agreement. | FALSE | real_data
Contractor's representative | Contractor's Obligations | (c) Status of obligations of the Contractor on Design and Construction of the Project Highway as per Article 10 of Agreement. | synthetic_template_20250913 | NHAIL, PIU - Krishnagiri - Six Laning of Karaipettai to Walajhapet section of NH-4 (New NH-48) from km.71.015 to km.107.091 in the State of Tamil Nadu under NHDP Phase-V under EPC Mode- M/s SPK é&Co -Declaration of Appointed Date—Reg. | We would like to inform you that With reference to the references 2nd & 3rd cited, the competent authority in NHAI vide reference 1st cited has communicated approval to declare appointed date as 11.02.2019 to commence the works. In view of the above, it is requested to submit the action taken on the following issues: (a) Status of obligations of the contractor as per Article 3 of agreement (b) Maintenance of the stretch during construction period as per clause 10.4 of Agreement for which the contractor is responsible for ensuring safe operation of Project Highway. (c) Status of obligations of the Contractor on Design and Construction of the Project Highway as per Article 10 of Agreement. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Contractor's representative | Contractor's Obligations | It is observed that even-though sufficient time has been lapsed after commencing the above said Contract Agreement, till date there is no full time Project Manager has been deployed at site from your end. How-ever it is to note that Mr. G. Vijayakumar who is representing as Project Manager is attending the Co-ordination meetings & site inspections and rest of the time his presence at Project site is minimal. Hence it has been advised to arrange a full time Project Manager for proper co-ordination and effective management of site activities. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LOT-10/102_17092019_Presence of Project Manager at site.pdf | Presence of Project Manager at site: -Reg | Dear Sir, It is observed that even-though sufficient time has been lapsed after commencing the above said Contract Agreement, till date there is no full time Project Manager has been deployed at site from your end. How-ever it is to note that Mr. G. Vijayakumar who is representing as Project Manager Is attending the Co-ordination meetings & site inspections and rest of the time his presence at Project site is minimal. Hence it has been advised to arrange a full time Project Manager for proper co-ordination and effective management of site activities. Yours faithfully, CH Balakrishneé Team Leader cu XS¢ vor Hie Engineer, S.A. Infrastructure anis-P vt. Ltd., Kar-Wal, Six Lanning Project, Package-ll, Kancheepuram Copy to: * 1. The Project Director, NHAI, PIU — Kancheepuram. 2. H.O. S.A. Infrastructure Consultants Pvt. Ltd. Uttar Pradesh. INDIA. Tel. :+91-120-6148000 ¦ Tel./Fax: +91-120-6148090 | FALSE | real_data
Appointment of Design Director | Contractor's Obligations | (c) Status of obligations of the Contractor on Design and Construction of the Project Highway as per Article 10 of Agreement. | synthetic_template_20250913 | NHAIL, PIU - Krishnagiri - Six Laning of Karaipettai to Walajhapet section of NH-4 (New NH-48) from km.71.015 to km.107.091 in the State of Tamil Nadu under NHDP Phase-V under EPC Mode- M/s SPK é&Co -Declaration of Appointed Date—Reg. | With reference to the references 2nd & 3rd cited, the competent authority in NHAI vide reference 1st cited has communicated approval to declare appointed date as 11.02.2019 to commence the works. In view of the above, it is requested to submit the action taken on the following issues: (a) Status of obligations of the contractor as per Article 3 of agreement (b) Maintenance of the stretch during construction period as per clause 10.4 of Agreement for which the contractor is responsible for ensuring safe operation of Project Highway. (c) Status of obligations of the Contractor on Design and Construction of the Project Highway as per Article 10 of Agreement. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Appointment of Design Director | Contractor's Obligations | we have appointed Mr. Pattabiram Yegulla as "Design Director'' for the above mentioned project. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-1/1. Appointment of Design Director.pdf | Appointment of Design Director - Reg. | In pursuant to the article 10, clause 10.1.(B) of the Contract Agreement, we have appointed Mr. Pattabiram Yegulla as “Design Director” for the above mentioned project. This is for your kind information & Record please. | FALSE | real_data
Modification of Appointed Date | Appointed Date, EoT, Dispute Resolution | In view of the above circumstances, we request you to kindly take a practical view and modify the Appointed Date already declared as 11.02.2019. This may be kindly modified to a date on which 90% of encumbrance free length of the Project Highway is made available to us. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/29_13052019_ Modifying the Appointed Date.pdf | Modifying the Appointed Date based on the length of project highway handed over in pursuant to Article 8 of EPC agreement - reg | 1. Pursuant to Clause 8.2.2 and 8.2.3 of the EPC Agreement, the Authority should have provided Right of way for 100% length of the project highway on appointed date plus 90 days, i.e. 11.05.2019. It is brought to your notice that this requirement has not been fulfilled by the Authority. 2. We also bring to your kind notice that the memorandum and appendix jointly signed on 11.01.2019 and submitted vide ref (3) cited above was prepared based on the available area without taking into consideration, the requirement of the contract provision as per Clause 4.1.3 (a) of the EPC agreement which talks about the handing over of land only in terms of length of the Project Highway. 3. When we started assessing the stretches affected in terms of length, we come to know that substantial length is affected due to existing buildings which are to be dismantled. The Authority has not started dismantling buildings at any location. The stretches passing through the villages are badly affected. 4. The memorandum and appendix prepared in terms of area is giving a deceptive/false picture about the availability of the vacant access. Power line and HT lines are still to be shifted and this work has not been started by the utility. 5. We have prepared a strip chart showing the existing encumbrance already enumerated in the Joint memorandum and appendix which is giving a clear picture of the percentage of length of project highway available on Appointed Date. As per this strip chart, only 63.26% of encumbrance free length has been made available. The minimum requirement of handing over of 90% of length of Project Highway as per Cl. 4.1.3 is not fulfilled for declaration of the Appointed Date. 6. Similarly, as per Clause 10.1.2 and Clause 18.1.2 of EPC agreement, the Authority Engineer should have been mobilised within 30 days from the date of signing of Agreement which was due on 14.11.2018. Even after seven months (from the date of signing of Agreement), the Authority Engineer has not been mobilised which is having its impact on the approvals of program, design and materials. 7. The Authority vide its recent circular — NHAI / Policy Guidelines / COS / 2019 / No.9.2.24 / 2019 dated 29.04.2019 has categorically mentioned that any Change of Scope / Reduction in Scope shall be finalised within a maximum period of 6 months from the Appointed Date. Hence the appointment of Authority Engineer is very crucial in deciding the COS / RIS and any further delay in appointment of Authority Engineer will have its impact on the as per the programme submitted by us as some crucial decisions and reviews are affected. Already three months have elapsed in the duration of six months given by the Authority. 8. In view of the above circumstances, we request you to kindly take a practical view and modify the Appointed Date already declared as 11.02.2019. This may be kindly modified to a date on which 90% of encumbrance free length of the Project Highway is made available to us. 9. Strip chart along with some photographs of the buildings to be dismantled, HT tower etc. are enclosed with this letter for your ready reference. This is for your information and further necessary action. | FALSE | real_data
Providing Right of Way as per Schedule A | Authority's Obligations, EoT, Dispute Resolution | It is pertinent to mention here, that the Authority is yet to fulfil the obligations relating to handing over of ROW as per Sub Clause 8.2of the Contract Agreement. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20210416_SPK_AE_067_EOT request with Delay analysis.pdf | Six laning of Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V -EOT recommendation by the Authority for a period of 112 days not agreeable to the EPC Contractor — Request for considering EOT as discussed during the Review Meetings- reg | We are writing to express our concerns regarding the EOT recommendation by the Authority for a period of 112 days, which is not agreeable to the EPC Contractor. We request that the EOT be considered as discussed during the Review Meetings. The project involves six laning of the Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km 71+015 to km 107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase-V. We have referenced several documents and meetings in support of our request, and we hope for a favorable consideration. | FALSE | real_data
Providing Right of Way as per Schedule A | Authority's Obligations, EoT, Dispute Resolution | As per this strip chart, only 63.26% of encumbrance free length has been made available. The minimum requirement of handing over of 90% of length of Project Highway as per Cl. 4.1.3 is not fulfilled for declaration of the Appointed Date. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/29_13052019_ Modifying the Appointed Date.pdf | Modifying the Appointed Date based on the length of project highway handed over in pursuant to Article 8 of EPC agreement - reg | 1. Pursuant to Clause 8.2.2 and 8.2.3 of the EPC Agreement, the Authority should have provided Right of way for 100% length of the project highway on appointed date plus 90 days, i.e. 11.05.2019. It is brought to your notice that this requirement has not been fulfilled by the Authority. 2. We also bring to your kind notice that the memorandum and appendix jointly signed on 11.01.2019 and submitted vide ref (3) cited above was prepared based on the available area without taking into consideration, the requirement of the contract provision as per Clause 4.1.3 (a) of the EPC agreement which talks about the handing over of land only in terms of length of the Project Highway. 3. When we started assessing the stretches affected in terms of length, we come to know that substantial length is affected due to existing buildings which are to be dismantled. The Authority has not started dismantling buildings at any location. The stretches passing through the villages are badly affected. 4. The memorandum and appendix prepared in terms of area is giving a deceptive/false picture about the availability of the vacant access. Power line and HT lines are still to be shifted and this work has not been started by the utility. 5. We have prepared a strip chart showing the existing encumbrance already enumerated in the Joint memorandum and appendix which is giving a clear picture of the percentage of length of project highway available on Appointed Date. As per this strip chart, only 63.26% of encumbrance free length has been made available. The minimum requirement of handing over of 90% of length of Project Highway as per Cl. 4.1.3 is not fulfilled for declaration of the Appointed Date. 6. Similarly, as per Clause 10.1.2 and Clause 18.1.2 of EPC agreement, the Authority Engineer should have been mobilised within 30 days from the date of signing of Agreement which was due on 14.11.2018. Even after seven months (from the date of signing of Agreement), the Authority Engineer has not been mobilised which is having its impact on the approvals of program, design and materials. 7. The Authority vide its recent circular — NHAI / Policy Guidelines / COS / 2019 / No.9.2.24 / 2019 dated 29.04.2019 has categorically mentioned that any Change of Scope / Reduction in Scope shall be finalised within a maximum period of 6 months from the Appointed Date. Hence the appointment of Authority Engineer is very crucial in deciding the COS / RIS and any further delay in appointment of Authority Engineer will have its impact on the as per the programme submitted by us as some crucial decisions and reviews are affected. Already three months have elapsed in the duration of six months given by the Authority. 8. In view of the above circumstances, we request you to kindly take a practical view and modify the Appointed Date already declared as 11.02.2019. This may be kindly modified to a date on which 90% of encumbrance free length of the Project Highway is made available to us. 9. Strip chart along with some photographs of the buildings to be dismantled, HT tower etc. are enclosed with this letter for your ready reference. This is for your information and further necessary action. | FALSE | real_data
Model code of conduct | EoT | We agree that model code of conduct was being in force and many activities were affected. Hence, we request the Authority to take this it into consideration as an event for extension of time if required. | synthetic_template_20250913 | Request for modification of appointed date - Reply made - reg. | from _all encroachments and encumbrances, and free access thereto for the execution of this agreement.” Even today, ROW handed over is not free from all encroachments and encumbrances. There are structures which are fouling within ROW which are to be dismantled. No action has been taken on this issue by the 2. It is also submitted that the following structures couldn’t be taken up due to encumbrances/ obstructions as given in the remark’s column in the table below. Bund, Buildi d_ shifti f electri 82/566 ¦ vup ¦ Hs ¦ Buildings, Hut and shifting of electric pole. 85/874 ¦ LvuP ¦ BHS ¦ Pylon ~ 2 Nos. (RHS) & Pond Bund (LHS). ¦S {93/115 ¦ vup ¦ Bris —¦ Buildings to be eno ¦ 6 ¦ 98/423 ¦ Vup ¦ BES _¦ Buildings to be removed. ¦ LHS ¦ Building and temporary shed to be removed. RHS Boundary wall, building, water tank and temporary structure. above mentioned structures is one year. The same is also endorsed in policy circular — Policy matters — Technical ( 195/2016) dated 19. 1.2016 of the Authority while determining Extension of Time. event for extension of time if required. However, it has been three weeks since model code of conduct has been lifted and work of removal of encumbrance/ obstruction has not been started. As per the discussion had with the appointed entity for utility shifting, it was identified and concluded that shifting of electrical poles in the already encumbered portion can be taken up only after removal of encumbrances/ obstructions as land was not available. Utility shifting is also interlinked with removal of encumbrance/encroachments. Hence i requested to remove the encumbrance and provide vacant acc Clause 8.1 of the Contract Agreement. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Model code of conduct | EoT | We agree that model code of conduct was being in force and many activities were affected. Hence, we request the Authority to take this it into consideration as an event for extension of time if required. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/49_17062019_ Modification of Appointed Date.pdf | Request for modification of appointed date - Reply made - reg. | from _all encroachments and encumbrances, and free access thereto for the execution of this agreement.” Even today, ROW handed over is not free from all encroachments and encumbrances. There are structures which are fouling within ROW which are to be dismantled. No action has been taken on this issue by the 2. It is also submitted that the following structures couldn’t be taken up due to encumbrances/ obstructions as given in the remark’s column in the table below. Bund, Buildi d_ shifti f electri 82/566 ¦ vup ¦ Hs ¦ Buildings, Hut and shifting of electric pole. 85/874 ¦ LvuP ¦ BHS ¦ Pylon ~ 2 Nos. (RHS) & Pond Bund (LHS). ¦S {93/115 ¦ vup ¦ Bris —¦ Buildings to be eno ¦ 6 ¦ 98/423 ¦ Vup ¦ BES _¦ Buildings to be removed. ¦ LHS ¦ Building and temporary shed to be removed. RHS Boundary wall, building, water tank and temporary structure. above mentioned structures is one year. The same is also endorsed in policy circular — Policy matters — Technical ( 195/2016) dated 19. 1.2016 of the Authority while determining Extension of Time. event for extension of time if required. However, it has been three weeks since model code of conduct has been lifted and work of removal of encumbrance/ obstruction has not been started. As per the discussion had with the appointed entity for utility shifting, it was identified and concluded that shifting of electrical poles in the already encumbered portion can be taken up only after removal of encumbrances/ obstructions as land was not available. Utility shifting is also interlinked with removal of encumbrance/encroachments. Hence i requested to remove the encumbrance and provide vacant acc Clause 8.1 of the Contract Agreement. | FALSE | real_data
Dismantling of structures | Authority's Obligations, EoT, Payments | We request your good self to arrange for removal of the structures and statues and provide encumbrance free land as per Clause 8.1, Article 8 of the EPC Agreement | synthetic_template_20250913 | Removal of Religious and Political statues- Reg. | Please note that We would like to bring to your kind notice that, there are few religious structures and political statues which are existing within the construction zone and are obstructing the construction activities. In this context, we request your good self to arrange for removal of the structures and statues and provide encumbrance free land as per Clause 8.1, Article 8 of the EPC Agreement, so as to enable us to proceed with the construction activities. The photographs along with chainage and location reference details of the structures / statues are enclosed for your ready reference. Thanking & assuring our best services always, | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Dismantling of structures | Authority's Obligations, EoT, Payments | substantial length is affected due to existing buildings which are to be dismantled. The Authority has not started dismantling buildings at any location. The stretches passing through the villages are badly affected. | synthetic_template_20250913 | Modifying the Appointed Date based on the length of project highway handed over in pursuant to Article 8 of EPC agreement - reg | Please note that 1. Pursuant to Clause 8.2.2 and 8.2.3 of the EPC Agreement, the Authority should have provided Right of way for 100% length of the project highway on appointed date plus 90 days, i.e. 11.05.2019. It is brought to your notice that this requirement has not been fulfilled by the Authority. 2. We also bring to your kind notice that the memorandum and appendix jointly signed on 11.01.2019 and submitted vide ref (3) cited above was prepared based on the available area without taking into consideration, the requirement of the contract provision as per Clause 4.1.3 (a) of the EPC agreement which talks about the handing over of land only in terms of length of the Project Highway. 3. When we started assessing the stretches affected in terms of length, we come to know that substantial length is affected due to existing buildings which are to be dismantled. The Authority has not started dismantling buildings at any location. The stretches passing through the villages are badly affected. 4. The memorandum and appendix prepared in terms of area is giving a deceptive/false picture about the availability of the vacant access. Power line and HT lines are still to be shifted and this work has not been started by the utility. 5. We have prepared a strip chart showing the existing encumbrance already enumerated in the Joint memorandum and appendix which is giving a clear picture of the percentage of length of project highway available on Appointed Date. As per this strip chart, only 63.26% of encumbrance free length has been made available. The minimum requirement of handing over of 90% of length of Project Highway as per Cl. 4.1.3 is not fulfilled for declaration of the Appointed Date. 6. Similarly, as per Clause 10.1.2 and Clause 18.1.2 of EPC agreement, the Authority Engineer should have been mobilised within 30 days from the date of signing of Agreement which was due on 14.11.2018. Even after seven months (from the date of signing of Agreement), the Authority Engineer has not been mobilised which is having its impact on the approvals of program, design and materials. 7. The Authority vide its recent circular — NHAI / Policy Guidelines / COS / 2019 / No.9.2.24 / 2019 dated 29.04.2019 has categorically mentioned that any Change of Scope / Reduction in Scope shall be finalised within a maximum period of 6 months from the Appointed Date. Hence the appointment of Authority Engineer is very crucial in deciding the COS / RIS and any further delay in appointment of Authority Engineer will have its impact on the as per the programme submitted by us as some crucial decisions and reviews are affected. Already three months have elapsed in the duration of six months given by the Authority. 8. In view of the above circumstances, we request you to kindly take a practical view and modify the Appointed Date already declared as 11.02.2019. This may be kindly modified to a date on which 90% of encumbrance free length of the Project Highway is made available to us. 9. Strip chart along with some photographs of the buildings to be dismantled, HT tower etc. are enclosed with this letter for your ready reference. This is for your information and further necessary action. We look forward to your response. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Mobilisation of Authority Engineer | Authority's Obligations | Moreover it should be noted that reasons submitted by the contractor for delay, the works, such appointment of AE and the procurement of borrow earth, is the prime responsibility of the Contactor. He has to apply for such permits before the Appointed Date, but unfortunately, these permits applied very late by the Contractor. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/20200827_AE_SPK_394_Delay in achieving of Project Milestones I and II.pdf | Delay in achieving of Project Milestones I and II - Reg | Dear Sir, In reference to the above-mentioned subject and Contractor letter refereed at (12) cited above, we would like to submit the following para wise reply: 1. Having gone through your disagreement with the approved for 112 days vide above said reference was reviewed and our comments was communicated through Ref. No.6. However, your contention for 324 vide above said No.4 by mentioning the points such as 1. Delay in handing over of ROW, 2. Delay in shifting of utilities, 3. Delay in Appointment of Authority Engineer 4. Delay in appointment of Proof & Safety Consultant & 5. Delay in procurement of Borrow earth was already addressed in our EoT recommendations letter. Hence, we stand by our earlier observations and reiterating the same issue is unprofitable. Further your request for 324 days and justifying yourself based on the above same grounds can’t be accepted. More ever, it should be noted that reasons submitted by the Contractor for delay, are nowhere concern with the delay in the works, such appointment of AE and the procurement of borrow earth, is the prime responsibility of the Contactor. He has to apply for such permits before the Appointed Date, but unfortunately, these permits applied very late by the Contractor. 2. The Extension of Time justifying for Mile Stone -1 based on the above said/suitable grounds was recommended vide C.C. CL. No. 10.5.1. & 2. Hence any delay in the Works effected due to the above reasons is already compensated in the EOT. However, mixing the same with WHOLE WORKS according Schedule “J” Point 6 is not accepted. This should also be noted that the progress of works is not appreciable even as on date. So, Contractor requested to please expedite the work progress instead of finding the reasons of delay. 3. Same as Point No.2 4. We reiterate that the approval of EoT for 112 days from the Competent Authority based on our recommendations and their own assessment. However, your disagreement on the same issue with the Authority is noted. 5. Same as point No.4. 6. Your contention for availability of land is deviating from the Joint Memorandum signed by both the parties. This issue was already addressed in the Point No.1. However, considering the balance in shifting of electrical utilities the EoT was recommended. But your contention to delay in achieving the Mile Stone due to non-shifting total electrical utilities is not acceptable. The AE do not agree the affected length as mentioned by the Contractor, however in case Contractor feels that encumbrances are not allowing him to proceed with the works, then Contractor may discuss with the Authority for the length not handed over in the Memorandum signed between the parties in light of Article 8 Right of Way of the Contract Agreement. 7. At no point of time the Authority Engineer has agreed to your contention of 324 days EoT. The AE opinion has been submitted while processing the EOT request. Presenting your grievances will not be accepted as approval of your contention for 324 days. It is requested to such one side conclusions shall not be accepted and they are beyond the good industry practice. Noted, but as mentioned in our letter as referenced No.9 and as on date the Project Mile Stone -3 has also lapsed where in which your stage payment certification should be 60% against which you achieved only 14.38%. This clear cut indicates in lack of progress at with in the available land itself. The delay in progress with specific points has already intimated to you vide our letter No’s SAICPL/Kar-Wal/TL/NH-48/TN/02B//71/2020/361, 367 & 380 Dated 10th July 2020, 23 July and 07th August 2020 respectively. Hence once again it is asked to mobilize your resources to achieve the required progress as per the scheduled completion date. | FALSE | real_data
Submission of Plan & Profile | Contractor's Obligations | The EPC contractor has already submitted plan and profile for a length of 10 Km from Km.71/015 to Km.81/OOO vide Lr.No.20/SPK/Kar - Wal/PD/NHA1 dated 03.04.2019. Hence, we disagree with the contention of the Authority that the EPC contractor has not submitted any designs for approval by Authority Engineer. | synthetic_template_20250913 | Request for modification of appointed date - Reply made - reg. | Kindly be informed that from _all encroachments and encumbrances, and free access thereto for the execution of this agreement.” Even today, ROW handed over is not free from all encroachments and encumbrances. There are structures which are fouling within ROW which are to be dismantled. No action has been taken on this issue by the 2. It is also submitted that the following structures couldn’t be taken up due to encumbrances/ obstructions as given in the remark’s column in the table below. Bund, Buildi d_ shifti f electri 82/566 ¦ vup ¦ Hs ¦ Buildings, Hut and shifting of electric pole. 85/874 ¦ LvuP ¦ BHS ¦ Pylon ~ 2 Nos. (RHS) & Pond Bund (LHS). ¦S {93/115 ¦ vup ¦ Bris —¦ Buildings to be eno ¦ 6 ¦ 98/423 ¦ Vup ¦ BES _¦ Buildings to be removed. ¦ LHS ¦ Building and temporary shed to be removed. RHS Boundary wall, building, water tank and temporary structure. above mentioned structures is one year. The same is also endorsed in policy circular — Policy matters — Technical ( 195/2016) dated 19. 1.2016 of the Authority while determining Extension of Time. event for extension of time if required. However, it has been three weeks since model code of conduct has been lifted and work of removal of encumbrance/ obstruction has not been started. As per the discussion had with the appointed entity for utility shifting, it was identified and concluded that shifting of electrical poles in the already encumbered portion can be taken up only after removal of encumbrances/ obstructions as land was not available. Utility shifting is also interlinked with removal of encumbrance/encroachments. Hence i requested to remove the encumbrance and provide vacant acc Clause 8.1 of the Contract Agreement. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Submission of Plan & Profile | Contractor's Obligations | The EPC contractor has already submitted plan and profile for a length of 10 Km from Km.71/015 to Km.81/OOO vide Lr.No.20/SPK/Kar - Wal/PD/NHA1 dated 03.04.2019. Hence, we disagree with the contention of the Authority that the EPC contractor has not submitted any designs for approval by Authority Engineer. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/49_17062019_ Modification of Appointed Date.pdf | Request for modification of appointed date - Reply made - reg. | from _all encroachments and encumbrances, and free access thereto for the execution of this agreement.” Even today, ROW handed over is not free from all encroachments and encumbrances. There are structures which are fouling within ROW which are to be dismantled. No action has been taken on this issue by the 2. It is also submitted that the following structures couldn’t be taken up due to encumbrances/ obstructions as given in the remark’s column in the table below. Bund, Buildi d_ shifti f electri 82/566 ¦ vup ¦ Hs ¦ Buildings, Hut and shifting of electric pole. 85/874 ¦ LvuP ¦ BHS ¦ Pylon ~ 2 Nos. (RHS) & Pond Bund (LHS). ¦S {93/115 ¦ vup ¦ Bris —¦ Buildings to be eno ¦ 6 ¦ 98/423 ¦ Vup ¦ BES _¦ Buildings to be removed. ¦ LHS ¦ Building and temporary shed to be removed. RHS Boundary wall, building, water tank and temporary structure. above mentioned structures is one year. The same is also endorsed in policy circular — Policy matters — Technical ( 195/2016) dated 19. 1.2016 of the Authority while determining Extension of Time. event for extension of time if required. However, it has been three weeks since model code of conduct has been lifted and work of removal of encumbrance/ obstruction has not been started. As per the discussion had with the appointed entity for utility shifting, it was identified and concluded that shifting of electrical poles in the already encumbered portion can be taken up only after removal of encumbrances/ obstructions as land was not available. Utility shifting is also interlinked with removal of encumbrance/encroachments. Hence i requested to remove the encumbrance and provide vacant acc Clause 8.1 of the Contract Agreement. | FALSE | real_data
Removal of Encumbrances and Encroachments from the ROW | EoT, Authority's Obligations | In view of the above, we once again request your office to arrange for handing over of the balance land & removal of encumbrances at the earliest. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-2/10. 20240109_191_Cont_AE_Request of handing of Balance land & Removal of Emcumbrances.pdf | Request for handing over of balance land & clearance of encumbrances & encroachments within the ROW- (Reminder-1)- Reg. | Please refer to our letter at #2 above, wherein we have requested for handing over of the balance hindrance-free Right of Way (ROW). As intimated in our letter, the land available with the Contractor for execution of the works as on that date was only 32.758 Kms out of 69.978 Kms which is 46.81% of the total length of the project. The details of the land available as on date is tabulated below & detailed chainages are shown in the strip map annexed herewith. Even after two months from our above referred letter, the land availability status remains same, as no further land is cleared / handed over by the Authority. We are progressing with the works at few of the locations where land acquisition is not yet complete, by convincing the land owners. However, there is a risk of the land owners stopping the work at any point in time. Though we have achieved the 1* Milestone much earlier than the scheduled date, we are running out of work fronts for achieving further progress, which will have a negative impact on the subsequent milestones. In view of the above, we once again request your office to arrange for handing over of the balance land & removal of encumbrances at the earliest. | FALSE | real_data
Providing Right of Way in terms of length of Project Highway | Authority's Obligations, Appointed Date | The appointed date was declared as 11.02.2019 by the Authority taking into account the land handed over in terms of area in lieu of the linear length as per Clause 4.1.3 (a) of the EPC agreement. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/40_07082019_Rescheduling of Project Milestones – Request for Extension of time.pdf | Rescheduling of Project Milestones - Request for Extension of time - Reg. | The Contract agreement for the above mentioned project was executed on 15.10.2018. The appointed date was fixed as 11.02.2019 and the same was communicated vide ref (3) cited above. The Copy of the same is herewith enclosed as Annexure 1. The Authority in its response vide ref (5) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. The copy of the same is enclosed as Annexure 3. The EPC contractor vide ref (6) cited above reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that still the condition remained the same and dismantling/ removal of structures fouling was not started and shifting of Electric pole and power line also not started. The impacted length due to encroachments and encumbrances was 12.18 Km which accounted to 33.77% of the project highway. The workable length available to the Contractor based on the impacted length was 66.23% of the Project Highway length. The EPC Contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of removal of encumbrance / encroachment / obstruction. The copy of ref (7) is herewith enclosed as Annexure 4. It is almost six months since the declaration of appointed date, removal/ dismantling of structures/encroachments have not been started. Also, the work of shifting of power line and electric pole of LT line and HT lines crossings have not been started yet. The following are some of the key contractual dates and events since the inception of the project to till date: 1. Total length of the project highway: 36.076 Km 2. Date of Signing of agreement: 152018 3. Submission of Performance BG as per Clause 7.1.1 of the Contract Agreement: 262018 4. Target date for preparation of Memorandum as per Clause 8.2.1 of the Contract Agreement: 142018 5. Actual date of signing of Memorandum of land handing over: 112019 6. Declaration of appointed date by the Authority: 112019 7. ROW to be handed over as on appointed date as per Clause 8.2.2 & Annexure II: 35.468 Km | FALSE | real_data
Labour License | Contractor's Obligations | The engagement of contract labour in the above said work is not prohibited under sub section (1) of section 10 of the Contract Labour (Regulation and Abolition) Act, 1970 (37 of 1970). | synthetic_template_20250913 | Form of Certificate of Principal Employer | Certified that National Highways Authority of India (NHAI), a body corporate under the Ministry of Road Transport & Highways, Government of India having its Corporate office at Plot G - 5 & 6, Sector -10, Dwaraka, New Delhi 100 075 through Project Implementation Unit, Kancheepuram have engaged M/s. S.P.K. & Co, Reg. Off 2/67, R.C. Middle Street, Keelamudimannarkottai, Kamuthi Taluk, Ramnad District 623 603 as contractor in this establishment for the work of “Six laning of karaipettai to Walajapet section of NH4 (New NH-48) from Km 71+015 to Km 107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase V” to be carried out from 11.02.2019 to 10.02.2021 for a period of two year. NHAI undertake to be bound by the provisions of the Contract Labour (Regulation and Abolition) Act 1970 (37 of 1970) and Contract Labour (Regulation and Abolition) Central Rules 1971, in so far as the Provisions are applicable to NHAI in respect of the Employment of Contract Labour by M/s. S.P.K. & CO in this establishment. The engagement of contract labour in the above said work is not prohibited under sub section (1) of section 10 of the Contract Labour (Regulation and Abolition) Act, 1970 (37 of 1970). Thank you for your attention to this matter. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Labour License | Others | The engagement of contract labour in the above said work is not prohibited under sub section (1) of section 10 of the Contract Labour (Regulation and Abolition) Act, 1970 (37 of 1970). | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/1316_28062019_Issue of Form III for Labour License.pdf | Form of Certificate of Principal Employer | Certified that National Highways Authority of India (NHAI), a body corporate under the Ministry of Road Transport & Highways, Government of India having its Corporate office at Plot G - 5 & 6, Sector -10, Dwaraka, New Delhi 100 075 through Project Implementation Unit, Kancheepuram have engaged M/s. S.P.K. & Co, Reg. Off 2/67, R.C. Middle Street, Keelamudimannarkottai, Kamuthi Taluk, Ramnad District 623 603 as contractor in this establishment for the work of “Six laning of karaipettai to Walajapet section of NH4 (New NH-48) from Km 71+015 to Km 107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase V” to be carried out from 11.02.2019 to 10.02.2021 for a period of two year. NHAI undertake to be bound by the provisions of the Contract Labour (Regulation and Abolition) Act 1970 (37 of 1970) and Contract Labour (Regulation and Abolition) Central Rules 1971, in so far as the Provisions are applicable to NHAI in respect of the Employment of Contract Labour by M/s. S.P.K. & CO in this establishment. The engagement of contract labour in the above said work is not prohibited under sub section (1) of section 10 of the Contract Labour (Regulation and Abolition) Act, 1970 (37 of 1970). | FALSE | real_data
Approval for Proof Consultant conveyed | Contractor's Obligations | Proof Consultant by the Contractor M/S. S.P.K & Co., approval is hereby conveyed to the firm M/S. Professional Civil Infra Pvt. Ltd., as a Proof Consultant for the above project. | synthetic_template_20250913 | Six laning of Karaipettai to Walajahpet section of NH-48 (old NH-4) from km.71+015 to km.107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase V-Appointment of Proof Consultant- Approval -Reg. | It is brought to your attention that Apropos your letter cited under reference seeking approval for engaging Proof Consultant by the Contractor M/s. S.P.K & Co., approval is hereby conveyed to the firm M/s. Professional Civil Infra Pvt. Ltd., as a Proof Consultant for the above project. Thank you for your attention to this matter. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Letter of Award issued by the Authority | Authority's Obligations, Others | Letter of Award | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km. 71+015 to Km 107+091 on EPC Mode in the state of Tamil Nadu under NHDP Phase-V- Letter of Award-Reg. | This is to notify that your bid submitted for the project of “Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km. 71+015 to Km 107+091 on EPC Mode in the state of Tamil Nadu”, is hereby accepted by NHAI for the contract price of Rs. 533,36,67,000/- (Rupees Five Hundred Thirty Three Crore Thirty Six Lakh and Sixty Seven Thousand Only) and declaring you a “Selected Bidder”. 2. In accordance with the Clause 3.3.4 of the RFP document (Volume-l), you are requested to sign the duplicate copy of the LOA and return the same as your acknowledgement within 7 (Seven) days of the receipt of LOA. It is requested to deliver a legal opinion from your legal counsel with respect to your authority to enter into Contract Agreement and the enforceability of the provision thereof, within 10 (Ten) days of issue of this LOA. 3. Further, as per RFP documents, the Contractor for due and faithful performance of its obligations during the Construction Period as well as Defects Liability Period required to furnish a Performance Security by way of an irrevocable and unconditional Bank Guarantee of Rs. 26,66,83,350/- (Rupees Twenty Six Crore Sixty Six Lakhs Eighty Three Thousand Three Hundred and Fifty Only) within 10 days from the date of signing of the Contract Agreement. The Performance Security shall be valid until 60 (sixty) days after the Defects Liability Period. (refer Clauses of Article-7 of EPC Agreement). 4. You are requested to Comply with the above and all the terms and conditions set forth in the RFP documents. In case of any default on your part, you shall be liable for action as stated in the RFP Document. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
BG's for Performance Security and Additional Performance Security | Contractor's Obligations | performance of its obligations during the Construction Period as well as Defects Liability Period required to furnish a Performance Security by way of an irrevocable and unconditional Bank Guarantee of Rs. 26,66,83,350/- (Rupees Twenty Six Crore Sixty Six Lakhs Eighty Three Thousand Three Hundred and Fifty Only) within 10 days from the date of signing of the Contract Agreement. The Performance Security shall be valid until 60 (sixty) days after the Defects Liability Period. (refer Clauses of Article-7 of EPC Agreement | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km. 71+015 to Km 107+091 on EPC Mode in the state of Tamil Nadu under NHDP Phase-V- Letter of Award-Reg. | This is to notify you that This is to notify that your bid submitted for the project of “Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km. 71+015 to Km 107+091 on EPC Mode in the state of Tamil Nadu”, is hereby accepted by NHAI for the contract price of Rs. 533,36,67,000/- (Rupees Five Hundred Thirty Three Crore Thirty Six Lakh and Sixty Seven Thousand Only) and declaring you a “Selected Bidder”. 2. In accordance with the Clause 3.3.4 of the RFP document (Volume-l), you are requested to sign the duplicate copy of the LOA and return the same as your acknowledgement within 7 (Seven) days of the receipt of LOA. It is requested to deliver a legal opinion from your legal counsel with respect to your authority to enter into Contract Agreement and the enforceability of the provision thereof, within 10 (Ten) days of issue of this LOA. 3. Further, as per RFP documents, the Contractor for due and faithful performance of its obligations during the Construction Period as well as Defects Liability Period required to furnish a Performance Security by way of an irrevocable and unconditional Bank Guarantee of Rs. 26,66,83,350/- (Rupees Twenty Six Crore Sixty Six Lakhs Eighty Three Thousand Three Hundred and Fifty Only) within 10 days from the date of signing of the Contract Agreement. The Performance Security shall be valid until 60 (sixty) days after the Defects Liability Period. (refer Clauses of Article-7 of EPC Agreement). 4. You are requested to Comply with the above and all the terms and conditions set forth in the RFP documents. In case of any default on your part, you shall be liable for action as stated in the RFP Document. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
BG's for Performance Security and Additional Performance Security | Contractor's Obligations | 1. We had submitted the Performance Security and Additional Performance Security in the form of Bank Guarantees (PBG and APBG) vide our letters dated 28.09.2021 and 02.11.2021. 2. Contractor have discharged its prime obligation i.e. submission of Performance Security and Additional Performance Security, well within time limit. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-1/8. Request to grant an Extension of Time under Clause 10.5 of the Contract Agreement..pdf | Request to grant an Extension of Time under Clause 10.5 of the Contract Agreement | 1. This is with reference to our various representations/submissions regarding various events on delay which has adversely affected the construction activities of Project and are still persisting at site resulting delay in completion of construction works as per scope envisaged under Contract Agreement. 2. We take this opportunity to summarize the facts chronologically as below giving rise to the claim for an Extension of Time (“EOT”) in accordance with the provisions of this Agreement on account of various delay events. Contract Particulars: Development Corporation Limited Authority Engineer Accepted Contract Price Construction Period Appointed Date 26.11.2021 Stipulated Completion Date ¦ 19.05.2023 Request for EOT by this 135 days Cl 01.10.2023 Revised Completion Date Background Facts: 3. The National Highway & Infrastructure Development Corporation Limited (“Authority”) had issued the LOA dated 02.09.2021 (Ref#01) in favor of B.R Goyal Infrastructure Limited (“Contractor"). The formal Contract Agreement was signed on 08.10.2021. In pursuant to the conditions of LOA, we had submitted the Performance Security and Additional Performance Security in the form of Bank Guarantees (PBG and APBG) vide our letters dated 28.09.2021 and 02.11.2021 (Ref #2 & 4 above). It is in place to mention that the Contractor have discharged its prime obligation i.e. submission of Performance Security and Additional Performance Security, well within time limit. To ensure the start of construction activities immediate after declaration of Appointed Date, Contractor has mobilized the adequate manpower & machinery resources at site after receiving of LOA. In pursuant to the provisions of the Contract Agreement, Authority’s primary obligation is to provide the 90% length of ROW within 30 days from the date of Agreement. However, after signing of CA, both the parties visited the site and it | FALSE | real_data
Fly ash supply | Others, EoT, Payments, Contractor's Obligations | In this regard, as per Article 3 (Obligations of the Contractor) of the Contract agreement, it is the responsibility of the contractor for the procurement of the materials, obtaining necessary permissions for materials etc. Further as per Article 6.1.1 of CA, the Contractor has to visit the site and made independent evaluation of RFP and scope of the project before submission of bid. As such procurement of materials involved in this regard is solely the contractor's responsibility only. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/20221108_PD_SPK_3511_Procurement of Ash from Thermal Power plant.pdf | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet section of NH-4 from Km 71/015 to Km 107/091 in the State of Tamilnadu — Procurement of Fly ash from Thermal Power Plant - Reg. | This has reference to the letter cited above, wherein the EPC Contractor requesting for the Authority support towards procurement of fly ash from the ash supplying agencies. In this regard, as per Article 3 (Obligations of the Contractor) of the Contract agreement, it is the responsibility of the contractor for the procurement of the materials, obtaining necessary permissions for materials etc. Further as per Article 6.1.1 of CA, the Contractor has to visit the site and made independent evaluation of RFP and scope of the project before submission of bid. As such procurement of materials involved in this regard is solely the contractor’s responsibility only. In this regard, the Plan & Profile / GAD has approved during July 2019 & March 2020 itself for structures i.e.,VUP/SVUP/flyover with filling materials for approaches as Soil only. As per the statement furnished by the Authority Engineer as on 10.10.2022, the total borrow earth quantity required is 20 Lakh Cum. However, the contractor has applied borrow earth permission for about 4.7 lakhs Cum and obtained permission for 3.41 lakh Cum which are now filled with water ie., lake area. Further, from the records available at PIU office, it is observed that the contractor M/s.SPK & Co, requesting only NHAI to obtain approval & support for supply of fly ash from the ash supplying agencies and the contractor never made any direct correspondence with the agencies till date regarding supply of fly ash, even though procurement of material is contractor obligation as per CA. As such the Contractor has made correspondence to NHAI only on 25.11.2019, 05.12.2020, 07.12.2020 & 20.08.2021 and after August 2021, no request has been received from the Concessionaire regarding Fly Ash. The Deputy Secretary to Govt. of India, Ministry of Power vide circular no. 9/7/2011-S.Th (Vol.IV) dated 22.09.2021, informed the following: The power plants shall provide the Fly Ash to end users through a transparent bidding process only. If after bidding/ auction some quantity of Fly Ash still remains un-utilized, then only, as one of the options, it could be considered to be given free of cost on first come first served basis if the user agency is willing to bear transportation cost. If ash remains unutilized even after the steps taken in Paras 2.1 and 2.2 above. TPP shall bear the transportation of fly ash to be provided free to eligible projects. The end users shall be obligated to source the fly ash from the nearest TPPs to reduce the cost of fly ash transportation. If the nearest TPP refuses to do so, the end user project shall approach Ministry of Power for appropriate directions. The fly ash will be offered to the end users on the competing demand basis, i.e the end users who offer the highest price for fly ash and seek minimum support for transportation cost will be offered the same fly ash on priority. This will reduce the tariff of electricity and burden on the consumers. However, the Contractor never made any direct correspondence with the agencies till date and not at all participated in the bidding/auction towards procurement of fly ash. As such it is clearly evident that not even minimum efforts have been made by the Contractor till date regarding procurement of fly ash. In this context, this office letter no.2597 dated 04.09.2021 also, it was already requested to coordinate with the Fly ash supplying agency to facilitate the supply of fly ash to the project site. Subsequently, based on the Review Meeting conducted by Chairperson, NHAI on 18.08.2022, it was instructed that “the contractor to apply for entire quantity of borrow earth permission immediately”. However, after Chairperson NHAI meeting held in Chennai on 18.08.2022. | FALSE | real_data
Fly ash supply | Others, EoT, Payments, Contractor's Obligations | In view of the above, it is informed that the Contractor is not entitled to claim any delays/ extension of time or any benefit on behalf procurement of fly ash / borrow earth material or any additional cost involved in this regard, the contractor is solely responsible and Authority is not responsible for any additional cost in regarding procurement of material. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/20221108_PD_SPK_3511_Procurement of Ash from Thermal Power plant.pdf | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet section of NH-4 from Km 71/015 to Km 107/091 in the State of Tamilnadu — Procurement of Fly ash from Thermal Power Plant - Reg. | This has reference to the letter cited above, wherein the EPC Contractor requesting for the Authority support towards procurement of fly ash from the ash supplying agencies. In this regard, as per Article 3 (Obligations of the Contractor) of the Contract agreement, it is the responsibility of the contractor for the procurement of the materials, obtaining necessary permissions for materials etc. Further as per Article 6.1.1 of CA, the Contractor has to visit the site and made independent evaluation of RFP and scope of the project before submission of bid. As such procurement of materials involved in this regard is solely the contractor’s responsibility only. In this regard, the Plan & Profile / GAD has approved during July 2019 & March 2020 itself for structures i.e.,VUP/SVUP/flyover with filling materials for approaches as Soil only. As per the statement furnished by the Authority Engineer as on 10.10.2022, the total borrow earth quantity required is 20 Lakh Cum. However, the contractor has applied borrow earth permission for about 4.7 lakhs Cum and obtained permission for 3.41 lakh Cum which are now filled with water ie., lake area. Further, from the records available at PIU office, it is observed that the contractor M/s.SPK & Co, requesting only NHAI to obtain approval & support for supply of fly ash from the ash supplying agencies and the contractor never made any direct correspondence with the agencies till date regarding supply of fly ash, even though procurement of material is contractor obligation as per CA. As such the Contractor has made correspondence to NHAI only on 25.11.2019, 05.12.2020, 07.12.2020 & 20.08.2021 and after August 2021, no request has been received from the Concessionaire regarding Fly Ash. The Deputy Secretary to Govt. of India, Ministry of Power vide circular no. 9/7/2011-S.Th (Vol.IV) dated 22.09.2021, informed the following: The power plants shall provide the Fly Ash to end users through a transparent bidding process only. If after bidding/ auction some quantity of Fly Ash still remains un-utilized, then only, as one of the options, it could be considered to be given free of cost on first come first served basis if the user agency is willing to bear transportation cost. If ash remains unutilized even after the steps taken in Paras 2.1 and 2.2 above. TPP shall bear the transportation of fly ash to be provided free to eligible projects. The end users shall be obligated to source the fly ash from the nearest TPPs to reduce the cost of fly ash transportation. If the nearest TPP refuses to do so, the end user project shall approach Ministry of Power for appropriate directions. The fly ash will be offered to the end users on the competing demand basis, i.e the end users who offer the highest price for fly ash and seek minimum support for transportation cost will be offered the same fly ash on priority. This will reduce the tariff of electricity and burden on the consumers. However, the Contractor never made any direct correspondence with the agencies till date and not at all participated in the bidding/auction towards procurement of fly ash. As such it is clearly evident that not even minimum efforts have been made by the Contractor till date regarding procurement of fly ash. In this context, this office letter no.2597 dated 04.09.2021 also, it was already requested to coordinate with the Fly ash supplying agency to facilitate the supply of fly ash to the project site. Subsequently, based on the Review Meeting conducted by Chairperson, NHAI on 18.08.2022, it was instructed that “the contractor to apply for entire quantity of borrow earth permission immediately”. However, after Chairperson NHAI meeting held in Chennai on 18.08.2022. | FALSE | real_data
Fly ash supply | Others, EoT, Payments, Contractor's Obligations | It is learnt that, considering the lead from the source of Fly-Ash material the Contractor is presently not having any plans to utilize the same. Hence our compliance is attached accordingly. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-7/20191109_AE_PD_161-Consumption requirement of Fly Ash.pdf | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Consumption requirement of Fly Ash -Reg. | With respect to the above said Ref. No.1 please find attached here with the information relating to the usage Fly-Ash in the ongoing Karaipettai to Walajapettai Project. It is learnt that, considering the lead from the source of Fly-Ash material the Contractor is presently not having any plans to utilize the same. Hence our compliance is attached accordingly. Assuring our best services at all times. | FALSE | real_data
Pond ash supply | Others, EoT, Payments, Contractor's Obligations | In view of the above, it is requested to take necessary action to supply fly ash to the site as requested by the contractor at the earliest after following procedure in vogue. | synthetic_template_20250913 | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet Section of NH - 4 (New NH-48) from Km. 71+015 to km. 107+091 in the State of Tamil Nadu under NHDP (Phase V) under Bharatmala Pariyojana on EPC Mode - Supply of Fly Ash by NTECL - Reg. | This is with reference to the meeting held with the undersigned by AGM, NTECL on 07.01.2020 at NHAI Office at Tambaram, it is informed that the contractor vide letter 1 cited above, requested this office to request NTECL to supply fly ash (approx. 13 lakh MT) for the said project. In this regard your attention is invited to the MoEF notification S.0. 254(E) dated 25th January 2016 wherein it was directed to use fly ash in construction of road or flyover embankments within a radius of 300 Km of a thermal power plant and the relevant paragraph are as follows: “10. The cost of transportation of ash for road construction projects or for manufacturing of ash based products or use as soil conditioner in agriculture activity within a radius of hundred kilometers from a coal or lignite based thermal power plant shall be borne by such coal or lignite based thermal power plant and the cost of transportation beyond the radius of hundred kilometers and up to three hundred kilometers shall be shared equally between the user and the coal or lignite based thermal power plant. The present road stretch mentioned in the subject is within 300 Km from the power plant. In view of the above, it is requested to take necessary action to supply fly ash to the site as requested by the contractor at the earliest after following procedure in vogue. We look forward to your response. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Filing of affidavit | Others | counter affidavit file on behalf of M/s NTECL in Hon'ble High Court of Madras | synthetic_template_20250913 | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet section of NH-4 from Km 71/015 to Km 107/091 in the State of Tamilnadu under residual NHDP (Phase — V) under Bharathmala Pariyojana on EPC Mode - Proposal for Utilization of Fly Ash from M/s. NTECL Vallur Thermal Power Projects - Reg. | This has reference to the letter cited 01st above, where in the Contractor has requested this office to obtain in principle approval from the nearby Thermal Power Plant M/s. NTECL Vallur Thermal Power Project for utilization of Pond ash for Construction of Road embankments. In this regard, as per Article 3.1.7 (Obligations of the Contractor) of the EPC Contract agreement, “The Contactor shall, at its own cost and expense, in addition to and not in derogation of its obligations elsewhere set out in this Agreement: (b) procure, as required, the appropriate proprietary rights, licenses, agreements and permissions for Materials, methods, processes and systems used or incorporated into the Project Highway”. From the above clause, it is clear that it is the responsibility of the contractor for the procurement of the materials, obtaining necessary permissions for materials etc. However, based on the request of the EPC Contractor - M/s. S.P.K & Co vide letter dated 07.12.2020, this office vide letters dated 15.12.2020 and 11.02.2021 requested the nearby Thermal Plant M/s. NTECL (NTPC Tamilnadu Energy Company Limited) to supply Fly ash to the site as per the MoEF notification S.O. 254 (E) dated 25th January 2016. Further, this office vide letter dated 28.06.2021, communicated the counter affidavit filed on behalf of M/s. NTECL in Hon’ble High Court of Madras in W.P No.33323 of 2019, wherein the current status and the availability of Fly ash has been submitted by M/s. NTECL. In view of the above, it is requested to coordinate with the Fly ash supplying agency M/s. NTECL and to facilitate the supply of Fly ash to the Project site. We await your further instructions. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Tree cutting | Contractor's Obligations, Authority's Obligations, EoT | It is requested to accord permission for felling of existing trees in the Govt. (NHAI) lands at the earliest | synthetic_template_20250913 | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet section of NH-4 from Km 71/015 to Km 107/091 (36.076 Km) in the State of Tamil Nadu - Felling of Trees in NHAI Lands - Reg. | This has reference to the Six laning of Karaipettai to Walajahpet section of NH-4 from Km 71/015 to Km 107/091 in the State of Tamil Nadu. In this regard, it is submitted that The Project Stretch from Km 85/910 to Km 107/091 passes through Ranipet District in the state of Tamil Nadu. Authority executed the Contract Agreement with M/s.S.P.K & Co., on 15.10.2018 and the appointed date has been declared with effect from 11.02.2019. The contractor for the project M/s.S.P.K & Co., has submitted report on the existing trees on Govt. (NHAI) in the Chennasamudram User Fee Plaza in the Ranipet District. As per the report, total 15 no. of trees in Govt. (NHAI) lands falling under Ranipet District which are needed to be felled towards the ongoing six lanning works and for the formation of the New User Fee Plaza at Chennasamudram. These trees had been planted by NHAI itself in the Public funded User Fee Plaza at Chennasamudram at Km 104/900 during the Four laning of Kanchipuram to Walajahpet Section (NH4) from Km 70/200 to Km 106/400 which was completed on 23rd Mar 2004 under Golden Quadrilateral Programme. Further, as a part of compensatory planting at 1:10 ration, ie., 150 No.s of trees shall be planted. The contractor has to do Median Plantation, Avenue Plantation and Landscaping at Toll Plaza as pr the Contract Agreement. Further, the Contractor has already completed the Median Plantation for a length of 12.00 Km. The details of the trees are given below; As per the G.O. issued by the Environmental, Climate Change and Forest (FR.13) dated 02.07.2021, permission of the Green Committee is required for felling of trees so that encumbrance free land can be provided to the contractor for commencement of New User Fee Plaza at Chennasamudram. In view of the above, it is requested to accord permission for felling of existing trees in the Govt. (NHAI) lands at the earliest. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Appointment of Safety & Proof Consultants | Contractor's Obligations | No impact on the preparation and approval of Design and Drawings due to delay in approval of Proof and Safety Consultant. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/189_Rescheduling of Project Milestones - EOT - 1.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under BharatmalaPariyojana on EPC mode — Rescheduling of Project Mile Stone- Request for Extension of Time -Reg. | Having gone through your documents related to Rescheduling of Project Milestone-Request for Extension of Time EoT-1 please find enclosed herewith the Authority Engineers recommendations on the same subject. This is for your information and necessary action. | FALSE | real_data
Appointment of Safety & Proof Consultants | Contractor's Obligations | In view of the above based on the experience the Consultant namely M/ s. RODES Infra Consultancy Services LLP appears to be suitable among the three names of qualified and experienced firms proposed by the Contractor as per clause 10.2.2 of contract agreement. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LOT-10/Lr.No.711_27042019_Appoinment of safety consultant (2).pdf | NHAI, PIU - Krishnagiri - Six laning of Karaipettai to Walajahpet section of NH-48 (old NH-4) from km.71+015 to km.107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase V- Request for appointment of Safety Consultant - Reg. | 2. Vide reference 294 cited the contractor M/s. S.P.K& Co.., has informed that as per the Provisions of clause 10.1.5 of the contract,“ The Contractor shall appoint the Safety Consultant (“ The Safety Consultant) to carry out safety audit at the design stage of the project highway in accordance with the applicable law and good industry practice. The Safety Consultant shall be appointed after Proposing to the Authority a panel of three names of qualified and experienced firm from whom the authority may choose one to be the safety Consultant...” 3. Accordingly the Contractor M/s. S.P.K & Co., has Proposed the following firms as Safety Consultants: , i M/s. RODES Infra Consultancy Services LLP. ii. M/s. Hivistra Projects Private Limited. iii, M/s. MNJ Consulting Engineers. 4, Vide reference 15t cited this office has circulated the details of Safety consulting firms with their key professionals through NHAI website on all. Division of PIUs of NHAI and requested to int | FALSE | real_data
Memorandum and Appendix | Appointed Date, Contractor's Obligations, Authority's Obligations | be available for joint inspection for preparation of memorandum from 1st January, 2019 to January, 2019. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km.71+015 (Existing Km 71/000) to Km 107+091 (Existing Km 107/068) on EPC Mode in the state of Tamil Nadu under NHDP Phase-V - Joint inspection for preparation of Memorandum - reg. | With reference to your request for joint inspection and preparation of Joint Memorandum vide letter dated S1.No.2 cited above, we would like to inform you that our team will be available for joint inspection for preparation of memorandum from 1% January, 2019 to 3 January, 2019. Kindly confirm your convenience to make necessary arrangements. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Change of scope proposal | Change of Scope | The approximate cost with the new 8+8 lane provisions is worked out to 18,14,66,425 and there is a savings of 5.68 Crores. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/Lot-11/20200821_AE_PD_392 - Provision of Toll Plaza at Ch. Km. 104+917 (Chennasamudram Village).pdf | Consultancy services for Authority's Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode - Provision of Toll Plaza at Ch. Km. 404+917 (Chennnasamudram Village) - Reg | Sir, It is to inform that as per the present Scope of Works vide Annexure -1 Schedule - C Clause 2.1 the number of Toll Lanes to be made at the Chennasamudram Toll Plaza are 24. However, based on the NHAI H.Q. letter No. NHAI/ Policy Guide Lines/ Civil Works/ 2019 No. 40.01.20/2019 dated 18.01.2019 which was communicated to us through above said Ref No.2 it is understood that the number of Toll Lanes to be re-designed duly considering Hybrid ETC system. Accordingly, it is to apprise that the number of Toll Lanes required at the Chennasamudram Village Toll Plaza located at Ch. Km. 104+917 are as illustrated below: It may be recalled that after getting necessary instructions from A.E. Contractor has conducted the Traffic Survey in this package near the proposed Toll Plaza location during the period of 3 to 5 September 2019 and the summary of Annual Average Daily Traffic (AADT) are as reproduced below: .No. Type of Vehicles ¦ Vehicles 2 ¦ Auto Rikshaw 451 . ill Car/ Zeep/ Van 10094 10094 Mri (op) Fat ° Page 1 of 3 | FALSE | real_data
Change of scope proposal | Change of Scope, EoT, Dispute Resolution, Payments | the Contractor is requested to submit the tentative implication towards increase in width of covered drain from Km.106.190 to Km.106.380 under provisions of Clause 13.1 | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/Lot-12/20241003_AE_SPK_1856_Thankadapanthangal village-provision of Increase in Drain width to 2.5m instead of 1.5m as per CA-From Km.106+190 to km 106+380(RHS)-Request to issue as COS(+).pdf | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajapet from km 71.015 to107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode — Thankadapanthangal village- Provision of “Increase in Drain width to 2.5m instead of 1.5m as per CA” — From Km.106+190 to Km 106+380(RHS)- Request to Issue as COS(+) for this Additional Scope of Work in accordance with Sub Clause 13.2.1 of Article-13 of Contract Agreement-Reg | This has reference to above cited letters, the Contractor requested to issued COS notice to construct covered drain with increased width from Ch. Km. 106+190 to 106+380 to cater the water flow from nearby existing wier/spillway. in this regard, the provisions of Schedule-B are as under: 6.13 (a) - A list of existing pipe culverts was given and these culverts are to be reconstructed. Under notes to this table, it was mentioned that the length, number of structures and bridges specified herein above shall be treated as an approximate assessment. The actual lengths as required on the basis of detailed investigations shall be determined by the Contractor in accordance with the Specifications and Standards. Any variations in lengths & numbers specified in this Schedule-B shall not constitute a Change of Scope. No culvert was provisioned between Km.106.190 to Km 106.380 in this list. i) 6.13 (b) — Under this head, a list of pipe culverts was mentioned and these culverts are to retained and widened. It was mentioned that the number/span/length of the culverts mentioned in above table is indicative and any change is deemed to be within ‘scope of works and no Change of Scope will be considered. No culvert was provisioned between Km.106.190 to Km 106.380 in this 6.13 (b) (i) — The Slab culverts provided in this table are to be retained and widened. In notes, it was mentioned that the number/span/length of the culverts mentioned in above table is indicative and any change is deemed to be within scope of works and no Change of Scope will be considered. No culvert was provisioned between Km.106.190 to Km 106.380 in this list. 6.13 (b) (ii) - The Slab culverts provided in this table are to be reconstructed. No culvert was provisioned between Km.106.190 to Km 106.380 in this list. There were no minor bridge nor major bridge was provisioned in the mentioned a Earlier, the water spilled from weir was flowing along the Main Carriageway to low laying areas. Now, the Services Road is constructed in the same alignment of free waterflow stream. Hence, the spilled water was hitting the drain directly which will disturb the foundation of the drain. in view of the above, a site visit of NHAI officials was conducted and wherein it was opined to construct a 2.5M width drain from Ch. Km. 106+190 to 106+380 i.e for a length of 190 m to carry the inflow towards the nearby culvert. Hence it was decided to collect the water of the wier as well as from the Service Road in to the proposed outer drain as per TCS-5 with an increase in width of drain. Accordingly, the works are being executed for construction of Drain & Service Road which will also be the part of diversion for the Pedestrian underpass located at Ch. Km. 106+010. As mentioned, there was no specific provision for a culvert at this location, the Contractor is requested to submit the tentative implication towards increase in width of covered drain from Km.106.190 to km.106.380 under provisions of Clause 13.1 so as to appraise the Authority for its decision/in-principal approval in this regard. | FALSE | real_data
Change of scope proposal | Change of Scope, EoT, Dispute Resolution, Payments | In view of the above, approval of the Competent Authority is solicited for the Final Change of Scope Proposal amounting to Rs.41,07,41,491/-( inclusive of 18% GST) | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/Lot-12/20230622_PD_RO_1509_Request for approval of COS after including Toll plaza COS.pdf | NHAI, PIU, Kancheepuram — Six Laning of Karaipettai to Walajahpet Section of NH-4 from Km 71/015 to Km 107/091 in the State of Tamilnadu under residual NHDP (Phase - V) under Bharathmala Pariyojana on EPC Mode - Final Change of Scope Proposal - Reg | This has reference to the letter cited 4% cited above, wherein the Authority Engineer - M/s. SA Infrastructure Consultants Pvt Ltd submitted the Final Change of Scope Proposal amounting to Rs.40,46,51,588/- towards Construction of Additional Service roads in Kancheepuram District, Additional Underpass (LVUP), Cattle Underpass and Pedestrian Underpass along the subject project. 2. In this context, the following are submitted; a) M/s.S.P.K & Co., has been awarded the work of Six laning of Karaipettai to Walajahpet section of NH-4 from Km 71/015 to Km 107/091 in the State of Tamil Nadu under NHDP Phase -V. Salient features of the contract is as below:- Total Length 36.076Km Date of Agreement 15.10.2018 Contract Value Rs.533.37 Cr Mode of Implementation EPC Duration of Contract 24 Months Construction Period 24 Months (730 Days) O&M Period /DLP Period 48 Months (DLP Period) Appointed Date 11.02.2019 Schedule date of Construction completed 09.02.2021 b) Based on various representations received from Shri. G. Selvam, Hon’ble Member of Parliament, The District Collector, Ranipet District and Local Public for Construction of Additional Service roads in Kancheepuram District, Additional Underpass (LVUP), Cattle Underpass and Pedestrian Underpass along the subject project, the Competent Authority, NHAI HQs vide letter cited 224 above, accorded in-principle approval for the Change of Scope Proposal for an amount of Rs.39,85,58,903/- as follows S. No. Description Amount (Rs.) (i) Service Road - 12,25,76,464 (ii) LVUP at Thiruppukuzhi Jn at Km 80/060 12,03,66,631 (iii) CUP at Dhamal lake Jn at Km 84/032 1,03,36,041 (iv) PUP at Musiri Village at Km 106/010 5,62,03,609 (v) Total Civil Cost 35,27,06,994 (vi) GST @ 12% on (vi) 4,23,24,839 (vii) Labour cess @ 1% of Civil Cost (vi) 35,27,070 (viii) Total Cost 39,85,58,903 Subsequently, the Settlement Agreement has been signed on 07.01.2023, both parties (NHAI & the Contractor) agreed to the work programme as given by the Contractor as follows; * By 31.03.2023, progress must be 67% (12% during the quarter) * By June 2023, progress must be 86% (19% during the quarter) * By 30% September 2023, progress must be 96% (10% during the quarter) | FALSE | real_data
Change of scope proposal | Change of Scope, Dispute Resolution, Payments | We are herewith forwarding the Contractor proposals to attain in-principal approvals from "Competent Authority" so as to commence the works. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/Lot-11/20210202_AE_PD_537-Change of Scope Proposal.pdf | Consultancy services for Authority's Engineer for Supervision of Six Lanning of Karaipettai to Walajapet from km 71.015 to107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode - Change of Scope Proposal - Reg. | Sir, Vide above said reference No’s from 4 to 12 considering the requests from different sources, Contractor has submitted a COS proposal numbered as COS-2 to make underpasses and service roads at the following locations by justifying the reasons. Se J Additional Scattered District Road 30,18,95,386 To segregate service roads locations Safety Council the local traffic Kancheepuram of each district. from the Main Dt. — 2.05 Km Carriageway so Ranipet Dt. - as to reduce 1.85 Km. the accidents. Page 1 of 3 3 It's is Additional Hon'ble There Underpass Member of temple, School MOST (LVUP @ size Parliament & and Bank on Identified 1x12x4.0 Local either side of Black Residents. the toad. Spot Hence considering the previous record of fatal accidents. | FALSE | real_data
Change of scope proposals clarifications | Payments, Dispute Resolution, Change of Scope, EoT | We once again bring to your notice that the issue of discount of 9.66% applied in the COS approval by the Authority was brought out in the meeting held with CGM(T) on 01.10.2021 at NHAI HQ which was attended by the DGM(T) Tamil Nadu, NE-IAI HQ, PD -PIU Kancheepuram and the Team Leader of the AE, along with representative of the EPC Contractor and it was informed by the CGM(T), Tamil Nadu NHAI that revised approval on the COS works will be issued by waiving off the applied "Discount of 9.66% which is awaited till date. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-6/20211030_SPK_AE_154_REPLY to AE “ Progress of Works intimated under COS.pdf | Change of Scope Proposal - REPLY to AE “ Progress of Works intimated under Change of Scope Proposals - reg | Dear Sir,\n\nYour kind attention is invited to our letter cited at (3) above. The in-principle approval of Cost Estimate towards COS (Change of Scope) works was communicated vide ref (2) above by the Authority.\n\nThe EPC Contactor responded to the Authority vide ref(3) above and informed that the “in-principal approval of COS communicated, a discount of 9.66% has been deducted in the Total Civil Cost amounting to Rs.3,40,71,496/- (Rupees Three crore forty lakhs seventy-one thousand four hundred and ninety-six) from the Total Civil Cost towards COS of Rs 35,27,06,944/- and clarified that this deduction is against the provisions of the Contract Agreement.\n\nAlso the EPC Contractor made further observations on the COS approved by the Authority and the same was communicated vide ref(4) above.\n\nFurther the PD, PIU Kancheepuram has also communicated vide reference (5) to the Authority Engineer to examine the points raised by the EPC Contractor and requested the Authority Engineer to submit a report on the clarification sought by the EPC Contractor.\n\nWe once again bring to your notice that the issue of discount of 9.66% applied in the COS approval by the Authority was brought out in the meeting held with CGM{(T) on 01.10.2021 at NHAI HQ which was attended by the DGM(T) Tamil Nadu, NHAI HQ, PD -PIU Kancheepuram and the Team Leader of the AE, along with representative of the EPC Contractor and it was informed by the CGM(T), TamilNadu NHAI that revised approval on the COS works will be issued by waiving off the applied “Discount of 9.66%” which is awaited till date.\n\nFor information; the EPC Contractor have already submitted the Plan and Profile Drawings for the Service Road and Grade separators location vide our letter cited at (7) above and the EPC Contractor have also commenced the COS start up works at the follow locations:\n\n1. Km75+580 to 76+240LHS -C&G,Excavation upto EmbTop in ProgressRHS LA Issue\n\n2. Km 77+400 to 78+100 LHS -C&G Completed\n\n3. Km 88+160 to 88+560 BHS -C&G Completed\n\n4. Km 94+640 to 94+860 BHS - C&G Completed\n\nImmediately after the receipt of revised COS order from the Authority, the EPC Contractor shall take up the works in full swing depending on the impact of prevailing monsoon and availability of borrow earth.\n\nIt is worth mentioning that the EPC Contractor is facing constraints in completing the original scope of works as the same is also affected at various isolated locations due to delay in communicating the revised approval of COS.\n\nWe hereby request the AE to provide detailed report sought by the Authority vide ref (5) above which shall enable the Authority in issuing revised COS order at the earliest.\n\n | FALSE | real_data
Change of scope proposals clarifications | Payments, Dispute Resolution, Change of Scope, EoT | You are hereby asked to submit the survey data in the enclosed format duly explaining the necessity of additional works for understanding and easy approvals from the Competent Authority. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/Lot-12/20200806_AE_SPK_377-Observations on Change of Scope proposal submitted.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode — Observations on Change of Scope proposal submitted - Reg. | in continuation to the above said Reference you are hereby asked to submit the survey data in the enclosed format duly explaining the necessity of additional Works for proper understanding and easy approvals from the Competent Authority. This is for your information and necessary action. | FALSE | real_data
Contractor's delay in submission of COS Proposals | Change of Scope, Contractor's Obligations, Dispute Resolution | It is to remind that your compliance to our earlier communication stated as reference No.1 relating to the COS proposals is long awaited. Please accord priority and comply. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/Lot-11/20201228_AE_SPK_507_Change of Scope Proposal reminder.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode — Change of Scope Proposal - Reg. | Dear Sir, It is to remind that your compliance to our earlier communication stated as Reference No.1 relating to the COS proposals is long awaited. Please accord priority and comply. With Regards, Yours faithfully, CH Balakrishna Team Leader cum Senior Highway Engineer, S.A. Infrastructure Consultants Pvt. Ltd., Kar-Wal, Six Lanning Project, Package-ll, Kancheepuram Copy to: 1. The Project Director, NHAI, PIU — Kancheepuram. 2. H.O. S.A. Infrastructure Consultants Pvt. Ltd. Con, OF I Aa ED Lares CS ye rc ae a ee www.sainfra.com | FALSE | real_data
change of scope due to local demand for additional structures, service road, utility ducts | Change of Scope, EoT, Dispute Resolution, Payments | FOB @ Km.84/050, The Project Director stated that instead of providing the FOB in such a remote location it is better to provide the same at a suitable location | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/119_01102019_Minutes of Monthly Progress review meeting Mom -3.pdf | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to 107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Minutes of Monthly Progress review meeting Mom -3 -Reg. | With respect to the above said reference please find enclosed herewith the minutes of meeting MoM -3 held on 25.09.2019. The venue and date for the next meeting will be intimated in due course of time. This is for your information and record. Assuring our best services at all times. | FALSE | real_data
change of scope due to local demand for additional structures, service road, utility ducts | Change of Scope, EoT, Dispute Resolution, Payments | the Authority Engineer has gone through the request for Construction of vehicular Underpass by the local villagers of village Thenkadapanthangal, Pulithangal and Musri of Walajahpet. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/Lot-11/20210224_563-Request for Vehicular Underpass at Tenkadapathangal & Musiri Villages Ch. Km. 106+000.pdf | Consultancy services for Authority's Engineer for Supervision of Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode — Request for Vehicular Underpass at Tenkadapathangal & Musiri Villages Ch. Km. 106+000 - Reg. | Sir, In reference to the above subject and letters, the Authority Engineer has gone through the request for construction of Vehicular Underpass by the local villagers of village Thenkadapanthangal, Pulithangal and Musiri of Walajahpet. The provision was discussed at length with the Design Team of Authority’s Engineer in consideration of site and the observation on the same are as follows: 1. It is observed that a Fly-Over is proposed at Ch.106+677 which is 677m ahead of the proposed location. It is submitted that the RE Wall approach for the Fly-Over starts from Ch. 406+320 and ends at Ch. Km. 106+990. However, Service road is proposed throughout this section. However, the local are demanding for an Underpass/Subway at Km 106+000. The designer found that and Underpass/Subway of 3m vertical height with desirable horizontal clearance as per the width of the cross-road carriageway may be proposed at Ch. 106+000 as requested by the local residents. As per the request made by the local resident, the underpass is to be constructed for the T-Junction located at Ch. 106+000. However, it is observed that at this location there is no embankment filling for the proposed road for which there will be additional raising required for the FRL of the proposed road. | FALSE | real_data
change of scope proposal | Change of Scope, EoT, Dispute Resolution, Payments | In view of the above, considering the safety of the Villagers, Road Users and to avoid any road mishap, it is recommended to provide additional service roads, LVUP, Cattle/Pedestrian Underpass, Foot over Bridges and Subway/pedestrian Underpasses on the above said locations and approval is solicited for an amount of Rs.44,65,72,437/- | synthetic_template_20250913 | NHAI, PIU, Kancheepuram - Six Laning of Karaipettai to Walajahpet Section of NH-4 from Km 71/015 to Km 107/091 in the State of Tamilnadu under residual NHDP (Phase — V) under Bharathmala Pariyojana on EPC Mode — Change of Scope Proposal 02 - Reg | Please note that I submit that, vide reference 18t cited above, the Authority Engineer — M/s. SA Infrastructure Consultants Pvt Ltd recommended the Comprehensive Change of Scope Proposal to obtain approval from the Competent Authority of NHAI for Rs. 44,65,72,437/- including GST for various representations received such as from Shri. G. Selvam, Hon’ble Member of Parliament, The District Collector, Ranipet District and Local Public vide 12t» to 224 reference cited above for Construction of Additional Service roads in Kancheepuram District, Additional Underpass (LVUP), Cattle Underpass and Pedestrian Underpass respectively. 2. Based on the above representations/requests received along the subject Project Stretch, the Authority Engineer vide letter 10" cited above recommended the Change of Scope Proposal submitted by the Contractor amounting for Rs. 93,85,74,885/- including GST. 3. After the scrutiny of the proposal, this office vide letter cited 9th above, recommended the Change of Scope proposal and approval of the competent authority was solicited for an amount of Rs. 102.06 Cr including GST towards providing Additional Service Roads in Kancheepuram & Ranipet District, Additional Underpass (LVUP) at Thiruppukuzhi Junction Km 80/060, Cattle/Pedestrian Underpass at Dhamal Lake Junction Km 84+032, Underpasses in Avalur Village at Km 89+124, in Srikarumbur Village at 94+090, in Bagaveli Village at 102+134 and Vehicular Underpass at Tenkadapathangal & Musuri Village at 106+000 respectively. Thank you for your attention to this matter. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
change of scope proposal | Change of Scope, EoT, Dispute Resolution, Payments | In view of the above, the Authority Engineer hereby recommends the Change of Scope (No.2) Proposal due to additional Service Road Provision, one no. of CUP at Km.84+032, one No.Underpass @ 80+060, Foot Over Bridge at Dhamal Colony i.e.@ Km 81+600 instead of at 84+032, two Foot Over Bridges at 89+120 & 94+040 and subway at ch. Km.106+010 as mentioned above amounting to Rs.44,65,72,437/- | synthetic_template_20250913 | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode—Resubmission of Change of Scope Proposal-2 -Reg. | In reference to the above-referred chronology of correspondence and based on the recent site visits on 3 & 17 of June, 2021, Contractor had submitted the revised Change of Scope -2 proposals vide letter No. 084 stated as Ref. No.1. to an amount of Rs/- 56,71,88,373. The submitted proposal reviewed by AE as per provision of the Contract Agreement and following is being submitted for ready reference and further needful, please; There are some additional works require based on the request received from Hon’ble Member of Parliament, Hon’ble Member of Legislative Assembly, Local District Level Authorities and as well as from the Local Residents. The same is being examined and considered for the COS-2. The details and the expenditure on each proposal is being worked out and submitted for the Approval of Competent Authority. Additional Service Roads in Kancheepuram & Ranipet District jurisdictions: It may be noted that the Project stretch, which is having a length of 36.076 Kms from Karaipettai to Walajhpet i.e. between Chainages 71+015 to 107+091 is in the territory of two districts namely Kancheepuram & Ranipet. The project length of 14.859 kms is under Kancheepuram District i.e. between 71+015 to 85+874. In Kancheepuram District, there is a shortage of service road provision. Hence the District Admission made a representation to the Authority (endorsed vide Ref. No.23) to have a continuous service road provision which will avoid merging & demerging of service road traffic with MCW. In view of this a survey was conducted and found that the service road provision has to be made between 75+580 to 76+240 & 77+400 to 78+800 which come to a length of 660+700 = 1360 Rmts. The same is being considered in this COS-2. Similarly, for the Ranipet district out of 21.145 kms length i.e between Ch. Km. 85+874 to 107+019 there is a shortage of service road provision. Hence as the similar representation was received from the District Safety Council of Ranipet District (Which was endorsed to this office vide ref. No.24) a survey was conducted and proposed to have the service road provision between Chainages 88+160 to 88+560 & 94+640 to 94+860 i.e. 220+400 = 620 Rimts lengths. Hence total length of additional service road proposed is 1360+620 = 1980 Rmts. Thiruppukuzhi Junction. (BLACK SPOT No. TN-02 /146) Ch. Km. 80+060. There is a cross road junction called Thiruppukuzhi at Ch. Km.80+060. On either side of the Project Highway there are temples, Primary school, Banks and it is one of the junction connecting the Baluchetty residents to other side of Carriageway. Nearer to this junction there is another junction called Musrivakkam at Ch. Km. 79+860. In similar fashion to the other junction, residents of Baluchetty village are crossing the Highway for their daily needs. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Contractor's delay in commencing the COS works | Change of Scope, Contractor's Obligations, Dispute Resolution | It is to note that despite Competent Authority's intimation vide above said reference No.1 relating to in-principle approvals to the additional works, efforts to commence these works are yet to be seen at site. Hence, it has been advised to commence the approved CoS works on priority. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode — Progress of Works intimated under Change of Scope proposals. | Dear Sir, It is to note that despite of Competent Authority's intimation vide above said reference No.1 relating to the in-principle approvals to the additional Works, efforts to commence these works are yet to be seen at site. You are aware that while according approvals to the EoT proposals it is informed that “The Contractor shall strictly adhere to the construction program submitted by him and complete the balance works including CoS works during this extended period by augmenting resources” Hence it has been advised to commence the approved CoS works on priority. This is for your information and necessary actions. With Regards, CH Balakri a a Team Leader cum‘ Senior Highway Engineer, S.A. Infrastructure Consultants Pvt. Ltd., Kar-Wal, Six Lanning Project, Package-ll, Kancheepuram Copy to: 1. The Project Director, NHAI, PIU — Kancheepuram. 2. H.O. S.A. Infrastructure Consultants Pvt. Ltd. EAE «1 1101A, 11th Floor, Tower A-ll, Corporate Park, Uttar Pradesh. INDIA. Tel. :+91-120-6148000 ¦ | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Rejection of COS request by Authority Engineer/Authority | Change of Scope, Payments, Dispute Resolution, EoT | In the view of the Contract Provision and IRC Specification, the Authority Engineer opines that Contractor request for COS does not attract the any variation from the scope of work. Thus request for consider COS is being rejected herewith. | synthetic_template_20250913 | Six lanning of Karaipettai to Walajahpet Section of NH-4 (New NH-48) from Km 71+015 (Existing Km 71+000) to Km 107+091 (Existing Km 107+068) on EPC mode in the State of Tamil Nadu under NHDP Phase-V) - Change of Scope Proposal- Clarification on Proposal for Increasing the Height of the Existing RCC barrier for (i) ROB at Km 72+200 (ii) Flyover at Km 106+687 (RHS) as per Contract Agreement Provisions- Reg. | Dear Sir, With respect to the above subject and letter stated in ref No: (5), the Contractor has submitted the clarification regarding proposal for increasing the RCC barrier height @ ROB at Km 72+200 & Flyover at Km 106+687 (RHS) for which our comments are as follows: 1) The Contractor submitted the drawings vide letter stated as Ref No (3) and requested for positive COS & Extra time for the work of Existing RCC barrier (i) ROB at Km 72+200 (ii) Flyover at km 106+687(RHS), the same has been replied vide AE letter as stated in above Ref No (4). 2) Further to AE letter, Contractor once again submitted clarifications & requested for COS vide letter stated in above Ref No (5), the same has been reviewed and submit that as per Clause 6.16 of Schedule B of the Contract, ““*“RR — Repair & Rehabilitation” which clearly states that “The repairing and restoration work such as protection work, replacement of railing by crash barrier, Replacement of bearing and expansion joint, wearing coat, spalling & corroded reinforcement, RE wall panel, MBCB etc. of bridge is not limited and any other item as per site condition shall be carried out as per direction of Authority / Independent Engineer. Any Change in location of above structure or change in approaches length not consider under Change of Scope’. he Page 1 of 2 | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Rejection of COS request by Authority Engineer/Authority | Change of Scope, Payments, Dispute Resolution, EoT | In the view of the Contract Provision and IRC Specification, the Authority Engineer opines that Contractor request for COS does not attract the any variation from the scope of work. Thus request for consider COS is being rejected herewith. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/Lot-11/20220127_AE_SPK_839_Change of Scope Proposal as per Article -13 of Contract Agreement-Proposal of Increasing the Height of the Existing RCC barrier for (i) ROB at Km 72+200 (ii) Flyover at Km 106+687 (RHS).pdf | Change of Scope Proposal as per Article -13 of Contract Agreement-Proposal of Increasing the Height of the Existing RCC barrier for (i) ROB at Km 72+200 (ii) Flyover at Km 106+687 (RHS) - Reg. | Dear Sir,\n\nIn reference to the subject matter and under letter ref (3), the Contractor has submitted the proposal for increasing the height of the existing RCC barrier for (i) ROB at Km 72+200 (ii) Flyover at Km 106+687(RHS) as COS proposal as per article-13 of Contract Agreement.\n\nIn this regards the Authority Engineer, issued the Monthly Progress review report vide letter no.785 dated 29.11.2021 and requested to the Contractor that “After laying of the DBM on the existing ROB at 72 km & at Fly over 106 km the height of the RCC Crash barrier has been reduced and further it will reduce after laying the BC. Hence it is advised to raise the height of the Crash barrier by\n\nproviding a Gl Pipe or any other suitable provision.”\n\nIt is submitted that, the existing height of the Crash barrier at ROB is averaging height 650 mm and similarly for flyover it is around 747mm. Thus, the EPC Contractor as requested to the Authority Engineer to increase the height of the Crash barrier as per IRC standard to 4.4m (1100mm).\n\nThe Contractor submitted the drawing with GI pipe over the top of Crash barrier to ensure requisite height as per IRC standards. And the length of railing provided for ROB and Flyover (RHS) are 881.259 and 685 m respectively. In this regard, the Contractor requested for positive COS & Extra time for the work of Existing RCC barrier (i) ROB at Km 72+200 (ii) Flyover at km 106+687(RHS). | FALSE | real_data
Design & Drawings for COS works | EoT, Payments, Dispute Resolution, Change of Scope, Others | Based on the above it is requested to recalculate the drain invert levels and to be resubmitted. | synthetic_template_20250913 | Change of Scope - Submission of Drain Invert Level Profile for Service Road (COS) Locations - Reg. | We would like to inform you that With respect to the above said reference regarding Submission of Drain Invert Levels following observations are communicated: a) At the following locations Drain and Road uniform offset of 225mm is not achieved. (i) 75+560 to 76+200 BHS (ii) 77+500 to 78+100 BHS (iii) 88+130 to 88+560 BHS Kindly correct the drain top levels accordingly to maintain the 225mm level difference. b) At the following locations Drain is shown on inner side (i.e., in between Service Road & Main Carriage Way), whereas it has to be in extreme outer side of Service Road as per present site condition. (i) 75+480 to 75+550 BHS (ii) 76+200 to 76+340 BHS (iii) 77+300 to 77+500 LHS 77+370 to 77+530 RHS (iv) 88+060 to 88+130 BHS (v) 94+860 to 94+960 BHS Hence based on the above it is requested to recalculate the Drain Invert levels and to be resubmitted. The Contractor is further requested to resubmit the revised drawing along with modifications marked in RED in the previous submission which is enclosed | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Design & Drawings for COS works | EoT, Payments, Dispute Resolution, Change of Scope, Others | Based on the above it is requested to recalculate the drain invert levels and to be resubmitted. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/Lot-11/20220131_AE_SPK_847_Change of Scope - Submission of Drain Invert Level Profile for Service Road (COS) Locations.pdf | Change of Scope - Submission of Drain Invert Level Profile for Service Road (COS) Locations - Reg. | With respect to the above said reference regarding Submission of Drain Invert Levels following observations are communicated: a) At the following locations Drain and Road uniform offset of 225mm is not achieved. (i) 75+560 to 76+200 BHS (ii) 77+500 to 78+100 BHS (iii) 88+130 to 88+560 BHS Kindly correct the drain top levels accordingly to maintain the 225mm level difference. b) At the following locations Drain is shown on inner side (i.e., in between Service Road & Main Carriage Way), whereas it has to be in extreme outer side of Service Road as per present site condition. (i) 75+480 to 75+550 BHS (ii) 76+200 to 76+340 BHS (iii) 77+300 to 77+500 LHS 77+370 to 77+530 RHS (iv) 88+060 to 88+130 BHS (v) 94+860 to 94+960 BHS Hence based on the above it is requested to recalculate the Drain Invert levels and to be resubmitted. The Contractor is further requested to resubmit the revised drawing along with modifications marked in RED in the previous submission which is enclosed | FALSE | real_data
Change of Scope Approval/order | Payments, Change of Scope, EoT, Dispute Resolution | Contractor is requested not to execute any COS work at site "without issuance of COS order" | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-6/20200624_AE_SPK_341_Change of Scope Provision of the Contract.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode — Change of Scope Provision of the Contract -Reg. | In continuation to provision of Change of Scope given in the Concession Agreement, please find attached herewith NHAI Circular no. 9.2.34/2020 dated 10 June 2020 para 5 (iii) regarding execution of COS at site. The para 5 (iii) is reproduced below: - “No Change of Scope shall be executed unless the Authority has issued the Change of Scope Order. Instructions given during inspections/meetings shall not be treated as approval to go ahead with execution of COS until formal approval of Competent Authority is obtained. Concerned Authority Engineer and project Director shall be held responsible for any failure on this account.” In view of above Concessionaire/Contractor is requested not to execute any COS work at site “without issuanceof COS order” or “formal approval of Competent Authority is obtained”. Any work executed by the Concessionaire/Contractor before issuanceof COS order or formal approval of Competent Authority, shall be solely at risk and Cost of the Contractor/Concessionaire. Authority Engineer shall not be held responsible for any failure on this account. | FALSE | real_data
QAP, EMP, EHS and Construction Programme | Contractor's Obligations | 1. Appointment of representative of Contractor 2. Appointment of Design Director 3. Submission of Programme etc., | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-3/4. Time schedule of Activity 15.05.2017.pdf | Rehabilitation and Upgradation of Ghogaspargaon-Phu Shirur-Rakshasbhuvan-Kholayachiwadi-Karegaon-Dongarkini-Chumbii-Patoda-Digho! Road Kharda. From KM 0+000 to KM 56+000 fo two lanes with paved shouiders | Dear Sir, With reference to the above mentioned subject and letter, we would like to convey the status of time schedule of activities as stated below: 1. Appointment of "Representative of Contractor" within 20 (Twenty) days of the Appointed date. 2. Appointment of "Design Director" within 30 (Thirty) days of the Appointed date. 3. Submission of the "Programme" within 30 (Thirty) days of the Appointed date. 4. Submission of "Quality Assurance Plan" will be submitted by 01.06.17. 5. Appointment of "Safety Consultant" at earliest (Before commencement of work). 6. Appointment of "Proof Consultant" at earliest. This is for your information and necessary action please. | FALSE | real_data
QAP, EMP, EHS and Construction Programme | Contractor's Obligations | The Project Director asked to develop a revised completion programme | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/119_01102019_Minutes of Monthly Progress review meeting Mom -3.pdf | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to 107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Minutes of Monthly Progress review meeting Mom -3 -Reg. | With respect to the above said reference please find enclosed herewith the minutes of meeting MoM -3 held on 25.09.2019. The venue and date for the next meeting will be intimated in due course of time. This is for your information and record. Assuring our best services at all times. | FALSE | real_data
Change in location of structures as per site requirement | Payments, Others | it was proposed to shift the Flyover to Km. 72+650. | synthetic_template_20250913 | Change of location for Flyover @ 72+760 - Reg. | We wish to draw your kind attention to our site visit along with RO regarding various issues. As per Schedule-B of the Contract Agreement (CA), a Flyover / Animal Underpass (3v x 25 m) is to be constructed at Km. 72+760 and the stretch falls under Wildlife Zone. The width of the structure is 12m, resting on RCC open foundations and I-girders. The applicable cross-section on the approaches of the flyover as per Schedule-B is TCS-9 for the stretch from Km. 72+350 to Km. 73+290. As per Annex-ll of Schedule-A, the Right of Way (ROW) is 20m between Km 72+460 to Km 73+396. The scope of work includes olf the existing 7m road to 12.9m overall width. The existing road level is 200.399 and the FRL of the proposed structure is 208.685, thus the road top level is increasing by more than 8m at this location. As you are aware, two High Tension (HT) grid lines are crossing the Project Highway at Km. 72+850 and Km 72+940 at a height of 10.2 m and 7.6 m respectively from the existing road top, with FRL of 208.403 and 207.251 respectively. Hence the minimum vertical clearance requirement of 8.5m (5.5m vertical clearance + 3m for Induction) is not being met at these two locations. During the recent Site Visit with RO and your good self, this issue was discussed at site and it Was proposed to shift the Flyover to Km. 72+650. The original ground level at this location is 4m below the existing road top level, i.e., approximately 196.77m. Thus, the structure can be fitted as per the proposed GAD in the CA, simultaneously ensuring the vertical clearance between the ground level and soffit of the structure. In view of the above, we request your office to kindly arrange for necessary approval from the Forest Department, to proceed with construction of the Flyover/Animal Underpass at the revised location at the earliest. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Change in location of structures as per site requirement | Payments, Others | Few culverts have been shifted to the appropriate locations | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-1/11. Change in loc of culverts.pdf | Change of location of culverts - Reg. | With reference to the above subject, we would like to inform your good self that during joint site inspection with the representatives of AE and Authority, few culverts have been shifted to the appropriate locations as mentioned in the enclosed statement. The reasons for change in location is due to- . 1) Un-matching of CA location with the existing culvert location and existing stream/ water way locations. 2) Culverts which are not possible to construct due to built-up section as the buildings exist on both sides of proposed location and there is no water way/ stream noticed. This is for your information and record please. | FALSE | real_data
Requirement of Additional land | Authority's Obligations | The available ROW of 45m is not adequate to accommodate the carriageways, slip roads, drain along with utility corridors on both sides. | synthetic_template_20250913 | Additional Land required at 20+100 VOP - Reg. | With reference to the subject matter, we wish to bring to your kind notice that as per Schedule-B of the Contract Agreement (CA), an Overpass (VOP) should be constructed at Km 20+100 along the N.A.M expressway, as a Grade separated structure. As per the typical cross section (TCS-6), there is no provision for utility corridor at the edge of the slip roads. The available ROW of 45m is not adequate to accommodate the carriageways, slip roads, drain along with utility corridors on both sides. However, there are existing utilities within the proposed Right of Way which need to be relocated. In view of the above we request you to take-up the issue with the concerned Authorities and take necessary action for acquiring the necessary land and resolve the issue so that the work progress will not be affected. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Change of scope request for additional works or works not in the scope | Payments, Dispute Resolution, Change of Scope, EoT | Mandatory Monthly drone recording communicated from your end vide ref(4) above is additional works and services which are not included in the Sope of the project as contemplated by this Agreement (" the Change of Scope"). | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-6/20210924_SPK_AE_133_Mandatory Monthly Drone Video Recording of Project Highway during the Development, Construction and O&M Period – Request to initiate COS -Reg..pdf | Mandatory Monthly Drone Video Recording of Project Highway during the Development, Construction and O&M Period - Request to initiate COS -Reg. | The Mandatory Monthly Drone recording of Project Highway during Development, Construction and O&M period as per the NHAI/Policy Guidelines ref (2) cited is being taken up by the EPC Contractor and submitted the Drone Based Video Recording for the last 3 months — however the EPC Contractor would like to represent the following: 1. The requirement of Mandatory Monthly Drone recording communicated from your end vide ref (4) above is additional works and services which are not included in the Scope of the Project as contemplated by this Agreement (“the Change of Scope’). 2. Pursuant to Clause 13.1.1 of the Contract Agreement,” Any such Change of Scope shall be made and valued in accordance with the provisions of this Article 13”. Drone Based Video Surveying of the Project Highways as per the Policy circular issued by NHAI HQ is being carried out with the NHAI empanelled agency M/s. Marvel Geospatial Solutions Pvt. Ltd and the Rates per kilometer for the Drone Based Video Surveying are as per NHAI guidelines excluding the overhead and other charges. We hereby request to issue “Change of Scope” notice as per Clause 13.2.1 of the Contract Agreement for mandatory monthly drone recording of Project Highway. The Drone Survey will be conducted in presence of Authority’s Representatives hereby ensuring that no inconvenience caused to the road users or any public. Since the Employer has requested to carry out this additional work of Drone Based Video Recording for uploading in NHAI datalake, the EPC Contractor, though not in his scope, had carried out the Drone Based Survey for the past three months covering the proposed ROW, showing chainages, Median Centreline etc. which will be uploaded in the NHAI datalake shortly, anticipating that the same shall be considered under positive COS by the Authority. We kindly request the Authority Engineer to forward this COS notice request and recommend for getting the approval by the Authority at the earliest in order to facilitate the Contractor in submitting the requisite data. | FALSE | real_data
Release of Performance security | Payments, Dispute Resolution | This is with reference to the Office Memorandum from Ministry of Finance, GOI dated 13-05-2020 (ref 1 above) on return of Performance Security in view of Force Majeure due to COVID-19 | synthetic_template_20250913 | Request for release of Performance Security due to COVID-19 as per Ministry office memorandum | This is with reference to the Office Memorandum from Ministry of Finance, GOI dated 132020 (ref 1 above) on return of Performance Security in view of Force Majeure due to COVID-19. As notified vide our above letters, the project progress has suffered badly in terms of time and cost due to land unavailability initially and due to occurrence of Force Majeure event (outbreak of Corona Virus) and subsequent lockdown in the recent past. Due to this there was huge idling of resources, disruption in payment schedule and cash flow issues which will affect future progress of the project. In order to mitigate the difficulties being faced by Contractors, the central government has issued the above stated Office Memorandum mentioning that “the contractor M/S RCM Infrastructure Ltd. — P V Ramanaiah & Co_JV (Government Department/Agency) may return the value of performance security to the contractor/supplier as is proportional to the supplies made/contract work completed to the total contract value”. Accordingly, we wish to avail the facility of revising the Bank guarantee (BG) for reduced amounts of Performance security, in place of original submitted BGs, for the amount equal to the latest stage payment (IPC-15), as mentioned below which will ease our credit facilities with the banks for better cash flow & in turn improve the progress of works. Original & Proposed Bank Guarantee details: Contract Price as per price schedule p.no.366 of CA 242,82,45,567 Value of Work Done till IPC-15 121,46,94,488 Balance Value of Work as per Contract Price = (A-B) 121,35,51,079 Performance security (PBG) submitted as per Cl.7.1.1 of the Contract = (5% of A) 12,14,00,000 Revised PBG value proposed as per the Office Memorandum under ref (1) above = (5% of C) 6,07,28,582 In view of the above, we request you to write to the bank to reduce the BG to the above effect which enables us to submit the revised BG at the earliest. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Release of Performance security | Payments, Dispute Resolution | This is with reference to the Office Memorandum from Ministry of Finance, GOI dated 13-05-2020 (ref 1 above) on return of Performance Security in view of Force Majeure due to COVID-19 | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/20. Request for release of performance security due to covid-19 as per ministry office memorandum..pdf | Request for release of Performance Security due to COVID-19 as per Ministry office memorandum | This is with reference to the Office Memorandum from Ministry of Finance, GOI dated 132020 (ref 1 above) on return of Performance Security in view of Force Majeure due to COVID-19. As notified vide our above letters, the project progress has suffered badly in terms of time and cost due to land unavailability initially and due to occurrence of Force Majeure event (outbreak of Corona Virus) and subsequent lockdown in the recent past. Due to this there was huge idling of resources, disruption in payment schedule and cash flow issues which will affect future progress of the project. In order to mitigate the difficulties being faced by Contractors, the central government has issued the above stated Office Memorandum mentioning that “the contractor M/S RCM Infrastructure Ltd. — P V Ramanaiah & Co_JV (Government Department/Agency) may return the value of performance security to the contractor/supplier as is proportional to the supplies made/contract work completed to the total contract value”. Accordingly, we wish to avail the facility of revising the Bank guarantee (BG) for reduced amounts of Performance security, in place of original submitted BGs, for the amount equal to the latest stage payment (IPC-15), as mentioned below which will ease our credit facilities with the banks for better cash flow & in turn improve the progress of works. Original & Proposed Bank Guarantee details: Contract Price as per price schedule p.no.366 of CA 242,82,45,567 Value of Work Done till IPC-15 121,46,94,488 Balance Value of Work as per Contract Price = (A-B) 121,35,51,079 Performance security (PBG) submitted as per Cl.7.1.1 of the Contract = (5% of A) 12,14,00,000 Revised PBG value proposed as per the Office Memorandum under ref (1) above = (5% of C) 6,07,28,582 In view of the above, we request you to write to the bank to reduce the BG to the above effect which enables us to submit the revised BG at the earliest. | FALSE | real_data
Notices for Achievement/ Non Achievement of Milestones | Dispute Resolution | It can be treated as that MS I,II and III have been not achieved by the Contractor on scheduled dates | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20201106_AE_SPK_463_Contractor’s failure in achieving the Project Mile Stone 1, 2 & 3.pdf | Contractor’s failure in achieving the Project Mile Stone 1, 2 & 3. Applying of Damages Vide Contract Article No. 10.3.2. & 10.3.3. - Reg. | This is with reference to the captioned subject and non-achievement of Project Mile Stones by the Contractor. In this regard it is submitted that the Contract Agreement was signed between EPC Contractor M/s S.P.K. & Co and the NHAI for Six laning of Karaipettai to Walajahpet Section of NH-4 ( New NH-48) i.e. from Ch. Km. 71+ 015 to 107+091 in the state of Tamil Nadu under NHDP Phase -V. The following are the main Contractual data. The Contract Signing date : 15/10/2018 Length of the Project : 36.076 Km Project Cost : INR 533,36,67,000 Appointed Date > 11/02/2019 Construction Period : 730 days from the Appointed date. Schedule Completion date: 09/02/2021 DLP Period : 4 Years from the Provisional certificate. Mile Stones : Detailed Below. In this regard, it is submitted that provisions of the Contract Agreement, Article. No. 10.3.2, which stated that, “The Contractor shall construct the Project highway in accordance with the Project completion Schedule set forth in Annexure -1 Schedule “J” Further to the above, as per the Project Milestones dates given in the Schedule “J” the Project Milestones are as follows; Description Original/revised P Milestone Date MS-1 Achievement of 10% of the Contract Price. Achieved. MS-2 Achievement of 30 % of the Contract Price. Achieved 20.03% of contract Price on 18.09.2020 MS-3 Achievement of 60 % of the Contract Price. 10.02.2020 13.07.2020 To be achieved 09.02.2021 To be achieved In view of the above, it is submitted that as on date, no data provided by the Contractor for achievement of the Milestones. Hence it can be treated as that MS — ¦, Il and Ill have been not achieved by the Contractor on scheduled dates. Therefore, as per provisions of the Contract Agreement Article 10.3.2, Contractor is liable to pay damages to the Authority. The damages amount to be payable is 0.05% of each delay days in non-achievement of the said Milestones. In this regard, it is being requested to please clarify the situation and submit reasons why not damages/ penalty be imposed as per the provisions of Contract Agreement. | FALSE | real_data
Notices for Achievement/ Non Achievement of Milestones | Dispute Resolution | It is our pleasure to mention that in accordance with Clause 3.2 of the Schedule-J, we have completed works for a value of INR 107.04 cr (42.27%) as certified under lPC-7 i.e., before end of March ZO22 and achieved project Milestone-ll. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-1/10. Notified achivement of MS-II artcl-10 Sch-J of EPC.pdf | Notification on achievement of Milestone-II pursuant to Article 10.3.2 and as per Clause 3.1 & 3.2 of Schedule J of the EPC Agreement - Reg. | We request your kind attention to Clause 3.1 & 3.2 of the Schedule-J of the EPC Agreement in accordance with which, prior to 365th day from the Appointed Date i.e., 23-Jul-2022, we are required to have submitted to the Authority duly and validly prepared Stage Payment Statements for an amount not less than 35% of the Contract Price. It is our pleasure to mention that in accordance with Clause 3.2 of the Schedule-J, we have completed works for a value of INR 107.04 Cr (42.27%) as certified under IPC-7 i.e., before end of March 2022 and achieved Project Milestone-II ahead of schedule (relevant page of IPC-7 attached for your ready reference). As intimated in our earlier letters, there are Land Acquisition issues in some of the sections of the Project Highway (first 19 Kms & at Major bridge @ 5+260). We request your office to kindly expedite clearances at these locations to help us progress at similar pace and in achieving our next milestones and maintaining a healthy cash flow. | FALSE | real_data
Releasing of BG submitted against mobilization advance | Authority's Obligations, Others | We request you to pass necessary orders for release of BGS towards Mobilization Advance amounting to Rs 8,00,00,000/- and return our BGs. | synthetic_template_20250913 | Request for release of Bank Guarantees (BGs) towards Mobilization Advance- Reg. | This is to notify you that We refer ta the above-mentioned correspondence regarding submission of Bank Guarantees (BGs) towards mobilization Advance for the above project. Through our ietters ref (2) above, we had submitted the BGs for Mobilization Advance as per Issuing Bank ¦, Amountiine) ¦ Validity 21931IGL0000723 UNION BANK OF INDIA 4,00,00,000 08-Feb-25 2 21931IGL0000723 UNION BANK OF INDIA 4,00,00,000 08-Feb-25 We request you to pass necessary orders for release of BGS towards Mobilization Advance amounting to Rs. 8,00,00,000/- and return our BGs (SL No. 1& 2 in the table above) to that extent accordingly. This will improve our cash flows and contribute to the progress of the project. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Extension of Time Proposals | EoT, Dispute Resolution | The Authoirty Engineer hereby recommends the Extension of Time for 398 days for the approval of the competent authority as revised milestone date including the scheduled competion date as mentioned above,without imposing any cost implication to either party | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210630_AE_PD_14484_Comprehensive EOT proposal.pdf | Extension of Time Comprehensive proposal- Reg. | With reference to the captioned subject and from the above mentioned chronology of correspondences, it can be understood that despite of approving an EoT for a period of 112 days for Mile Stone-1, the Contractor is disagreeing with the approval of the Authority and again highlighted the impediments adversely effected the First Mile Stone as well as other Milestone including the Scheduled Completion Date. The Contractor submitted the comprehensive proposal and requested for an extension of time. | FALSE | real_data
Extension of Time Proposals | EoT, Dispute Resolution | Though during the meeting held on 22.10.2020 it was decided to grant EOT for 210 days purely based on (i) account of election as well as the issue of (ii) non-availability of earth only but was not communicated in time/till date, we request the Authority Engineer to review the details submitted from our end and recommend Extension of time for a period of 678 days to the Authority pursuant to Clause 10.5.1 of the Contract Agreement. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20210416_SPK_AE_067_EOT request with Delay analysis.pdf | Six laning of Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V -EOT recommendation by the Authority for a period of 112 days not agreeable to the EPC Contractor — Request for considering EOT as discussed during the Review Meetings- reg | We are writing to express our concerns regarding the EOT recommendation by the Authority for a period of 112 days, which is not agreeable to the EPC Contractor. We request that the EOT be considered as discussed during the Review Meetings. The project involves six laning of the Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km 71+015 to km 107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase-V. We have referenced several documents and meetings in support of our request, and we hope for a favorable consideration. | FALSE | real_data
Extension of Time Proposals | EoT, Dispute Resolution | The Competent Authority has accorded his approval for extending Project Milestone - I to a period of 112 days from its stipulated completion date i.e. from 10.08.2019 to 29.11.2019 without any change in the Scheduled Project Completion Date. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/20200518_AE_SPK_316_Extension of Time & Rescheduling of Project Mile Stones.pdf | Extension of Time & Rescheduling of Project Mile Stones - Reg. | Vide above said references, it is to inform you that the Competent Authority has accorded his approval for extending Project Mile Stone-1 to a period of 112 days from its stipulated completion date i.e. from 10.08.2019 to 29.11.2019 without any change in the Scheduled Project Completion Date. Hence it has been asked to reschedule your activities by considering above extension and submit the same for monitoring purpose. Further it has been advised to mobilize your resources such a way to achieve the balance Milestones and the Scheduled completion date without fail. This is for your information and necessary action from your end. | FALSE | real_data
Extension of Time Proposals | EoT, Dispute Resolution | In view of the above, Authority's Engineer has scrutinized the EOT application and Authority's Engineer observations are being summarized hereunder in light of the provisions of the Contract Agreement; | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/189_Rescheduling of Project Milestones - EOT - 1.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under BharatmalaPariyojana on EPC mode — Rescheduling of Project Mile Stone- Request for Extension of Time -Reg. | Having gone through your documents related to Rescheduling of Project Milestone-Request for Extension of Time EoT-1 please find enclosed herewith the Authority Engineers recommendations on the same subject. This is for your information and necessary action. | FALSE | real_data
Extension of Time Proposals | EoT, Dispute Resolution | The EPC Contractor disagrees and does not accept the grant of EOT approval for 112 days, the reasons for disagreement if this approval are elaborated in our submission to the Authority Engineer vide ref (4) cited above and copy of the same is herewith enclosed as Annexure 1. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/28_25052020_Request for revisiting the EOT already recommended.pdf | Extension of Time and Rescheduling of Project Milestones - EOT granted for 112 days not acceptable to the EPC contractor ~ Request for revisiting the EOT recommended — Reg. | This is with respect to the Extension of Time(EOT) approved by the Authority for a period of 112 days for Project Milestone I without effecting changes in Scheduled Project Completion Period vide ref (3) cited above.The EPC Contrator disagrees and does not accept the grant of KU’! approval tor 112 days, the reasons for disgreeement of this approval are elaborated in our submission to the Authority Engineer vide ref (4) cited above and copy of the same is herewith enclosed as Annexure 1. It is also submitted that EOT is granted by rescheduling all the Project Milestones and not for a specific Project Milestone pursuant to Clause 6 of Schedule J of the Contract Agreement. We hereby request the Authority to revisit the EOT determined/approved and communicate 324 days as interim Extension of time. | FALSE | real_data
Extension of Time Proposals | EoT, Dispute Resolution | We hereby request the Authority Engineer to recommend Extension of time for a period of 324 days pursuant to Clause 10.5.1 of the Contract Agreement and project milestones accordingly. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/40_07082019_Rescheduling of Project Milestones – Request for Extension of time.pdf | Rescheduling of Project Milestones - Request for Extension of time - Reg. | The Contract agreement for the above mentioned project was executed on 15.10.2018. The appointed date was fixed as 11.02.2019 and the same was communicated vide ref (3) cited above. The Copy of the same is herewith enclosed as Annexure 1. The Authority in its response vide ref (5) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. The copy of the same is enclosed as Annexure 3. The EPC contractor vide ref (6) cited above reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that still the condition remained the same and dismantling/ removal of structures fouling was not started and shifting of Electric pole and power line also not started. The impacted length due to encroachments and encumbrances was 12.18 Km which accounted to 33.77% of the project highway. The workable length available to the Contractor based on the impacted length was 66.23% of the Project Highway length. The EPC Contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of removal of encumbrance / encroachment / obstruction. The copy of ref (7) is herewith enclosed as Annexure 4. It is almost six months since the declaration of appointed date, removal/ dismantling of structures/encroachments have not been started. Also, the work of shifting of power line and electric pole of LT line and HT lines crossings have not been started yet. The following are some of the key contractual dates and events since the inception of the project to till date: 1. Total length of the project highway: 36.076 Km 2. Date of Signing of agreement: 152018 3. Submission of Performance BG as per Clause 7.1.1 of the Contract Agreement: 262018 4. Target date for preparation of Memorandum as per Clause 8.2.1 of the Contract Agreement: 142018 5. Actual date of signing of Memorandum of land handing over: 112019 6. Declaration of appointed date by the Authority: 112019 7. ROW to be handed over as on appointed date as per Clause 8.2.2 & Annexure II: 35.468 Km | FALSE | real_data
Handing over of land /Possession of site. | Authority's Obligations | the stretches we programmed to work are not available even today due to non acquisition of land. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/9. Un-gainful Deployement of Resources 28.01.2019.pdf | Rehabilitation and Up-gradation of Paithan (Pategaon) — Mungi - Hadgaon - Bodhegaon- Ladjalgaon ~ Ghogaspargaon ~ Phulsangvi - Ukhandachakla ~ Dahiwandi — Shirur to 2-Lane with paved shoulder (Project Length 55.937 Km) on EPC basis in the state of Maharashtra (Package I - 56 KM) - Un-gainful Deployment of Resources - Reg. | Please refer our revised programme submitted in vide letter no RCM PVR JV/MH PWD/2018-19/235 dated 02 May 2018 which revised & resubmitted recently vide letter no RCM PVR JV/MH PWD/2018-19/402/A dated 29 December 2018. As you are aware, the stretches we programmed to work are not available even today due to non acquisition of land. Further the area/work fronts which were made available by property owners at our request, was also withdrawn by them, since the compensation was not paid in time. Kindly refer our application for revision of milestone dates RCM PVR JV/MH PWD/2018-19/374 dated 17 November 2018 which details elaborately the reasons under relevant clauses of contract agreement. We have sufficient resources but they are not gainfully deployed so far. Please refer our letter RCM PVR JV/MH PWD/2018-19/406 date 04 January 2019 on availability of work front & land acquisition status also. The reasons stated above, has led to erosion of revolving capital. We will summarise the losses & submit the Comprehensive report, when 90% land is made available. | FALSE | real_data
Handing over of land /Possession of site. | Authority's Obligations | For the above six laning work, enter upon permission for the following tanks / ponds belonging to block development office, Kancheepuram are requested. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/1910_16082019_ Permission to enter PWD Tanks.pdf | NHAI, PIU, Kancheepuram — Six laning of Karaipettai to Walajahpet section of NH-48 (old NH-4) from Km 71+015 to Km 107+091 on EPC mode in the State of Tamil Nadu under NHDP Phase-v — Permission to enter upon the tanks /ponds - Reg. | I wish to inform that. NHAI has taken up the work of ‘Six laning of Karaipettai to Walajahpet section of NH-48(Old No. NH-4) from Km 71+015 to Km 107+091 and the work is under progress. The above work was transferred from PIU-Krishnagiri to PIU-Kancheepuram on 17.06.2019, 2. For the above six laning work, enter upon permission for the following tanks/ ponds belonging to Block Development Office, Kancheepuram are requested: Sl. ¦ Taluk Name Village Name Revenue Design - Name of Water No Survey Chainage body No Kanchipuram Karaipettai 311/1.- Km 71+040 to Karaipettai 71+205 (LHS Kanchipuram ¦ Chitherimedu 88/1 Km 73+570 [PerveEr] 73+920 (LHS Kanchipuram Thulukkanthandalam 168 Km 74+740 to Nallavanthangal 74+900 (RHS Kanchipuram Melambi 30 Melambi Km_78+580 Dhamal 699 Km 81+490 to Kondappan 81+555 (RHS Nayakkan Kulam Kanchipuram ¦ Dhamal Km 81+960 to 82+000 (RHS Kanchipuram Dhamal] 1309 Km 85+390 to p ; “¦ 85+450 (LHS ; | FALSE | real_data
Handing over of land /Possession of site. | Authority's Obligations | The Authority has provided only 8 .5 KM (27.17 %) length of ROW and balance 22.78 KM (72.83 %) is still to be handed over by the Authority. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-1/8. Request to grant an Extension of Time under Clause 10.5 of the Contract Agreement..pdf | Request to grant an Extension of Time under Clause 10.5 of the Contract Agreement | 1. This is with reference to our various representations/submissions regarding various events on delay which has adversely affected the construction activities of Project and are still persisting at site resulting delay in completion of construction works as per scope envisaged under Contract Agreement. 2. We take this opportunity to summarize the facts chronologically as below giving rise to the claim for an Extension of Time (“EOT”) in accordance with the provisions of this Agreement on account of various delay events. Contract Particulars: Development Corporation Limited Authority Engineer Accepted Contract Price Construction Period Appointed Date 26.11.2021 Stipulated Completion Date ¦ 19.05.2023 Request for EOT by this 135 days Cl 01.10.2023 Revised Completion Date Background Facts: 3. The National Highway & Infrastructure Development Corporation Limited (“Authority”) had issued the LOA dated 02.09.2021 (Ref#01) in favor of B.R Goyal Infrastructure Limited (“Contractor"). The formal Contract Agreement was signed on 08.10.2021. In pursuant to the conditions of LOA, we had submitted the Performance Security and Additional Performance Security in the form of Bank Guarantees (PBG and APBG) vide our letters dated 28.09.2021 and 02.11.2021 (Ref #2 & 4 above). It is in place to mention that the Contractor have discharged its prime obligation i.e. submission of Performance Security and Additional Performance Security, well within time limit. To ensure the start of construction activities immediate after declaration of Appointed Date, Contractor has mobilized the adequate manpower & machinery resources at site after receiving of LOA. In pursuant to the provisions of the Contract Agreement, Authority’s primary obligation is to provide the 90% length of ROW within 30 days from the date of Agreement. However, after signing of CA, both the parties visited the site and it | FALSE | real_data
Handing over of land /Possession of site. | Authority's Obligations | Handing over of Balance Land | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-2/2. 20231215_165_Cont_AE_Accumulated delays till Nov-23.pdf | Notice under clause 10.5.(V)- Accumulated delays till 30" November 2023 - Reg. | We refer to the above letters, wherein we have intimated the Authority about the following issues/Bottlenecks prevailing in the project which are hampering the progress of the works: 1. Handing over of the Balance land. 2. Clearance from the Forest department. 3. GAD Approval from the Railway Authorities. However, the issues are yet to be cleared and hence the same continue to hamper the progress. In this regard, pursuant to clause 10.5.(V) of the EPC Contract agreement, we herewith submit the accumulated delays as on 30" November 2023. SLMI — DMCPL (JV) (A Joint Venture of M/s. SLMI Infra Projects Private Limited & M/s. Dwarakamai Constructions Pvt. Ltd.) H.No.1223, Street No.5, Tarnaka, Secunderabad — 500017. Accumulated delays Till 30-Nov-2023. Description of Delay Events From the above the total accumulated delay as on 30.11.2023 is 303 days. Handing over of ROW/Construction Zone on at least 90% of the total length of the Project Highway Still Continuing. Handing over of the balance Land (to be handed over in 150 days) Still Continuing. Clearance from Forest Department Still Continuing. GAD Approval from Railway Authorities ~ Owing to the above delays, we may not be able to achieve Milestone-II which is due in April’24. It may please be noted that we may run out of work fronts and our resources may become idle as all the available work fronts are already being tackled. In view of the above, we request your office to pursue with the Authority to clear the issues at the earliest and provide hindrance free work fronts over the entire length of the Project Highway. | FALSE | real_data
Handing over of land /Possession of site. | Authority's Obligations | The dispute regarding land acquisition still continues among landowners, Authority and Revenue Authority (CALA). | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/19. Intention to issue cure period notice 02.11.2019.pdf | Intention to issue Cure Period Notice to the Authority under clause 23.2.1 for temporary demobilization | This is regarding non-availability of encroachment and encumbrance free Right of Way (ROW) along the project highway, regarding which we wish to mention the following: 1. Subsequent to the signing of EPC Agreement dated 18.04.2017 the Appointed Date was fixed on 02.06.2017 and was communicated through Authority's letter no. 1190. It was mentioned in the letter that requirements under Clause 8.2 and obligations under 4.1.3(a), Annex II of Schedule-A are fulfilled by the Authority. 2. However, when we actually mobilised to site, we realised that the Obligations are not fulfilled by the Authority, in terms of the provisions relating to ROW and Appointed Date cited above. We noticed that there is no clarity even on the existing ROW widths. 3. We had submitted the Memorandum / Appendix through our letter no. 71 dated 10th Aug 2017, which indicates that the vacant access and ROW have not been granted at certain locations. Despite several requests, joint site inspection was not done and till date duly countersigned copy of the Memorandum / Appendix prepared by us is not returned till to date. 4. We have been reporting the lack of ROW through our Monthly Progress Reports every month, in addition among various letters on the subject. It is pertinent to mention that even as on date, not a single kilometre/ hectare of additional land has been acquired by the Authority under this project. However, we had convinced the local public and could get some progress in the project due to our efforts. 5. The dispute regarding land acquisition still continues among landowners, Authority and Revenue Authority (CALA). 6. There are realignments in the project for a length of 5.350 Kms, the land acquisition of which is not yet taken up where in there are no ROW boundaries and which area can be acquired directly. Two minor bridges are held up in the realignments. 7. As mentioned in Authority’s and AE's EOT recommendations, Gazette notification for land acquisition was issued on 31st December 2018, after a lapse of 18 months from appointed date. 8. It is also mentioned in your letter no. 78 dated 02.03.2019, that the EOT duration determined was subject to the condition that the ROW for the affected reaches will be handed over to the Contractor by 31.03.2019 and all the hindrances/obstructions will also be removed by 31.03.2019. 9. However, even till date, no further land has been handed over by the Authority we regret to maintain that even the existing ROW width is disputed between land owners concerned Authority. In addition the Acquisition was to be mobilized: the area of ACQUISITION FOR DIFFERENT Land owners is a single survey numbers. Some of them in this case having different survey numbers. 10. As intimated earlier, we have been facing financial losses due to idling of resources and simultaneously incurring fixed and renewing costs. In view of the above, we intend to issue a Notice to the Authority under clause 23.2.1 of the Contract to cure their material default in handing over of ROW which has a huge material adverse effect on our works. We once again request you to pursue with the Authority in expediting handing over of the balance ROW as soon as possible. Due to the above breach of the obligations by the Authority in terms of land handing over, a situation has arisen wherein we have no option other than temporarily demobilizing from site, to avoid further financial loss to us. We shall remobilize upon intimation from you / Authority regarding the availability of balance ROW. | FALSE | real_data
Outbreak of epidemic or pandemic | EoT | The surge of Covid-19 third wave has been witnessed by the project region too. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-1/8. Request to grant an Extension of Time under Clause 10.5 of the Contract Agreement..pdf | Request to grant an Extension of Time under Clause 10.5 of the Contract Agreement | 1. This is with reference to our various representations/submissions regarding various events on delay which has adversely affected the construction activities of Project and are still persisting at site resulting delay in completion of construction works as per scope envisaged under Contract Agreement. 2. We take this opportunity to summarize the facts chronologically as below giving rise to the claim for an Extension of Time (“EOT”) in accordance with the provisions of this Agreement on account of various delay events. Contract Particulars: Development Corporation Limited Authority Engineer Accepted Contract Price Construction Period Appointed Date 26.11.2021 Stipulated Completion Date ¦ 19.05.2023 Request for EOT by this 135 days Cl 01.10.2023 Revised Completion Date Background Facts: 3. The National Highway & Infrastructure Development Corporation Limited (“Authority”) had issued the LOA dated 02.09.2021 (Ref#01) in favor of B.R Goyal Infrastructure Limited (“Contractor"). The formal Contract Agreement was signed on 08.10.2021. In pursuant to the conditions of LOA, we had submitted the Performance Security and Additional Performance Security in the form of Bank Guarantees (PBG and APBG) vide our letters dated 28.09.2021 and 02.11.2021 (Ref #2 & 4 above). It is in place to mention that the Contractor have discharged its prime obligation i.e. submission of Performance Security and Additional Performance Security, well within time limit. To ensure the start of construction activities immediate after declaration of Appointed Date, Contractor has mobilized the adequate manpower & machinery resources at site after receiving of LOA. In pursuant to the provisions of the Contract Agreement, Authority’s primary obligation is to provide the 90% length of ROW within 30 days from the date of Agreement. However, after signing of CA, both the parties visited the site and it | FALSE | real_data
Outbreak of epidemic or pandemic | EoT | In view of above facts,considering the COVID-19 pandemic effect, the Authority Engineer hereby recommends Extension of Time for 6 months in totla as per the NHAI/Policy Guidelines/Atmanirbhar Bharat Policy No.18.46/2020 dated 22/06/2020 for the Project Milestones and Scheduled Completion Date as mentioned above without imposition of any cost or penalty to either party, due to prevailing situation of Covid-19. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210618_AE_SPK_634_Extension of Time on account of COVID-19 Pandemic.pdf | Extension of Time on account of COVID-19 Pandemic - Reg. | In response to the above said reference please find enclosed herewith the Authority Engineers recommendations on” Extension of Time on account of COVID-19 Pandemic”. This is for your information and necessary action. | FALSE | real_data
Outbreak of epidemic or pandemic | EoT | It has been asked to organise the project works by maintaining proper coordination with the District Administration to achieve the required progress | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210509_AE_SPK_622-Carrying out the construction work.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode — Carrying out the Construction Work - Reg. | Please find enclosed herewith two communications bearing numbers NHAI/11036/4/2019/PIU.Kanchee/1448 & 1449 both dated 08 May 2021 addressed to the District Collectors of Kancheepuram and Ranipet districts informing that as per the relaxation given to the “Ongoing Works” while announcing the Lock Down from 10 May 2021 04.00 AM to 24.05.2021 04.00 AM in the state of Tamil Nadu through a press release; the Project Works of Karaipettai to Walajahpet will progress as usually. Accordingly, it is requested to issue necessary instructions to the concerned officials to extend their cooperation for carrying out the construction works by allowing free movement of Materials, Machineries, Personnel and staff of Consultants & Contractor etc. Further it is assured to both the District Collectors necessary SOP will be followed while executing the Works. Hence it has been asked to organize the Project Works by maintaining proper coordination with the District Administration to achieve the required progress. This is for your information and necessary action. | FALSE | real_data
Outbreak of epidemic or pandemic | EoT | Further, the Ministry of Home Affairs vide its order under ref (13) cited above extended the lockdown for a further period of 14 days from 04.05.2020. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/23_30042020_Extension of lockdown till 17.05.2020.pdf | Six laning of Karaipettai to Walajahpet Section of NH-4 (New NH-48) - Force Majeure Event due to outbreak of Covid 19 - Lockdown imposed by Government of India from 24.03.2020 to 03.05.2020 - Further extension of lockdown till 17.05.2020 - Intimation of the same - Reg. | Dear Sir, This is in continuation of our letter under ref (14) cited above wherein we requested your good self to obtain permission from District Administration for commencing the construction activities with available men and machinery. The Ministry of Home Affairs vide ref (13) cited above made certain inclusion on the consolidated revised guidelines issued already vide ref (6) cited above. This allowed the movement of migrant persons under Sub clause (iv) under Clause 17 on movement of persons by road. Copy of the above mentioned order relating to movement of migrant labourers is herewith enclosed as Annexure 1. Accordingly, the state administration across the country started making arrangements for bringing back the stranded migrant labourers to their respective states. Further request was also made by various chief ministers across the country to arrange rail transport for facilitating movement of migrant labourers which has also been acknowledged by the Government of India. The above mentioned movement of migrant labourers to their respective states would result in further delay of kick-starting the already stalled activities at the project site since 1st week of March 2020. Further, the Ministry of Home Affairs vide its order under ref (13) cited above extended the lockdown for a further period of 14 days from 04.05.2020.Based on the risk profile criteria, various districts across the country divided into three zones - Red, Orange and Green respectively. Red zones or hotspot districts are the ones where the prevalence of COVID 19 is more taking into account total number of active cases, doubling rate of confirmed cases, extent of testing and surveillance feedback. Copy of the above mentioned notification along with Red zone districts in Tamilnadu is herewith enclosed as Annexure 2.Irrespective of the zones, all passenger movement by rail or road or air has been prohibited except for security purposes or for purposes as permitted by Ministry of Home Affairs. Our project highway traverses through Kanhceepuram and Ranipet districts both declared as Red zone or hotspot districts by Ministry of Health and Family welfare, Government of India. Though construction activities are permitted in rural areas under point no.7 (ii) ( c ),we shall be in a position to commence full-fledged construction activities only after the return of migrant labourers. | FALSE | real_data
Mix Designs for Pavement Layers & Structural Concrete | Contractor's Obligations | We are here with submitting the Concrete Mix designs for PQC (M40 Grade) along with test reports | synthetic_template_20250913 | Submission of PQC (M40 Grade) Mix Design for approval- Reg. | With reference to above subject, we are here with submitting the Concrete Mix designs for PQC (M40 Grade) along with Test reports for your kind perusal and approval. The following Sources of the Materials have been used in the mix design. 1. Aggregate (SLMI Crusher, 32+400, RHS, 2.0Km lead, Cherla Gauraram Village) 2. Water (SLMI Crusher camp) 3. Cement (Orient - OPC 53 grade) 4. Admixture (Asian Paints SC Maximoplast PC 200) | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Delay in construction activities | EoT, Dispute Resolution | The above mentioned movement of migrant laborers to their respective states would result in further delay in kick-starting the already stalled activities at the project site since 1st week of March 2020. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/23_30042020_Extension of lockdown till 17.05.2020.pdf | Six laning of Karaipettai to Walajahpet Section of NH-4 (New NH-48) - Force Majeure Event due to outbreak of Covid 19 - Lockdown imposed by Government of India from 24.03.2020 to 03.05.2020 - Further extension of lockdown till 17.05.2020 - Intimation of the same - Reg. | Dear Sir, This is in continuation of our letter under ref (14) cited above wherein we requested your good self to obtain permission from District Administration for commencing the construction activities with available men and machinery. The Ministry of Home Affairs vide ref (13) cited above made certain inclusion on the consolidated revised guidelines issued already vide ref (6) cited above. This allowed the movement of migrant persons under Sub clause (iv) under Clause 17 on movement of persons by road. Copy of the above mentioned order relating to movement of migrant labourers is herewith enclosed as Annexure 1. Accordingly, the state administration across the country started making arrangements for bringing back the stranded migrant labourers to their respective states. Further request was also made by various chief ministers across the country to arrange rail transport for facilitating movement of migrant labourers which has also been acknowledged by the Government of India. The above mentioned movement of migrant labourers to their respective states would result in further delay of kick-starting the already stalled activities at the project site since 1st week of March 2020. Further, the Ministry of Home Affairs vide its order under ref (13) cited above extended the lockdown for a further period of 14 days from 04.05.2020.Based on the risk profile criteria, various districts across the country divided into three zones - Red, Orange and Green respectively. Red zones or hotspot districts are the ones where the prevalence of COVID 19 is more taking into account total number of active cases, doubling rate of confirmed cases, extent of testing and surveillance feedback. Copy of the above mentioned notification along with Red zone districts in Tamilnadu is herewith enclosed as Annexure 2.Irrespective of the zones, all passenger movement by rail or road or air has been prohibited except for security purposes or for purposes as permitted by Ministry of Home Affairs. Our project highway traverses through Kanhceepuram and Ranipet districts both declared as Red zone or hotspot districts by Ministry of Health and Family welfare, Government of India. Though construction activities are permitted in rural areas under point no.7 (ii) ( c ),we shall be in a position to commence full-fledged construction activities only after the return of migrant labourers. | FALSE | real_data
Safety measures during construction. | Contractor's Obligations | This is with reference to the subject matter; the Compliance Report is attached as Annexure -I. This is for information that most of the recommendations of the Safety Expert have been complied as per requirement at site. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LOT-10/20210831_SPK_AE_119_Submission of Compliance Report – Site Safety report for the month of July 2021 by Road Safety Expert.pdf | Submission of Compliance Report — Site Safety report for the month of July 2021 by Road Safety Expert —Reg. | Dear Sir, This is with reference to the subject matter; the Compliance Report is attached as Annexure -I. This is for information that most of the recommendations of the Safety Expert have been complied as per requirement at site. This is for your information and record. Thanking you and assuring our best of services always. Yours faithfully, For SPK AND Co., Managing ner Encl - As Above Ce - The Project Director, NHAI, PIU - Kancheepuram, kancheepurampiu@gmail.com 1¦Page Six Lanning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km.71+015 (Existing Km 71/000) to Km 107+091 (Existing Km 107/068) on EPC Mode in the state of Tamil Nadu under NHDP Phase-V Annexure-I | FALSE | real_data
Completion certificate | Authority's Obligations | Completion Certificate in the form set forth in Schedule - L is herewith attached. | synthetic_template_20250913 | Issuance of Completion Certificate pursuant to Article 12.4 of the EPC Agreement - Regarding. | Please note that In pursuant to approval for issuance of Completion Certificate as per Article - 12 of EPC Agreement, conveyed by Superintending Engineer (R&B) National Highway Circle, Hyderabad vide letter 3"4 cited, the Completion Certificate in the form set forth in Schedule - L (the “Completion Certificate”) is herewith attached. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Completion certificate | Authority's Obligations | Completion Certificate in the form set forth in Schedule - L is herewith attached. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-2/17. 20240711_3270_AE_Cont_Issuance of Completion Certificate for the Project.pdf | Issuance of Completion Certificate pursuant to Article 12.4 of the EPC Agreement - Regarding. | In pursuant to approval for issuance of Completion Certificate as per Article - 12 of EPC Agreement, conveyed by Superintending Engineer (R&B) National Highway Circle, Hyderabad vide letter 3"4 cited, the Completion Certificate in the form set forth in Schedule - L (the “Completion Certificate”) is herewith attached. | FALSE | real_data
Delinking impacted length | Authority's Obligations, Payments, Dispute Resolution | We hereby request that the hindered stretch of 5.410 Km be delinked from the original scope of work and Completion Certificate be issued to us as per the Article 12 of the EPC Contract. | synthetic_template_20250913 | Upgradation to 2-lane with Paved Shoulders of Khawkawn-Ngopa section of NH-102B of Aizawl-Imphal Economic Corridor from existing chainage Km 0.000 to Km 32.976 (Design chainage Km 0.000 to Km 31.280(Package-I) in the State of Mizoram under Bharatmala Pariyojna on EPC mode: (Delinking of hindered stretches and issuance of Completion Certificate — Reg) | Reference is invited towards the Review Meeting chaired by the Director (T), HQ, NHIDCL on 15 Jul 2024, wherein it was informed by the chair that the balance works within the hindered stretches can be delinked and Completion Certificate can be issued. It was also informed that the delinked stretches can be taken up for execution, as and when the land is made available by the Authority. In this regard, the following facts, as already communicated to your good office, are reproduced as under: - a) A stretch of 5.410 Km out of the total stretch of 31.280 Km is impeded till dated due to non-availability of work front within the Forest Land (5.15 Km) and non-acquisition of land at proposed re-alignment (0.260 Km). b) The works in the available stretch of 25.870 Km has been completed in all respects as on 31 May 2024 and intimated to your good office vide our letter mentioned at sl (iii). c) The Physical & Financial Progress of the project as on date is as under- Physical Progress: - 84.68% (achieved on 31 May 2024) Financial Progress: - 83.23% d) Our manpower & machineries are idle on the project site awaiting handing over of the balance work-front by the Authority. In light of the above, we hereby request that the hindered stretch of 5.410 Km be delinked from the original scope of work and Completion Certificate be issued to us as per the Article 12 of the EPC Contract. The delinked stretch shall be constructed during the Defects Liability Period, as and when made available by the Authority. Please confirm receipt of this correspondence. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Submission of Design and Drawings | Contractor's Obligations | As intimated in our letter 3 referred above, we are proceeding with submission of design / drawings / tentative cost impact, in anticipation of the aforesaid notice. | synthetic_template_20250913 | Change of Scope notice under 13.2.1 by Authority Engineer | It is brought to your attention that Respected Sir, This refers to all the letters referred above instructing us to execute certain additional works, under change of scope. We have been instructed additional Minor Bridges, Box Culverts and Pipe culverts under Article — 13 & 13.1.1 whereas clause 13.2 “Procedure for change of scope” instructs for a notice from Authority Engineer to be issued to the contractor (please refer clause 13.2.1 & 13.2.2 in this regard) As intimated in our letter 3 referred above, we are proceeding with submission of design / drawings / tentative cost impact, in anticipation of the aforesaid notice. However, we request you to direct the Authority Engineer, to issue us the Change of Scope notice, for the sake of good order and procedure for Change of Scope. Meanwhile, by way of submitting a copy of this letter to Authority Engineer/Team Leader, we are requesting him for necessary action for issuing the notice and simultaneously approving the designs & drawings. Please confirm receipt of this correspondence. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Submission of Design and Drawings | Contractor's Obligations | As intimated in our letter 3 referred above, we are proceeding with submission of design / drawings / tentative cost impact, in anticipation of the aforesaid notice. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/4. COS notice under 13.2.1 by AE 27.10.2018.pdf | Change of Scope notice under 13.2.1 by Authority Engineer | Respected Sir, This refers to all the letters referred above instructing us to execute certain additional works, under change of scope. We have been instructed additional Minor Bridges, Box Culverts and Pipe culverts under Article — 13 & 13.1.1 whereas clause 13.2 “Procedure for change of scope” instructs for a notice from Authority Engineer to be issued to the contractor (please refer clause 13.2.1 & 13.2.2 in this regard) As intimated in our letter 3 referred above, we are proceeding with submission of design / drawings / tentative cost impact, in anticipation of the aforesaid notice. However, we request you to direct the Authority Engineer, to issue us the Change of Scope notice, for the sake of good order and procedure for Change of Scope. Meanwhile, by way of submitting a copy of this letter to Authority Engineer/Team Leader, we are requesting him for necessary action for issuing the notice and simultaneously approving the designs & drawings. | FALSE | real_data
Slow Progress of Works | EoT | It is advised to make suitable arrangements to commence the approach ramp works by arranging the filling materials to erect RE panels and re organising the men and machinery. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210802_AE_SPK_667-Slow Progress from Ch. Km. 71+015 to 107+091, in particular at underpass approaches.pdf | Slow Progress from Ch. Km. 71+015 to 107+091, in particular at underpass approaches | During the routine site inspection’s, it is observed that at many locations despite of having clear scope to progress different layers of road crust and structural works the progress is not up to the mark. We opine that the delays are mainly due to improper planning and organization of men & machinery. Further it may be recalled that despite of completing/progressing the Boxes of Light Vehicular Underpasses at Ch. Km. 85+874, 90+092. 95+412, 96+477, 100+603 & 102+980 the approach ramp works are not progressing. Similarly, at vehicular underpasses locations such as 76+846, 79+302. 80+805, 82+566 & 87+540 even after completing the main structure works the approaches are not progressing. Hence it is advised to make suitable arrangements to commence the approach ramp works by arranging the filling materials to erect RE panels and re-organizing the men & Machinery. This is for information and necessary action. | FALSE | real_data
Authority Engineer | Authority's Obligations | 3.As per para- 4 ,Annex-I ,Schedule-N of agreement ,the Authority' Engineer shall review the programme for the works submitted by the contractor as per cl 10.1.3 of agreement and shall convey its comments to the contractor within a stipulated period of time. | synthetic_template_20250913 | NHALI PIU - Krishnagiri - Consultancy services for Authority Engineer for supervision of Six laning of Karaipettai to Walajahpet section of NH-48 (old NH-4) from km.71+015 to km.107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase V- Mobilization at Site ~ Reg. | Please note that As you know that your firm has been appointed as Authority Engineer for the ee work and the contract agreement for civil work is signed on 15.10.2018 and appointed date is: declared as 11.2.2019 and the contractor has started the work and is in progress. 2.AS a part of contract agreement the contractor has submitted programme for the works as per clause 10.1.3 of agreement and Plan & Profile drawings and requesting for approvals. 3.As per para- 4 ,Annex-I ,Schedule-N of agreement ,the Authority Engineer shall review the programme for the works submitted by the contractor as per cl 10.1.3 of agreement and shall convey its comments to the contractor within a stipulated period of time. 4. As no communication is received on mobilisation of the Authority Engineer till date, it is requested to mobilise the staff at site under intimation to this office immediately for performing the duties of Authority Engineer. Please confirm receipt of this correspondence. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Video recording of the Project Highway (before inception & during construction) | Contractor's Obligations | It is mandatory to submit the drone based video recording of the project highway during the construction period covering the entire ROW showing the chainages,proposed ROW,Median centreline etc. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71 015 to 107.091 of NH-4 (New NH-48) in the State of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojna on EPC mode — Mandatory monthly Drone Video Recording of Project Highway during the development, Construction and O & M period — Reg. | Please find enclosed herewith a communication bearing No. NHAI/11036/4/2019/PIU.Kanchee/1607 dated 15 June 2021 from the Project Director PIU NHAI Kancheepuram which is a self-explanatory about the Contract Article No. 11.16; according to which it is mandatory to submit the Drone-based Video Recording” of the Project Highway during the construction period covering the entire ROW showing the Chainages, proposed ROW, median centreline, etc. Hence it has been asked to make necessary arrangements to comply the NAHI Circular stated as Ref. No. 2 and to upload the same in the Data Lake. This is for your information and immediate necessary actions. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Video recording of the Project Highway (before inception & during construction) | Contractor's Obligations | We acknowledge receipt of your letter NHAI/PIU-K'giri/NH4/SPK/PS/2019/233 dated 11.02.2019 S.No.2 cited above, please find enclosed herewith a copy of site videography conducted in the month December from 12.12.2018 to 13.12.2018 to ascertain the existing condition of the road and other pictures as required by you. | synthetic_template_20250913 | Site Videography conducted in December | Dear Sir, We acknowledge receipt of your letter NHAI/PIU-K'gini/NH4/SPK/PS/2019/233 dated 11.02.2019 SLNo.2 cited above, please find enclosed herewith a Copy of site videography conducted in the month of December from 12.12.2018 to 13.12.2018 to ascertain the existing condition of the road and other pictures as required by you. This is submitted for your information and necessary record please. Thanking you, Yours faithfully, For SPK And Co., Encl: As Above Scanned by CamScanner | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Elections in the state | EoT | Considering general election and the festival, period from 10.03.2019 to 18.08.2019 may be considered for the EOT for the first milestone as unforeseen event under the Non political and Political events | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under BharatmalaPariyojana on EPC mode — Rescheduling of Project Mile Stone- Request for Extension of Time -Reg. | Having gone through your documents related to Rescheduling of Project Milestone-Request for Extension of Time EoT-1 please find enclosed herewith the Authority Engineers recommendations on the same subject. This is for your information and necessary action. We await your further instructions. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Elections in the state | EoT | Considering general election and the festival, period from 10.03.2019 to 18.08.2019 may be considered for the EOT for the first milestone as unforeseen event under the Non political and Political events | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under BharatmalaPariyojana on EPC mode — Rescheduling of Project Mile Stone- Request for Extension of Time -Reg. | Having gone through your documents related to Rescheduling of Project Milestone-Request for Extension of Time EoT-1 please find enclosed herewith the Authority Engineers recommendations on the same subject. This is for your information and necessary action. Thank you for your attention to this matter. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Damages | Payments, Dispute Resolution | This is with reference to our payments to the tune of Rs. 1 that are withheld till our Stage Payment IPC-07 against non-achievement of Milestones | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/13.Request for Releasee of Payment Withheld against Non Achived of Milestones 02.03.2019.pdf | Request for Release of Payment Withheld against Non-Achievement of Milestones | This is with reference to our payments to the tune of Rs.1,500,0000 that are withheld till our Stage Payment IPC-07 against non-achievement of Milestones. We wish to clarify the following in this regard: 1. We have applied for Extension of Time vide our letter ref (3) above along with SOP format for EOT vide ref (2) above, wherein the reasons for non-achievement of Milestones as defined in Schedule-J of the Agreement are elaborated. 2. The Authority/AE are yet to communicate their approval on the EOT, which is pending since long. 3. Pursuant to Clause 10.3.3 of the EPC Agreement, “The Authority shall notify the Contractor of its decisions to impose Damages in pursuance with the provisions of this Clause 10.3. Provided that no deductions on account of Damages shall be effected by the Authority without notifying the Contractor of its decision to impose the Damages, and taking into consideration the representation, if any, made by the Contractor within 20 (twenty) days of such notice....". There was no notification from the Authority in this regard. 4. We invite to your attention letter no. 01041028/02/0021, dated 26 July 2018, by the Team Leader, specifically stating that no damages are recommended by them on non achievement of milestone, even though Executive Engineer referred Clause 10.3.2 of the EPC Agreement. In view of the above, withholding payments for non-achievement of Milestones is against the provisions of the EPC Agreement. Also, our application for extension of time / revision of milestone dates are being considered benignly. Hence, we request you to recommend for release of the withheld amounts at the earliest. | FALSE | real_data
Occurrence of unseasonal rainfall | EoT | This is in reference to the above referred communications bearing No's 384 & 394 dated 25.05.204 & 24.06.2024 respectively regarding rain fall during the months of May & June of 2024 for which after verification of the same, our observations are as stated below: | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LOT-10/20240704_SPK_AE_1786 Unseasonal rainfall during the month of May 2024 and in JUNE month 1 to 22.06.2024 Reporting of same-reg..pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode: Unseasonal rainfall during the month of May 2024 and in June month 1* to 22.06.2024 — Reporting of the same-Reg. | Dear Sir, This is in reference to the above referred communications bearing No’s 384 & 394 dated 25.05.204 & 24.06.2024 respectively regarding rain fall during the months of May & June of 2024 for which after verification of the same, our observations are as stated below: The data and the dates mentioned in both the communications are not matching for one page to the other page. Further it is to be noted that till date we did not receive any hard copy of the letter No. 394 dated 24.06.2024 and the supporting documents/Annexures as well. Considering the above you are hereby asked to re-submit these communications properly with relevant data for evaluation/verifications. This is for your information and necessary immediate actions. | FALSE | real_data
Borrow area | Contractor's Obligations | The Contractor has taken sincere effort for getting Permission for extraction of Borrow earth since from the Appointed Date. But, considering the Contract Clause No. 3.17 (a), which reproduced here, "The Contractor shall, at its own cost and expense, in addition to and not in derogation of its obligation elsewhere set out in this Agreement, (a) make, or cause to be made, necessary applications to the relevant Government Instrumentalities with such particulars and details as may be required for obtaining Applicable Permits set forth in Schedule F." Therefore, on this ground, Contractors request for EOT cannot be entertained. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/20191130_AE_PD_10451_Recommendation of EOT I for a period of 178 days.pdf | Application for EOT | This is with reference to the captioned subject and application for EOT received from the Contractor, in this regard, it is submitted that the Contract Agreement was signed between Contractor M/s SPK & Co. and the NHAI for Six Laning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km 71+015 to Km 107+091 in the State of Tamil Nadu under NHDP Phase - V. The following are the main contractual data ; Contract Seen Date : 15/10/2018 Length of the Project 36.076 Km Project Cost INR 533,36,67,000 Appointed Date : 11/02/2019 Construction Period : 730 days from Appointed Date Scheduled Completion Date: 09/02/2021 DLP Period : 4 years from the Provisional Certificate Project Milestone ~ Days from Project Milestone Appointed Date Milestone - -1 180 Days 09/08/2019 Not achieved 365 Days 10/02/2020 To be achieved 550 Days 13/08/2020 730 Days 09/02/2021 To be Achieved In view of the above, Authority's Engineer has scrutinized the EOT application and Authority's Engineer observations are being summarized hereunder in light of the Contract Agreement; Scheduled Date ¦ Status Procurement of the Site; As mentioned in the Clause 8.2.1 of the Contract Agreement, which reproduced herewith “the Authority Representative and the Contractor shall, within 30 days of the date of this Agreement, inspect the Site and prepare a memorandum containing an inventory of the site including the vacant and unencumbered land, buildings, structures, road works, trees and any other immovable property on or attached to the site. Subject to the provisions of Clause 8.2.3, such memorandum shall have appended thereto an appendix (the “Appendix”) specifying in reasonable detail those parts of the site to which vacant access and Right of Way has not been given to the Contractor. Signing of the memorandum, in two counterparts (each of which shall constitute an original), by the Authorized Representatives of the Parties shall be deemed to constitute a valid evidence of giving the Right of Way to the Contractor for discharging its obligations under and in accordance with the provisions of this Agreement and for no other purpose whatsoever.” | FALSE | real_data
Borrow area | Contractor's Obligations | As per the provision of the Contract Agreement,Contractor has to arrange all applicable permits for extracting the earth from the borrow area. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210217_AE_SPK_559-Slow Progress of Underpasses works.pdf | Slow Progress of Underpasses works - Reg. | It's time and again brought to your kind notice that the Works of the Underpasses, its approach ramp activities & Fly over at Ch. Km. 106+687 are not progressing according to completion targets. There is a considerable delay in all activities as illustrated below: Ch. Km. 76+846: Size: 1 X 30.0 X 5.5 kilambi junction: There is a delay in construction of slip/diversion road works at this junction. The culverts wing wall/ return wall activities had prolonged for a longer time. These reasons delayed the diversion of traffic and as well as construction of underpass at this location. Ch. Km. 79+302: Size: 1 X 20.0 X 5.5 Baluchetty East: The bitumen works for the left service road were completed on 22.05.2020. It took much time to divert the traffic on Left Service road so as to commence the Left Carriageway Works of underpass. However, PCC was laid for the Left carriageway structure on 09.10.2020. Similarly, for the Right Carriageway DBM has completed on 24.05.2020. Diversion of traffic got delayed and completed the PCC for right Carriageway structure on 27.12.2020. But, unfortunately, till date no approach ramp/ RE wall works commenced at both the side, reasons best known to the Contractor. Ch. Km. 80+805: Size: 1 X 20.0 X 5.5 Baluchetty West. Right side service road DBM works are completed on 27.11.2020. Hence traffic can be diverted for Right Carriageway. But till date no action taken by the Contractor, which getting delayed the work progress at this location also. Ch. Km. 82+566: Size: 1 X 20.0 X 5.5 Damal East: Right side service road DBM was completed on 16.09.2020, but till date no activity for diverting the traffic and commencement of underpass works taken by the Contractor. Similarly, for Left Carriageway also, works are almost completed except a small stretch, which may not affect the works of diversion. Ch. Km. 85+874: Size: 1 X 12.0 X 4.0 Ponniammanpattarai. Despite of diverting the traffic for underpass works well before 06.02.2020 laying of PCC for RE wall works ranged from 02.08.2020 to 25.01.2021. but, RE wall works progress is very slow, which may be seen at site. Ch. Km. 87+540: Size: 1 X 15.0 X 5.5 Perumbulipakkam. Despite of completing the service roads on either side of the underpass on 26.05.2020, but, as on date, diversion of traffic has not been taken up. Hence, underpass construction works are yet to start, as without diverting the traffic that cannot be taken up. Ch. Km. 90+092: Size: 1 X 12.0 X 4.0 Kalathur Village. Commencing of Service road works are getting delayed. Ch. Km. 93+115: Size: 1 X 20.0 X 5.5 Ocheri. Dismantling of structures has been completed. But to remove the debris and commencement of service road works are getting delayed due to unknown reasons as there is no hinderances. Ch. Km. 95+412: Size: 1 X 12.0 X 4.0 Perikarumbur. PCC for the shell has completed on 49.08.2020 which indicates that RE Wall works can start simultaneously. But till date approaches are yet to start. Ch. Km. 96+477: Size: 1 X 12.0 X 4.0 Periya Gramam village. PCC for the shell has been laid on 11.08.2020, but work progress at approaches are very slow. Ch. Km. 98+423: Size: 1 X 20.0 X 5.5 Kaveripakkam Jn. Dismantling of structures was completed. Removal of debris and commencement of service road activities are yet to be attended. Ch. Km. 99+175: Size: 1 X 12.0 X 4.0 Bajana kovil village (RHS) and Anna Street (LHS) dismantling of structures had been completed. But Service road works are getting delayed. Ch. Km. 100+603: Size: 1 X 12.0 X 4.0 Sumaithangi Jn. Drain works are in progress Service road activities are to be commenced. Ch. Km. 102+980: Size: 1 X 12.0 X 4.0 Vanichatram : Service road works are now in progress. Ch. Km. 106+687: Size: 3 X 25.0 X 5.5 Fly over at Walajahpet junction. — Despite of approving the drawings for the flyover on 11.09.2020 till date no activity has commenced. From the above it is clear that despite having sufficient work front to commence the RE wall works, but no serious efforts are being made by the Contractor. There is a clear chance of commencement of earth work at 80+805, 85+874, 95+412 & 96+477 but the works are getting delayed due to the reasons best known to you. Hence it is a clear evident that wherever and whenever earth is available efforts to extract the same and commence the works, but same is being delayed at your end. As per the provision of the Contract Agreement, Contractor has to arrange all applicable permits for extracting the earth from the borrow area, but despite making serious efforts, stating that non availability of earth through your communication number SPK/KW/SAIC/NH-48/2021/009 dated 08.01.2021, is just eyewash. There is penalty of work fronts available, as listed above, if Contractor diverted the traffic, he may commenced the works. But no serious efforts are being made by the Contractor. | FALSE | real_data
Borrow area | Contractor's Obligations | 1.We have been facing several constraints in procurement of borrow earth since inception of the Project Highway. This fact has also been acknowledged by the MoRT&H and it is pertinent to mention that NHAI foreclosed 4 major highway projects in Tamil Nadu as the Contractors couldn't procure soil for earthwork and had to wait for months together to get statutory clearances. 2.It is pertinent to mention that our adjacent package of Six laning of Sriperumbudur to Kanchipuram has come to stand still as the Contractor could not source borrow earth and not a single structure approach has been completed as on date. This reiterates the fact that there is extreme difficulty in procuring the borrow earth along our Project Highway. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LOT-10/20240729_SPK_AE_405_Intimation of unseasonal rainfall during the period from 01.07.2024 to 15.07.2024 – Reply made.pdf | Intimation of unseasonal rainfall during the period from 01.07.2024 to 15.07.2024 — Reply made - Reg. | Dear Sir, This is w.r.t your letter under ref (2) above regarding your views on unseasonal rainfall and our response is as follows: 1. We have been facing several constraints in procurement of borrow earth since inception of the Project Highway. This fact has also been acknowledged by the MoRT&H and it is pertinent to mention that NHAI foreclosed 4 major highway projects in Tamil Nadu as the Contractors couldn’t procure soil for earthwork and had to wait for months together to get statutory clearances. 2. NHAI projects awarded to Contractors from 2018 to 2022 costing approximately 17000 crores in TN and were originally scheduled to be completed within a year to 30 months are running behind the schedule. NHAI officials said that the delay of the project was due to various reasons including land acquisition issues, forest department clearances and non-availability of borrow earth permission as the water bodies were brimming due to heavy rainfall in recent months. News article of DT Next dated 25t» December 2023 is herewith enclosed as Annexure 1 for your kind reference.( 32 NHAI's projects costing Rs 17,000 crore delayed in TN (dtnext.in)) 3. It is pertinent to mention that our adjacent package of Six laning of Sriperumbudur to Kanchipuram has come to stand still as the Contractor could not source borrow earth and not a single structure approach has been completed as on date. This reiterates the fact that there is extreme difficulty in procuring the borrow earth along our Project Highway. . We have been updating regularly AE about the status of procurement of borrow earth and the AE is also very much aware of the difficulties faced from our end in | FALSE | real_data
Descoping/deletion of works under original scope | Payments, Dispute Resolution, Change of Scope | Proposed construction at Ch.Km.104+271 may be deleted from scope of enforced contract. | synthetic_template_20250913 | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Provision of Rest Area at Ch. Km. 104/271 - Reg. | It is brought to your attention that With respect to the Contract Agreement, there is a provision of Rest Area at Ch. Km. 104+271 adjacent to the Left Carriageway of the Project Corridor. Please refer Annexure-1 Schedule -C Point No. 2.5 Page No. 163 of the Contract Agreement. However, based on your letter as Referenced No.1 a site inspection was carried out on 15th May 2020 and findings are as follows: 1. According to the Contract provision at Ch. Km. 104+271 a Rest area is to be made i.e. at Katteri village. 2. But there is already a fully functional Rest Area at Ch. Km. 109+250 near Devadanam village in the continuity Package i.e from Wallajahpet to Krishnagiri which is 5 kms away from the proposed Katteri village Rest Area. Further it is lying on the same side of the Project Corridor. Hence considering the proximity distance of 5kms between the proposed and the existing Rest Areas Authority Engineer is opined that proposed construction at Ch. Km. 104+271 may be deleted from scope of enforced Contract, which will be a negative C.O.S. The necessary sketch showing the proposed and existing Rest Areas is being enclosed for your easy understanding. This is for your in-principle approvals. Assuring our best services at all times. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Change of scope approval revisit | Payments, Dispute Resolution, Change of Scope, EoT | We hereby requesting the Competent Authority for revisiting the approval of COS works without taking into account the deduction towards discount of 9.66% and issue a revised COS order. | synthetic_template_20250913 | Change of Scope Proposal - Change of Scope Approval Communicated with Deduction of 9.66% in the Cost Estimate is outside the purview of the Contract Agreement - Reg | We acknowledge the in-principle approval of Cost estimate towards COS (Change of Scope) works communicated by the PD- PIU Kanchipuram vide ref (3) above and our response is as follows: 1. Clause 13.1.1 of the Contract Agreement states, “The Authority may, notwithstanding anything to the contrary contained in this Agreement, require the Contractor to make modifications / alterations to the works (“Change of Scope”) before the issue of the Completion Certificate either by giving an instruction or by requesting the Contractor to submit a proposal for Change of Scope involving additional cost or reduction in cost. Any such Change of Scope shall be made and valued in accordance with the provisions of this Article 13.” 2. Accordingly, the COS proposal submitted by the Contractor was based on Clause 13.2.3 of the Contract Agreement wherein SOR (2020 - 2021) of Public Works Department, Government of Tamilnadu and MoRTH Standard Data book 2003 was adopted. The same was reviewed by the Authority Engineer and recommended to the Project Director NHAI/Authority. The Regional Officer, NHAI Chennai also acknowledged the Cost Estimate and the same was recommended to NHAI HQ (New Delhi) for in-principle approval. 3. But in the in-principal approval of COS communicated from your end vide ref (3) above, a discount of 9.66% has been deducted in the Total Civil Cost amounting to Rs.3,40,71,496/= (Rupees Three crore forty lakhs seventy-one thousand four hundred and ninety-six) from the Total Civil Cost towards COS of Rs 35,27,06,944/- This deduction is against the provisions of the Contract Agreement. 4. It is worth mentioning that the EPC Contractor has already executed the Black spot rectification works under Change of Scope (COS) and raised invoiced vide IPC and no such deductions were made relating to the above-mentioned discount of 9.66%. 5. We hereby request the Competent Authority for revisiting the approval of COS works without taking into account the deduction towards discount of 9.66% and issue a revised COS order. As original scope of works is also affected at various isolated locations due to delay in approval of COS, the EPC Contractor is facing constraints in completing the original scope of works. It would be highly appreciated if an early response as requested at (5) above is communicated. We look forward to your response. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Delay due to Change of Scope approval | EoT, Payments, Dispute Resolution, Change of Scope | We wish to inform that the same was not scrutinized and recommended by the Engineer even after a period of 43 days | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-6/20230121_SPK_AE_197_Delay in Toll Plaza cost estimate review and recommendation - Request for early COS Approval of Proposed Toll Plaza with 16 lanes at Km.104+981 - Reg..pdf | Delay in Toll Plaza cost estimate review and recommendation - Request for early COS Approval of Proposed Toll Plaza with 16 lanes at Km.104+981 - Reg. | Dear Sir, Vide reference (3) the submissions related to the proposed 16 Nos (8+8) Toll Lanes at Km104+981 have been submitted and as instructed at NHAI RO, Chennai on 29.10.2022 by the Advisor (Tech) NHAI RO office to submit the Cost Estimate for User Fee Plaza with 16 lanes and instructed to get it reviewed at the RO Office at the earliest, for onward recommendation to the NHAI HQ for approval. But with regret we wish to inform that the same was not scrutinized and recommended from your end even after a period of 43 days. The observations on the submitted Drawings has been communicated from your end vide above reference letter (9) after a period of more than a month from our submission. However, the said observations will be incorporated and submitted at the earliest. Due to delay in review of cost estimate from your end, the construction of this new User Fee Plaza within the revised SPCD will become an arduous task and we shall not be held accountable for any delay in this regard. | FALSE | real_data
Intimation of Change in law | Payments | Change in Law circular bearing No.3.3.26/2022 dated 23-11-2022 clarifying applicability of GST in EPC Contracts. | synthetic_template_20250913 | Clarification regarding calculation of GST against change in rates from 18.07.2022 on the activity of construction of road in case of EPC projects under Change in Law -Reg. | We would like to inform you that Please find enclosed herewith a Circular bearing No. 3.3.26/2022 dated 23 November 2022 stated as Ref. No. 1 from NHAI clarifying the applicability of GST on EPC Contracts. Hence it is hereby asked to submit the upcoming IPC’s duly following GST calculations accordingly. This is for your kind information and necessary actions. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Intimation of Change in law | Payments | Change in Law circular bearing No.3.3.26/2022 dated 23-11-2022 clarifying applicability of GST in EPC Contracts. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-6/20221124_AE_SPK_1195_Clarification regarding calculation of GST against change in rates from 18.07.2022 on the activity of construction of road in case of EPC projects under Change in Law.pdf | Clarification regarding calculation of GST against change in rates from 18.07.2022 on the activity of construction of road in case of EPC projects under Change in Law -Reg. | Please find enclosed herewith a Circular bearing No. 3.3.26/2022 dated 23 November 2022 stated as Ref. No. 1 from NHAI clarifying the applicability of GST on EPC Contracts. Hence it is hereby asked to submit the upcoming IPC’s duly following GST calculations accordingly. This is for your kind information and necessary actions. | FALSE | real_data
Change in law reimbursement | Payments | requested for reimbursement of 6% towards additional paid GST | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-6/20240322_SPK_PD_.89 _Change of GST Rate Request for payment of 91 lakhs.pdf | Change of GST Rate on Construction Services of Highways and Road Contract w.e.f. 18.07.2023 — Request for information to produce before DGGI and reimbursement of taxes paid on your behalf. | With reference to the above, we submit that with effect from 18th July 2022, we need to charge the GST at the rate of 18% (CGST 9% & SGST 9%) for the RA Bills raised by us and the same will have to be collected and paid to the Central Government before the 20th of every month. Now, our project site of Balance work of two laning with paved shoulder of Tindivanam - Krishnagiri section of NH-66 from Km. 37.600 to km.219.782 under NHDP Phase-II in the state of Tamil Nadu on Item Rate Contract at Tindivanam was subjected to physical inspection by the Directorate General of Goods and Service Tax, Intelligence, Puducherry Regional Unit on Thursday, the 2nd November, 2023. During the course of inspection, the GST authorities asked us to submit the details of work done during the period from August 2022 to October 2023 and after perusing all the relevant documents, the authorities demanded us to pay the extra 6% (CGST 3% and SGST 3%) along with the applicable rate of interest @ 18% with immediate effect as detailed below: Amount in Rs. Additional Rate Total GST Work / Date of . P of GST and Ea Eet Receipt paid @ Total GST Interest Taxable Value 6% 6% Interest Paid 2 ¦ Panchayat ¦ 29-Jun-22 34,26,921 12,64,85,460 73,83,512 ¦ 20,04,065 ¦ 93,87,577 In this regard, we defended with a view stating that the above Taxable Turnover was completed before the date of amendment i.e. before 18th July 2022 and in this aspect, the department relied on the Section 14 of the CGST Act,2017 in respect of change in rate of tax and it states that: Change in rate of tax in respect of supply of goods or services “Notwithstanding anything contained in section 12 or Section 13, the time of supply, where there is a change in the rate of tax in respect of goods or services or both, shall be determined in the following manner, namely.” a. In case the goods or services or both have been supplied before the change in rate of tax: Where the invoice for the same has been issued and the payment is also received after the change in rate of tax, the time of supply shall be the date of receipt of payment or the date of issue of invoice, whichever is earlier Thus, it appears that, as both the Invoice as well as the payment received dates are “after the change in rate of tax,” that is after 172022, GST is payable at the changed rate of 18%, whereas, GST @12% has been remitted and the additional 6% is levied on the same. Under these circumstances, as per the Directorate General of Goods and Service Tax, Intelligence, Puducherry Regional Unit instructions, we have to pay immediately the above said tax liability and through the borrowed funds in order to reduce the interest element through DRC-O3. Under this Circumstances, we hereby kindly request you to reimburse us a sum of Rs. 73,83,512/- towards GST Tax paid (as per table 1 Rs. 73,83,512/-) and Rs. 20,04,065/- towards interest payable for the delayed payment of above GST thereby total of GST and Taxes paid was amounting to Rs. 93,87,577/- being the amount paid to the Government by ourselves on your behalf at the earliest. In support of our claim, we enclose herewith 1. Notification of Government with respect to Construction of Road contract for your kind perusal and records 2. Intimation of GST Payable raised by DGGI, Puduchery Unit | FALSE | real_data
Descoping of works under original scope | Payments, Dispute Resolution, Change of Scope | The computation of cost estimate for negative scope of shall be carried out in the following manner, The above said pipe culvert at Km.103+473 could not be identified at site. | synthetic_template_20250913 | Requisition for De-scoping of Hume Pipe Culverts 2 +1 Total (3Nos) as per Schedule - B which is not existing on ground at project site — Reg. | Please note that Dear Sir, With reference to the above subject, the Authority Engineer had communicated to the Authority that the following Hume Pipe Culverts are missing based on the site verification. The requirement at the project site is being submitted for your kind information and further advice. The details of the pipe culverts are as follows: (i) Clause 6.13 (b) of Schedule-B (Page 143): S1.No Exiting ¦ Proposed Existing ¦ Proposed Existing Proposed Chainage ¦ Chainage ¦ Structure ¦ Structure Span Arrangement Arrangement 33 84+099 84+117 HPC HPC 1 Row of 1 Row of 34 844+115 844133 HPC ¦ HPC 0.90m Dia 1.20m Dia Further to the above missing Hume Pipe Culverts, one more Pipe Culvert missing is as listed as below: (ii) Clause 10(a) of Schedule-A (Page 125) S1.No Exiting Proposed Type Width Dia Chainage Chainage ¦ 59 103+450 103+461 ¦ Pipe Culvert 2x2 lane 1 Row of 0.60m Dia (iii) Clause 6.13 (a) of Schedule-B (Page 142): Sl. ¦ Exiting Proposed ¦ Existing Proposed ¦ Proposed Span Remarks No ¦ Chainage ¦ Chainage ¦ Structure ¦ Structure ¦ Arrangement 10 ¦ 103+450 ¦ 103+473 HPC HPC 1 Row of 1.2m ¦ Reconstruction ¦ Dia with Pipe Culvert The above said Pipe Culvert at Km.103+473 could not be identified at site and the same is also submitted for de-scoping along with the above 2 Nos of Hume Pipe Culverts. This is for information that joint site verification at the above location and the facts communicated above are justified. Some photographs at the above-mentioned location of Km.103+473 are herewith attached for reference. The computation of cost estimate for negative scope of work shall be carried out in the following manner: (i) Hume Pipe Culverts at Km.84+117 & Km.84+133 - 1.2m diameter Pipe laying in the widening portion. (ii) Hume Pipe Culverts at Km.103+473 — Reconstruction of pipe culvert with 1.2m dia for the entire barrel length. We hereby request the Authority Engineer to intimate and remind the Authority for further necessary action. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Descoping of works under original scope | Payments, Dispute Resolution, Change of Scope | The computation of cost estimate for negative scope of shall be carried out in the following manner, The above said pipe culvert at Km.103+473 could not be identified at site. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-6/20231128_SPK_AE_313_Requisition for De-scoping of Hume Pipe Culverts 2 +1 Total (3Nos) as per Schedule - B which is not existing on ground at project site – Reg..pdf | Requisition for De-scoping of Hume Pipe Culverts 2 +1 Total (3Nos) as per Schedule - B which is not existing on ground at project site — Reg. | Dear Sir, With reference to the above subject, the Authority Engineer had communicated to the Authority that the following Hume Pipe Culverts are missing based on the site verification. The requirement at the project site is being submitted for your kind information and further advice. The details of the pipe culverts are as follows: (i) Clause 6.13 (b) of Schedule-B (Page 143): S1.No Exiting ¦ Proposed Existing ¦ Proposed Existing Proposed Chainage ¦ Chainage ¦ Structure ¦ Structure Span Arrangement Arrangement 33 84+099 84+117 HPC HPC 1 Row of 1 Row of 34 844+115 844133 HPC ¦ HPC 0.90m Dia 1.20m Dia Further to the above missing Hume Pipe Culverts, one more Pipe Culvert missing is as listed as below: (ii) Clause 10(a) of Schedule-A (Page 125) S1.No Exiting Proposed Type Width Dia Chainage Chainage ¦ 59 103+450 103+461 ¦ Pipe Culvert 2x2 lane 1 Row of 0.60m Dia (iii) Clause 6.13 (a) of Schedule-B (Page 142): Sl. ¦ Exiting Proposed ¦ Existing Proposed ¦ Proposed Span Remarks No ¦ Chainage ¦ Chainage ¦ Structure ¦ Structure ¦ Arrangement 10 ¦ 103+450 ¦ 103+473 HPC HPC 1 Row of 1.2m ¦ Reconstruction ¦ Dia with Pipe Culvert The above said Pipe Culvert at Km.103+473 could not be identified at site and the same is also submitted for de-scoping along with the above 2 Nos of Hume Pipe Culverts. This is for information that joint site verification at the above location and the facts communicated above are justified. Some photographs at the above-mentioned location of Km.103+473 are herewith attached for reference. The computation of cost estimate for negative scope of work shall be carried out in the following manner: (i) Hume Pipe Culverts at Km.84+117 & Km.84+133 - 1.2m diameter Pipe laying in the widening portion. (ii) Hume Pipe Culverts at Km.103+473 — Reconstruction of pipe culvert with 1.2m dia for the entire barrel length. We hereby request the Authority Engineer to intimate and remind the Authority for further necessary action. | FALSE | real_data
Stoppage of Works by locals/public | EoT, Authority's Obligations | We would like to bring to your kind attention that works on A2 side approach of LVUP@ Km.79/860 - COS location has been stopped by locals on 31.07.2024. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-6/20240802_SPK_PD_098_Brief Stoppage of works at A2 side approach of LVUP at Km.79860 - COS Location – Intimation of the same.pdf | Six laning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km. 71+015 (Existing km 71+000) to Km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - Brief Stoppage of works at A2 side approach of LVUP at Km.79/860 - COS Location - Intimation of the same - Reg. | 1. We would like to bring to your kind attention that works on A2 side approach of LVUP at Km.79/860 - COS Location has been stopped by locals on 31.07.2024 while RE wall approach works were in progress between Km 80+070 to Km 80+100. 2. The local people insisted for construction of LVUP at originally proposed location viz. Thiruppukuzhi junction (Km.80+060) and also demanded that the present access from crossroad to Thirupukuzhi temple, School and Ration Shops shall not be closed/blocked by way of RE wall construction activities. Necessary photographs are herewith enclosed as Annexure 1. 3. We immediately intimated this incident to the nearby Police Station and police officials also came to the site. The police officials also spoke to local people, and it was agreed that as a stop gap solution, the excavated portion will be backfilled and access shall be restored by temporarily leaving a gap of around 30m near Thirupukuzhi junction. Now the EPC Contractor is proceeding with balance approach works on A2 side. 4. As suggested by the Authority, we made sincere attempts to resolve the issue on our own and could succeed partially. We will continue our liasoning with police officials/local people for complete resolving of this issue. 5. District Collector, Kancheepuram vide letter No 0043 dated 27.04.2024 has also replied to the Project Director PIU Kancheepuram that consent has been accorded towards changing the location for Construction of LVUP from Thiruputkuzhi (Km80+060) to Musaravakkam Junction (Km 76+860) which will be helpful in convincing the local people. In the meanwhile, as such finally the gap of around 30m near Thirupukuzhi junction has to be taken up, we also request your good self to apprise this situation to District Administration, Kanchipuram for their kind intervention and provide necessary support & cooperation to us as per clause 4.1.6 (e) of the Contract Agreement for successful implementation of the Project Highway. | FALSE | real_data
Descoping of a work from the scope of additional works under COS | Payments, EoT, Dispute Resolution, Change of Scope | SPK AND Co.. , the issue was discussed at CUP location. It has been instructed by the Regional Officer NHAI Chennai to stop the CUP at Km.84/032 works and instructed us to restore the excavated portion and complete it with the required layers so that the RHS carriageway is restored back and traffic will be diverted as normal. Also, it was informed that this COS (CUP at Km.84/032) will be descoped from the scope of additional works. | synthetic_template_20250913 | Six laning of Karaipettai to Walajapet Section of NH-4 (New NH-48) from Km. 71+015 (Existing km 71+000) to Km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - CUP at Km.84/032 —- Works stopped by locals - Restoration of Excavated Portion and Opening to Traffic on the RHS - Intimation of the same - Reg. | 1. The EPC Contractor had started the construction of Cattle Underpass (CUP) at kKm.84+032 under positive COS after carrying out traffic diversion as per the traffic diversion plan. 2. The excavation for the CUP commenced on RHS side of the Project Highway on 25.07.2024 and excavation up to Subgrade top of the existing road was completed for part width of CUP. 3. But on 26.07.2024, local people along with Damal Panchayath President came to CUP location and stopped us from executing further works. They demanded construction of Vehicular Underpass for cross movement of vehicles in lieu of the CUP under positive change of scope. 4. Further during the site inspection on 27.07.2024 by the Regional Officer NHAI Chennai along with the Project Director, Team Leader of AE, Project Manager of SPK AND Co.., the issue was discussed at CUP location. It has been instructed by the Regional Officer NHAI Chennai to stop the CUP at Km.84/032 works and instructed us to restore the excavated portion and complete it with the required layers so that the RHS carriageway is restored back and traffic will be diverted as normal. Also, it was informed that this COS (CUP at Km.84/032) will be descoped from the scope of additional works. 5. This is for information that the restoration works have been completed on 31.07.2024 and the MCW traffic coming from Bangalore which was diverted on LHS from Km.83+920 to Km.84+250 is now plying as normal on the RHS carriageway. Photographs enclosed for your reference as Annexure 1. 6. The EPC Contractor had incurred additional expenses (i) By engaging man power and machinery towards the traffic diversion and restoration of diverted traffic (ii) Excavation for the construction of CUP up to original subgrade level and replacing it back with the same crust viz. Subgrade, GSB, WMM DBM and BC and restoration of centre median kerbs. This additional expenditure is being worked out and will be submitted at the earliest. This may please be scrutinised and recommended for payment to the Authority. This is for your information and further necessary action. Thank you for your attention to this matter. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Topography/Geo-tech survey | Contractor's Obligations | we have mobilized rigs for carrying out soil investigation work of the bridges | synthetic_template_20250913 | Rehabilitation and Upgradation of Ghogaspargaon-Phulsangvi-Ukhandachakla-Dahiwandi-Shirur-Rakshasbhuvan-Kholayachiwadi-Karegaon-Dongarkini-Chumbli-Patoda-Dighol Road (SH-62) Kharda. From KM 0+000 to KM 56+000 to two lanes with paved shoulders” (Project Length 55.937 KM) on EPC basis in the State of Maharashtra (Package — I) — Delay in start of work | We are planned fo start the execution of the project from 14th June 2017 as intimated to you verbally and as per the construction programme submitted to you to complete the project execution in stipulated period. Based on this, we have submitted initial Plan & Profile for a length of 34 Km, starting from Ch: 0+000 to Ch: 34+000 and also at the same time, we have mobilized rigs for carrying out soil investigation work of the bridges. , So far, we have completed detailed survey including establishment of bench marks for a length of 56 km. We are planning to submit the balance Plan & Profile of 22 Km by this weekend. Initially, we have submitted the Plan & Profile in oe copy for your review. Please go through it and suggest for 5 a modifications if any. (amr aT igre wera PUT ty, we are establishing centre line marking on the existing road and will be completed by s. In mean time, we have placed order to procure the lab equipment required for this project e€ are expecting. the delivery of the material by this weekend and we are establishing the NM temporary laboratory at the camp location and can be utilized for the time being till the camp construction completes. As per the discussions we had earlier with the Department, we are forced to take appointed date as 30.05.17, We are mobilizing our equipment to start preliminary works like Clearing and Grubbing and base compaction of the existing ground making suitable for embankment construction. But you L have given instruction not to start the work due to the various reasons which are known to you. This delay will cause slippage in achievement of milestones & completion of the project. Hence we would like to bring to your notice that, if any delay occurs due to any reason and circumstances which are beyond our control in achieving the milestone would not be considered as a failure from our side. So please permit us to start the work at the earliest. We appreciate your cooperation in this regard. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Topography/Geo-tech survey | Contractor's Obligations | we have mobilized rigs for carrying out soil investigation work of the bridges | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-3/5. Delay in start of work 13.06.2017.pdf | Rehabilitation and Upgradation of Ghogaspargaon-Phulsangvi-Ukhandachakla-Dahiwandi-Shirur-Rakshasbhuvan-Kholayachiwadi-Karegaon-Dongarkini-Chumbli-Patoda-Dighol Road (SH-62) Kharda. From KM 0+000 to KM 56+000 to two lanes with paved shoulders” (Project Length 55.937 KM) on EPC basis in the State of Maharashtra (Package — I) — Delay in start of work | We are planned fo start the execution of the project from 14th June 2017 as intimated to you verbally and as per the construction programme submitted to you to complete the project execution in stipulated period. Based on this, we have submitted initial Plan & Profile for a length of 34 Km, starting from Ch: 0+000 to Ch: 34+000 and also at the same time, we have mobilized rigs for carrying out soil investigation work of the bridges. , So far, we have completed detailed survey including establishment of bench marks for a length of 56 km. We are planning to submit the balance Plan & Profile of 22 Km by this weekend. Initially, we have submitted the Plan & Profile in oe copy for your review. Please go through it and suggest for 5 a modifications if any. (amr aT igre wera PUT ty, we are establishing centre line marking on the existing road and will be completed by s. In mean time, we have placed order to procure the lab equipment required for this project e€ are expecting. the delivery of the material by this weekend and we are establishing the NM temporary laboratory at the camp location and can be utilized for the time being till the camp construction completes. As per the discussions we had earlier with the Department, we are forced to take appointed date as 30.05.17, We are mobilizing our equipment to start preliminary works like Clearing and Grubbing and base compaction of the existing ground making suitable for embankment construction. But you L have given instruction not to start the work due to the various reasons which are known to you. This delay will cause slippage in achievement of milestones & completion of the project. Hence we would like to bring to your notice that, if any delay occurs due to any reason and circumstances which are beyond our control in achieving the milestone would not be considered as a failure from our side. So please permit us to start the work at the earliest. | FALSE | real_data
Delay in commencement/starting of work | EoT, Payments, Dispute Resolution | This delay will cause slippage in achievement of milestones & completion of the project. | synthetic_template_20250913 | Rehabilitation and Upgradation of Ghogaspargaon-Phulsangvi-Ukhandachakla-Dahiwandi-Shirur-Rakshasbhuvan-Kholayachiwadi-Karegaon-Dongarkini-Chumbli-Patoda-Dighol Road (SH-62) Kharda. From KM 0+000 to KM 56+000 to two lanes with paved shoulders” (Project Length 55.937 KM) on EPC basis in the State of Maharashtra (Package — I) — Delay in start of work | We are planned fo start the execution of the project from 14th June 2017 as intimated to you verbally and as per the construction programme submitted to you to complete the project execution in stipulated period. Based on this, we have submitted initial Plan & Profile for a length of 34 Km, starting from Ch: 0+000 to Ch: 34+000 and also at the same time, we have mobilized rigs for carrying out soil investigation work of the bridges. , So far, we have completed detailed survey including establishment of bench marks for a length of 56 km. We are planning to submit the balance Plan & Profile of 22 Km by this weekend. Initially, we have submitted the Plan & Profile in oe copy for your review. Please go through it and suggest for 5 a modifications if any. (amr aT igre wera PUT ty, we are establishing centre line marking on the existing road and will be completed by s. In mean time, we have placed order to procure the lab equipment required for this project e€ are expecting. the delivery of the material by this weekend and we are establishing the NM temporary laboratory at the camp location and can be utilized for the time being till the camp construction completes. As per the discussions we had earlier with the Department, we are forced to take appointed date as 30.05.17, We are mobilizing our equipment to start preliminary works like Clearing and Grubbing and base compaction of the existing ground making suitable for embankment construction. But you L have given instruction not to start the work due to the various reasons which are known to you. This delay will cause slippage in achievement of milestones & completion of the project. Hence we would like to bring to your notice that, if any delay occurs due to any reason and circumstances which are beyond our control in achieving the milestone would not be considered as a failure from our side. So please permit us to start the work at the earliest. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Preliminary / preparatory works | Contractor's Obligations | Presently, we are establishing centre line marking on the existing road and will be completed by 25.06.17. Simultaneously we have identified stone quarry at Chainage 30+000 and land for camp was finalized at Chainage 33+000 -and planning to start the camp construction by next week | synthetic_template_20250913 | Rehabilitation and Upgradation of Ghogaspargaon-Phulsangvi-Ukhandachakla-Dahiwandi-Shirur-Rakshasbhuvan-Kholayachiwadi-Karegaon-Dongarkini-Chumbli-Patoda-Dighol Road (SH-62) Kharda. From KM 0+000 to KM 56+000 to two lanes with paved shoulders” (Project Length 55.937 KM) on EPC basis in the State of Maharashtra (Package — I) — Delay in start of work | We are planned fo start the execution of the project from 14th June 2017 as intimated to you verbally and as per the construction programme submitted to you to complete the project execution in stipulated period. Based on this, we have submitted initial Plan & Profile for a length of 34 Km, starting from Ch: 0+000 to Ch: 34+000 and also at the same time, we have mobilized rigs for carrying out soil investigation work of the bridges. , So far, we have completed detailed survey including establishment of bench marks for a length of 56 km. We are planning to submit the balance Plan & Profile of 22 Km by this weekend. Initially, we have submitted the Plan & Profile in oe copy for your review. Please go through it and suggest for 5 a modifications if any. (amr aT igre wera PUT ty, we are establishing centre line marking on the existing road and will be completed by s. In mean time, we have placed order to procure the lab equipment required for this project e€ are expecting. the delivery of the material by this weekend and we are establishing the NM temporary laboratory at the camp location and can be utilized for the time being till the camp construction completes. As per the discussions we had earlier with the Department, we are forced to take appointed date as 30.05.17, We are mobilizing our equipment to start preliminary works like Clearing and Grubbing and base compaction of the existing ground making suitable for embankment construction. But you L have given instruction not to start the work due to the various reasons which are known to you. This delay will cause slippage in achievement of milestones & completion of the project. Hence we would like to bring to your notice that, if any delay occurs due to any reason and circumstances which are beyond our control in achieving the milestone would not be considered as a failure from our side. So please permit us to start the work at the earliest. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Clearances from Irrigation department for construction of Canal Bridges | Others | The Irrigation department may please be apprised of our construction programme. | synthetic_template_20250913 | Rehabilitation and Up-gradation of Paithan (Pategaon) — Mungi - Hadgaon — Bodhegaon- ~*~ Ladjaigaon — Ghogaspargaon — Phulsangvi — Ukhandachakla ~ Dahiwandi — Shirur to 2-Lane — with paved shoulder (Project Length 55.937 Km) on EPC basis in the state of Maharashtra (Package ¦ - 56 KM) — Cross drainage works in irrigation canals — reg. | We have submitted our construction programme, under reference cited above, which includes five no’s of minor bridges and existing causeways. As it is obligatory to keep the state irrigation department regarding commencement of works coming under them, we request that the irrigation department may please be apprised of our construction programme. We look forward to your response. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Handing over of cut tree/ salvaged material to the concerned authority | Contractor's Obligations, Others | we request you to intimate us the relevant authority to handover the material | synthetic_template_20250913 | Heavy wind - damages - Reg. | In the night between 19th & 20th of August, there was heavy wind, followed by rain in the stretch between Km 43 & Km 47. Due to this, a few (8 nos) trees at the edge of ROW fell down on the existing road between Km 43 & Km 45, where we had already commenced construction activity. The trees which fell on the existing road, disrupting the traffic, had to be cut and removed, to enable traffic flow. A few photographs of the cut & stockpiled trees are enclosed. We request you to intimate us the relevant authority to handover the material. We look forward to your response. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Schedule-H Division | Payments | We are once again requesting for your benign consider our appeal, to amend table 1.3.1 of schedule "H", suitably. | synthetic_template_20250913 | Modification in minimum criteria for payment — Reg. | We have been assigned the work mentioned in the captioned subject and the EPC agreement was signed on 18! April 2017 Schedule “H” of the agreement gives the activity wise, weightage and the table 1.3.1 details (in the last column) the payment procedure. The construction period is 24 months, whereas as per the table, value of the billable payment will be 10% of Bridge works and 5% of road works, when completed. In other words, until the percentage is reached, it is not measurable. We submit to state that we have not availed the mobilization advance and due to this stringent yardstick & payment procedure, the requirement of revolving capital will be to the tune of 3 /4 months turnover, considering the minimum criteria requirement of varies key activities. M/S RCM Infrastructure lid. -P V Ramanaiah & Co. JV As this payment procedure will lead to cash flow constraints, we request that a) monthly bills of all completed works may be paid, without any percentage limitations. (OR) b) reduce the percentage which is stated as 5% to 1% and which is stated as 10% to 2%. This will enable advance procurement actions smoothly and also timely completion of the project. We are once again requesting for your benign consideration of our appeal, to amend table 1.3.1 of schedule “H”, suitably. Thank you for your attention to this matter. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Schedule-H Division | Payments | The Contractor requested the Authority for bifurcation of Schedule H for their cash flow purpose. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/20191205_AE_NHAI_188_Minutes of Monthly Progress review meeting Mom-5.pdf | Consultancy services for Authority’s Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to 107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode- Minutes of Monthly Progress review meeting Mom-5 -Reg. | With respect to the above said reference please find enclosed herewith the Minutes of Meeting Numbered as MoM-S held on 29.11.2019. The next meeting will be likely on 27.12.2019 at the Consultants office around 11.00 A.M in Kancheepuram. All the concerned are requested to attend with necessary documents. This is for your information and record. Assuring our best services at all times. | FALSE | real_data
Pending approvals | Others, EoT, Payments | In the absence of above approvals, we are-not able to take up high value items, without which achievement of Milestone — I is not practically possible. | synthetic_template_20250913 | Rehabilitation and Up-gradation of Paithan (Pategaon) — Mungi — Hadgaon - Bodhegaon- Ladjalgaon — Ghogaspargaon — Phulsangvi — Ukhandachakla — Dahiwandi - —_ Shirur to 2-Lane with paved shoulder (Project Length 55.937 Km) on EPC basis in the state ~ of Maharashtra (Package ¦- 56 KM) - Approvals pending — Reg. | Respected Sir,\n\nVide our letter referred above, we submitted the correspondence of the past - fill then. Though Authority was kind enough to accord approval on a few key matters, we await approval of Authority Engineer on the following matters\n\ni. 2row pipe culverts drawing\nii. Method statement\niii. Drain in built-up area — drawings\niv. Toe wall with PCC (up to 3m height) drawing\nv. GSB for full formation width to serve as drainage layer(as per pre bid meetings page no 085 Of volume-ll of contract agreement}\n\nIn the absence of above approvals, we are_not able to take up high value items, without which achievement of Milestone — ¦ is not practically possible.\n\nHence, we request you to accord your approval on top priority in the aforesaid matters.\n\n Please confirm receipt of this correspondence. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Stage Payments Statements | Contractor's Obligations, Authority's Obligations, Payments | In continuation to our earlier letter stated as Ref.No.1 and based on Schedule "J" point 2 & 3 of Contract document it is to ask you to submit the "Stage Payment Statement" for further necessary action. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode ~— Implementation of Mile Stone -1 & 2 - Reg. | It is brought to your attention that In continuation to our earlier letter stated as Ref. No.1 and based on SCHEDULE “J” point 2 & 3 of Contract Document it is to ask you to submit the “Stage Payment Statement” for further necessary action. Thank you for your attention to this matter. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Stage Payments Statements | Contractor's Obligations, Authority's Obligations, Payments | we request you to immediately recommend for release 90% of claimed amount and process the bill there after. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-3/14. Part payment of IPC-02 03.01.2018.pdf | Part payment of Interim payment certificate (IPC-2) — Reg. | We have submitted the Second IPC vide reference above for certification. We understand that it is under process and the review of already approved drawings is also on going. As you're aware that, we have not availed mobilization advance and machinery advance, and this is a good working season for high value items such as DLC, PQC are to be executed as per the construction programme know. These activities are cost-intensive and hence we require sufficient cash flow hence, we request you to immediately recommend for release 90% of claimed amount and process the bill there after. | FALSE | real_data
Change of scope due to realignment | Change of Scope, Dispute Resolution, EoT, Payments | 1. We have been instructed by Authority to change the alignment, which being a major deviation, forms change of scope. 2. we are entitled for all additional expenses/costs arising out of this variation, by Authority. | synthetic_template_20250913 | Submission of Re-alignment proposal between Km 12+700 and 13+500 — Reg. | We have for reference your letter cited above and clarify as follows: The PCL / ROW Coordinates are already furnished. The GAD with 2 spans, for skewed Minor Bridge, will be submitted separately. We have been instructed by Authority to change the alignment, which being a major deviation, forms change of scope. The conditions on the length of the bridge /span, stipulated in Contract agreement, are applicable for the bridge, which was inspected before bidding. The particular clause requires the bidder to study the ground condition and to do a survey, to decide the span as stated in schedule B (or otherwise) and quote the rates accordingly. The subject, location is in the re-alignment suggested by Authority after signing of the agreement, by both the parties which could not be foreseen by any bidder. So, no bidder could have speculated / imagined such location or a skew bridge to consider this additional cost as incidental. Hence we are entitled for all additional expenses / costs arising out of this variation, by Authority. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Providing and maintaining highway patrol, ambulance, emergency medical services and cranes etc. for safe operation of the Highway | Contractor's Obligations, Dispute Resolution, Change of Scope | In view of the above and as per Article 2.1(a), Schedule-C, Sl.No.2.7,2.8,2.9 & 2.10 and as per Article 10.4.1, it is requested you to take necessary action for deploying the Highway Patrol, Ambulance, Emergency Medical Services and Cranes immediately. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode. Maintenance of Highway Patrol, Ambulance, Cranes etc., — reg. | This is in reference to the vide cited reference letter (1), the Authority has requested the Contractor to mobilize the Highway Patrol, Ambulance, Emergency Medical Services and Cranes. We reiterate the Article quoted by the Authority once again below for your ready reference, i, As per Article 2. 1(a), - the scope of the project includes construction of highway on the site set forth in Schedule — A and as specified in Schedule — B together with provision of Project Facilities as specified in Schedule — C and in conformity with the specifications and standards set forth in Schedule — D. ii. As per Schedule — C, Annexure — I — Project facility for Six laning, vide item No. 2.7, 2.8, 2.9 & 2.10 the Contractor has to maintain Highway Patrol, Ambulances, Emergency Medical Services and Cranes covering the entire project Highway. Further as per Clause 10.4 Maintenance during Construction period, the Contractor shall at all times be responsible for ensuring safe operation of the Project Highway. In this regard, it is informed that Article 10.4.1 states that”......For the avoidance of doubt, it is agreed that the Contractor shall at all times be responsible for ensuring safe operation of the Project Highway” Further article 10.4.2 states that “ Notwithstanding anything to the contrary contained in this Agreement, in the event of default by the Contractor in discharging the obligations specified in clause 10.4.1 above, the Authority shall get these maintenance works done as recommended by the Authority’s Engineer to avoid public inconvenience at the risk at the risk and cost of the Contractor in order to keep the road in traffic worthy condition.” Providing Highway Patrol, Ambulance, Emergency Medical Services and Cranes etc. are required for the safe operation of the Highway. Also the Authority has informed, during the inspection on 04.07.2019, it is noticed that the Contractor has not been mobilized the Highway Patrol, Ambulances, Emergency Medical Services and Cranes so far. In view of the above and as per Article 2.1(a), Schedule — C, SI. No. 2.7, 2.8, 2.9 & 2.10 and as per Article 10.4.1, it is requested you to take necessary action for deploying the Highway Patrol, Ambulance, Emergency Medical Services and Cranes immediately. This is for your information and necessary action please. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Providing and maintaining highway patrol, ambulance, emergency medical services and cranes etc. for safe operation of the Highway | Contractor's Obligations, Dispute Resolution, Change of Scope | In view of the above, it is requested the Contractor may be requested to take necessary action for the deploying the Highway Patrol, Ambulance, Emergency Medical Services and Cranes as per Article 2.1(a), Schedule-C, Sl.No.2.7,2.8,2.9 & 2.10 and as per Article 10.4.1 immediately. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/Lot-12/1400_05072019_Maintenance of highway patrol.pdf | NHAI — PIU, Kancheepuram - Six laning of Karaipattai - Walajahpet Section of NH-4 from Km 71/015 to Km 107/091 in the State of Tamil Nadu under NHDP Phase V under EPC mode - M/s. SPK & CO — Scope of the Project - Maintenance of Highway Patrol, Ambulance, Cranes etc - reg. | Vide reference 2nd cited above, wherein the Contractor was requested to submit the action taken report on achievements of the stretch during construction period. Further vide reference 1st cited above, the Contractor was once again requested to mobilize the Highway Patrol, Ambulance, Emergency Medical Services and Cranes duly mentioning the following: i. As per Article 2.1(a), - the scope of the project includes construction of highway on the site set forth in Schedule - A and as specified in Schedule — B together with the provision of Project Facilities as specified in Schedule — C and in conformity with the specifications and standards set forth in Schedule — D. ii. As per Schedule — C, Annexure — I — Project facility for six laning, vide item No.2.7, 2.8, 2.9 & 2.10 the Contractor has to maintain Highway Patrol, Ambulances, Emergency Medical Services and Cranes covering the entire project Highway. Further as per Clause 10.4 — Maintenance during construction period the Contractor shall at all times be responsible for ensuring safe operation of the Project Highway. 3: In this regard, it is informed that article 10.4.1 states that “..... For the avoidance of doubt, it is agreed that the Contractor shall at all times be responsible for ensuring safe operation of the Project Highway”. Further article 10.4.2 states that “Notwithstanding anything to the contrary contained in this Agreement, in the event of default by the Contractor in discharging the obligations specified in Clause 10.4.1 above, the Authority shall get these maintenance works done as recommended by the Authority’s Engineer to avoid public inconvenience at the risk and cost of the Contractor in order to keep the road in traffic worthy condition.” Providing Highway Patrol, Ambulance, Emergency Medical Services and Cranes etc are required for the safe operation of the Highway. 4. During the inspection on 04.07.2019, it is noticed that the Contractor had not been mobilized the Highway Patrol, Ambulances, Emergency Medical Services and Cranes so far. The copy of references are enclosed herewith. 5. In view of the above, it is requested the Contractor may be requested to take necessary action for the deploying the Highway Patrol, Ambulance, Emergency Medical Services and Cranes as per article 2.1(a), Schedule C, S1.No.2.7, 2.8, 2.9 & 2.10 and as per article 10.4.1 immediately. | FALSE | real_data
Maintenance of diversion road/ existing road | Contractor's Obligations | As regards maintenance of the existing road,the directions given in para 2(iii) and 2(iv) will apply to the Contractor in this package also | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20201213_RO_PD_3721_Inspection Report by RO on 22.12.2020.pdf | NHAI Chennai Region - PIU Kancheepuram - Inspection of Maduravoyal - Wallajahpet / Ranipet section of NH-4 by RO-Chennai on 22.12.2020 - Inspection Report forwarded - Reg | Enclosed please find herewith the Report on the Inspection of the project highway carried out by the undersigned on 22.12.2020 for necessary action and to submit the Action Taken Report. | FALSE | real_data
Maintenance of diversion road/ existing road | Contractor's Obligations | lot of pot holes were observed along the stretch as per the details enclosed herewith. In view of the above, It is requested to take necessary action to rectify the same through the Contractor at the earliest as the maintenance of the existing road is the obligations of the Contractor | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/Lot-12/20201127_PD_AE_3901_Rectification of pot holes.pdf | NHAI, PIU-Kancheepuram - Six laning of Karaipettai to Walajahpet section of NH-4 from km 71/015 to km 107/091 in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharathmala Pariyojana on EPC mode - Rectification of potholes — Reg. | It is to inform that during the inspection by the undersigned on 26.11.2020, lot of potholes were observed along the stretch as per the details enclosed herewith. 2. In view of the above, it is requested to take necessary action to rectify the same through the contractor at the earliest as the maintenance of the existing road is the obligations of the contractor and the action taken in this regard may be submitted to this office. | FALSE | real_data
Maintenance of existing project highway with overlay | Contractor's Obligations, Dispute Resolution, Change of Scope | Project Director PIU, Kancheepuram inspected the Project site on 22.12.2020 and instructed to maintain the Project Highway to Standards and specifications by overlaying Bituminous Courses as per specifications and laying the BC to standards to full width | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode - Maintenance of Project Highway by Overlaying with 30mm thick BC - Reg. | This is to notify you that Dear Sir, In view of above-mentioned subject and letters, it is of grave concern and apprehension about the probable consequence, arising out of the Hon'ble High Court verdict, and media report and pouring in of complaints by the road users of the above stretch regarding the maintenance and upkeep of the project corridor to standards and specification from Ch. 71+015 to Ch. 107+091. Specially, when Authority is collecting the Toll from the road users. In this regard, the Authority Engineer requested verbally and written instruction issued vide above referred letter. Subsequently, the Regional Officer, NHAI Chennai and Project Director PIU, Kancheepuram inspected the Project site on 22.12.2020 and instructed to maintain the Project Highway to standards and specifications by overlaying Bituminous Courses as per specifications and laying the BC to standards to full width so as to cover all the potholes to avoid bumpy rides with proper ramping/easing so as to provide a smooth and safe ride without any deficiency. This would help in regaining the lost ground on repute of the Authority. It would therefore be in the interest of the Contractor to immediately take-up the repair work as advised. Enclosed herewith are the stretches, which requires the overlay works. Further to above, your kind attention is also being drawn to on the following Contractual Provisions; Clause 10.4.1 of the Contract, which stated that “During the Construction Period, the Contractor shall maintain, at its cost, the existing lane(s) of the Project Highway so that the traffic worthiness and safety thereof are at no time materially inferior as compared to their condition 10 (ten) days prior to the date of this Agreement, and shall undertake the necessary repair and maintenance works for this purpose; provided that the Contractor may, at its cost, interrupt and divert the flow of traffic if such interruption and diversion is necessary is necessary for the efficient progress of works and conforms to Good Industry Practice; provided further the such interruption and diversion shall be undertaken by the Contractor only with the prior written approval of the Authority's Engineer which approval shall not be unreasonably withheld. For the avoidance of doubt, it is agreed that the Contractor shall at all times be responsible for ensuring safe operation of the Project Highway. It is further agreed that in the event the Project includes construction of a bypass or tunnel and realignment of the existing carriageway, the Contractor shall maintain the existing highway in such sections until the new works are open to traffic.” Clause 10.4.2, which stated that “Notwithstanding anything to the contrary contained in this Agreement, in the event of default by the Contractor in discharging the obligations specified in Clause 10.4.1 above, the Authority shall get these maintenance works done as recommended by the Authority’s Engineer to avoid public inconvenience at the risk and cost of the Contractor in order to keep the road in traffic worthy condition.” In view of above, the EPC Contractor is advised to attend to the repair work as per the instructions of the Authority Given vide reference first cited and to carry out the work on war footing basis and submit the compliance report on daily basis. Any lapses in the aforesaid works shall be reviewed as per the provisions of the Contract Agreement. This letter is issued for your needful and necessary compliance. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Occurrence of Force Majeure event | EoT, Dispute Resolution | Indirect Political event on 10 Sep 2018 | synthetic_template_20250913 | Rehabilitation and Up-gradation of Paithan (Pategaon) - Mungi — Hadgaon — Bodhegaon- : Ladjalgaon - Ghogaspargaon — Phulsangvi - Ukhandachakla — Dahiwandi - Shirur to 2-Lane with paved shoulder (Project Length 55.937 Km) on EPC basis in the state of Maharashtra (Package ¦ ~ 56 KM) = Indirect Political event on 10 September 2018 ~ Reg. | Respected Sir, With reference to above mentioned subject and reference we would like to bring to your kind notice that Congress party called for a BHARAT BANDH on 20th July 2018 against rising fuel price. We are herewith attaching the Newspaper cuttings highlighting the issue of BHARAT BANDH on 20th July 2018 against rising fuel price for your reference and record. We are also bringing to your kind notice that the progress of the Work was hampered yesterday. This is for your kind information and record. We appreciate your cooperation in this regard. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Right of way | Authority's Obligations, EoT, Dispute Resolution | we have intimated to the Authority & Authority Engineer as and when we had faced obstructions to the progress of work due to encroachments & encumbrances. | synthetic_template_20250913 | Encroachments & Encumbrances in the ROW -Reg. | With reference to above subject & letters, we would like to bring to your kind notice that the progress of work continues to suffer the ramifications of presence of Encroachments & Encumbrances in the ROW. Please refer to your letter ref (2) above wherein it was intimated that ROW to the tune of 90.44% was available for execution, enclosing Schedule-A of the Agreement. However, when we subsequently visited the Site we had encountered numerous encroachments & encumbrances and thus realized the fact that the available ROW was far less than 90.44%. Hence, we have submitted an Appendix containing the encroachments & encumbrances, vide letter ref (3) above for your joint verification and signing. The same was also communicated in our Extension of Time (EOT) letters ref (8) & (13) above. Further, through various letters referred above, we have intimated to the Authority & Authority Engineer as and when we had faced obstructions to the progress of work due to encroachments & encumbrances. We are once again enlisting below the locations which are not comprehensive, where we are unable to progress with the works even today along with the reasons. We appreciate your cooperation in this regard. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Under utilisation / idling of resources | Payments, EoT, Dispute Resolution | As intimated earlier, we have been facing financial losses due to idling of resources and simultaneously incurring fixed and renewing costs. | synthetic_template_20250913 | Intention to issue Cure Period Notice to the Authority under clause 23.2.1 for temporary demobilization | This is regarding non-availability of encroachment and encumbrance free Right of Way (ROW) along the project highway, regarding which we wish to mention the following: 1. Subsequent to the signing of EPC Agreement dated 18.04.2017 the Appointed Date was fixed on 02.06.2017 and was communicated through Authority's letter no. 1190. It was mentioned in the letter that requirements under Clause 8.2 and obligations under 4.1.3(a), Annex II of Schedule-A are fulfilled by the Authority. 2. However, when we actually mobilised to site, we realised that the Obligations are not fulfilled by the Authority, in terms of the provisions relating to ROW and Appointed Date cited above. We noticed that there is no clarity even on the existing ROW widths. 3. We had submitted the Memorandum / Appendix through our letter no. 71 dated 10th Aug 2017, which indicates that the vacant access and ROW have not been granted at certain locations. Despite several requests, joint site inspection was not done and till date duly countersigned copy of the Memorandum / Appendix prepared by us is not returned till to date. 4. We have been reporting the lack of ROW through our Monthly Progress Reports every month, in addition among various letters on the subject. It is pertinent to mention that even as on date, not a single kilometre/ hectare of additional land has been acquired by the Authority under this project. However, we had convinced the local public and could get some progress in the project due to our efforts. 5. The dispute regarding land acquisition still continues among landowners, Authority and Revenue Authority (CALA). 6. There are realignments in the project for a length of 5.350 Kms, the land acquisition of which is not yet taken up where in there are no ROW boundaries and which area can be acquired directly. Two minor bridges are held up in the realignments. 7. As mentioned in Authority’s and AE's EOT recommendations, Gazette notification for land acquisition was issued on 31st December 2018, after a lapse of 18 months from appointed date. 8. It is also mentioned in your letter no. 78 dated 02.03.2019, that the EOT duration determined was subject to the condition that the ROW for the affected reaches will be handed over to the Contractor by 31.03.2019 and all the hindrances/obstructions will also be removed by 31.03.2019. 9. However, even till date, no further land has been handed over by the Authority we regret to maintain that even the existing ROW width is disputed between land owners concerned Authority. In addition the Acquisition was to be mobilized: the area of ACQUISITION FOR DIFFERENT Land owners is a single survey numbers. Some of them in this case having different survey numbers. 10. As intimated earlier, we have been facing financial losses due to idling of resources and simultaneously incurring fixed and renewing costs. In view of the above, we intend to issue a Notice to the Authority under clause 23.2.1 of the Contract to cure their material default in handing over of ROW which has a huge material adverse effect on our works. We once again request you to pursue with the Authority in expediting handing over of the balance ROW as soon as possible. Due to the above breach of the obligations by the Authority in terms of land handing over, a situation has arisen wherein we have no option other than temporarily demobilizing from site, to avoid further financial loss to us. We shall remobilize upon intimation from you / Authority regarding the availability of balance ROW. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Under utilisation / idling of resources | Payments, EoT, Dispute Resolution | We have sufficient resources but they are not gainfully deployed so far. Please refer our letter RCM PVR JV/MH PWD/2018-19/406 date 04th January 2019 on availability of work front & land acquisition status also. The reasons stated above, has led to erosion of revolving capital. we will summaries the losses & submit the comprehensive report, when 90% land is made available, | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/9. Un-gainful Deployement of Resources 28.01.2019.pdf | Rehabilitation and Up-gradation of Paithan (Pategaon) — Mungi - Hadgaon - Bodhegaon- Ladjalgaon ~ Ghogaspargaon ~ Phulsangvi - Ukhandachakla ~ Dahiwandi — Shirur to 2-Lane with paved shoulder (Project Length 55.937 Km) on EPC basis in the state of Maharashtra (Package I - 56 KM) - Un-gainful Deployment of Resources - Reg. | Please refer our revised programme submitted in vide letter no RCM PVR JV/MH PWD/2018-19/235 dated 02 May 2018 which revised & resubmitted recently vide letter no RCM PVR JV/MH PWD/2018-19/402/A dated 29 December 2018. As you are aware, the stretches we programmed to work are not available even today due to non acquisition of land. Further the area/work fronts which were made available by property owners at our request, was also withdrawn by them, since the compensation was not paid in time. Kindly refer our application for revision of milestone dates RCM PVR JV/MH PWD/2018-19/374 dated 17 November 2018 which details elaborately the reasons under relevant clauses of contract agreement. We have sufficient resources but they are not gainfully deployed so far. Please refer our letter RCM PVR JV/MH PWD/2018-19/406 date 04 January 2019 on availability of work front & land acquisition status also. The reasons stated above, has led to erosion of revolving capital. We will summarise the losses & submit the Comprehensive report, when 90% land is made available. | FALSE | real_data
Mobilisation of additional resources | Payments, Dispute Resolution | This is with reference to your *ester ref (1 J above, regarding slow progress of work. wherein you have instructed us to mobilise additional resources in order to complete the works within the stipulated time | synthetic_template_20250913 | Regarding Slow progress of Work | We hereby confirm that This is with reference to your letter ref (1) above, regarding slow progress of work, wherein you have instructed us to mobilise additional resources in order to complete the works within the stipulated time. We invite your kind attention to our letter ref (3) above; we have clearly mentioned that works in 34.35 Km of the project are held up due to pending COS orders/decisions. Further, we have also mentioned that works are also hampered due to Land Acquisition (LA) problems at various stretches. From the above, it is clear that pending COS orders/decisions & LA problems are the reasons for slow progress of works. Even our existing resources are being subjected to unfruitful deployment, due to lack of work fronts, as already intimated in our letter ref (2) above. At this juncture, mobilising additional resources will only add to the huge financial loss already incurred by us. In view of the above, we request you to pursue the Authority on issuing COS orders and handing over balance ROW, free of encroachments and encumbrances. We look forward to your response. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Intimation of Occurrence of Force majeure Events | EoT, Dispute Resolution | The EPC Contractor notified the out break of Pandemic Covid 19 as Force Majeure event vide ref (3) above as per Article 21 of the Contract Agreement. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20210419_SPK _AE_069_EOT under Atmanirbhar Bharat Relief.pdf | Contractor’s Entitlement to Extension of Time (EOT) due to COVID Pandemic - Force Majeure Event-EOT application for interim extension of time of 270 days under Atmanirbhar Bharat Relief - reg | Your kind attention is invited to the references cited above which in brief are as below: 1. The EPC Contractor notified the outbreak of Pandemic Covid 19 as Force Majeure Event vide ref (3) above as per Article 21 of the Contract Agreement. 2. The restrictions imposed through various Orders / Circulars / Communications / Guidelines by various Government instrumentalities had severe impact on the scheduled progress. 3. We are enlisting below the major implications and direct effects due to outbreak of Pandemic COVID - 19 on the Project below for your ready reference: a. Scarcity of workers and labourers and persistent fear of contracting COVID — 19 is reducing their general productivity. b. Those working at Site are performing under restrictive conditions with additional protections and safety, which are affecting the productivity of our manpower. c. Exodus of skilled works and huge problem in getting the skilled and unskilled labour. d. Non-availability of technicians / Engineers required for undertaking periodic and time bound maintenance of various plant and machineries e. Maintaining social distancing and other norms ordered by the Governments have impacted the productivity of existing labour at site. f. Due to the closure of factories / manufacturing units on account of lock down and constraints in transportation, procurement of various of critical raw materials & supplies required for various critical construction activities etc.is seriously affected. g. Procurement of materials for shifting of utilities are also delayed as the manufactures are unable to supply ordered quantities. 4. Some of the examples of the execution of works that were delayed due to COVID-19 and nationwide lockdown/unlocking in phased manner are listed below: a. During the process of unlocking to boost up the economy. Government has awarded several projects simultaneously. Because of this, the demand for all major construction material has shot up and _ outpaced _ the production /manufacturing capacity. The primary manufactures of cement and steel are not able to meet the supply required for the Project. b. Due to continued restrictions on public transportation and fear of pandemic, labour scarcity persists. | FALSE | real_data
Intimation of Occurrence of Force majeure Events | EoT, Dispute Resolution | Vide ref (22) above the EPC Contractor notified the out break of second wave of COVID 19 as Force Majeure Event pursuant to Article 21 of the Contract Agreement. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20210706_SPK_NHAI_ 046_Update on Force Majeure Event.pdf | Six laning of Karaipettai to Walajahpet Section of NH-4 (New NH-48) - Regarding spread of Second wave of “Covid 19”- Government restrictions and its effect on the Project -Update on Force Majeure Event - Lockdown extended till 12/07/2021 with further relaxations - Reg. | Vide ref (22) above the EPC Contractor notified the outbreak of Second wave of COVID-19 as Force Majeure Event pursuant to Article-21 of the Contract Agreement. The second wave of COVID-19 Pandemic in the country is more severe than the first wave of the Pandemic. The total active cases in the country as on 05/07/2021 is 4,82,071 and in last 24 hours fresh cases reported are 39,796. The second wave of the COVID-19 Pandemic is very severe which once again compelled the Government instrumentalities to impose strict restrictions to contain the spread of the second wave. | FALSE | real_data
Intimation of Occurrence of Force majeure Events | EoT, Dispute Resolution | We place on record that this is a strange phenomena not foreseen at the time of bidding and has resulted in additional cost to us. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-4/11. Acute shortage of water 23.02.2019.pdf | Rehabilitation and Up-gradation of Paithan (Pategaon) - Mungi - Hadgaoen - Bodhegaon- Ladjalgaon — Ghogaspargaon ~ Phulsangvi ~ Ukhandachakla - Dahiwandi - Shirur to 2-Lane with paved shoulder (Project Length 55.937 Km) on EPC basis in the state of Maharashtra (Package ¦ - 56 KM) - Acute shortage of water-Reg. | The execution of road works, particularly concrete roads needs huge quantity of water before, during and after concreting. Further, in earth work, road maintenance, washing plant etc also the consumption is high. The ground water table had gone down in the last year itself due to poor rainfall. This year the total failure of monsoon in where we are working, has further lowered the water table. Almost all the open wells and bore wells have dried up between km 20 & 56. There is acute shortage of drinking water. This part of Maharashtra is drought area now. We submit to state that under these circumstances, we are executing the works by purchasing water from various sources far away, distancing between 50km to 65 km, since November 2018. We place on record that this is a strange phenomena not foreseen at the time of bidding and has resulted in additional cost to us. The details / costing is being summarized, for submission later. | FALSE | real_data
Additional cost / compensation | Payments, Dispute Resolution | We place on record that this is a strange phenomena not foreseen at the time of bidding and has resulted in additional cost to us. The details / costing is being summarized, for submission later. | synthetic_template_20250913 | Rehabilitation and Up-gradation of Paithan (Pategaon) - Mungi - Hadgaoen - Bodhegaon- Ladjalgaon — Ghogaspargaon ~ Phulsangvi ~ Ukhandachakla - Dahiwandi - Shirur to 2-Lane with paved shoulder (Project Length 55.937 Km) on EPC basis in the state of Maharashtra (Package ¦ - 56 KM) - Acute shortage of water-Reg. | The execution of road works, particularly concrete roads needs huge quantity of water before, during and after concreting. Further, in earth work, road maintenance, washing plant etc also the consumption is high. The ground water table had gone down in the last year itself due to poor rainfall. This year the total failure of monsoon in where we are working, has further lowered the water table. Almost all the open wells and bore wells have dried up between km 20 & 56. There is acute shortage of drinking water. This part of Maharashtra is drought area now. We submit to state that under these circumstances, we are executing the works by purchasing water from various sources far away, distancing between 50km to 65 km, since November 2018. We place on record that this is a strange phenomena not foreseen at the time of bidding and has resulted in additional cost to us. The details / costing is being summarized, for submission later. Thank you for your attention to this matter. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Payment of Royalty/Seignoirage charges for use of Minor Minerals | Contractor's Obligations, Payments | So please release the deducted amount of royalty fee in our bill (IPC -5) | synthetic_template_20250913 | Rehabilitation and Up-gradation of Paithan (Pategaon) - Mungi - Hadgaon - Bodhegaon- Ladjalgaon — Ghogaspargaon — Phulsangvi - Ukhandachakla — Dahiwandi - Shirur to 2-Lane with paved shoulder (Project Length 55.937 Km) on EPC basis in the state of Maharashtra (Package ¦ — 56 KM) — Release of Royalty money -Reg | With respect to above subject we submitting attachment of Royalty deduct from our interim payment certificate (IPC-05), but still now it is not credited in concerned taluka they asking us several time regarding the royalty amount. So please release the deducted amount of royalty fee in our bill (IPC -5). | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Cure period Notice | Payments, Dispute Resolution | Intend to issue a Notice to the Authority under Clause 23.2.1 of the Contract to cure their material default | synthetic_template_20250913 | Intention to issue Cure Period Notice to the Authority under clause 23.2.1 for temporary demobilization | This is regarding non-availability of encroachment and encumbrance free Right of Way (ROW) along the project highway, regarding which we wish to mention the following: 1. Subsequent to the signing of EPC Agreement dated 18.04.2017 the Appointed Date was fixed on 02.06.2017 and was communicated through Authority's letter no. 1190. It was mentioned in the letter that requirements under Clause 8.2 and obligations under 4.1.3(a), Annex II of Schedule-A are fulfilled by the Authority. 2. However, when we actually mobilised to site, we realised that the Obligations are not fulfilled by the Authority, in terms of the provisions relating to ROW and Appointed Date cited above. We noticed that there is no clarity even on the existing ROW widths. 3. We had submitted the Memorandum / Appendix through our letter no. 71 dated 10th Aug 2017, which indicates that the vacant access and ROW have not been granted at certain locations. Despite several requests, joint site inspection was not done and till date duly countersigned copy of the Memorandum / Appendix prepared by us is not returned till to date. 4. We have been reporting the lack of ROW through our Monthly Progress Reports every month, in addition among various letters on the subject. It is pertinent to mention that even as on date, not a single kilometre/ hectare of additional land has been acquired by the Authority under this project. However, we had convinced the local public and could get some progress in the project due to our efforts. 5. The dispute regarding land acquisition still continues among landowners, Authority and Revenue Authority (CALA). 6. There are realignments in the project for a length of 5.350 Kms, the land acquisition of which is not yet taken up where in there are no ROW boundaries and which area can be acquired directly. Two minor bridges are held up in the realignments. 7. As mentioned in Authority’s and AE's EOT recommendations, Gazette notification for land acquisition was issued on 31st December 2018, after a lapse of 18 months from appointed date. 8. It is also mentioned in your letter no. 78 dated 02.03.2019, that the EOT duration determined was subject to the condition that the ROW for the affected reaches will be handed over to the Contractor by 31.03.2019 and all the hindrances/obstructions will also be removed by 31.03.2019. 9. However, even till date, no further land has been handed over by the Authority we regret to maintain that even the existing ROW width is disputed between land owners concerned Authority. In addition the Acquisition was to be mobilized: the area of ACQUISITION FOR DIFFERENT Land owners is a single survey numbers. Some of them in this case having different survey numbers. 10. As intimated earlier, we have been facing financial losses due to idling of resources and simultaneously incurring fixed and renewing costs. In view of the above, we intend to issue a Notice to the Authority under clause 23.2.1 of the Contract to cure their material default in handing over of ROW which has a huge material adverse effect on our works. We once again request you to pursue with the Authority in expediting handing over of the balance ROW as soon as possible. Due to the above breach of the obligations by the Authority in terms of land handing over, a situation has arisen wherein we have no option other than temporarily demobilizing from site, to avoid further financial loss to us. We shall remobilize upon intimation from you / Authority regarding the availability of balance ROW. We appreciate your cooperation in this regard. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Demobilisation and Remobilisation | EoT, Payments, Dispute Resolution | losses, the cost of demobilizing and remobilizing would also be attributable to the Authority and will be submitted at an appropriate time. | synthetic_template_20250913 | Intention to issue Cure Period Notice to the Authority under clause 23.2.1 for temporary demobilization | This is regarding non-availability of encroachment and encumbrance free Right of Way (ROW) along the project highway, regarding which we wish to mention the following: 1. Subsequent to the signing of EPC Agreement dated 18.04.2017 the Appointed Date was fixed on 02.06.2017 and was communicated through Authority's letter no. 1190. It was mentioned in the letter that requirements under Clause 8.2 and obligations under 4.1.3(a), Annex II of Schedule-A are fulfilled by the Authority. 2. However, when we actually mobilised to site, we realised that the Obligations are not fulfilled by the Authority, in terms of the provisions relating to ROW and Appointed Date cited above. We noticed that there is no clarity even on the existing ROW widths. 3. We had submitted the Memorandum / Appendix through our letter no. 71 dated 10th Aug 2017, which indicates that the vacant access and ROW have not been granted at certain locations. Despite several requests, joint site inspection was not done and till date duly countersigned copy of the Memorandum / Appendix prepared by us is not returned till to date. 4. We have been reporting the lack of ROW through our Monthly Progress Reports every month, in addition among various letters on the subject. It is pertinent to mention that even as on date, not a single kilometre/ hectare of additional land has been acquired by the Authority under this project. However, we had convinced the local public and could get some progress in the project due to our efforts. 5. The dispute regarding land acquisition still continues among landowners, Authority and Revenue Authority (CALA). 6. There are realignments in the project for a length of 5.350 Kms, the land acquisition of which is not yet taken up where in there are no ROW boundaries and which area can be acquired directly. Two minor bridges are held up in the realignments. 7. As mentioned in Authority’s and AE's EOT recommendations, Gazette notification for land acquisition was issued on 31st December 2018, after a lapse of 18 months from appointed date. 8. It is also mentioned in your letter no. 78 dated 02.03.2019, that the EOT duration determined was subject to the condition that the ROW for the affected reaches will be handed over to the Contractor by 31.03.2019 and all the hindrances/obstructions will also be removed by 31.03.2019. 9. However, even till date, no further land has been handed over by the Authority we regret to maintain that even the existing ROW width is disputed between land owners concerned Authority. In addition the Acquisition was to be mobilized: the area of ACQUISITION FOR DIFFERENT Land owners is a single survey numbers. Some of them in this case having different survey numbers. 10. As intimated earlier, we have been facing financial losses due to idling of resources and simultaneously incurring fixed and renewing costs. In view of the above, we intend to issue a Notice to the Authority under clause 23.2.1 of the Contract to cure their material default in handing over of ROW which has a huge material adverse effect on our works. We once again request you to pursue with the Authority in expediting handing over of the balance ROW as soon as possible. Due to the above breach of the obligations by the Authority in terms of land handing over, a situation has arisen wherein we have no option other than temporarily demobilizing from site, to avoid further financial loss to us. We shall remobilize upon intimation from you / Authority regarding the availability of balance ROW. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Request for revisit of EOT determined/approved | EoT, Dispute Resolution | We hereby request the Authority Engineer to revisit the EOT/Rescheduling of Milestones already recommended in light of the justifications cited above. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20200129_SPK_AE_001_Reply on Rescheduling of Project Milestone - Request for EoT.pdf | Reply on Rescheduling of Project Milestones — Request for Extension of Time - Reg. | The Authority Engineer vide ref (3) cited above communicated his recommendation on the above captioned subject. The EPC Contractor would like to submit his observations which are as follows: 1. The EPC Contractor vide his letter No. 49 / SPK / Kar - Wal / PD / NHAI dated 17.06.2019 requested the Authority to consider the ROW handed over in terms of length (as per Cl. 4.1.3 and not in terms of area and shift the Appointed Date based on the actual date of removal of encumbrance / encroachment / obstruction for which response is still awaited from the Authority. Further, it is worth mentioning that the AE also reiterated our stand wherein it was mentioned in Authority Engineer recommendation that “It is also worth mentioning that this memorandum was signed based on the % of area of the project ROW, in place of % of length, as mentioned in the Clause 4.1.3 (a).” 2. The assessment of hindrance length by the EPC contractor is correct as irrespective of hindrance available on one side, the same has to be considered for entire six laning width. In this regard it is hereby requested that the definition of ROW as per Article 28 shall be referred for further clarity. Further a working strip of at least 3 m wide shall be available parallel from the toe of the embankment pursuant to Clause 8.3.1 of the Contract Agreement. Authority Engineer has not based on this provision. 3. We totally deny with the observation of the Authority Engineer in not considering delay in handing over of land by the Authority pursuant to 4.1.3 (a) and 8.3.2 of the Contract Agreement. It is worth mentioning that even as on date 90% of encumbrance free land is yet to be handed over which is against the provisions of the Contract Agreement as 90% of land should have been handed over within 30 days of the execution of the agreement as per 4.1.3 (a) i.e on or before 15/11 / 2019. The joint inspection done on 24.10.2019 and on which the Authority Engineer’s representative signed would prove that only 62.51% of length was available on that day. Even today the Authority Engineer may carry out a joint inspection and will find that hardly 70% of the length is available for work front if imparted length is considered. 4. The EPC Contractor is obligated to comply only with the provisions of the Contract Agreement and not bound by any internal circular of the Authority as mentioned in AE recommendation. Hence, we disagree with the contention of the Authority Engineer that the EPC Contractor is not entitled for EOT in light of the circular issued by the Authority dated 16.08.2019. 5. It has been explicitly mentioned in Authority Engineer’s recommendation that shifting of utilities was being taken care by the Authority. Further the Contract Agreement between the Authority and Utility shifting agency was executed only on 19.07.2019. It is evident that shifting of utilities was not taken up till 19.07.2019, i.e 158 days from the declaration of Appointed Date by the Authority. Since the Authority is taking care of utility shifting and the agency appointed by the Authority commenced the works only after 180 days of the Appointed Date, period of 180 days mentioned in Clause 9.2is has no relevance. Hence, we deny with the contention of the Authority Engineer that the Contractor is entitled for time extension only beyond 180 days. The project duration is only 24 months and first 6 months are very crucial for the EPC contractor to progress the works based on his targeted programme. The Authority Engineer is also reiterating our concern wherein it has been mentioned that, ’The shifting of Utilities is important for this project, as the project is a Toll road and considering this, the Contractor submitted Construction Methodology, stating that first service road is to be constructed and after diverting the traffic over there, Main carriageway would be constructed ” . Utility shifting work is also not progressing as the encumbrances have not been removed and space is not made available for relocating the utility. 6. We would like to submit that as per Cl. 6 of Schedule-J , the Extension of Time recommendation is for Scheduled Project Completion Date and not confined to Milestone I. Based on the EOT recommended, all the milestones get automatically rescheduled accordingly. Hence, we do not agree with the contention of the Authority Engineer that the Extension of Time for Project. | FALSE | real_data
Joint inspection | Appointed Date, Contractor's Obligations, Authority's Obligations | It was also emphasized that during the Joint inspection along with the representatives of Authority's Engineer from 14.10.2019 to 24.10.2019, only 62.52% of length of project highway was available and the same was also acknowledged by Authority Engineer (refer EPC Contractor letter vide ref (7) cited above). | synthetic_template_20250913 | Six laning of Karaipcttai to Walajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - Contractor’s failure in achieving Project Mile Stone 1,2 & 3 applying of Damages vide Contract Article No. 10.3.2 & 10.3.3 - Reply made -Reg. | We are in receipt of your letter ref (26) cited above, our reply for the same is as follows: 1. The Contract Agreement for this Project was executed on 15.10.2018. The Appointed Date was fixed as 11.02.2019 and the same was communicated vide ref (2) cited above. 2. The Appointed date was declared as 11.02.2019 by the Authority taking into account the land handed over in terms of the available area without taking into consideration, the requirement of the Contract provision as per Clause 4.1.3 (a) of the EPC agreement which talks about the handing over of land only in terms of length of the Project Highway. The memorandum and appendix prepared in terms of area gave a deceptive / false picture about the availability of vacant access. Taking into consideration all the encumbrances, hindrances, utilities etc. the vacant access available on the appointed date declared was worked out and it was less than 90% and hence requested the Authority vide letter under ref (3) cited above for modification of the appointed date on which 90% of encumbrance free land would be made available to the Contractor. 3. The Authority in its response vide ref (4) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. 4. The EPC contractor vide ref (5) cited above in reply reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that the impacted length due to encroachments and encumbrances was 12.18 km which accounted to 33.77% of the project length. The workable length available to the contractor was only 66.23% of the project length. The EPC contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of encumbrance / encroachment / obstruction. We appreciate your cooperation in this regard. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Joint inspection | Appointed Date, Contractor's Obligations, Authority's Obligations | It was also emphasized that during the Joint inspection along with the representatives of Authority's Engineer from 14.10.2019 to 24.10.2019, only 62.52% of length of project highway was available and the same was also acknowledged by Authority Engineer (refer EPC Contractor letter vide ref (7) cited above). | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20201119_SPK_AE_160_Contractor failure in achieving mile stone 1,2,&3.pdf | Six laning of Karaipcttai to Walajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V - Contractor’s failure in achieving Project Mile Stone 1,2 & 3 applying of Damages vide Contract Article No. 10.3.2 & 10.3.3 - Reply made -Reg. | We are in receipt of your letter ref (26) cited above, our reply for the same is as follows: 1. The Contract Agreement for this Project was executed on 15.10.2018. The Appointed Date was fixed as 11.02.2019 and the same was communicated vide ref (2) cited above. 2. The Appointed date was declared as 11.02.2019 by the Authority taking into account the land handed over in terms of the available area without taking into consideration, the requirement of the Contract provision as per Clause 4.1.3 (a) of the EPC agreement which talks about the handing over of land only in terms of length of the Project Highway. The memorandum and appendix prepared in terms of area gave a deceptive / false picture about the availability of vacant access. Taking into consideration all the encumbrances, hindrances, utilities etc. the vacant access available on the appointed date declared was worked out and it was less than 90% and hence requested the Authority vide letter under ref (3) cited above for modification of the appointed date on which 90% of encumbrance free land would be made available to the Contractor. 3. The Authority in its response vide ref (4) cited above justified its assessment of availability of vacant access and did not consider the request to modify the appointed date. 4. The EPC contractor vide ref (5) cited above in reply reiterated that the ROW handed over was not free from all encroachments and encumbrances and also pointed out that the impacted length due to encroachments and encumbrances was 12.18 km which accounted to 33.77% of the project length. The workable length available to the contractor was only 66.23% of the project length. The EPC contractor once again requested the Authority to consider the ROW handed over in terms of length and not in terms of area and shift the appointed date based on the actual date of encumbrance / encroachment / obstruction. | FALSE | real_data
Demands by local villagers for additional structures/service road/utility ducts | Change of Scope, EoT, Dispute Resolution, Payments | This is to bring to your kind notice that the construction of drain works has been stopped from Km 106+190 to Km 106+650 (RHS) by the local people from Thenkadapanthangal village (photographs enclosed) for want of increase in size of drain width to 3.0 m in lieu of 1.5m. We kindly request you to take up this issue with the District Administration and provide necessary support in resolving the issue as per Clause 4.1.6 (e) of the Contract Agreement. | synthetic_template_20250913 | Disruption of works by local people of Thenkadapanthangal Village for demand in “Increase in Drain width to 3.0m instead of 1.5m as per CA”— Works hampered from Km.106+190 to Km 106+650 (RHS) - Reg. | 1. This is to bring to your kind notice that the construction of drain works has been stopped from Km.106+190 to Km.106+650(RHS) by the local people from Thenkadapanthangal village (Photographs enclosed) for want of increase in size of drain width to 3.0m in lieu of 1.5m. The locals also informed that they will permit construction works only if the width of drain is increased to 3.0 m for the above mentioned length of 460m. 2. The reason stated by the villagers is that the adjacent water course coming from nearby source that flows across Minor Bridge at Km.106+677, will overflow towards the village side and that overflowing water should be allowed to flow in the drain otherwise the water will enter into their houses. 3. This is for information that already a length of 160m of storm water drain with width of 2.5m in lieu of 1.5m from Km.98+214 to Km.98+374 (160m) on LHS for diversion of the storm water into the PWD canal has been constructed for which the additional amount incurred up to Rs.28,49,564/- by the EPC Contractor is still pending for reimbursement with the Authority (Refer our letter No. SPK/KW/SAIC/NH-48/2022/185 dated 19.12.2022) 4. We kindly request you to take up this issue with the District Administration and provide necessary support in resolving the issue as per Clause 4.1.6 (e) of the Contract Agreement. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Progress Review | EoT, Payments, Others | Hon'ble MoS (RT&H) will be holding physiccal inspection of the works at NH 4 from Maduravoyal to Wallajahpet stretch | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210121_PD_SPK_260_Inspection of union minister of State.pdf | Visit of General (Dr.) V.K.Singh(Retd.) Hon’ble Union Minister of State for Road Transport and Highways to Chennai and Vellore on 24th and 25th January, 2021 - Inspection of Maduravoyal to Walajahpet stretch of NH-4 by Hon’ble MoS(RT&H) -Reg. | It is to inform that, General(Dr.) V.K.Singh (Retd.), Hon’ble Union Minister of State for Road Transport and Highways has proposed to travel from Chennai to Vellore via NH-4. During the above travel Hon’ble MoS(RT&H) will be holding physical inspection of the works at NH-4 from Maduravoyal to Walajahpet stretch. In view of the above, it is requested to make necessary arrangements for the inspection of the Hon’ble MoS(RT&H) including the presentation on the projects under implementation at site. Further, it is requested to ensure that necessary safety measures and proper barricading of all work zones shall be ensured as per relevant IRC & MoRTH specifications. The road stretch shall be maintained free of Garbage, Plastics and litter. The top management of the Consultant and Contractor shall be appraised of the site visit of Hon’ble MoS(RT&H), and they may be present at site during the inspection. | FALSE | real_data
Progress Review | EoT, Payments, Others | Please find enclosed herewith the minutes of meeting numbered as MOM-08 held on 21.11.2020 | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20201123_AE_SPK_480_Minutes of Monthly Progress review meeting Mom – 08.pdf | Consultancy services for Authority's Engineer for Supervision of Six Lanning of Karaipettai to Walajhapet from km 71.015 to107.91 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode - Minutes of Monthly Progress review meeting Mom — 08 — Reg. | With respect to the above said reference please find enclosed herewith the Minutes of Meeting Numbered as MoM - 08 held on 21.11.2020 The next meeting will be likely on 23.12.2020 at the Consultants office around 11.00 A.M in Kancheepuram. All the concerned are requested to attend with necessary documents. This is for your information and record. Assuring our best services at all times. | FALSE | real_data
Delay due to Change of Scope works | EoT, Payments, Dispute Resolution, Change of Scope | The EPC Contractor has substantially completed majority of the road works at grade sections where unencumbered land has been provided by the Authority and presently finding it difficult to open up further stretches due to a) non availability of unencumbered land, b) temporary suspension of works due to COS proposals warranted by the Authority pursuant to sub clause 13.1.1 of the Contract Agreement. | synthetic_template_20250913 | Six laning of Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km. 71+015 (Existing km 71+000 to km 107+091 (Existing km 107+068) on EPC mode in the state of Tamil Nadu under NHDP Phase-V -EOT recommendation by the Authority for a period of 112 days not agreeable to the EPC Contractor — Request for considering EOT as discussed during the Review Meetings- reg | We hereby confirm that We are writing to express our concerns regarding the EOT recommendation by the Authority for a period of 112 days, which is not agreeable to the EPC Contractor. We request that the EOT be considered as discussed during the Review Meetings. The project involves six laning of the Karaipettai to Wallajahpet Section of NH-4 (New NH-48) from km 71+015 to km 107+091 on EPC mode in the state of Tamil Nadu under NHDP Phase-V. We have referenced several documents and meetings in support of our request, and we hope for a favorable consideration. We await your further instructions. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Delay due to Change of Scope works | EoT, Payments, Dispute Resolution, Change of Scope | The EPC Contractor has substantially completed majority of the road works at grade sections where unencumbered land has been provided by the Authority and presently finding it difficult to open up further stretches due to non availability of unencumbered land, temporary suspension of works due to COS proposals warranted by the Authority pursuant to clause 13.1.1 of the Contract Agreement. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20200713_SPK_RO_42_Reminder - Request for revisiting the EOT already recommended - Rev2.pdf | Extension of Time and Rescheduling of Project Milestones - EOT granted for 112 days not acceptable to the EPC contractor - Request for revisiting the EOT recommended - Reminder sent - Reg. | 1. This is with respect to the Extension of Time(EOT} approved by the Authority for. a period of 112 days for Project Milestone-I without effecting changes in Scheduled Project Completion Period vide ref (3) cited above.The EPC Contrator disagrees and does not accept the grant of EOT approval for 112 days, the reasons for disgreeement of this approval are elaborated in our submission to the Authority Engineer vide ref (4) cited above. 2. The EPC contractor requested the Authority/NHAI to revisit the EOT determined/approved and communicate 324 days as interim Extension of time vide ref (5) cited above but, we are yet to receive response in this regard. Copy of the same is herewith enclosed as Annexure 1. 3. The Authority is yet to fulfil the obligations relating to handing over of ROW as per Sub Clause 8.2 of the Contract Agreement. Copy of the newspaper publication regarding LA status / notification for acquiring land for the Project Highway (Kanchipuram District} is herewith enclosed as Annexure 2. By not fulfilling the obligations as per the provisions of the Contract Agreement, the Authority committed a material default pursuant to Sub clause 23.2.1 (a) of the Contract Agreement. 4. The electrical pole/Transformer shifting is yet to be completed by the Authority even as on date and following are the Chainages whether shifting is required to be carried out: No.of Transformers In addition to the above, following locations listed below where shifting of High Tension(HT) Towerlines are required to be carried out: No. of HT Towers Status All Material mobilized at site. Due to Lockdown Estimate Approved on 22.02.2020. Electrical Contractor engaged by EPC Contractor on 20.03.2020 for shifting works. Due to Lockdown work yet to be taken-up. Estimate yet to be approved. Estimate yet to be approved. | FALSE | real_data
Release of Retention Money | Payments | It is pertinent to mention that the AE after observing the substantial progress made by the EPC Contractor at site has recommended the release of Retention Money vide his Lr. No. 356 dated 09.07.2020 and copy of the same is herewith enclosed as Annexure 4. | synthetic_template_20250913 | Extension of Time and Rescheduling of Project Milestones - EOT granted for 112 days not acceptable to the EPC contractor - Request for revisiting the EOT recommended - Reminder sent - Reg. | 1. This is with respect to the Extension of Time(EOT} approved by the Authority for. a period of 112 days for Project Milestone-I without effecting changes in Scheduled Project Completion Period vide ref (3) cited above.The EPC Contrator disagrees and does not accept the grant of EOT approval for 112 days, the reasons for disgreeement of this approval are elaborated in our submission to the Authority Engineer vide ref (4) cited above. 2. The EPC contractor requested the Authority/NHAI to revisit the EOT determined/approved and communicate 324 days as interim Extension of time vide ref (5) cited above but, we are yet to receive response in this regard. Copy of the same is herewith enclosed as Annexure 1. 3. The Authority is yet to fulfil the obligations relating to handing over of ROW as per Sub Clause 8.2 of the Contract Agreement. Copy of the newspaper publication regarding LA status / notification for acquiring land for the Project Highway (Kanchipuram District} is herewith enclosed as Annexure 2. By not fulfilling the obligations as per the provisions of the Contract Agreement, the Authority committed a material default pursuant to Sub clause 23.2.1 (a) of the Contract Agreement. 4. The electrical pole/Transformer shifting is yet to be completed by the Authority even as on date and following are the Chainages whether shifting is required to be carried out: No.of Transformers In addition to the above, following locations listed below where shifting of High Tension(HT) Towerlines are required to be carried out: No. of HT Towers Status All Material mobilized at site. Due to Lockdown Estimate Approved on 22.02.2020. Electrical Contractor engaged by EPC Contractor on 20.03.2020 for shifting works. Due to Lockdown work yet to be taken-up. Estimate yet to be approved. Estimate yet to be approved. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
occurrence of cyclones | EoT | With reference to the above subject, we wish to bring your notice that, due to occurrence of "NIVAR & BUREVI Cyclone" there has been a heavy/continuous rain in Kanchipuram & Ranipet Districts. | synthetic_template_20250913 | Intimation of Stagnation of Water in Identified Borrow Areas — Reg. | With reference to the above subject; we wish to bring your notice that, due to occurrence of “NIVAR & BUREVI Cyclone” there has been a heavy/continuous rain in Kanchipuram & Ranipet Districts. The entire works of the Project Highway have come to standstill owing to non-operation of Borrow area due to unexpected heavy downpour. Since, there has been a complete waterlogging in all the identified Borrow areas of Kanchipuram & Ranipet District, it is not possible to operate the Borrow Areas for a minimum period of 3 months. RE wall back filling for approaches of 3.Nos. of LVUP’s are hampered due to ponding of borrow areas. RE Panels are even stacked at site for commencement of back filling works. Photos showing the stagnation of water in the identified borrow areas of Kanchipuram & Ranipet Districts is enclosed as Annexure - I. This is for your kind information & record, please. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
occurrence of cyclones | EoT | Now due to the recent cyclones such as NIVAR & BUREVI, the district had experienced heavy and copious rains and all the above identified borrow locations have been completely filled up with the water. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-8/20210120_005_SPK_RO_Delay in obtaining permission for Borrow area.pdf | Delay in Obtaining Permission of Borrow Earth - Ranipet District - Reg. | Dear Sir, This is with reference to the above said references (2) to (7); we wish to submit that, since from the Appointed Date we have been approaching the Ranipet District administration for obtaining necessary permission for extracting Borrow earth. Correspondences for the same is enclosed as ready reference. Application for extracting borrow earth from the identified Borrow area which were submitted to the district administration are as follows: S.No ¦ Chainage ¦ 1 ¦ 101+310 2 ¦ 101+310 Name of the tank Marutheri Lake Bagaveli Lake Sumaithangi Lake Kaveripakkam Lake However, we wish to inform that. we are awaiting for the necessary permission from the District Collector to date. Now due to the recent cyclones such as NIVAR & BUREVI, the district had experienced heavy and copious rains and all the above identified borrow locations have been completely filled up with water. In this connection, we wish to mention that; widening sections of project road (i.e, 20.77Km.) is in the verge of completion and only balance scope for earthwork is required for approaches of the elevated sections. Due to non-availability of Borrow earth, all Elevated sections (i.e, totalling 13.90Km.) of RE Wall/RE Fill works has come to standstill despite more than 70% of completion of casting of RE panel. Further, delay. in extraction of Borrow earth will lead to delay in achieving the target. In this regard, we kindly request your good-self to intervene and forward our difficulties in obtaining permission of Borrow Earth to the Chief Secretary -— Government of Tamil nadu to issue suitable instructions to the concerned officials to accord permission to extract earth in order to facilitate the EPC Contractor in early completion of Project. This is for your immediate 8& necessary action, please. | FALSE | real_data
Submission of additional information/clarifications on Extension of time proposal | EoT, Dispute Resolution | Entitlement of EOT for Milestone I, EOT for Milestone - I, Your claim for EOT | synthetic_template_20250913 | Entitlement of EoT for Milestone-!l - Supporting details -Reg | Please note that This is in reference to your letter cited 1 above regarding EoT of Milestone -I and subsequent discussion had with your representative on 17.08.2019. The submitted details are not substantiating your claim for EoT and found lacking of supporting particulars. So, you are requested to submit your reasoning specifically based on conditions of Contract Agreement. This is for your information and necessary action. We look forward to your response. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Submission of additional information/clarifications on Extension of time proposal | EoT, Dispute Resolution | Entitlement of EOT for Milestone I, EOT for Milestone - I, Your claim for EOT | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/079_20082019_Entitlement of EoT for Milestone-I – Supporting details.pdf | Entitlement of EoT for Milestone-!l - Supporting details -Reg | This is in reference to your letter cited 1 above regarding EoT of Milestone -I and subsequent discussion had with your representative on 17.08.2019. The submitted details are not substantiating your claim for EoT and found lacking of supporting particulars. So, you are requested to submit your reasoning specifically based on conditions of Contract Agreement. This is for your information and necessary action. | FALSE | real_data
Permission for extracting soil from minor irrigation tanks and ponds | Others | Executive Engineer, Irrigation Division No.7, Gajwel has requested to instruct the agency to submit the list of vehicles to be used for lifting of Canal spoil before starting the work. | synthetic_template_20250913 | Widening to 2 lanes with paved shoulders of Medak-Siddipet Section from km. 0.000 to 69.978 of NH-765DG in the State of Telangana under annual plan 2021-22 on EPC Basis Permission proposal for extracting canal spoil from Tail end Distributary of Package 13 at Km 18+000 near Bachurajpalli (V), Nizampet (M), Medak (Dist.) - Permission accorded for lifting of Canal spoil-Regarding. | We hereby confirm that Please find here with the copy of the reference 24 cited, which is self explanatory, wherein, the Executive Engineer, Irrigation Division No.7, Gajwel has accorded permission for lifting of 6000 Cum of spoil for the above work. While according permission, the Executive Engineer, Irrigation Division No.7, Gajwel has requested to instruct the agency to submit the list of vehicles to be used for lifting of Canal spoil before starting the work. Further requested to recover initial charges and seignorage charges and stated that if any damages occurred to the Canal during the lifting of spoil, the same would be restored before leaving the loading point as per the instructions of the Engineer concerned. The Executive Engineer has also informed that permission is valid for 10 days from the date of permission. That is upto 30.09.2023. In view of the above, it is requested take suitable safety measures to avoid any damages to the Canals as desired by Irrigation Department. You are requested to conduct test on the soil and ensure that results are satisfying as per the Contract Agreement before use of material. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Permission for extracting soil from minor irrigation tanks and ponds | Others | The Contractor has taken sincere effort for getting Permission for extraction of Borrow earth since from the Appointed Date. But, considering the Contract Clause No. 3.17 (a), which reproduced here, "The Contractor shall, at its own cost and expense, in addition to and not in derogation of its obligation elsewhere set out in this Agreement, (a) make, or cause to be made, necessary applications to the relevant Government Instrumentalities with such particulars and details as may be required for obtaining Applicable Permits set forth in Schedule F. " Therefore, on this ground, Contractor's request for EOT cannot be entertained. However, due to Aadhi Athi Varadhar festival which happens once in 40 years the same shall be considered for Entitlement of EoT. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/189_Rescheduling of Project Milestones - EOT - 1.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under BharatmalaPariyojana on EPC mode — Rescheduling of Project Mile Stone- Request for Extension of Time -Reg. | Having gone through your documents related to Rescheduling of Project Milestone-Request for Extension of Time EoT-1 please find enclosed herewith the Authority Engineers recommendations on the same subject. This is for your information and necessary action. | FALSE | real_data
Design & Drawings of Highways & Structures | Contractor's Obligations | Please find enclosed herewith the comments / observations of Drainage Expert Mr.R.Nagarajan on the drainage works being carried out in the project. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode — Inspection report of Drainage Expert - Reg | In continuation to the above said references please find enclosed herewith the comments/observations of Drainage Expert Mr. R. Nagarajan on the drainage works being carried out in the Project. Hence it is hereby asked to submit your compliance to the same in consultation with the Design Director for onward processing of the same. This is for your information and necessary immediate action. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Design & Drawings of Highways & Structures | Contractor's Obligations | By copy of this letter, concerned local self-government bodies are being requested to depute their Engineer for site inspection. It is requested to arrange joint inspection in consultation with the Engineers of local self-government bodies. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots5-9/LOT-5/20200723_NHAI_TEL&IE_ 605_Drainage Adequacy and effectiveness.pdf | Design, Construction, Development, Finance, Operation & Maintenance of 6-laning of Vadakkenchery to Thrissur (km 240.000 to 270.000) section of NH-544 (old No.47) on DBFOT(Toll) basis - Under construction project - Drainage systems: Adequacy & Effectiveness - reg. | Please refer to this office e-mail dated 09.07.2020 & 13.07.2020 communicating therewith NHAI policy guidelines regarding drainage systems: adequacy & effectiveness for compliance. In continuation to above, it is requested to inspect the site along with Engineers of concerned local panchayat / municipal / corporation bodies duly following the guidelines defined for under construction projects and submit drainage plan to this office, which will be reviewed by the Drainage Expert being identified by PIU / Regional Office. By copy of this letter, concerned local self-government bodies are being requested to depute their Engineer for site inspection. It is requested to arrange joint inspection in consultation with the Engineers of local self-government bodies. The drainage plan / report shall be submitted to this office latest by 31.07.2020. | FALSE | real_data
Safety measures during construction | Contractor's Obligations | Conractor informed that they are attending all the locations and further it will be improved. | synthetic_template_20250913 | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode. - Minutes of Monthly Progress review meeting Mom — 09 — Reg. | With respect to the above said reference please find enclosed herewith the Minutes of Meeting Numbered as MoM - 09 held on 26.02.2021 The next meeting will be likely on 19 March 2021 at Team Leader office around 11.00 A.M in Kancheepuram. All the concerned are requested to attend with necessary documents. This is for your information and record. Assuring our best services at all times. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Safety measures during construction | Contractor's Obligations | Conractor informed that they are attending all the locations and further it will be improved. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/LotsYetToProcess/tmp/LOT-9/20210302_AE_SPK_569-Minutes of Monthly Progress review meeting Mom – 09.pdf | Six Lanning of Karaipettai to Walajapet from km 71.015 to 107.091 of NH-4 (New NH-48) in the state of Tamil Nadu under residual NHDP (Phase-V) under Bharatmala Pariyojana on EPC mode. - Minutes of Monthly Progress review meeting Mom — 09 — Reg. | With respect to the above said reference please find enclosed herewith the Minutes of Meeting Numbered as MoM - 09 held on 26.02.2021 The next meeting will be likely on 19 March 2021 at Team Leader office around 11.00 A.M in Kancheepuram. All the concerned are requested to attend with necessary documents. This is for your information and record. Assuring our best services at all times. | FALSE | real_data
Occurrence of cyclones | EoT | An EOT of 10 days can be considered on account of NIVAR and BURVI cyclones | synthetic_template_20250913 | Extension of Time Comprehensive proposal- Reg. | With reference to the captioned subject and from the above mentioned chronology of correspondences, it can be understood that despite of approving an EoT for a period of 112 days for Mile Stone-1, the Contractor is disagreeing with the approval of the Authority and again highlighted the impediments adversely effected the First Mile Stone as well as other Milestone including the Scheduled Completion Date. The Contractor submitted the comprehensive proposal and requested for an extension of time. We appreciate your cooperation in this regard. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Clearances from Forest Department | Authority's Obligations | From Ch. 90+818 to Ch. 93+380, we have been unable to proceed due to the non-clearance of forest land. | synthetic_template_20250913 | Request for Relaxation in Schedule H Due to Non-Availability of Workfront Caused by ROW Issues | We would like to bring to your attention the current status and challenges we are facing in our ongoing project. As per the details mentioned above, we have successfully completed the work in full width from Ch. 94+000 to Ch. 101+000, covering a total of 7 kilometers out of the 37.14 kilometers. However, we are currently encountering significant obstacles that are hindering our progress: 1. Local Farmer Land Dispute: From Ch. 75+400 to Ch. 90+818, there has been an ongoing dispute with local farmers for the past four months. 2. Forest Land Non-Clearance: From Ch. 90+818 to Ch. 93+380, we have been unable to proceed due to the non-clearance of forest land since the appointed date of 15.05.2023. These issues have severely limited our available work front to only 12.28 kilometers out of the total 37.14 kilometers. Within this 12.28 kilometers, 3.80 kilometers are in built-up areas where encroachments have not been removed, further restricting our ability to proceed at full capacity. Consequently, our work in these sections is progressing slowly and in a fragmented manner. Thus, we have only 8.48 kilometers of stretch where we can execute the work with full machinery and manpower. As per Schedule H, Clause No. 1.3, a minimum length of 5 kilometers is required for stage payment eligibility. While we meet this criterion with the available 8.48 kilometers, the overall progress and financial flow of the project are significantly affected due to the aforementioned hindrances. We kindly request your assistance in resolving the land dispute with the local farmers and expediting the clearance of the forest land to ensure our project progresses smoothly. Additionally, we seek a relaxation in the requirements stipulated in Schedule H to support our financial needs. This relaxation will enable us to maintain the project's timeline and ensure timely completion. Thank you for your understanding and cooperation. Please confirm receipt of this correspondence. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Clearances from Forest Department | Authority's Obligations | From Ch. 90+818 to Ch. 93+380, we have been unable to proceed due to the non-clearance of forest land. | /Users/hareeshkb/GenAIWork/krishna/NewCategories/EPC_Lot 1 to 8/YetToProcess_lots1-4/LOT-2/14. 20240624_543_Cont_AE_Request for Relaxation in Schedule H.pdf | Request for Relaxation in Schedule H Due to Non-Availability of Workfront Caused by ROW Issues | We would like to bring to your attention the current status and challenges we are facing in our ongoing project. As per the details mentioned above, we have successfully completed the work in full width from Ch. 94+000 to Ch. 101+000, covering a total of 7 kilometers out of the 37.14 kilometers. However, we are currently encountering significant obstacles that are hindering our progress: 1. Local Farmer Land Dispute: From Ch. 75+400 to Ch. 90+818, there has been an ongoing dispute with local farmers for the past four months. 2. Forest Land Non-Clearance: From Ch. 90+818 to Ch. 93+380, we have been unable to proceed due to the non-clearance of forest land since the appointed date of 15.05.2023. These issues have severely limited our available work front to only 12.28 kilometers out of the total 37.14 kilometers. Within this 12.28 kilometers, 3.80 kilometers are in built-up areas where encroachments have not been removed, further restricting our ability to proceed at full capacity. Consequently, our work in these sections is progressing slowly and in a fragmented manner. Thus, we have only 8.48 kilometers of stretch where we can execute the work with full machinery and manpower. As per Schedule H, Clause No. 1.3, a minimum length of 5 kilometers is required for stage payment eligibility. While we meet this criterion with the available 8.48 kilometers, the overall progress and financial flow of the project are significantly affected due to the aforementioned hindrances. We kindly request your assistance in resolving the land dispute with the local farmers and expediting the clearance of the forest land to ensure our project progresses smoothly. Additionally, we seek a relaxation in the requirements stipulated in Schedule H to support our financial needs. This relaxation will enable us to maintain the project's timeline and ensure timely completion. Thank you for your understanding and cooperation. | FALSE | real_data
Construction work methodologies | Contractor's Obligations | we are here with submitting the Method Statement for Paver Blocks & Foot Path Chequered Cement Concrete Tiles. | synthetic_template_20250913 | Submission of Method Statement- Reg. | With reference to above cited subject, we are here with submitting the Method Statement for Paver Blocks & Foot Path Chequered Cement Concrete Tiles. We request for your kind perusal & necessary approval please. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Obstruction/Halt of works by local farmers/ Land owners | Authority's Obligations | From Ch. 75+400 to Ch. 90+818, there has been an ongoing dispute with local farmers for the past four months. | synthetic_template_20250913 | Request for Relaxation in Schedule H Due to Non-Availability of Workfront Caused by ROW Issues | It is brought to your attention that We would like to bring to your attention the current status and challenges we are facing in our ongoing project. As per the details mentioned above, we have successfully completed the work in full width from Ch. 94+000 to Ch. 101+000, covering a total of 7 kilometers out of the 37.14 kilometers. However, we are currently encountering significant obstacles that are hindering our progress: 1. Local Farmer Land Dispute: From Ch. 75+400 to Ch. 90+818, there has been an ongoing dispute with local farmers for the past four months. 2. Forest Land Non-Clearance: From Ch. 90+818 to Ch. 93+380, we have been unable to proceed due to the non-clearance of forest land since the appointed date of 15.05.2023. These issues have severely limited our available work front to only 12.28 kilometers out of the total 37.14 kilometers. Within this 12.28 kilometers, 3.80 kilometers are in built-up areas where encroachments have not been removed, further restricting our ability to proceed at full capacity. Consequently, our work in these sections is progressing slowly and in a fragmented manner. Thus, we have only 8.48 kilometers of stretch where we can execute the work with full machinery and manpower. As per Schedule H, Clause No. 1.3, a minimum length of 5 kilometers is required for stage payment eligibility. While we meet this criterion with the available 8.48 kilometers, the overall progress and financial flow of the project are significantly affected due to the aforementioned hindrances. We kindly request your assistance in resolving the land dispute with the local farmers and expediting the clearance of the forest land to ensure our project progresses smoothly. Additionally, we seek a relaxation in the requirements stipulated in Schedule H to support our financial needs. This relaxation will enable us to maintain the project's timeline and ensure timely completion. Thank you for your understanding and cooperation. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Relaxation for schedule-H payment criteria | Payments | Additionally, we seek a relaxation in the requirements stipulated in Schedule H to support our financial needs. | synthetic_template_20250913 | Request for Relaxation in Schedule H Due to Non-Availability of Workfront Caused by ROW Issues | We would like to bring to your attention the current status and challenges we are facing in our ongoing project. As per the details mentioned above, we have successfully completed the work in full width from Ch. 94+000 to Ch. 101+000, covering a total of 7 kilometers out of the 37.14 kilometers. However, we are currently encountering significant obstacles that are hindering our progress: 1. Local Farmer Land Dispute: From Ch. 75+400 to Ch. 90+818, there has been an ongoing dispute with local farmers for the past four months. 2. Forest Land Non-Clearance: From Ch. 90+818 to Ch. 93+380, we have been unable to proceed due to the non-clearance of forest land since the appointed date of 15.05.2023. These issues have severely limited our available work front to only 12.28 kilometers out of the total 37.14 kilometers. Within this 12.28 kilometers, 3.80 kilometers are in built-up areas where encroachments have not been removed, further restricting our ability to proceed at full capacity. Consequently, our work in these sections is progressing slowly and in a fragmented manner. Thus, we have only 8.48 kilometers of stretch where we can execute the work with full machinery and manpower. As per Schedule H, Clause No. 1.3, a minimum length of 5 kilometers is required for stage payment eligibility. While we meet this criterion with the available 8.48 kilometers, the overall progress and financial flow of the project are significantly affected due to the aforementioned hindrances. We kindly request your assistance in resolving the land dispute with the local farmers and expediting the clearance of the forest land to ensure our project progresses smoothly. Additionally, we seek a relaxation in the requirements stipulated in Schedule H to support our financial needs. This relaxation will enable us to maintain the project's timeline and ensure timely completion. Thank you for your understanding and cooperation. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Trial patch | Contractor's Obligations | we are initiating a PQC trial patch at Chainage 94+090 to 94+120. | synthetic_template_20250913 | Intimation for Laying of PQC Trail Patch | Kindly be informed that With Reference to above mentioned subject and ref letter no.2, we would like to inform you that we have now hereby submitting our revised plan for the location of the PQC trial patch at Chainage 94+090 to 94+120 LHS Side. After completing the PQC trial patch at the specified Chainage and upon receiving a satisfactory result, we will commence the PQC laying from Chainage 94+090 LHS side towards end of project Ch. 101+140km. We would further like to inform you that we are initiating a PQC trial patch at Chainage 94+090 to 94+120. We are hereby giving our Declaration that the PQC trial patch is at our own risk and cost. In the event that the results of the PQC trial patch are deemed unsatisfactory, we will dismantle the entire length of the patch, and all materials will be promptly removed from the site. This is for your kind information and record please. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Black spots | Change of Scope, EoT | Providing road safety interventions at identified blackspots on ORR to Medak road section of NH-765D from 0+000 to 62+920. | synthetic_template_20250913 | Rehabilitation and Upgradation of Hyderabad Outer Ring Road to Medak section of NH-765D from existing Km 15.970 (Design Km 0.00) to existing Km 78.700 (Design Km 62.92) to Two Lane with paved shoulders / Four Lane in the State of Telangana on EPC Mode. | With reference to 4" cited (copy enclosed) you are hereby notified to undertake the short term road safety measures at identified Black spots on ORR Hyderabad to Medak Road Section of NH-765D from km 0/000 to Km 62/920 in the State of Telangana and submit the compliance report immediately. We appreciate your cooperation in this regard. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Source / vendor / Manufacturer / supplier credential submission and approval | Contractor's Obligations | we are here with submitting the Profile and credentials of lndian Oil Corporation LTD (IOCL) for obtaining Source approval. | synthetic_template_20250913 | Submission of Profile and Credentials for Source approval- Reg. | It is brought to your attention that With reference to above cited subject, we are here with submitting the Profile and credentials of Indian Oil Corporation LTD (IOCL) for obtaining Source approval to procure Bitumen for execution of the Bituminous works in the project. Please confirm receipt of this correspondence. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0
Submission of Stage Payment Application | Contractor's Obligations, Authority's Obligations, Payments | we are herewith submitting 3 hard copies of the "lnterim Payment Certificate (lPC) -8. | synthetic_template_20250913 | Submission of Interim Payment Certificate (IPC) -8 - Reg. | With reference to the above subject, pursuant to the clause No. 19.4 of the article.19 of the Contract Agreement, we are herewith submitting 3 hard copies of the “Interim Payment Certificate (IPC) -8” for the period of 1** October 2023 to 2" November 2023 for an amount of Gross Value of work done 20,57,28,679 /- (Rupees Twenty Crores Fifty Seven Lakhs Twenty Eight Thousand Six Hundred and Seventy Nine only) with price adjustment value 20,59,961 /- (Rupees Twenty Lakhs Fifty Nine Thousand Nine Hundred and Sixty One Only) and the Grand total is 20,77,88,640 /- (Rupees Twenty Crores Seventy Seven Lakhs Eighty Eight Thousand Six Hundred and Forty Only) for your kind perusal and necessary recommendation please. We await your further instructions. | TRUE | template_variation | 2025-09-13T12:59:38.011701 | 1.0