## issues_to_category_mapping
Description of the Issue | Category
BG's for Performance Security and Additional Performance Security | Contractor's Obligations
Appointment of Design Director | Authority's Obligations
Permission for extracting soil from minor irrigation tanks and ponds | Others
Appointment of Safety & Proof Consultants | Contractor's Obligations
Submission of 3rd party lab test reports | Contractor's Obligations
Video recording of the Project Highway (before inception & during construction) | Contractor's Obligations
Handing over of land /Possession of site. | Authority's Obligations
QAP, EMP, EHS and Construction Programme | Contractor's Obligations
Construction work methodologies | Contractor's Obligations
Material test reports for Source Approvals | Contractor's Obligations
Mix Designs for Pavement Layers & Structural Concrete | Contractor's Obligations
Design & Drawings of Highways & Structures | Contractor's Obligations
BG's for Mobilization Advance | Contractor's Obligations
Slow Progress of Works | EOT
Delay in payment of Supervision Charges to utility departments | EOT, Authority's Obligations
Removal of Encumbrances and Encroachments from the ROW | EOT, Authority's Obligations
Monthly Progress Reports | Contractor's Obligations
Stage Payments Statements | Contractor's Obligations, Authority's Obligations, Payments
Non Compliance Reports | Others, Contractor's Obligation
Safety measures during construction. | Contractor's Obligations
Providing of GAD drawings from Railway Authorities | Authority's Obligations
Maintenance of diversion road/ existing road | Contactor's Obligations
Schedule-H Division | Payments
Change in location of structures as per site requirement | Payments, Others
Change in cross section/span arrangement of structures as per site condition | Change of scope, EoT, Dispute Resolution, Payments, Others | Change of scope, EoT, Dispute Resolution
Request for Inspection reports, test reports | Others
Notices for Achievement/ Non Achievement of Milestones | Dispute Resolution
Intimation of Occurrence of Force majeure Events | EoT, Dispute Resolution
Occurrence of unprecedent rainfall | EoT
Occurrence of unseasonal rainfall | EoT
Occurrence of land slides | EoT
Occurrence of floods | EoT
Strikes/ boycotts/ agitations | EoT
Elections in the state | EoT
Declaration of Emergency by State/ Central Government | EoT
occurrence of cyclones | EoT
Outbreak of epidemic or pandemic | EoT
Intimation of Change in Law | Payments
Change of Scope Proposals | Change of scope, EoT, Dispute Resolution, Payments | Change of scope, EoT, Dispute Resolution
Change of scope due to change in structural dimensions | Change of scope, EoT, Dispute Resolution, Payments | Change of scope, EoT, Dispute Resolution
change of scope due to local demand for additional structures, service road, utility ducts | Change of scope, EoT, Dispute Resolution, Payments | Change of scope, EoT, Dispute Resolution
Change of scope due to heavy rainfall and floods | Change of scope, Dispute Resolution, EoT, Payments | Change of scope, Dispute Resolution
Change of scope due to realignment | Change of scope, Dispute Resolution, EoT, Payments | Change of scope, Dispute Resolution
Change of scope due to redesign | Change of scope, Dispute Resolution, EoT, Payments | Change of scope, Dispute Resolution
Change of scope due to reconstruction of pavement | Change of scope, Payments, EoT, Dispute Resolution | Change of scope
Extension of Time Proposals | EoT, Dispute Resolution
Release of Retention Money | Payments
Policies during construction period (Workmen's Compensation Policy, CAR, etc.,) | Contractor's Obligations
Permissions/licences for use of blasting/explosive materials for roadway excavation | Contractor's Obligations
Payment of Royalty/Seignoirage charges for use of Minor Minerals | Contractor Obligations, Payments
Submission of Applicable permits as per Schedule-F | Contractor's Obligations
Calibration of Machinery & Equipment present at site | Contractor's Obligations
Obstruction/Halt of works by local farmers/ Land owners | Authority's Obligations
Delay in payment of certified stage payment amounts | Authority's Obligations, Payments
Inadequate Manpower/ staff at site | Contractor's Obligations, Payments
Inadequate machinery at site | Contractor's Obligations, Payments
Relaxation for schedule-H payment criteria | Payments
Clearances from Environmental & Forest Departments | Authority's Obligations
Repairs to existing PWD roads | Contactor's Obligations, Payments
usage of unapproved materials in the construction works | Others
Demands by local villagers for additional structures/service road/utility ducts | Change of scope, EoT, Dispute Resolution, Payments | Change of scope, EoT, Dispute Resolution
Clearances from Irrigation department for construction of Canal Bridges | Others
High Embankment slope protection works | Contractor's Obligations, Others, Payments
Slope protection for Hill Cutting works | Contractor's Obligations, Others, Payments
Delay in payment of stage payments | Payments
Tests on completion | Contractor's Obligations
Punchlist items | Contractor's Obligations
Provisional completion certificate | Authority's Obigations
Completion certificate | Authority's Obigations
Repairs to road furniture during maintenance period | Contractor's Obligations
Rectification of defects at toll plaza (Static weigh bridges/ In motion weigh bridges/ ATMS/ HTMS) | Contractor's Obligations
Fly ash supply | Others, EoT, Payments, Contractor's Obligations
Pond ash supply | Others, EoT, Payments
Joint inspection | Appointed Date, Contractor's Obligations, Authority's Obligations
Memorandum & Appendix | Appointed Date, Contractor's Obligations, Authority's Obligations
Utility shifting | Authority's Obligations, Contractor's Obligation, EoT
Declaration of Appointed Date | Appointed Date
Contractor's representative | Contractor's Obligations
Providing Right of Way as per Schedule A | Authority's Obligations, EoT, Dispute Resolution
Model code of conduct | EoT
Modification of Appointed Date | Appointed Date, EoT, Dispute Resolution
Dismantling of structures | Authority's Obligations, EoT, Payments
Authority Engineer | Authority's Obligations
Mobilisation of Authority Engineer | Authority's Obligations
Submission of Plan & Profile | Contractor's Obligations
Submission of Design and Drawings | Contractor's Obligations
Providing Right of Way in terms of length of Project Highway | Authority's Obligations, Appointed Date
Letter of Award | Authority's Obligations, Others
Filing of affidavit | Others
Settlement Agreement | Dispute Resolution, Payments, EoT
DRB | Dispute Resolution
Arbitration | Dispute Resolution
Price escalation | Payments, EoT
Court's decision | EoT, Others
Borrow area | Contractor's Obligations
Damages | Payments, Dispute Resolution
DLP | Contractor's Obligations
Maintenance period | Contractor's Obligations
Bonus | Payments, EoT, Dispute Resolution
Tree cutting | Contractor's Obligations, Authority Obligations, EoT
Labour License | Contractor's Obligations
Change in law reimbursement | Payments
Change of Scope Approval/order | Payments, Change of scope, EoT, Dispute Resolution | Change of scope, EoT, Dispute Resolution
Change of scope Approval revisit | Payments, Dispute Resolution, Change of scope, EoT | Change of scope, EoT
Change of scope request for additional works or works not in the scope | Payments, Dispute Resolution, Change of scope, EoT | Change of scope, EoT
Change of scope proposals clarifications | Payments, Dispute Resolution, Change of scope, EoT | Change of scope, EoT
Delay due to Change of Scope approval | EoT, Payments, Dispute Resolution, Change of scope | Change of scope
Delay due to Change of Scope works | EoT, Payments, Dispute Resolution, Change of scope | Change of scope
Design & Drawings for COS works | EoT, Payments, Dispute Resolution, Change of scope, Others | Change of scope, Others
Descoping/deletion of works under original scope | Payments, Dispute Resolution, Change of Scope | Change of Scope
Stoppage of Works by locals/public | EOT, Authority's Obligations
Descoping of a work from the scope of additional works under COS | Payments, EoT, Dispute Resolution, Change of Scope | Change of Scope
Progress Review | EoT, Payments, Others
Delay in construction activities | EOT, Dispute Resolution
Request for revisit of EOT determined/approved | EOT, Dispute Resolution
Submission of additional information/clarifications on Extension of time proposal | EOT, Dispute Resolution
Disputing the issue pursuant to Article 26 | Dispute Resolution
Right of way | Authority's Obligations, EoT, Dispute Resolution
Under utilisation / idling of resources | Payments, EoT, Dispute Resolution
Mobilisation of additional resources | Payment, Dispute Resolution
Additional cost / compensation | Payments, Dispute Resolution
Releasing of pending/ outstanding amount | Payments, Dispute Resolution
Cure period Notice | Payments, Dispute Resolution
Demobilisation and Remobilisation | EoT, Payments, Dispute Resolution
Release of Performance security | Payment, Dispute Resolution
Topography/Geotech survey | Contractor's Obligations
Delay in commencement/starting of work | EoT, Payments, Dispute Resolution
Preliminary / preparatory works | Contractor's Obligations
Handing over of cut tree/ salvaged material to the concerned authority | Contractor's Obligations, Others
Pending approvals | Others, EoT, Payments
Trial patch | Contractor's Obligations
Black spots | Change of Scope, EoT
Source / vendor / Manufacturer / supplier credential submission and approval | Contractor's Obligations
Requirement of Additional land | Authority's obligations
Releasing of BG submitted against mobilization advance | Authority's obligations, Others
Delinking impacted length | Authority's Obligations, Payments, Dispute Resolution
Contractor's delay in submission of COS Proposals | Change of Scope, Contractor's Obligations, Dispute Resolution
Contractor's delay in commencing the COS works | Change of Scope, Contractor's Obligations, Dispute Resolution
Rejection of COS request by Authority Engineer/Authority | Change of scope,Payments,Dispute Resolution,EOT