## Sheet1
subject | body | issue_type | category | correspondence_type | synthetic | generated_date | generator
Notice for Delayed Stage Payment - IPC No. 23 - NH-65 Four Laning Project | Ref: HWAY/NH65/PMT/2023-24/156 Date: 15 November 2023 To, The Project Director, National Highways Authority of India Project Implementation Unit Hyderabad, Telangana Sub: Four Laning of NH-65 from km 182.000 to km 230.200 - Delay in Release of Payment against IPC No. 23 Ref: 1. Contract Agreement No. NHAI/NH65/EPC/2021-22/001 dated 15.03.2021 2. IPC No. 23 submitted on 30.09.2023 for Rs. 12.45 crore Dear Sir, We wish to bring to your kind attention that the payment against our IPC No. 23 amounting to Rs. 12.45 crore, submitted on 30.09.2023, is still pending despite the stipulated 28-day payment period as per Article 19.6 of the Contract Agreement having elapsed. The delayed payment is severely affecting our cash flow and project progress, particularly for critical activities between chainage 195.400 to 205.600 including the major bridge at km 198.300. We request your immediate intervention for expediting the payment release to enable us to maintain the project schedule. Yours faithfully, For ABC-XYZ (JV) [Authorized Signatory] Project Manager | Delay in payment of stage payments | ('Payments', 0.91) | contractor_to_authority | TRUE | 2025-09-18T12:18:18.527898 | claude
RE: Status Update - Pending Stage Payments - Package-II NH-27 | From: executive.engineer@nhai.org To: projectmanager@contractor.com Date: 22 November 2023 Time: 14:30 IST Dear Sir, This refers to your email dated 18.11.2023 regarding pending payments for IPC 15 & 16. I wish to inform that the delay is due to ongoing reconciliation of quantities for cement concrete pavement works from km 45.200 to km 52.400. The Authority Engineer has noted some discrepancies in the measurements recorded in MB No. 324. Kindly arrange to submit the revised quantity calculations as per MORTH specifications and actual joint measurements taken on site. Upon verification, we shall process the payment within 7 working days. The payment for other completed items amounting to Rs. 3.85 crore is being processed separately to minimize financial impact. Regards, Executive Engineer NHAI PIU-Bangalore | Delay in payment of stage payments | ('Payments', 0.91) | authority_to_contractor | TRUE | 2025-09-18T12:18:18.527921 | claude
Final Notice - Outstanding Payments Against Multiple IPCs | Ref: DEF/NHAI/PMT/2023/89 Date: 25 November 2023 To, The Chief General Manager National Highways Authority of India Regional Office Mumbai, Maharashtra Sub: Six Laning of Mumbai-Nashik Highway (NH-160) - Critical Payment Delay Notice Ref: 1. Contract Agreement No. NHAI/MH/NH160/2020-21/003 2. Previous correspondence dated 15.10.2023 and 05.11.2023 Dear Sir, This is in continuation of our previous communications regarding severely delayed payments for the following IPCs: 1. IPC No. 28 - Rs. 18.75 crore (Pending since 15.08.2023) 2. IPC No. 29 - Rs. 22.30 crore (Pending since 30.09.2023) 3. IPC No. 30 - Rs. 15.45 crore (Pending since 25.10.2023) Total outstanding amount: Rs. 56.50 crore As per Article 19.7 of the EPC Agreement, interest is applicable on delayed payments beyond 56 days. We hereby notify that we shall be constrained to claim interest and may have to slow down the works if payments are not released by 05.12.2023. The delay is severely impacting critical activities including: - Elevated structure at km 78.400 - Toll plaza construction at km 82.200 - ROW development from km 75.000 to 85.000 We request your urgent intervention in this matter. Yours faithfully, For DEF Constructions Ltd. [Authorized Signatory] Vice President (Projects) | Delay in payment of stage payments | ('Payments', 0.91) | contractor_to_authority | TRUE | 2025-09-18T12:18:18.527924 | claude