## Sheet1
LOT-21 (EPC)
Sr. No | Letter No. | Name of the letter | Subject of the letter | Issues discussed in the letter | Category | Subject/Body | Reference sentence in the letter
1 | 12 | 12. 225_Acknowlegement Copy of Clause 26.3 | Items denied for payment by the Independent Engineer not acceptable to the EPC Contractor-Matter referred to Arbitration as per Clause 26.3 of the EPC Agreement | Arbitration | Dispute Resolution | Subject/Body | 1. Items denied for payment by the Independent Engineer not acceptable to the EPC Contractor-Matter referred to Arbitration as per Clause 26.3 of the EPC Agreement 2. The following are the list of claims that the EPC contractor shall be referring to Arbitration tribunal for resolving of dispute: 3. In accordance with Clause 26.3.2 - 1 - Selection of Arbitrators of the EPC agreement, we are herewith appointing Mr.S.Arunachalam as nominee arbitrator from our side and we request your good self to nominate arbitrator on your behalf so that the Arbitration Tribunal shall be constituted at the earliest.
2 | 11 | 11. 175_EPC-10 Letter | Final PJym~nt submission - Civil works (Works contracts EPG 10) - Items denied for payment by the Independent Engineer not acceptable to the EPG Contractor | Authority Engineer | Authority's Obligations | Body | The same has been reviewed by the Authority Engineer and recommended to the Authority for disallowing claims made by the EPG contractor vide ref (8) cited above 2. The following is the abstract statement of final bill certified by EPC contractor vis a vis recommended by the Authority Engineer: 3. we request the Authority to consider our claims stated above which were excluded in his recommendation by the Authority Engineer in his recommendation of Final Payment Certificate and release the payment along with amount deducted for W-Beam Crash Barrier for a length of 2600.68m under negative change of scope by the Authority Engineer at the earliest in order to settle the issues amicably. .
3 | 13 | 13. Price Adjustment | Price Adiustment | Base Date | Payments, Dispute Resolution | Body | 1. Regarding the Base Rate, The Government of Tamilnadu has issued an Order in their G.O MS No 101 PW (G2) Department Dt 10-06-2009 2. so, as per the above Article, the Government order referred in previous para is applicable to this Project also. Accordingly the date of Agreement i.e. 04-06-2015 has to be taken as base date to arrive the Base Rate, since the 'Agreement was not executed within the specified time. 3. There is no specific mention about the date on which it is applicable' ln the absence of such specific mention the date for the Base Rate has to be taken as per the orders of the Tamilnadu Government which is in force and being followed by all wings of the Tamilnadu Highways Department as well as in Public works Department' 4. Hence we request that the date of Agreement i.e. on 04-06-2015 may please be approved as the date for arriving the Base Rate' 5. Hence we request to consider the above two points for arriving the date for fixing the ,,Base Rate" and take the date of Agreement i.e. on 04-06-2015 as the Base Date
4 | 15 | 15. DE 582 Calculation of Price Escalatio - Particulars Submitted Reg | Calculation of Price Escalation - Particulars- Submitted | Base Date | Payments, Dispute Resolution | Body | Kind attention is invited to the references 1st to 3rd cited above wherein it was instructed to revise the Price Escalation for EPC-OS & EPC-I0 works on checking the base dates adopted for Price Escalation calculation.
5 | 18 | 18. PD_Implementation of GST | Implementation of GST - Change in Law - Cost Implication on the Contractor | Base Date | Payments, Dispute Resolution | Body | A change in the interpretation or application of any Indian law by a judgement of a court of record which has become final, conclusive and binding, as compared to such interpretation or application by a court of record prior to the Base Date
6 | 28 | 28. 080_Price Adjustment GST | Submission of Revised Price variation 'Calculation Considering the date of Agreement as Base date and increase in Contract Price on account of GST | Base Date | Payments, Dispute Resolution | Body | In view of the above, it is once again requested to review the above case and modify the price variation based UI1 the base Indices applicable on the date of Agreement as per GO MS No. 101 PW (G2) Department Dt. 10 6 2009.
7 | 13 | 13. Price Adjustment | Price Adiustment | BG's for Performance Security and Additional Performance Security | Contractor's Obligations | Body | 1. Wherein we have been asked to submit the Bank Guarantee towards the Performance Security 2. Accordingly we have submitted the Legal Opinion within 10 days and subsequently submitted the Original Bank Guarantee,
8 | 9 | 9. 100_Final Stage Payment | Final Payment Statement | Bonus | Payments, EoT, Dispute Resolution | Body | Bonus payable under clause 19.20 for completing the project 106 days before the scheduled or extended date of completion (100 x 0.03% of contract price)
9 | 10 | 10. 2917 - Final Payment Statement Submission (EPC10) | Final Payment Statement Submission - Civil Works | Bonus | Payments, EoT, Dispute Resolution | Body | 1. Bonus payable under clause 19.20 2. The Contractor. has completed the work in all respect on 21.12.2018 i.e. 106 days before extended period. The Contractor has claimed bonus of Rs. 8,59,49,8201- against the early completion and as per provision of Clause 19.20 subject 'to a maximum of 3% of the Contract Price.
10 | 11 | 11. 175_EPC-10 Letter | Final PJym~nt submission - Civil works (Works contracts EPG 10) - Items denied for payment by the Independent Engineer not acceptable to the EPG Contractor | Bonus | Payments, EoT, Dispute Resolution | Body | Bonus payable under Clause 19.20 for completing the project 100 days before the Scheduled or extended date of completion
11 | 9 | 9. 100_Final Stage Payment | Final Payment Statement | Change in law reimbursement | Payments | Body | Claims on account of GST Implementation by Government of India from 01.07.2017 under Change In Law as per Clause 19.17.
12 | 10 | 10. 2917 - Final Payment Statement Submission (EPC10) | Final Payment Statement Submission - Civil Works | Change in law reimbursement | Payments | Body | 1. Claims on GST under Change in Law as per Clause 19.17 2. The Contractor has claimed additional cost due to implementation of GST for balance 'works carried out as on 01.07.2017. 3. We have informed the Contractor that the claim on GST under Change in Law. cannot be · considered in this payment due' to 'inadequate information and is subject to appropriate information and auditing vis-a-vis the Contractor was required to pay as on the date of the submission of the bid. 4. Hence the Claims cannot be' considered at this stage due to insufficient details. 5. Further the Contractor has already been advised 'to submit the GST calculation as per G.O.Ms.No. 296 dated 09-10-2017.
13 | 11 | 11. 175_EPC-10 Letter | Final PJym~nt submission - Civil works (Works contracts EPG 10) - Items denied for payment by the Independent Engineer not acceptable to the EPG Contractor | Change in law reimbursement | Payments | Body | Claims on GST under Change in law as per Clause 19.17 | J16:J19
14 | 17 | 17. PD_Applicability of GST in Construction Service in Highways and Road Works | implementation of GST change in Law - Addition of 18% GST in Stage Payment Certificate - intimation | Change in law reimbursement | Payments | Subject/Body | 1. Construction of Highways and Road Contracts have become Taxable at the Rate of 18% as against the exemption under the Erstwhile Service Tax Act, 1994 and Works Contract (WCT) under Tamilnadu Value Added Tax Act 2006. 2. Further with effect from 01 st July 201 7, we need to charge the GST at the rate of 18% (CGST 9% & SGST 9%) in the RA Bill raised by us and the same will have to be collected and paid to the Central Government before the 20th of every month. We h hereby notify to the authority as per Clause 19.17.1 of the Agreement. 3. Hence we hereby inform to the authority that we will add the GST at the rate of 18% (CGST 9% and SGST 9%) in each and every stage payment bill. We request your good self to admit and make payment according to comply with the notifications of the Government of India. 4. Please note that our GSTIN : 33AANAS1482NIZZ the same may be quoted in all future correspondence instead of our TIN.
15 | 18 | 18. PD_Implementation of GST | Implementation of GST - Change in Law - Cost Implication on the Contractor | Change in law reimbursement | Payments | Subject/Body | 1. As specified above, the Contractor now has to procure the said materials after paying he taxes as per new CGST rates and various other components for the construction Works also attracts CGST which are resulting in additional cost implication to the Contractor. 2. Besides the contractor has also to add GST at the rate of 18% (CGST 9% and SGST 9%) in the stage payment bills to be raised. A separate letter for the same is being sent to authority for making effect 3. The Contractor is entitled for the Contract Price adjustment in line with the Change in Law provisions under this Contract agreement. In this connection, we would like to draw your kind attention to the Change in Law provisions as below: 4. "Change in Law" means the occurrence of any of the following after the Base Date: 5. And as such the present introduction of CGST Act, 2017 falls under the category (a) of the definition above and further Contractor refers to the Subclause 19.17.1. of the Contract Agreement, 6. "If as a result of Change in Law, the Contractor suffers any additional costs in the execution of the Works or in relation to the performance of its other obligations under this Agreement, the Contractor shall, within 15 (fifteen) days from the date it becomes reasonably aware of such addition in cost, notify the Authority with a copy to the Authority Engineer of such additional cost due to Change in Law." 7. hereby notifies accordingly to the Authority and Authority's Engineer that this CGST Act,2017 implementation is resulting in additional cost to the Contractor. 8. The Contractor shall be submitting the consolidated cost implication for adjustment to the Contract price as envisaged in Clause 19.17 of the Agreement. | discussions have been made regarding submission of source approval of Metal Beam Crash Barrier and the Project Director expressed displeasure in the delay of source approval. So far you have submitted the proposals of a number of sources. But none of the companies are manufacturing Crash Barrier using material as specified in EPC Contract Agreement. In this connection you are advised to submit the proposal of source approval of Metal Beam Crash Barrier to satisfy the EPC J16:J19Contract Agreement Conditions and MoRTH's Standards and Specifications at the earliest
16 |  |  |  | Change in law reimbursement | Payments | Subject/Body | 1. This is in reference to TNRSP letter cited above, regarding the Price Escalation and Linking Factor of Price Indices, Applicability of GST and Applicability of Excise Duty Exemption in lieu of Implementation of GST for construction works. The same matter was thoroughly discussed in review meeting held at TNRSP, PIU et Chennai on 06.01 .2017 2. Applicability of GST on works Contract shall be analysed and submitted along with supporting documents for further submission to the Authority for taking decision in this regard 3. A format of the Applicability of Excise Duty Exemption in lieu of Implementation of GST as prescribed by the Authority is attached. The same needs to be properly filled up by the Contractor up to 30.06.2017 along with supporting documents for further submission to the Authority for taking further action.
17 | 23 | 23. 046_Price Escalation and Linking of Price Indices, Applicability of GST | Price Escalation and Lin king of Price Indices, Applicability of GST and Applicability of Excise Duty Exemption in lieu of Implementation of GST. | Change in law reimbursement | Payments | Subject/Body | In this connection, we wish to refer our letter SPK-KMC/EPC-1 0/ LASAl2018/006 dated 03.01.2018 which is submitted to your good office regarding change in law implication cost. Hence the same may brief the additional implication for a period 01.07.2017 to 31.12.2017 in lieu of new Tax regime. However the details as sought by the prescribed format referred vide your letter (1) above will also be submitted in due course.
18 | 29 | 29. 082_GST Change in Law | Financial Implication and Revision of Contract Price Balance as on 01.07.2017 due to implementation of GST under Change in Law. | Change in law reimbursement | Payments | Subject/Body | 1. The tax structure of various materials and services are completely changed due to implementation of GST as compared to the taxes applicable before implementation of GST .. We are incurring additional expenses due to implementation of GST and revision of contract price is essential in pursuant to Clause 19.17. 2. We have notified vide our letters under reference about the additional expenses on GST we also informed that we would be submitting the Consolidated Cost implication for adjustment to the Contract Price as envisaged in Clause 19.17. Accordingly, the consolidated cost implication and the revision in Contract Price for the balance work as on 0 1st July 2017 (Date of Implementation of GST) are determined based on taxes applicable for the works before implementation of GST and after implementation of GST. 3. The Additional Cost Implication due to implementation of GST based on the -applicable Pre GST taxes and post GST taxes .is · Rs.13,90,17,302/- for the balance work as on 01.07.2017 and revision in Contract Price determined due to implementation of GST is to Rs.300,40,11,302/- 4. Then 12% GST as applicable is added to the final basic price. Then the taxes on account of Excise Duty and Vat on Excise Duty is added for the HSD which are additional cost due to implementation of GST as originally the project is excise duty exempt for these items. Accordingly the Contract Price due to implementation of GST for the balance value of work as on 01.07.2017 works out to Rs.138,45,14,488/-
19 | 5 | 5. MOM - Project Review Meeting dt 22.05.2018 | Project Review Meeting - 30 | Change of Scope Approval/order | Payments, Change of scope, EoT, Dispute Resolution | Body | The Project Director requested all the Team Leaders (for all EPC works) to submit a detailed report on COS (so far approved by the PIU and executed at site etc.).
20 | 2 | 2. AE to SPK ltr no 2444 dt 24.04.2018 | Metal Beam Crash Barrier | Change of scope request for additional works or works not in the scope | Payments, Dispute Resolution, Change of scope, EoT | Body | the Contractor may submit the proposal for Change of Scope.
21 | 3 | 3. SPK to AE ltr no 118 dt 27.04.2018 | Sch"uul" uf Metal Beam Crash barrier | Change of scope request for additional works or works not in the scope | Payments, Dispute Resolution, Change of scope, EoT | Body | the increase in height and nos. of W Beams on account of the same do attract "Change of scope (COS)" as per article 13.1.2 of contract.
22 | 8 | 8. SPK to AE ltr no 81 dt 14.03.2019 | Providing w Beam Crash Barrier at locations olher than mentioned in Schedule-B under Positive Change of Scope. | Change of scope request for additional works or works not in the scope | Payments, Dispute Resolution, Change of scope, EoT | Subject/Body | 1. Providing w Beam Crash Barrier at locations other than mentioned in Schedule-B under Positive Change of Scope. 2. After this, the Authority Engineer vide his letter under reference (1) instructed that the W-Beam crash barrier are to be Provided as per Part 3 Drawings as mentioned in Schedule-B as well as Schedule-D and list of locations for a length of 29,038m. But, this was not accepted by us vide our letter under reference (2) above, wherein we have stated that the all high embankment locations, Minor Bridge approaches would be carried out under change of scope after careful l examination of Schedule-B, Schedule-D and Section 9 of the Manual. 3. As the scope of providing W-Beam Crash Barrier is only 660m as per Schedule-B of the Contract Agreement, the Additional length of l0,565m (1122S-660=10565m) of W-Beam Crash Barrier provided in actual is to be treated as change of scope under Article 13 of the EPC Agreement and Change of Scope notice is required to be issued under clause 13.2. 4. The Cost for Providing W-Beam' Crash barrier for a length of l0,565m under Change of Scope is Rs.3,79,63,766/- and the details with rate' analysis is endorsed as Annexure- II. 5. In view of the above it is requested to issue the change of scope order for providing W-Beam Crash Barri er for the additional length of l0,565m
23 | 10 | 10. 2917 - Final Payment Statement Submission (EPC10) | Final Payment Statement Submission - Civil Works | Change of Scope works | Authority's Obligations, Payments, EOT, Dispute Resolution | Body | The Contractor has executed works under Change of Scope as follows. 2. So the item is not a positive change of scope as stated by the Contractor and the Contractor's claim cannot be admitted. The Contractor has installed 10793 m of Metal beam crash barrier against the finalized length 3. No Change of Scope Work can be taken up without Change of Scope Order from the Authority. In this case no Change of Scope Order was sought by the Contractor. So the claim is not maintainable.
24 | 11 | 11. 175_EPC-10 Letter | Final PJym~nt submission - Civil works (Works contracts EPG 10) - Items denied for payment by the Independent Engineer not acceptable to the EPG Contractor | Change of Scope works | Authority's Obligations, Payments, EOT, Dispute Resolution | Body | Work executed under positive Change of Scope as per Article 13 of EPC Agreement 2. Providing and fixing W beam crash barrier under positive COS as per Article 13 of EPC Agreement
25 | 12 | 12. 225_Acknowlegement Copy of Clause 26.3 | Items denied for payment by the Independent Engineer not acceptable to the EPC Contractor-Matter referred to Arbitration as per Clause 26.3 of the EPC Agreement | Change of Scope works | Authority's Obligations, Payments, EOT, Dispute Resolution | Body | The EPC Contractor also requested for releasing the payment along with amount deducted for W beam crash barrier for a length of 2600.68 m under negative change of scope at the earliest in order to resolve the issues amicably.
26 | 9 | 9. 100_Final Stage Payment | Final Payment Statement | Claims | EOT, Payments, Dispute Resolution | Body | Claims on account of GST Implementation by Government of India from 01.07.2017 under Change In Law as per Clause 19.17.
27 | 10 | 10. 2917 - Final Payment Statement Submission (EPC10) | Final Payment Statement Submission - Civil Works | Claims | EOT, Payments, Dispute Resolution | Body | The contractor has claimed against construction of Quality Control Laboratory Building for an amount of Rs. 37,00,000/-.
28 | 11 | 11. 175_EPC-10 Letter | Final PJym~nt submission - Civil works (Works contracts EPG 10) - Items denied for payment by the Independent Engineer not acceptable to the EPG Contractor | Claims | EOT, Payments, Dispute Resolution | Body | 1. The EPG contractor vide reference (5) cited above submitted final payment certificate along witlh aII supporting and back up details incorporating various claims within the ambit of tile EPCagreement.+H43:H48H42H43:H52H43:H50H42H43:H52H43:H51H42H43:H52H43:H52H42H43:H52H43:H54H43:H53
29 | 12 | 12. 225_Acknowlegement Copy of Clause 26.3 | Items denied for payment by the Independent Engineer not acceptable to the EPC Contractor-Matter referred to Arbitration as per Clause 26.3 of the EPC Agreement | Claims | EOT, Payments, Dispute Resolution | Body | 1. The same has been reviewed by the Authority Engineer and recommended to the Authority after disallowing claims made by the EPC contractor 2. The EPC Contractor vide ref (9) cited above requested the Authority to consider the claims which were excluded in recommendation of final payment certificate by the Authority Engineer vide
30 | 9 | 9. 100_Final Stage Payment | Final Payment Statement | Completion certificate | Authority's Obigations | Body | We have received the Completion Certificate for the above project
31 | 10 | 10. 2917 - Final Payment Statement Submission (EPC10) | Final Payment Statement Submission - Civil Works | Completion certificate | Authority's Obigations | Body | The above works was completed on 21 .12.2018, within the extended peri0d i.e. .. Upto 06.04.2019 and the Completion Certificate was issued on 18.03.2019
32 |  |  |  | Completion certificate | Authority's Obigations | Body | We have received the Completion Certificate for the above project under subject on 18.03.2019
33 | 5 | 5. MOM - Project Review Meeting dt 22.05.2018 | Project Review Meeting - 30 | Delay from the Authority Engineer for material source approval/approval of design/finalisation of locations of Project facilites | EOT, Change of Scope, Dispute Resolution, Payments | Body | 1. The Project Director displeased with the delay in deciding quantity and source approval of metal beam crash barrier, and asked the Team Leader to take final decision on the quantity and source approval, strictly as per the agreement provisions,. before 31.05.2018 and submit a report.
34 | 10 | 10. 2917 - Final Payment Statement Submission (EPC10) | Final Payment Statement Submission - Civil Works | Disputing the issue pursuant to Article 26 | Dispute Resolution | Body | Regarding disputed items payment, if any, shall be considered after settlement of the dispute.
35 | 12 | 12. 225_Acknowlegement Copy of Clause 26.3 | Items denied for payment by the Independent Engineer not acceptable to the EPC Contractor-Matter referred to Arbitration as per Clause 26.3 of the EPC Agreement | DRB | Dispute Resolution | Body | 1. During execution at several occasions, we requested the Authority ,to constitute DRB as per Clause 26.2.2 of contract agreement. 2. Hence constitution of DRB at this stage is not required. Hence, we are constrained to refer the issue to Arbitration Tribunal as per Clause 26.3 of the EPC agreement.
36 | 9 | 9. 100_Final Stage Payment | Final Payment Statement | Final Payment | Contractor's Obligations, Authority's Obligations, Payments, Completion Certificate, Dispute Resolution | Subject/Body | 1. we are herewith submitting the Final Payment Statement for works under. 2. We hereby confirm that the above amount of the Final Payment Statement represents the full and final settlement of all monies due to us in respect of this agreement for all the works arising out of this Agreement except for any monies due on any account of defect in accordance with Clause 19.14 of Article 19 of Contract Agreement.
37 | 10 | 10. 2917 - Final Payment Statement Submission (EPC10) | Final Payment Statement Submission - Civil Works | Final Payment | Contractor's Obligations, Authority's Obligations, Payments, Completion Certificate, Dispute Resolution | Subject/Body | 1. Final Payment Statement Submission - Civil Works 2. The Contractor has submitted the Final Payment Statement along with all supporting and backup details. 3. final statement represents the full and final settlement of all monies due to the Contractor:. We have verified · the Final Statement and our comments are as follows. 4. Thus we recommended a sum of Rs. 11,05,00,919/· (Rupees Eleven Crores Five Lakhs Nine Hundred and Nineteen only) against Final Statement of Civil Works. Payment may be done after deducting necessary statutory taxes at your end.
38 | 11 | 11. 175_EPC-10 Letter | Final PJym~nt submission - Civil works (Works contracts EPG 10) - Items denied for payment by the Independent Engineer not acceptable to the EPG Contractor | Final Payment | Contractor's Obligations, Authority's Obligations, Payments, Completion Certificate, Dispute Resolution | Subject/Body | 1. The EPG contractor vide reference (5) cited above submitted final payment certificate along with aII supporting and back up details incorporating various claims within the ambit of tile EPC agreement. 2. The following is the abstract statement of final bill certified by EPC contractor vis a vis recommended by the Authority Engineer: - 3. we request the Authority to consider our claims stated above which were excluded in his recommendation by the Authority Engineer in his recommendation of Final Payment Certificate and release the payment along with amount deducted for W-Beam Crash Barrier for a length of 2600.68m under negative change of scope by the Authority Engineer at the earliest in order to settle the issues amicably. .
39 | 12 | 12. 225_Acknowlegement Copy of Clause 26.3 | Items denied for payment by the Independent Engineer not acceptable to the EPC Contractor-Matter referred to Arbitration as per Clause 26.3 of the EPC Agreement | Final Payment | Contractor's Obligations, Authority's Obligations, Payments, Completion Certificate, Dispute Resolution | Body | The EPC contractor vide reference (5) cited above submitted final payment certificate along with all supporting and back up details incorporating various claims within the ambit of the EPC agreement
40 | 30 | 30. 100_Final Stage Payment | Final Payment Statellltmt | Final Payment | Contractor's Obligations, Authority's Obligations, Payments, Completion Certificate, Dispute Resolution | Subject/Body | 1. As per clause 19. 13, we are herewith submitting the Final Payment Statement for works under. 2. We hereby confirm that the above amount of the Final Payment Statement represents the full and final settlement of all monies due to us in respect of this agreement for all the works arising out of this Agreement except for any monies due on any account of defect in accordance with Clause 19.14 of Article 19 of Contract Agreement.
41 | 4 | 4. AE to SPK ltr no 2485 dt 16.05.2018 | Provision and Installation of Metal Beam Crash Barrier at Site | Joint inspection | Appointed Date, Contractor's Obligations, Authority's Obligations | Body | The Location may be interchanged and finalised as per the site requirement if necessary by having a joint site inspection along with the representatives of Authority, CSC and the Contractor.
42 | 8 | 8. SPK to AE ltr no 81 dt 14.03.2019 | Providing w Beam Crash Barrier at locations olher than mentioned in Schedule-B under Positive Change of Scope. | Joint inspection | Appointed Date, Contractor's Obligations, Authority's Obligations | Body | As the above issue was lingering for long period and the Scheduled Project Completion was nearing, in order to finalise the issue, the Superintendent Engineer of Authority conducted joint site inspection on 22.06.18 and identified the locations and instructed us to provide W-Beam Crash Barrier for a length of 11225 m. The location details of W-beam crash barrier provided at Site as per instructions given during instructed by the Superintendent Engineer of Authority during Joint Site Inspection is enclosed as Annexure-I.
43 | 10 | 10. 2917 - Final Payment Statement Submission (EPC10) | Final Payment Statement Submission - Civil Works | Joint inspection | Appointed Date, Contractor's Obligations, Authority's Obligations | Body | The Contractor has installed 10793 m of Metal beam crash barrier against the finalized length, as per Contract agreement and joint inspection,
44 | 11 | 11. 175_EPC-10 Letter | Final PJym~nt submission - Civil works (Works contracts EPG 10) - Items denied for payment by the Independent Engineer not acceptable to the EPG Contractor | Joint inspection | Appointed Date, Contractor's Obligations, Authority's Obligations | Body | it was mentioned that after a joint inspection the length and location of metal beam crash barrier has been finalized as 13393.68m
45 | 13 | 13. Price Adjustment | Price Adiustment | LOA | Contractor's Obligations, Authority's Obligations | Body | 1. In this regard we wish to state that the LOA was issued to us by The Project Director 2. As per Recital D (ii) of the Conditions of Contract the Agreement has to be executed within 28 days of the date of LOA, i.e. the Agreement has to be executed on or before 06-05-2015.
46 | 28 | 28. 080_Price Adjustment GST | Submission of Revised Price variation 'Calculation Considering the date of Agreement as Base date and increase in Contract Price on account of GST | LOA | Contractor's Obligations, Authority's Obligations | Body | Once again, we 'Would like reiterate for your better understanding that As per Recital D(ii) of the Conditions of Contract, the Contract Agreement has to be executed within 28 days from the date of LOA
47 | 10 | 10. 2917 - Final Payment Statement Submission (EPC10) | Final Payment Statement Submission - Civil Works | Maintenance of diversion road/ existing road | Contactor's Obligations | Body | the condition of the road was in damaged stage at the time of Appointed Date and hence the maintenance work of the road was arranged under Change of Scope Number 1 and the amount paid as per site measurement is Rs. 94,82,847.501-. .
48 | 13 | 13. Price Adjustment | Price Adiustment | Policy Circular/ G.O | Others | Body | 1. Regarding the Base Rate, The Government of Tamilnadu has issued an Order in their G.O MS No 101 PW (G2) Department Dt 10-06-2009 2. so, as per the above Article, the Government order referred in previous para is applicable to this Project also. Accordingly the date of Agreement i.e. 04-06-2015 has to be taken as base date to arrive the Base Rate, since the 'Agreement was not executed within the specified time.
49 | 19 | 19. SE - 2398 Appli. G.O. in price escalation Intimation | Letter No. 23981201S/TNRSP II/PMC dated 24.10.2017. | Policy Circular/ G.O | Others | Body | A meeting is scheduled to be convened on 26.10.2017 at 11.00 A.M. at PIU to discuss on the applicability of G.O. cited in price escalation calculation for the projects under TNRSP II. The Divisional Engineers(H), TNRSP II and Team Leaders are requested to attend the meeting along with estimates, copy of agreements and other relevant details of their respective works, to offer their suggestions/guidance/remarks on the applicability of G.O on bitumen and other materials. The Contractor shall be submitting the consolidated cost implication for adjustment to the Contract price as envisaged in Clause 19.17 of the Agreement.
50 | 20 | 20.1 448_TL - 2042 - Price Adjustment Mechanisim for Civil Works TNRSPII (EPC 10) | Submissiono f price AdjustmentM echanismfo r Civil Works _TNRSPII | Policy Circular/ G.O | Others | Body | In reference to TNRSP letter cited above regarding caption subject, the Government had brought in to effect a new Price Adjustment Mechanism in respect of Contraction of Works. So you are requested to submit the details of components like Cement, Rebar, Bitumen, HSD (Petroleum Products) All Commodity, plant& Machinery, etc, according to EPC Contract Agreement and new Price Adjustment Mechanism for our review and further submission to the Authority
51 | 28 | 28. 080_Price Adjustment GST | Submission of Revised Price variation 'Calculation Considering the date of Agreement as Base date and increase in Contract Price on account of GST | Policy Circular/ G.O | Others | Subject/Body | 1. We have requested for fixing the base date for price variation as date of Agreement in accordance with the Government Order GO MS No.101 PW .(G2) Department Dt. 10-06-2009 2. We will reproduce the Government of Tamilnadu issued an order vide GO M5 NO.101 PW (G2) Department Dt. 10-06-2009 wherein it is mentioned as 3. This Government Order referred above is in force and being followed by all wings of Tamilnadu Highways department and Public Works Department. Accordingly the date of Agreement i.e. 04- 06-2015 had to be the base date for .fixing the base indices for price variation under clause 19.10 of the Contract Agreement. .
52 | 9 | 9. 100_Final Stage Payment | Final Payment Statement | Price escalation | Payments, EoT | Body | Price Variation as per Clause 19.10 (Base Date is changed as Date of Agreement as per GO MS No.1D1 PW (G2) Department Dt. 10-06-2009)
53 | 10 | 10. 2917 - Final Payment Statement Submission (EPC10) | Final Payment Statement Submission - Civil Works | Price escalation | Payments, EoT | Body | 1. The Price adjustments for the works executed is arrived based on the Formula given in the . EPC . Contract Agreement and Price· Variations of each materials. 2. Claims on Price Variation difference as per Clause 19.10. 3. The contractor has claimed on Ptice ·Variation difference as per Clause 19.10 (Base date is changed as Date of Agreement as per G.O.Ms.No.101 PW (G2).Rs. 13,43,04,446/-.
| 11 | 11. 175_EPC-10 Letter | Final PJym~nt submission - Civil works (Works contracts EPG 10) - Items denied for payment by the Independent Engineer not acceptable to the EPG Contractor | Price escalation | Payments, EoT | Body | Price Variation as per Clause 19.10 (Base date is changed as date of agreement as per GO MS. No. 101 PW (G2) department dated 10.06.2009.
| 13 | 13. Price Adjustment | Price Adiustment | Price escalation | Payments, EoT | Subject/Body | 1.we feel that the matter regarding the Price Adjustment has to be finalised, for which we herby submit the following facts for approval. 2. "As per the formula from the last date of Submission of BID up to the end of the Agreement Period provided, if the Agreement is signed with in the minimum specified time, failing which the Price Variation will be applicable from the date of Agreement on! 3. so, as per the above Article, the Government order referred in previous para is applicable to this Project also. Accordingly the date of Agreement i.e. 04-06-2015 has to be taken as base date to arrive the Base Rate, since the 'Agreement was not executed within the specified time.
| 14 | 14. TNRSP ltr dt 16.03.2017 | Accounts - Tamil Nadu Road Sector Project-II- EPCOI - EPCI0 and OPRC 01 & OPRC02- Calculation of Price Escalation -Particulars - | Price escalation | Payments, EoT | Subject/Body | 1. The Revised Price escalation ' statement implemented as per the above references. 2. The difference between the earlier price escalation and the Revised escalation statements 3. The amount of price adjustment for all the IPCs to be adjusted in the current IPC.
| 15 | 15. DE 582 Calculation of Price Escalatio - Particulars Submitted Reg | Calculation of Price Escalation - Particulars- Submitted | Price escalation | Payments, EoT | Subject/Body | Kind attention is invited to the references 1st to 3rd cited above wherein it was instructed to revise the Price Escalation for EPC-OS & EPC-I0 works on checking the base dates adopted for Price Escalation calculation.
| 16 | 16. 410_TL - 1409 - Calculation of Price Escalation -Particulars Submitted (PD to EPC 08 & EPC 10) | Calculationo f Price Escalation- Particulars- Submitted | Price escalation | Payments, EoT | Body | 1. There is No difference between the earlier price escalation and the revised escalation statement in this IPC 2. The amount of price adjusimenft for all the IPCS upto date has been adjusted in the Current IPC.
| 21 | 21. 2 700_TL - 2263 - Applicability of GST and Linking factor in Price Escalation (Works Contract EPC 08 and EPC 10) | Applicability of GST and Linking factor in Price Escalation (Works Contract EPC 08 and EPC 10 | Price escalation | Payments, EoT | Subject/Body | This is in reference to TNRSP email dated above regarding linking factor in price escalation. The Authority has requested the CSC for their observations and remarks on the linking factor to be used in the place of Grey Cement, Rebars, Construction Machinery and All Commodities for use in the price escalation. The CSC has reviewed and recommended the linking factor and alternative material I component in annexure I and II
| 22 | 22. 490_TL - 2286 - Price Escalation and Linking of Price Indices, Applicability of GST | Price Escalation and Linking of Price Indices, Applicability of GST and Applicability of Excise Duty Exemption in lieu of Implementation of GST - | Price escalation | Payments, EoT | Subject/Body | 1. This is in reference to TNRSP letter cited above, regarding the Price Escalation and Linking Factor of Price Indices, Applicability of GST and Applicability of Excise Duty Exemption in lieu of Implementation of GST for construction works. The same matter was thoroughly discussed in review meeting held at TNRSP, PIU et Chennai on 06.01 .2017 2. Price Escalation and Linking Factor of Price Indices needs to be properly derived and report submitted by the Contractor along with supporting documents for review of the Authority's Engineer and to submit to the Authority for taking decision in this regard.
| 23 | 23. 046_Price Escalation and Linking of Price Indices, Applicability of GST | Price Escalation and Lin king of Price Indices, Applicability of GST and Applicability of Excise Duty Exemption in lieu of Implementation of GST. | Price escalation | Payments, EoT | Subject/Body | We hereby wish to submit linking factor proposals and price indices from Apr-17 to Oct-1 7 which are derived as per the analysis detailed herewith. An abstract along with a detailed analysis statement is enclosed herewith for your kind review and approval. Please be noted that the proposal is derived by considering 2011 -12 price indices of alternate similar materials as suggested by TNRSP in place of the components Cement, Steel, Other materials and Plants, Machinery & Spares. Hope this proposal may comply in line with requirement under this subject.
| 24 | 24. GST PD LR | Memo No. Accts 1 / Che / 9 /2018 Dt. 27.02.2018 | Price escalation | Payments, EoT | Subject/Body | In continuation to the reference 3rd cited, the particulars received regarding the Linking Factor for indices between WPI (2011-12) and WPI (2004-05) in the references cited were considered and orders are issued for adoption for the purpose of Price Escalation in respect of all EPC and OPRC Contracts as follows:- 2. The Divisional Engineers (ill are requested to inform the above to the concerned EPC 1 OPRC Contractors 1 Consultants for adoption in respect of price escalation and effecting changes in the respective agreements.
| 25 | 25. GST DE lr | Accounts - Price AdjustmentCommodities item and linking factor for indices between WPI (20] 1-12 and WPI 2004-05) for all EPC and OPRC contracts - Order - Communicated | Price escalation | Payments, EoT | Body | I enclose herewith the copy of reference cited for adoption in respect of Price Escalation.
| 26 | 26. 089_Price Escalation and Linking of Price Indices | Price Escalation and Linking of price indices | Price escalation | Payments, EoT | Subject/Body | 1. we have been suggested by TNRSP to select "alternate similar materials" in place of the "base material (which is as per contract)" due to non-availability of price indices since 01.04.2017 onwards 2. we have analyzed the price variation trend of the alternate materials in comparison with base material to derive linking factor. As the trend of price indices variation of the identified alternate materials differ from the price indices variation trend of base materials for the previous period 3. We hereby sincerely request your good self to review our previous submission once again and kindly append the linking factor as proposed by us.
| 27 | 27. 506_TL - 2399 - Price Escalation and Linking Factor of Price | Price Escalation and Linking of Price Indices | Price escalation | Payments, EoT | Subject/Body | 1. We have examined your submission and verified as per provisions given in the Article 19 of EPC Contract Agreement. While calculating the Linking Factor there is no logic for consideration of correlation factor between WPI 2011-2012 and WPI 2004-2005. 2. The Authority has taken a tendon decision and orders are issued for adoption of Commodities items and Linking Factor for the purpose of Price Escalation in respect of all EPC Packages of TNRSPII
| 28 | 28. 080_Price Adjustment GST | Submission of Revised Price variation 'Calculation Considering the date of Agreement as Base date and increase in Contract Price on account of GST | Price escalation | Payments, EoT | Subject/Body | 1. We have requested for fixing the base date for price variation as date of Agreement in accordance with the Government Order GO MS No.101 P'W .(G2) Department Dt. 10-06-2009 2. As per the formula from the last dote of submission of BID up to the end of the Agreement Period Provided, if the Agreement is signed with in .the minimum specified time, failing which the price variation will be applicable from the date of Agreement only" 3. In view of the above, it is once again requested to review the above case and modify the price variation based on the base Indices applicable on the date of Agreement as per GO MS No. 101 PW (G2) Department Dt. 10 6 2009. 4. Accordingly, the net amount payable on account of this revision in the base indices and GST implementation works out to Rs. 13,43,04,446/- 5. In view of the above, it is requested to recommend to the Authority for releasing the above amount on account of price variation at the earliest.
| 29 | 29. 082_GST Change in Law | Financial Implication andRevision of Contract Price Balance as on 01.07.2017 due to implementation of GST under Change in Law. | Price escalation | Payments, EoT | Subject/Body | 1. The Basic Price of various components without taxes for the work balance as on 01.07.2017 is Calculated by deducting the tax as applicable before implementation of G5T for these various components as tabulated below and detailed In Annexure -III 2. For the balance work, the value of various components like labour, cement, steel, Bitumen, Fuel, Plant & Machinery and other materials are arrived after deducting 15% for Contractor's OH and Margin in line with Price Adjustment clause 19.10.4 as tabulated below.
| 5 | 5. MOM - Project Review Meeting dt 22.05.2018 | Project Review Meeting - 30 | Progress Review | EoT, Payments, Others | Subject/Body | 1. The monthly progress review meeting of EPC 10 was conducted on 22.05 .2018 at PIU,TNRSP II, Chennai.
| 2 | 2. AE to SPK ltr no 2444 dt 24.04.2018 | Metal Beam Crash Barrier | Project Facilities as per Scheule- B and C | Contractor's Obligations, Change of Scope, EOT, Dispute Resolution, Completion Certifcate | Subject/Body | 1. Metal Beam Crash Barrier 2. whether Contractor's Contractual responsibility was limited to providing only to the extent as mentioned in Schedule B of Contract. After careful examination of the Contractual interpretation furnished by the Authority's Engineer in this aspect vis-a-vis codal provisions, 3. Metal Beam Crash Barriers are to be provided as per Part 3 - Drawings as mentioned in Schedule B as well as per Schedule . D of the Contract 4. Single Beam is to be provided at all places as per enclosed list excepting at the Bridge Approaches and at the places where the embankment height is more than 3.0 meter and at pond locations as mentioned in Schedule B where Double "W" Beam Crash Barriers are to be provided
| 3 | 3. SPK to AE ltr no 118 dt 27.04.2018 | Sch"uul" uf Metal Beam Crash barrier | Project Facilities as per Scheule- B and C | Contractor's Obligations, Change of Scope, EOT, Dispute Resolution, Completion Certifcate | Subject/Body | 1. With reference to your good office letter referred vide above and careful examination of the contract provisions in line with Schedule-B and the suggestions quoted vide your letter referred above, we have compiled our schedule of metal beam crash barrier locations in line with Schedule-B and Schedule-D. 2. The above stated Schedule-B and Schedule-D do not warrant the locations where curve radii is less than 450m radii in general and Box / Slab culverts are already provided with RCC barrier (Rigid). Hence these locations as stated under your list are not considered by us.
| 4 | 4. AE to SPK ltr no 2485 dt 16.05.2018 | Provision and Installation of Metal Beam Crash Barrier at Site | Project Facilities as per Scheule- B and C | Contractor's Obligations, Change of Scope, EOT, Dispute Resolution, Completion Certifcate | Subject/Body | 1. Provision and Installation of Metal Beam Crash Barrier at Site 2. During the Project Review Meeting on 06.01 .2018 and 03.05.2018 it was discussed and concluded that Metal Beam Crash Barrier shall be provided as per Schedule B and Part III Drawings of the EPC Contract Agreement and we have already clarified this to you several times. 3. Now the Authority vide their letter cited at 3 above once again reiterated that the length at Metal Beam Crash Barrier as per Schedule B of the EPC Contract Agreement and Part III Drawings are the bare Minimum requirement of the Project. It is also clarified that only Single Beam Metal Beam Crash Barrier shall be provided. The Metal Beam Crash Barrier has to be installed to the length as indicated by the Part III drawings and Schedule B of the EPC Contract Agreement which lies as the Scope of the EPC Contract Agreement. 4. The Location may be interchanged and finalised as per the site requirement if necessary by having a joint site inspection along with the representatives of Authority, CSC and the Contractor.
| 5 | 5. MOM - Project Review Meeting dt 22.05.2018 | Project Review Meeting - 30 | Project Facilities as per Scheule- B and C | Contractor's Obligations, Change of Scope, EOT, Dispute Resolution, Completion Certifcate | Body | The length of W beam crash barrier is listed in Schedule 'B.' _However, in the part 3 drawings the legend representation are drawn in more locations. The Project Director enquired how the difference crept in and asked the officials to verify with DPR/RFP/agreement documents.
| 7 | 7. SPK to AE ltr no 173 dt 11.06.2018 | Submission of Schedules for Metal Beam Crash Barrier. | Project Facilities as per Scheule- B and C | Contractor's Obligations, Change of Scope, EOT, Dispute Resolution, Completion Certifcate | Subject/Body | With reference to your letter cited above under subject matter; we are hereby submitting the schedule of locations for Metal Beam Crash Barrier (Single - W Beam). This is after careful examination of provisions stipulated in Schedule -B and Part - 3 Drawings as per your suggestions.
| 8 | 8. SPK to AE ltr no 81 dt 14.03.2019 | Providing w Beam Crash Barrier at locations olher than mentioned in Schedule-B under Positive Change of Scope. | Project Facilities as per Scheule- B and C | Contractor's Obligations, Change of Scope, EOT, Dispute Resolution, Completion Certifcate | Body | 1. As per Scope of the project, W-Beam Crash Barriers are to be provided as per Schedule-B and in accordance with the Specifications and Standards mentioned in Schedule-D of the Contract agreement. 2. As per Clause B.3 of Schedule-B, the locations of W-Beam Crash barrier to be provided is defined and as tabulated below for ready reference and it states that "W-Beam Crash Barrier Shall be Provided along the Project Highway at the following locations as per Section-9 of the Manual as a minimum." 3. Hence, our scope of providing W-Beam Crash Barrier is limited to 660m as per above table pursuant to clause 8.3 of Schedule-B. The same was reiterated by us in project review meetings dated 06:01.18 & 03.05.18 and the same were acknowledged in Authority Engineer letter under reference (3). 4. After this, the Authority Engineer vide his letter under reference (1) instructed that the W-Beam crash barrier are to be Provided as per Part 3 Drawings as mentioned in Schedule-B as well as Schedule-D and list of locations for a length of 29,038m. But, this was not accepted by us vide our letter under reference (2) above, wherein we have stated that the all high embankment locations, Minor Bridge approaches would be carried out under change of scope after careful l examination of Schedule-B, Schedule-D and Section 9 of the Manual. 5. In response to this instruction of Authority Engineer, vide our letter under reference (4),we proposed locations in line with the Part -3 drawings and Schedule-B even though our contention was that our scope of providing W-Beam Crash Barrier is only 660m as mentioned in clause 8.3 of Schedule B.
| 10 | 10. 2917 - Final Payment Statement Submission (EPC10) | Final Payment Statement Submission - Civil Works | Project Facilities as per Scheule- B and C | Contractor's Obligations, Change of Scope, EOT, Dispute Resolution, Completion Certificate | Body | As per Schedule B (clause 2.1), 3 specification and standards the description of the requirements for the various elements of the project highway given in schedule B, schedule D and part - 3 drawings are the bare minimum requirements of the Project. 2. As per Schedule C Project facilities, General Ite.ms of EPC Contract Agreement, the Contractor has to construct a Quality Control Laboratory with r:ninimum carpet area of 80 sqm.
| 10 | 10. 2917 - Final Payment Statement Submission (EPC10) | Final Payment Statement Submission - Civil Works | Schedule-H Division | Payments | Body | The work done details' are verified and arrived based on clause 19.3.1 in length, number or area as specified and valued in accordance with the proportions of the Contract Price assigned to each item and its Stage in Schedule - H.
| 11 | 11. 175_EPC-10 Letter | Final PJym~nt submission - Civil works (Works contracts EPG 10) - Items denied for payment by the Independent Engineer not acceptable to the EPG Contractor | Schedule-H Division | Payments | Body | Balance amount payable in Contract price as per Schedule H of Contract Agreement after adjusting the stage payment already (i) received. 2. The justifications cited by the Authority Engineer for not honouring our claim pertaining to fixing of W beam crash barrier under positive COS, claims on GST. and Construction of additional lab with construction & maintenance and claim on price variation by changing the base date to date of agreement as per G.O. MS NO.101 PW(G2) Department Dated 10.06.2009 are not acceptable to us.
| 8 | 8. SPK to AE ltr no 81 dt 14.03.2019 | Providing w Beam Crash Barrier at locations olher than mentioned in Schedule-B under Positive Change of Scope. | Schedule-J | Contractor's Obligations, EOT, Payments, Dispute Resolution | Body | We had provided W-Beam Crash Barrier as per the instruction of the Superintendent Engineer of Authority even though our scope was limited to Schedule-B. Being the professional Contracting firm, this work .was carried out only in the interest of completion of the project as per Schedule-J of the Project wherein our objection/raising the dispute in this regard at that time might have delayed the completion of the project as the issue was lingering for long time.
| 28 | 28. 080_Price Adjustment GST | Submission of Revised Price variation 'Calculation Considering the date of Agreement as Base date and increase in Contract Price on account of GST | Signing of Agreement | Contractor's Obligations, Authority's Obligations | Body | 1. Once again, we 'Would like reiterate for your better understanding that As per Recital D(ii) of the Conditions of Contract, the Contract Agreement has to be executed within 28 days from the date of LOA 2. the Agreement has to be executed on or before 06-05-2015. But, the agreement was signed on 04-06-2015 i.e. beyond the minimum specified time in the Contract Conditions. 3. In our case, the execution of agreement was delayed beyond minimum specified time in the Condition of the Contract.
| 6 | 6. AE to SPK ltr no 2528 dt 30.05.2018 | Submission of Source Approval of Metal Beam Crash Barrier - | Source / vendor / Manufacturer / supplier credential submission and approval | Contractor's Obligations | Subject/Body | 1. Submission of Source Approval of Metal Beam Crash Barrier - 2. discussions have been made regarding submission of source approval of Metal Beam Crash Barrier and the Project Director expressed displeasure in the delay of source approval. So far you have submitted the proposals of a number of sources. But none of the companies are manufacturing Crash Barrier using material as specified in EPC Contract Agreement. In this connection you are advised to submit the proposal of source approval of Metal Beam Crash Barrier to satisfy the EPC Contract Agreement Conditions and MoRTH's Standards and Specifications at the earliest
| 14 | 14. TNRSP ltr dt 16.03.2017 | Accounts - Tamil Nadu Road Sector Project-II- EPCOI - EPCI0 and OPRC 01 & OPRC02- Calculation of Price Escalation -Particulars - | Stage Payments Statements | Contractor's Obligations, Authority's Obligations, Payments | Body | The amount of price adjustment for all the IPCs to be adjusted in the current IPC.
| 16 | 16. 410_TL - 1409 - Calculation of Price Escalation -Particulars Submitted (PD to EPC 08 & EPC 10) | Calculationo f Price Escalation- Particulars- Submitted | Stage Payments Statements | Contractor's Obligations, Authority's Obligations, Payments | Body | 1. There is No difference between the earlier price escalation and the revised escalation statement in this IPC 2. The amount of price adjusimenft for all the IPCS upto date has been adjusted in the Current IPC.
| 1 | 1. AE to SPK ltr no 1963 dt 16.09.2017 | Metal Beam Crash Barrier, Earthen and lined Trapezoidal Drain Details | Submission of Design and Drawings | Contractor's Obligations | Subject/Body | 1. The project is at its final stage now. So far you have not given the details of locations of Metal Beam Crash Barrier, Earthen and lined Trapezoidal Drain. 2. You are advised to submit the location along with length of Metal Beam Crash Barrier, Earthen and lined Trapezoidal Drain as per Schedule B. part 3 drawing (Traffic signs and lane marking plan) of EPC Contract Agreement and Manual of specifications and standards, for our review.
| 2 | 2. AE to SPK ltr no 2444 dt 24.04.2018 | Metal Beam Crash Barrier | Submission of Design and Drawings | Contractor's Obligations | Body | 1. a question was raised by a Contractor as to whether Contractor's Contractual responsibility was limited to providing only to the extent as mentioned in Schedule B of Contract. After careful examination of the Contractual interpretation furnished by the Authority's Engineer in this aspect vis-a-vis codal provisions, the Authority has been pleased to instruct that Metal Beam Crash Barriers are to be provided as per Part 3 - Drawings
| 7 | 7. SPK to AE ltr no 173 dt 11.06.2018 | Submission of Schedules for Metal Beam Crash Barrier. | Submission of Design and Drawings | Contractor's Obligations | Subject/Body | With reference to your letter cited above under subject matter; we are hereby submitting the schedule of locations for Metal Beam Crash Barrier (Single - W Beam). This is after careful examination of provisions stipulated in Schedule -B and Part - 3 Drawings as per your suggestions.
| 10 | 10. 2917 - Final Payment Statement Submission (EPC10) | Final Payment Statement Submission - Civil Works | Withheld amount | Payments, Dispute Resolution, EOT | Body | 1. Release of Withheld Amount 2. Certain amount (Rs.2, 19,90,826/-). was withheld against miscellaneous and finishing works like protection works, 3. proposal is given in this Final payment statement for . releasing the amount Rs. 2,19,90,826/-
| 11 | 11. 175_EPC-10 Letter | Final PJym~nt submission - Civil works (Works contracts EPG 10) - Items denied for payment by the Independent Engineer not acceptable to the EPG Contractor | Withheld amount | Payments, Dispute Resolution, EOT | Body | Release of withheld amount